## Risk Register
Fictitious Space Mission — Risk Register
Planning example ¦ Cost impacts and weighted exposure are in CAD $000 ¦ Weighted exposure = Probability × Most Likely Cost Impact
Mission ID | 1001 |  | Number of risks | 200 |  | Average probability | 37.68% |  | Total weighted exposure | 106395.6667
Mission ID | Risk Category | Risk Title | Risk Description | Mitigation Strategy | Mitigation Strategy Narrative | Probability | Cost Impact – Optimistic ($000) | Cost Impact – Most Likely ($000) | Cost Impact – Pessimistic ($000) | Weighted Exposure ($000)
1 | Launch & Early Orbit | Solar array deployment is delayed | There is a risk that arrays do not deploy or latch on the nominal timeline, resulting in available energy becomes insufficient during LEOP. | Mitigate | Instrument deployments, preserve battery margin and prepare incremental recovery procedures. | 40% | 1840 | 5400 | 7180 | 2160
2 | Launch & Early Orbit | Range safety requirements expand | There is a risk that range safety imposes new analysis, inhibit or documentation requirements, resulting in late hardware and procedural changes are needed. | Accept | Engage range safety early and track compliance evidence as scheduled deliverables. | 40% | 1210 | 4223.3333 | 5730 | 1689.3333
3 | Launch & Early Orbit | Initial acquisition takes longer | There is a risk that ground stations do not acquire the spacecraft within the expected passes, resulting in battery, thermal or attitude margins erode. | Mitigate | Arrange geographically diverse stations and rehearse search patterns and contingency commanding. | 40% | 1470 | 4403.3333 | 5870 | 1761.3333
4 | Launch & Early Orbit | Interface adapter changes | There is a risk that the separation system or adapter interface changes after spacecraft design freeze, resulting in mechanical and electrical redesign delays shipment. | Mitigate | Freeze interface control data contractually and maintain a qualified adapter contingency. | 40% | 1530 | 5083.3333 | 6860 | 2033.3333
5 | Launch & Early Orbit | Launch failure causes mission loss | There is a risk that the launch vehicle fails before successful deployment, resulting in the spacecraft and invested development cost are lost. | Transfer | Transfer a portion of exposure through launch insurance and preserve design records and critical spares for a potential rebuild. | 40% | 1070 | 4323.3333 | 5950 | 1729.3333
6 | Launch & Early Orbit | Separation is not confirmed | There is a risk that telemetry does not clearly verify separation and initial state, resulting in recovery actions are delayed during a critical period. | Mitigate | Use independent separation indications and pre-plan time-tagged safe sequences. | 40% | 1140 | 3506.6667 | 4690 | 1402.6667
7 | Launch & Early Orbit | Launch loads exceed qualification | There is a risk that updated coupled-loads analysis produces environments above tested levels, resulting in reinforcement or repeat qualification is needed. | Mitigate | Obtain preliminary environments early and retain structural margins through final loads cycles. | 40% | 1180 | 4073.3333 | 5520 | 1629.3333
8 | Launch & Early Orbit | Upper-stage contamination affects payload | There is a risk that plume or venting products reach sensitive surfaces, resulting in payload performance is degraded immediately after launch. | Mitigate | Analyze contamination geometry and negotiate attitude, venting and separation constraints. | 40% | 1320 | 3593.3333 | 4730 | 1437.3333
9 | Launch & Early Orbit | Rideshare payload creates constraints | There is a risk that another payload introduces schedule, contamination or operational restrictions, resulting in mission design and launch processing become more complex. | Accept | Define rideshare constraints in contracts and retain a compatible standalone or alternate-manifest option. | 40% | 850 | 3916.6667 | 5450 | 1566.6667
10 | Manufacturing, Assembly & Test | Protoflight approach proves too aggressive | There is a risk that combined qualification and acceptance testing leaves inadequate recovery margin, resulting in a test failure threatens delivery of the only flight unit. | Mitigate | Select protoflight only with mature design evidence and retain spare parts, repair plans and schedule reserve. | 60% | 710 | 2130 | 2840 | 1278
11 | Manufacturing, Assembly & Test | Qualification test causes damage | There is a risk that qualification loads damage flight-like hardware or reveal insufficient margin, resulting in replacement hardware and repeat testing are required. | Accept | Validate models and fixtures, use staged testing and hold readiness reviews with clear abort criteria. | 60% | 750 | 2483.3333 | 3350 | 1490
12 | Manufacturing, Assembly & Test | Acceptance test limits are incorrect | There is a risk that pass-fail limits do not reflect requirements or measurement uncertainty, resulting in good hardware is rejected or defective hardware is accepted. | Mitigate | Derive limits from controlled requirements and validate them through independent review and dry runs. | 60% | 520 | 2113.3333 | 2910 | 1268
13 | Launch & Early Orbit | Payload performance is reduced | There is a risk that final launch trajectory or rideshare constraints reduce delivered mass or orbit performance, resulting in spacecraft redesign or added propulsion is required. | Mitigate | Confirm performance with provider analyses and preserve mass and delta-v margin until interface closure. | 40% | 880 | 3166.6667 | 4310 | 1266.6667
14 | Launch & Early Orbit | Collision avoidance is required during LEOP | There is a risk that a conjunction occurs before routine operations are established, resulting in commissioning is interrupted and propellant is consumed. | Mitigate | Establish conjunction support before launch and predefine rapid manoeuvre authority. | 40% | 990 | 2763.3333 | 3650 | 1105.3333
15 | Manufacturing, Assembly & Test | Instrumentation produces invalid data | There is a risk that sensors, calibration or data acquisition fail during a major test, resulting in test results are unusable and must be repeated. | Mitigate | Calibrate instrumentation, use redundant critical measurements and perform pre-test end-to-end checks. | 60% | 560 | 1726.6667 | 2310 | 1036
16 | Schedule & Program Management | Partner milestones are misaligned | There is a risk that international or interdepartmental partner schedules do not support mission need dates, resulting in interfaces and deliveries arrive late. | Mitigate | Maintain an integrated partner milestone register and negotiate binding need dates and escalation paths. | 50% | 580 | 2186.6667 | 2990 | 1093.3333
17 | Launch & Early Orbit | Weather causes prolonged delay | There is a risk that weather repeatedly violates launch constraints, resulting in campaign and standby costs increase. | Mitigate | Use historical weather in schedule risk analysis and negotiate clear standby and demobilization terms. | 40% | 1000 | 3133.3333 | 4200 | 1253.3333
18 | Manufacturing, Assembly & Test | Workmanship defects require rework | There is a risk that manufacturing or assembly defects are discovered during inspection or test, resulting in hardware must be repaired, rebuilt or retested. | Mitigate | Use certified processes, in-process inspections and first-article demonstrations for critical workmanship. | 60% | 590 | 2030 | 2750 | 1218
19 | Manufacturing, Assembly & Test | Supplier process change is undisclosed | There is a risk that a supplier changes materials, tooling or process without timely notice, resulting in delivered parts differ from the qualified configuration. | Accept | Require change notification clauses and audit critical supplier configuration records. | 60% | 660 | 1793.3333 | 2360 | 1076
20 | Schedule & Program Management | Change control backlog grows | There is a risk that engineering changes wait too long for assessment and disposition, resulting in work proceeds against obsolete baselines. | Accept | Staff the change board to demand and fast-track time-critical changes with documented authority. | 50% | 710 | 2276.6667 | 3060 | 1138.3333
21 | Schedule & Program Management | Critical path has no float | There is a risk that major integration and test activities have no schedule reserve, resulting in any anomaly delays launch readiness. | Mitigate | Protect management reserve and create alternate sequencing for recoverable work. | 50% | 740 | 1866.6667 | 2430 | 933.3333
22 | Schedule & Program Management | Risk register is not actively managed | There is a risk that risks are recorded but not linked to actions, schedule and reserve, resulting in known exposure materializes without preparation. | Mitigate | Review top risks monthly and link funded mitigations to owners, dates and schedule activities. | 50% | 510 | 2230 | 3090 | 1115
23 | Manufacturing, Assembly & Test | Test procedure errors damage hardware | There is a risk that an incorrect step, limit or configuration in a procedure causes an incident, resulting in flight hardware requires repair or replacement. | Mitigate | Independently verify hazardous steps, use peer-reviewed automated limits and rehearse with simulators. | 60% | 430 | 1976.6667 | 2750 | 1186
24 | Launch & Early Orbit | Launch price escalates | There is a risk that provider pricing, surcharges or mission-specific services exceed the estimate, resulting in launch procurement exceeds the approved budget. | Accept | Secure pricing assumptions contractually and hold a launch-specific management reserve. | 40% | 630 | 2356.6667 | 3220 | 942.6667
25 | Launch & Early Orbit | LEOP staffing is insufficient | There is a risk that specialists are unavailable across continuous early-orbit shifts, resulting in anomalies are handled slowly and fatigue increases error rates. | Mitigate | Develop a staffed shift plan with backups and run full-duration simulations. | 40% | 720 | 2926.6667 | 4030 | 1170.6667
26 | Schedule & Program Management | Earned value data are unreliable | There is a risk that progress claims do not reflect objective completion, resulting in management reacts late to performance problems. | Mitigate | Define measurable completion criteria and validate schedule and cost status through surveillance. | 50% | 550 | 1836.6667 | 2480 | 918.3333
27 | Manufacturing, Assembly & Test | Long-lead parts arrive late | There is a risk that critical electronic, optical or mechanical parts miss required delivery dates, resulting in assembly and test activities are delayed. | Mitigate | Authorize early procurement, track supplier milestones and qualify alternates for schedule-critical parts. | 60% | 450 | 1616.6667 | 2200 | 970
28 | Manufacturing, Assembly & Test | Late engineering change disrupts build | There is a risk that a design change is released after fabrication has started, resulting in parts are scrapped and assembly sequencing is reworked. | Mitigate | Use change cut-off criteria and assess inventory, tooling, test and schedule impacts before approval. | 60% | 510 | 1410 | 1860 | 846
29 | Schedule & Program Management | Requirements baseline is delayed | There is a risk that stakeholders cannot agree on the requirements baseline, resulting in design work proceeds on unstable assumptions. | Accept | Time-box resolution, elevate unresolved trades and baseline controlled assumptions where evidence is incomplete. | 50% | 580 | 2113.3333 | 2880 | 1056.6667
30 | Schedule & Program Management | Work packages are poorly defined | There is a risk that scope, interfaces and completion criteria are unclear at control-account level, resulting in estimates and performance measures are unreliable. | Mitigate | Use a controlled work breakdown structure and objective work-package exit criteria. | 50% | 640 | 1880 | 2500 | 940
31 | Launch & Early Orbit | Launch-site facilities are inadequate | There is a risk that cleanliness, power, handling or test capabilities differ from assumptions, resulting in additional equipment and campaign time are required. | Mitigate | Survey the site, define facility interfaces and ship verified portable support equipment. | 40% | 710 | 2290 | 3080 | 916
32 | Manufacturing, Assembly & Test | Non-conformance backlog grows | There is a risk that material review boards cannot disposition defects as quickly as they are found, resulting in hardware flow stops and risk accumulates. | Accept | Set disposition turnaround targets, staff boards during peak testing and trend recurring defect causes. | 60% | 520 | 1626.6667 | 2180 | 976
33 | People, Safety & Security | Physical security is breached | There is a risk that unauthorized access occurs at a laboratory, control centre or storage site, resulting in hardware or information is damaged, altered or stolen. | Mitigate | Layer access control, surveillance and inventory checks, and investigate anomalies promptly. | 60% | 450 | 1550 | 2100 | 930
34 | Schedule & Program Management | Management reserve is consumed early | There is a risk that reserve is used before high-risk development and test phases, resulting in later problems have no funded response. | Mitigate | Set reserve release authority and monitor drawdown against the remaining risk profile. | 50% | 420 | 1446.6667 | 1960 | 723.3333
35 | Manufacturing, Assembly & Test | Foreign object debris is discovered | There is a risk that debris remains inside flight hardware after assembly, resulting in short circuits, mechanism jams or contamination occur. | Mitigate | Apply tool and part accountability, borescope inspections and controlled close-out procedures. | 60% | 380 | 1553.3333 | 2140 | 932
36 | People, Safety & Security | Unsafe handling injures personnel | There is a risk that hazardous energy, lifting, propellant or cleanroom activities are inadequately controlled, resulting in people are harmed and work is suspended. | Mitigate | Complete hazard analyses, certify procedures and equipment, and enforce stop-work authority. | 60% | 470 | 1283.3333 | 1690 | 770
37 | People, Safety & Security | Organizational restructuring removes capacity | There is a risk that a reorganization changes priorities, reporting lines or available staff, resulting in continuity and decision speed decline. | Accept | Document commitments, preserve core roles and brief new authorities on mission decisions and risks. | 60% | 330 | 1523.3333 | 2120 | 914
38 | Launch & Early Orbit | Launch vehicle schedule slips | There is a risk that the selected launch vehicle is not available in the required window, resulting in storage, staffing and mission schedule costs increase. | Mitigate | Maintain schedule liaison with the provider and evaluate alternate windows and compatible vehicles. | 40% | 690 | 1736.6667 | 2260 | 694.6667
39 | Launch & Early Orbit | Initial orbit differs from plan | There is a risk that injection dispersions exceed assumptions, resulting in commissioning and orbit correction consume additional time and propellant. | Accept | Analyze worst-case dispersions and pre-authorize correction strategies with sufficient reserve. | 40% | 480 | 2080 | 2880 | 832
40 | Schedule & Program Management | Decision cycle is too slow | There is a risk that governance and technical decisions exceed planned turnaround times, resulting in teams wait or proceed at risk. | Mitigate | Set decision deadlines, pre-brief authorities and document delegated thresholds. | 50% | 440 | 1673.3333 | 2290 | 836.6667
41 | Schedule & Program Management | Independent review is scheduled too late | There is a risk that external reviewers identify fundamental issues after design commitments, resulting in correction is expensive and disruptive. | Accept | Plan independent reviews before irreversible decisions and provide complete evidence early. | 50% | 490 | 1470 | 1960 | 735
42 | People, Safety & Security | Supply-chain cyber compromise occurs | There is a risk that vendor software or remote access introduces malicious code, resulting in mission systems are compromised before delivery. | Mitigate | Require secure development evidence, scan deliverables and isolate supplier access. | 60% | 350 | 1263.3333 | 1720 | 758
43 | Manufacturing, Assembly & Test | Cleanroom capacity is insufficient | There is a risk that cleanroom space, classification or operating hours cannot support the integration plan, resulting in parallel work is prevented and the schedule extends. | Mitigate | Confirm capacity, book shifts and establish overflow or partner-facility options. | 60% | 390 | 1250 | 1680 | 750
44 | Regulatory, Environmental & External | Orbital debris rules tighten | There is a risk that new debris-mitigation requirements apply before launch, resulting in design, analysis or disposal capability must change. | Mitigate | Track regulatory developments and design to a conservative disposal and passivation standard. | 40% | 570 | 1703.3333 | 2270 | 681.3333
45 | Regulatory, Environmental & External | Data policy limits distribution | There is a risk that open-data, sovereignty or security rules conflict, resulting in science products cannot be distributed as planned. | Mitigate | Approve a data policy and classify products and release timelines before system design is finalized. | 40% | 630 | 2103.3333 | 2840 | 841.3333
46 | Schedule & Program Management | Cost estimate is immature | There is a risk that the estimate relies on incomplete engineering data and unsupported assumptions, resulting in funding decisions use false precision. | Mitigate | Document estimate maturity, apply uncertainty ranges and update the baseline as design data mature. | 50% | 500 | 1666.6667 | 2250 | 833.3333
47 | People, Safety & Security | Partner clearances are delayed | There is a risk that personnel cannot obtain required site or information access, resulting in collaboration and integration activities slip. | Mitigate | Initiate clearances early and structure unclassified or escorted work packages as contingencies. | 60% | 370 | 1036.6667 | 1370 | 622
48 | People, Safety & Security | Emergency response is inadequate | There is a risk that the facility response plan does not address mission-specific hazards, resulting in an incident has greater human and program consequences. | Mitigate | Coordinate mission hazards with facility responders and conduct realistic drills. | 60% | 420 | 1300 | 1740 | 780
49 | Regulatory, Environmental & External | Space weather exceeds design basis | There is a risk that a severe solar event creates radiation and charging beyond nominal assumptions, resulting in hardware degrades or operations are suspended. | Mitigate | Use alert services, safe configurations and design margins based on credible extreme environments. | 40% | 420 | 1686.6667 | 2320 | 674.6667
50 | Launch & Early Orbit | Export or customs delays shipment | There is a risk that hardware or technical data are delayed by permits and border processes, resulting in launch-site campaign starts late. | Mitigate | Prepare classifications and permits early and use experienced logistics and customs support. | 40% | 460 | 1546.6667 | 2090 | 618.6667
51 | Manufacturing, Assembly & Test | Shipping damages flight hardware | There is a risk that transport loads or handling conditions exceed limits, resulting in hardware requires inspection, repair or replacement. | Mitigate | Qualify shipping containers, monitor environments and rehearse handling and customs steps. | 60% | 270 | 1170 | 1620 | 702
52 | People, Safety & Security | Ransomware disrupts development | There is a risk that malware encrypts engineering or operational systems, resulting in work stops and data may be lost. | Accept | Segment networks, maintain offline backups and rehearse incident recovery. | 60% | 270 | 1016.6667 | 1390 | 610
53 | Schedule & Program Management | Schedule estimates are optimistic | There is a risk that activity durations exclude learning, review and rework, resulting in milestones slip and labour costs increase. | Mitigate | Use historical durations, three-point estimates and schedule risk analysis for critical work. | 50% | 320 | 1280 | 1760 | 640
54 | Schedule & Program Management | Benefits assumptions change | There is a risk that the strategic or user need changes during development, resulting in the mission business case weakens. | Mitigate | Revalidate benefits at key decision points and maintain scalable mission options. | 50% | 360 | 1113.3333 | 1490 | 556.6667
55 | Regulatory, Environmental & External | Spectrum licence is delayed | There is a risk that frequency authorization is not obtained by the required date, resulting in communications testing or operations cannot proceed. | Accept | Submit coordinated applications early and maintain a compliant alternate frequency plan. | 40% | 450 | 1383.3333 | 1850 | 553.3333
56 | Regulatory, Environmental & External | Liability allocation is disputed | There is a risk that partners disagree about responsibility for damage or third-party claims, resulting in agreements and launch approvals are delayed. | Mitigate | Resolve cross-waivers and liability clauses before major commitments. | 40% | 500 | 1733.3333 | 2350 | 693.3333
57 | Supply Chain & Commercial | Intellectual property access is insufficient | There is a risk that the contract does not provide data or rights needed for operation and repair, resulting in the agency becomes dependent on the vendor. | Mitigate | Negotiate mission-lifecycle data rights, escrow and transition support before award. | 30% | 580 | 2066.6667 | 2810 | 620
58 | People, Safety & Security | Team fatigue causes errors | There is a risk that sustained overtime during integration or operations degrades judgement, resulting in mistakes, rework and safety incidents increase. | Mitigate | Set shift and overtime limits, plan surge staffing and monitor workload and fatigue indicators. | 60% | 280 | 1160 | 1600 | 696
59 | People, Safety & Security | International travel disruption occurs | There is a risk that key personnel cannot reach partner or launch sites, resulting in reviews, integration or campaign activities are delayed. | Mitigate | Cross-train local personnel and prepare secure remote-support and alternate-travel arrangements. | 60% | 320 | 1026.6667 | 1380 | 616
60 | Regulatory, Environmental & External | Radio-frequency coordination conflicts | There is a risk that another system has priority or harmful interference concerns, resulting in operating bands or contact plans must change. | Mitigate | Coordinate domestically and internationally early and retain tunable or alternate communication options. | 40% | 520 | 1420 | 1870 | 568
61 | Manufacturing, Assembly & Test | Ground support equipment is late | There is a risk that specialized test or handling equipment is not ready for hardware integration, resulting in acceptance testing and shipment are delayed. | Mitigate | Treat support equipment as deliverable hardware with its own requirements, schedule and acceptance tests. | 60% | 270 | 903.3333 | 1220 | 542
62 | Manufacturing, Assembly & Test | Spares are insufficient | There is a risk that critical components are damaged or fail with no replacement available, resulting in the program waits for a new production lot. | Mitigate | Identify high-risk spares using failure and lead-time analysis and procure them with flight hardware. | 60% | 310 | 1123.3333 | 1530 | 674
63 | Schedule & Program Management | Scope grows without funding | There is a risk that new objectives and features are approved without corresponding resources, resulting in budget and schedule baselines become unachievable. | Accept | Apply configuration control and require quantified cost and schedule impacts before scope approval. | 50% | 360 | 1253.3333 | 1700 | 626.6667
64 | Supply Chain & Commercial | Vendor estimate is understated | There is a risk that a vendor quotation omits non-recurring engineering, testing or support, resulting in contract value grows after award. | Mitigate | Require a priced work breakdown, assumptions and exclusions, and complete an independent estimate. | 30% | 610 | 1690 | 2230 | 507
65 | Supply Chain & Commercial | Material allocation favours other customers | There is a risk that a constrained supplier prioritizes larger commercial orders, resulting in mission components miss the production slot. | Accept | Secure allocation through advance commitments and monitor raw-material and fab capacity. | 30% | 680 | 2113.3333 | 2830 | 634
66 | People, Safety & Security | Phishing compromises accounts | There is a risk that mission personnel credentials are stolen, resulting in systems or sensitive communications are accessed. | Mitigate | Use phishing-resistant authentication, awareness exercises and conditional access controls. | 60% | 330 | 836.6667 | 1090 | 502
67 | Regulatory, Environmental & External | Space traffic environment worsens | There is a risk that conjunction frequency exceeds operational assumptions, resulting in analysis workload and avoidance manoeuvres increase. | Accept | Procure reliable tracking data and automate screening and decision support. | 40% | 390 | 1390 | 1890 | 556
68 | Supply Chain & Commercial | Export controls restrict collaboration | There is a risk that technical data or hardware cannot be transferred as planned, resulting in partner work and integration are delayed. | Mitigate | Classify controlled items early and structure compliant data, staffing and technical interfaces. | 30% | 440 | 1673.3333 | 2290 | 502
69 | Mission & Science | Calibration accuracy is insufficient | There is a risk that the calibration approach cannot achieve the required measurement accuracy, resulting in science products fail to meet uncertainty requirements. | Mitigate | Build a calibration error budget, test representative standards, and retain an in-flight cross-calibration capability. | 50% | 300 | 913.3333 | 1220 | 456.6667
70 | Mission & Science | Science team turnover removes knowledge | There is a risk that key investigators leave before knowledge and rationale are captured, resulting in science decisions are reopened and validation slows. | Mitigate | Document decision rationale, appoint deputies, and maintain succession coverage for each critical science role. | 50% | 330 | 1143.3333 | 1550 | 571.6667
71 | People, Safety & Security | Hiring takes longer than planned | There is a risk that specialized positions cannot be staffed when needed, resulting in work is delayed or shifted to expensive contractors. | Accept | Start staffing early and maintain contracting, secondment and training contingencies. | 60% | 210 | 910 | 1260 | 546
72 | People, Safety & Security | Training records are incomplete | There is a risk that required certifications cannot be demonstrated, resulting in personnel are removed from critical work until retrained. | Mitigate | Maintain a skills matrix with automated expiry alerts and verified records. | 60% | 240 | 800 | 1080 | 480
73 | Regulatory, Environmental & External | Remote sensing licence imposes constraints | There is a risk that operating or data-distribution conditions are more restrictive than assumed, resulting in mission utility or ground design is reduced. | Mitigate | Engage the licensing authority during concept development and implement controllable data-access modes. | 40% | 400 | 1126.6667 | 1490 | 450.6667
74 | Supply Chain & Commercial | Sole-source supplier fails | There is a risk that a single qualified supplier cannot deliver a critical item, resulting in the project faces redesign or a long production delay. | Mitigate | Assess supplier health, procure strategic spares and qualify a second source or redesign path. | 30% | 480 | 1946.6667 | 2680 | 584
75 | Supply Chain & Commercial | Subcontractor performance is opaque | There is a risk that the prime contractor lacks effective visibility into critical lower-tier suppliers, resulting in problems reach the project late. | Mitigate | Require flow-down reporting, critical-item reviews and direct access for high-risk subcontractors. | 30% | 540 | 1726.6667 | 2320 | 518
76 | Schedule & Program Management | Integrated schedule is incomplete | There is a risk that supplier and subsystem schedules omit dependencies and constraints, resulting in the critical path is misunderstood and delays are discovered late. | Mitigate | Maintain an integrated master schedule with logic quality checks and monthly critical-path reviews. | 50% | 360 | 973.3333 | 1280 | 486.6667
77 | Schedule & Program Management | Reporting burden displaces delivery | There is a risk that duplicative reporting consumes scarce technical and management effort, resulting in productive work slows without improving oversight. | Mitigate | Consolidate reports around authoritative data and tailor frequency to risk and decision need. | 50% | 250 | 1150 | 1600 | 575
78 | Manufacturing, Assembly & Test | Configuration control fails during integration | There is a risk that hardware, software or procedures are used in an unapproved configuration, resulting in test evidence becomes invalid or defects are introduced. | Accept | Use serialized as-built records and verify configuration at every test readiness gate. | 60% | 300 | 866.6667 | 1150 | 520
79 | Mission & Science | Instrument stability degrades | There is a risk that thermal or mechanical drift exceeds assumptions over an observation, resulting in data require more correction or become unusable. | Accept | Characterize drift in thermal-vacuum testing and implement on-board references and ground correction algorithms. | 50% | 350 | 943.3333 | 1240 | 471.6667
80 | Spacecraft & Payload Technical | Reaction wheels saturate frequently | There is a risk that disturbance torques exceed momentum-management assumptions, resulting in observations are interrupted and propellant use increases. | Mitigate | Update disturbance models and optimize wheel sizing, unloading logic and operational scheduling. | 15% | 910 | 2810 | 3760 | 421.5
81 | Spacecraft & Payload Technical | Redundancy architecture has common causes | There is a risk that redundant strings share hidden common failure modes, resulting in a single event defeats the intended fault tolerance. | Mitigate | Perform common-cause analysis and separate power, routing, software and environmental dependencies where practical. | 15% | 1030 | 3536.6667 | 4790 | 530.5
82 | Supply Chain & Commercial | Counterfeit parts enter supply chain | There is a risk that untrusted or obsolete components are substituted, resulting in reliability and certification are compromised. | Accept | Buy from authorized sources and apply traceability, inspection and authentication testing. | 30% | 560 | 1406.6667 | 1830 | 422
83 | Regulatory, Environmental & External | Pandemic restrictions recur | There is a risk that health restrictions reduce on-site staffing and travel, resulting in integration and launch campaign efficiency declines. | Mitigate | Preserve remote-work processes, cross-train local staff and plan protected critical shifts. | 40% | 290 | 1090 | 1490 | 436
84 | Software & Autonomy | Cybersecurity controls arrive late | There is a risk that security requirements are added after interfaces and architecture are fixed, resulting in major software and ground-system rework is required. | Mitigate | Perform threat modelling at architecture start and integrate security verification into each release. | 30% | 440 | 1346.6667 | 1800 | 404
85 | Mission & Science | Target catalogue is incomplete | There is a risk that the target catalogue is delivered late or lacks validated priorities, resulting in mission planning and performance analyses require rework. | Mitigate | Baseline a representative catalogue, define update cut-off dates, and validate priority rules with the science team. | 50% | 230 | 1050 | 1460 | 525
86 | Mission & Science | Data quality flags are inadequate | There is a risk that quality flags do not identify known measurement limitations, resulting in users draw incorrect conclusions from released data. | Mitigate | Define quality metadata with users, test it on simulated anomalies, and include it in product validation. | 50% | 260 | 933.3333 | 1270 | 466.6667
87 | People, Safety & Security | Insider threat compromises data | There is a risk that an authorized person intentionally or negligently exposes sensitive information, resulting in mission security and partner trust are damaged. | Mitigate | Apply least privilege, monitoring, training and rapid access revocation. | 60% | 240 | 893.3333 | 1220 | 536
88 | Spacecraft & Payload Technical | Electromagnetic interference exceeds limits | There is a risk that equipment emissions or susceptibility create interference, resulting in communications or measurements are corrupted. | Avoid | Maintain an EMC control plan, test high-risk unit combinations early, and reserve filtering and grounding fixes. | 15% | 1080 | 2940 | 3870 | 441
89 | Schedule & Program Management | Review actions remain open | There is a risk that major review findings are not closed before the next lifecycle stage, resulting in technical debt and uncertainty accumulate. | Mitigate | Assign owners and due dates, track closure evidence and block progression for critical actions. | 50% | 250 | 890 | 1210 | 445
90 | Supply Chain & Commercial | Bid competition is inadequate | There is a risk that too few compliant bids are received, resulting in price leverage falls and award may need to restart. | Mitigate | Conduct early market engagement and tailor requirements to preserve feasible competition. | 30% | 410 | 1370 | 1850 | 411
91 | Software & Autonomy | Navigation software diverges | There is a risk that estimation filters become unstable under off-nominal sensor conditions, resulting in pointing or trajectory errors grow. | Mitigate | Test Monte Carlo dispersions and sensor outages, and provide reset and alternate-estimator modes. | 30% | 510 | 1396.6667 | 1840 | 419
92 | Mission & Science | Science operations are understaffed | There is a risk that the science operations team is not staffed early enough to prepare and validate procedures, resulting in commissioning and routine planning are delayed. | Mitigate | Phase staffing into development, cross-train analysts, and rehearse operations using a mission simulator. | 50% | 270 | 763.3333 | 1010 | 381.6667
93 | Regulatory, Environmental & External | Launch-state authorization changes | There is a risk that the responsible state introduces new licensing or liability conditions, resulting in launch arrangements and insurance costs change. | Accept | Monitor the launch jurisdiction and preserve contractual flexibility for alternate providers. | 40% | 300 | 1240 | 1710 | 496
94 | Regulatory, Environmental & External | Policy priority shifts | There is a risk that government priorities move away from the mission theme, resulting in funding or approvals are reduced. | Mitigate | Maintain clear strategic alignment and scalable options with independently valuable outcomes. | 40% | 340 | 1100 | 1480 | 440
95 | Spacecraft & Payload Technical | Pointing performance is insufficient | There is a risk that attitude knowledge or control errors exceed the payload allocation, resulting in image quality or measurement accuracy is degraded. | Transfer | Maintain a pointing error budget, test representative sensors and actuators, and validate performance in simulation. | 15% | 710 | 3270 | 4550 | 490.5
96 | Spacecraft & Payload Technical | Clock stability is inadequate | There is a risk that timing drift or synchronization error exceeds the allocated budget, resulting in measurements and event reconstruction lose accuracy. | Mitigate | Budget end-to-end timing error and verify clock stability, synchronization and time-correlation processing. | 15% | 810 | 2896.6667 | 3940 | 434.5
97 | Manufacturing, Assembly & Test | Test facility is unavailable | There is a risk that a required thermal-vacuum, vibration or EMC facility is not available as scheduled, resulting in the integrated test campaign slips. | Mitigate | Reserve facilities early and maintain qualified alternate facilities and portable test configurations. | 60% | 180 | 613.3333 | 830 | 368
98 | Manufacturing, Assembly & Test | Integration access is inadequate | There is a risk that the physical design prevents installation, inspection or replacement of units, resulting in assembly labour and risk of damage increase. | Mitigate | Perform digital and physical accessibility reviews with technicians before design release. | 60% | 200 | 766.6667 | 1050 | 460
99 | Software & Autonomy | Memory corruption is not contained | There is a risk that software or radiation-induced corruption propagates through shared memory, resulting in multiple functions fail simultaneously. | Mitigate | Apply memory protection, checksums, scrubbing and partitioning, then inject faults during qualification. | 30% | 340 | 1553.3333 | 2160 | 466
100 | People, Safety & Security | Critical expertise is concentrated | There is a risk that only one person can perform or approve a mission-critical activity, resulting in absence or departure stops progress. | Mitigate | Identify single points of knowledge, assign deputies and require documented handover and paired work. | 60% | 240 | 706.6667 | 940 | 424
101 | People, Safety & Security | Workplace conflict impairs delivery | There is a risk that persistent conflict prevents constructive technical decisions, resulting in coordination slows and staff turnover increases. | Accept | Clarify roles, use facilitated decision processes and intervene early through management channels. | 60% | 170 | 583.3333 | 790 | 350
102 | Mission & Science | Observation concept proves infeasible | There is a risk that the planned observation cadence cannot be achieved within pointing, power or data constraints, resulting in the mission returns fewer useful observations than assumed. | Accept | Run end-to-end observing simulations early and reserve alternate cadence modes in the concept of operations. | 50% | 290 | 896.6667 | 1200 | 448.3333
103 | Mission & Science | Extended mission assumptions are optimistic | There is a risk that consumables and component life do not support the planned extended mission, resulting in expected lifetime science return is not achieved. | Mitigate | Separate prime and extended mission requirements and qualify life-limited items to a defined extension goal. | 50% | 200 | 753.3333 | 1030 | 376.6667
104 | Spacecraft & Payload Technical | Avionics interface incompatibility emerges | There is a risk that units implement inconsistent electrical or data interfaces, resulting in integration requires adapters, redesign or schedule-consuming troubleshooting. | Mitigate | Control interface documents, use interface simulators, and hold incremental compatibility tests before delivery. | 15% | 850 | 2363.3333 | 3120 | 354.5
105 | Supply Chain & Commercial | Supplier financial distress emerges | There is a risk that a key supplier restructures or ceases operations, resulting in deliveries, warranties and technical support are disrupted. | Mitigate | Monitor financial health and secure design data, work-in-progress rights and transition assistance. | 30% | 420 | 1553.3333 | 2120 | 466
106 | Regulatory, Environmental & External | Natural disaster affects key facility | There is a risk that wildfire, flood, earthquake or severe storm closes a critical site, resulting in hardware or operations are interrupted. | Mitigate | Assess site hazards, protect assets and maintain geographically separated backup capability. | 40% | 340 | 860 | 1120 | 344
107 | Software & Autonomy | Data compression loses science content | There is a risk that compression settings introduce unacceptable artefacts or information loss, resulting in science products fail quality criteria. | Accept | Validate compression with representative scenes and retain selectable lossless or lower-compression modes. | 30% | 400 | 1126.6667 | 1490 | 338
108 | Mission & Science | Field-of-view is obstructed | There is a risk that the final spacecraft configuration introduces unmodelled obscuration or contamination, resulting in usable science coverage is reduced. | Mitigate | Maintain a field-of-view keep-out model and verify it at configuration and accommodation reviews. | 50% | 210 | 863.3333 | 1190 | 431.6667
109 | Spacecraft & Payload Technical | Structural modes couple with launcher | There is a risk that spacecraft natural frequencies conflict with launch vehicle requirements, resulting in structural redesign and repeat testing are needed. | Avoid | Perform coupled-loads analysis early and reserve stiffness and mass for local reinforcement. | 15% | 880 | 2760 | 3700 | 414
110 | Spacecraft & Payload Technical | Micrometeoroid exposure is underestimated | There is a risk that debris or micrometeoroid flux exceeds design assumptions, resulting in critical hardware is damaged during the mission. | Transfer | Update environment models, add localized shielding and orient or schedule operations to reduce exposure. | 15% | 620 | 2320 | 3170 | 348
111 | Schedule & Program Management | Governance roles are unclear | There is a risk that sponsors, project leaders and functional authorities interpret accountability differently, resulting in decisions are duplicated or avoided. | Mitigate | Approve a responsibility matrix and decision map at project start and revisit it after organizational changes. | 50% | 260 | 813.3333 | 1090 | 406.6667
112 | Supply Chain & Commercial | Procurement approval is delayed | There is a risk that internal review and contracting take longer than the schedule assumes, resulting in critical work starts late. | Mitigate | Engage procurement during planning and maintain a realistic acquisition schedule with complete documentation. | 30% | 300 | 1046.6667 | 1420 | 314
113 | People, Safety & Security | Security classification changes | There is a risk that information is reclassified or assigned tighter handling restrictions, resulting in tools, facilities and collaboration methods require replacement. | Mitigate | Confirm classifications early and design separable data sets and compliant environments. | 60% | 170 | 656.6667 | 900 | 394
114 | Software & Autonomy | Software timing margins disappear | There is a risk that worst-case execution time exceeds allocations under peak load, resulting in deadlines are missed and control performance degrades. | Mitigate | Measure timing on target hardware and enforce task budgets with representative stress cases. | 30% | 420 | 1313.3333 | 1760 | 394
115 | Software & Autonomy | Licensing constrains deployment | There is a risk that software licensing terms restrict flight, partner or long-term operational use, resulting in replacement or renegotiation creates unplanned cost. | Mitigate | Review licence terms before selection and prefer transferable, supportable components. | 30% | 290 | 1103.3333 | 1510 | 331
116 | Spacecraft & Payload Technical | On-board computer capacity is inadequate | There is a risk that processing or memory demand grows beyond flight-computer capacity, resulting in software features are removed or hardware is replaced. | Mitigate | Profile representative workloads early and retain processor, memory and timing margin with growth thresholds. | 15% | 650 | 2663.3333 | 3670 | 399.5
117 | Regulatory, Environmental & External | Indigenous consultation is incomplete | There is a risk that activities affecting rights or lands proceed without sufficient consultation, resulting in approvals, trust and schedule are jeopardized. | Mitigate | Begin meaningful consultation early and integrate commitments into mission plans and contracts. | 40% | 210 | 923.3333 | 1280 | 369.3333
118 | Regulatory, Environmental & External | Records obligations are unmet | There is a risk that mission records are not captured in approved repositories, resulting in evidence is lost and audits require reconstruction. | Accept | Define records classes, automate transfer where possible and audit compliance at reviews. | 40% | 240 | 813.3333 | 1100 | 325.3333
119 | Mission & Science | Science traceability breaks down | There is a risk that the science traceability matrix is incomplete or not maintained, resulting in design features cannot be justified against mission objectives. | Mitigate | Assign an owner to the traceability matrix and reconcile it at monthly science and systems-engineering reviews. | 50% | 220 | 700 | 940 | 350
120 | Mission & Science | Seasonal observation window is missed | There is a risk that development or launch delays cause the mission to miss a critical seasonal target, resulting in science return is deferred or reduced. | Accept | Model seasonal windows in the integrated schedule and protect launch and commissioning margin around critical dates. | 50% | 240 | 606.6667 | 790 | 303.3333
121 | Ground Segment & Operations | Mission control software is late | There is a risk that ground-system functions are not ready for spacecraft integration, resulting in end-to-end tests and operator training slip. | Mitigate | Deliver core command and telemetry functions incrementally and test against spacecraft simulators. | 20% | 600 | 1506.6667 | 1960 | 301.3333
122 | Ground Segment & Operations | Consumables trend is detected late | There is a risk that operations do not accurately estimate propellant, battery or mechanism life, resulting in mission-life decisions are made too late. | Mitigate | Establish calibrated trending models and review life-limited resources at regular health meetings. | 20% | 420 | 1806.6667 | 2500 | 361.3333
123 | Software & Autonomy | Simulation fidelity is insufficient | There is a risk that the software test environment omits important hardware or environmental behaviour, resulting in defects appear only during late system testing or flight. | Mitigate | Correlate simulators against hardware, document fidelity limits and add hardware-in-the-loop coverage for critical paths. | 30% | 310 | 1276.6667 | 1760 | 383
124 | Supply Chain & Commercial | Inflation exceeds escalation assumptions | There is a risk that labour and material prices rise faster than the estimate, resulting in multi-year contract and internal costs exceed plan. | Mitigate | Update escalation indices and use contract clauses and reserves matched to exposure. | 30% | 310 | 1196.6667 | 1640 | 359
125 | Supply Chain & Commercial | Cloud service pricing changes | There is a risk that usage or vendor pricing grows beyond forecast, resulting in ground-system operating costs exceed plan. | Mitigate | Set usage budgets and alerts, optimize architecture and preserve portability for major services. | 30% | 350 | 1050 | 1400 | 315
126 | Ground Segment & Operations | Command authorization is bypassed | There is a risk that weak workflow or access control allows an unauthorized command, resulting in spacecraft safety or mission objectives are compromised. | Accept | Enforce role-based approval, strong authentication and auditable command release. | 20% | 450 | 1496.6667 | 2020 | 299.3333
127 | Spacecraft & Payload Technical | Thermal design lacks margin | There is a risk that hot or cold case temperatures exceed component limits, resulting in qualification failures or on-orbit degradation occur. | Mitigate | Correlate thermal models with testing and retain heater, radiator and operational constraint margins. | 15% | 670 | 2163.3333 | 2910 | 324.5
128 | Spacecraft & Payload Technical | Contamination degrades payload | There is a risk that molecular or particulate contamination reaches sensitive surfaces, resulting in throughput, thermal performance or measurement accuracy declines. | Avoid | Implement a contamination-control plan with budgets, witness samples, bake-out and monitored clean handling. | 15% | 750 | 1890 | 2460 | 283.5
129 | People, Safety & Security | Privacy obligations are overlooked | There is a risk that mission services collect personal information without adequate controls, resulting in compliance work and system changes are required. | Mitigate | Perform a privacy assessment and minimize, protect and retain personal data only as authorized. | 60% | 190 | 616.6667 | 830 | 370
130 | Mission & Science | Reference data are unavailable | There is a risk that external reference data needed to interpret observations are unavailable or restricted, resulting in science products cannot be validated on schedule. | Mitigate | Secure data-sharing agreements and identify independent backup reference sources. | 50% | 150 | 663.3333 | 920 | 331.6667
131 | Regulatory, Environmental & External | Sanctions affect supplier access | There is a risk that new sanctions prohibit transactions or technical support, resulting in contracts must be terminated or replaced. | Mitigate | Screen ownership and jurisdictions continuously and include termination and transition clauses. | 40% | 240 | 893.3333 | 1220 | 357.3333
132 | Software & Autonomy | Fault protection masks root causes | There is a risk that fault-management actions overwrite evidence needed for diagnosis, resulting in recovery takes longer and recurrence is likely. | Accept | Preserve event logs and snapshots, test fault interactions, and provide ground-selectable diagnostic modes. | 30% | 320 | 1026.6667 | 1380 | 308
133 | Software & Autonomy | Logging volume exceeds storage | There is a risk that diagnostic and science logs fill allocated storage during anomalies, resulting in new data are lost or essential logs are overwritten. | Mitigate | Set quotas and priorities, compress logs, and test extended anomaly scenarios. | 30% | 360 | 900 | 1170 | 270
134 | Ground Segment & Operations | Link margin is insufficient | There is a risk that actual antenna, weather or interference performance reduces communications margin, resulting in data volume and commanding reliability decline. | Mitigate | Validate link budgets with measured parameters and preserve lower-rate and alternate-station modes. | 20% | 470 | 1730 | 2360 | 346
135 | Ground Segment & Operations | Encryption keys are mishandled | There is a risk that keys expire, are lost or are exposed, resulting in secure commanding or data access is interrupted. | Mitigate | Use controlled key management, dual custody, tested rollover and emergency recovery procedures. | 20% | 530 | 1543.3333 | 2050 | 308.6667
136 | Supply Chain & Commercial | Minimum order quantities increase cost | There is a risk that specialized materials or parts require purchases beyond actual need, resulting in procurement cost and obsolete inventory increase. | Accept | Aggregate demand across units and missions and negotiate lot-sizing or supplier-held inventory. | 30% | 350 | 1170 | 1580 | 351
137 | Spacecraft & Payload Technical | Detector performance degrades | There is a risk that detector noise, defects or radiation damage exceed predictions, resulting in science sensitivity and calibration stability decline. | Transfer | Screen detectors, characterize radiation response, and include annealing, redundancy or correction algorithms where feasible. | 15% | 480 | 2080 | 2880 | 312
138 | Mission & Science | Science requirements remain ambiguous | There is a risk that science requirements are not made measurable and stable before design decisions, resulting in instrument performance is optimized against the wrong success criteria. | Mitigate | Facilitate requirement workshops, establish measurable thresholds and objectives, and maintain bidirectional traceability through each review. | 50% | 160 | 533.3333 | 720 | 266.6667
139 | Mission & Science | Planetary protection constraints expand | There is a risk that planetary protection classification or implementation requirements become more stringent, resulting in additional sterilization, documentation and verification work is required. | Mitigate | Engage the responsible authority early and maintain a compliant design option with explicit cost and schedule reserves. | 50% | 180 | 660 | 900 | 330
140 | Ground Segment & Operations | Telemetry archive loses data | There is a risk that archive failures or retention errors delete raw mission data, resulting in anomaly evidence and science records cannot be recovered. | Mitigate | Use replicated immutable storage, integrity checks and tested restoration procedures. | 20% | 350 | 1203.3333 | 1630 | 240.6667
141 | Software & Autonomy | Software configuration is inconsistent | There is a risk that development, test and flight environments use different versions or parameters, resulting in results cannot be reproduced and defects escape. | Mitigate | Automate configuration baselines and require signed release manifests for every test and upload. | 30% | 230 | 983.3333 | 1360 | 295
142 | Regulatory, Environmental & External | Environmental assessment expands | There is a risk that additional environmental evidence or consultation is required, resulting in approval and site work are delayed. | Mitigate | Engage authorities early and maintain complete environmental data and mitigation commitments. | 40% | 240 | 693.3333 | 920 | 277.3333
143 | Regulatory, Environmental & External | Accessibility requirements are added late | There is a risk that public or internal digital services do not meet accessibility standards, resulting in interfaces and content require redesign. | Mitigate | Include accessibility criteria, user testing and compliance evidence from the first release. | 40% | 160 | 573.3333 | 780 | 229.3333
144 | Spacecraft & Payload Technical | Power demand exceeds generation | There is a risk that peak or average power demand exceeds available generation and storage, resulting in operating modes must be curtailed or hardware redesigned. | Mitigate | Maintain mode-based power budgets, test worst-case profiles, and preserve load-shedding and array-sizing options. | 15% | 500 | 1653.3333 | 2230 | 248
145 | Spacecraft & Payload Technical | Harness design grows late | There is a risk that cable routing, connectors and service loops are underestimated, resulting in mass increases and integration access deteriorates. | Mitigate | Release routing models early, maintain harness margins, and conduct physical fit checks before final fabrication. | 15% | 560 | 2046.6667 | 2790 | 307
146 | Supply Chain & Commercial | Foreign exchange increases costs | There is a risk that exchange rates move adversely before foreign-currency payments, resulting in approved funding buys less contracted work. | Mitigate | Use hedging where permitted, stage commitments and hold currency contingency. | 30% | 220 | 880 | 1210 | 264
147 | Supply Chain & Commercial | Insurance coverage contains exclusions | There is a risk that policy wording excludes a material mission failure scenario, resulting in expected financial recovery is unavailable. | Mitigate | Use specialist review and compare exclusions, deductibles and recovery timing before placement. | 30% | 250 | 763.3333 | 1020 | 229
148 | People, Safety & Security | Hazard controls are not verified | There is a risk that identified safety controls exist only in documentation, resulting in a hazardous condition remains during test or operations. | Accept | Track controls to objective verification evidence and independently close safety actions. | 60% | 110 | 436.6667 | 600 | 262
149 | Ground Segment & Operations | Ground station availability is lower | There is a risk that scheduled contacts are displaced or unavailable, resulting in commands and science data delivery are delayed. | Accept | Contract diverse stations, monitor service levels and retain emergency contact capacity. | 20% | 370 | 1410 | 1930 | 282
150 | Ground Segment & Operations | Frequency interference disrupts contacts | There is a risk that external emitters interfere with uplink or downlink, resulting in contacts fail or data must be retransmitted. | Mitigate | Coordinate spectrum use, monitor interference and provide alternate rates, sites or frequencies where permitted. | 20% | 410 | 1243.3333 | 1660 | 248.6667
151 | Mission & Science | Science algorithm maturity is low | There is a risk that key retrieval or processing algorithms remain below the maturity assumed in the schedule, resulting in late algorithm changes drive redesign and reprocessing. | Accept | Prototype algorithms with representative data and hold algorithm-readiness reviews before freezing interfaces. | 50% | 180 | 526.6667 | 700 | 263.3333
152 | Software & Autonomy | Autonomy logic behaves unexpectedly | There is a risk that autonomous decisions encounter states not represented in test scenarios, resulting in the spacecraft enters an unsafe or unproductive mode. | Mitigate | Use model-based scenario testing, independent logic review and conservative fallback states. | 30% | 240 | 786.6667 | 1060 | 236
153 | Software & Autonomy | Machine-learning model is unverified | There is a risk that an on-board model performs poorly outside its training distribution, resulting in autonomous classifications or decisions become unreliable. | Accept | Define an operational envelope, test independent datasets and retain deterministic override logic. | 30% | 270 | 976.6667 | 1330 | 293
154 | Data & Science Products | Algorithm changes break comparability | There is a risk that processing updates create discontinuities in the science record, resulting in trend analysis and published conclusions are affected. | Mitigate | Version algorithms and products, quantify changes and reprocess the archive when scientifically necessary. | 20% | 440 | 1293.3333 | 1720 | 258.6667
155 | Data & Science Products | Data rights delay release | There is a risk that partner or commercial rights are not resolved, resulting in products cannot be released on the planned schedule. | Mitigate | Agree ownership, embargo and licensing terms before data collection begins. | 20% | 310 | 1070 | 1450 | 214
156 | Ground Segment & Operations | Time synchronization is inconsistent | There is a risk that ground sites and processing systems use inconsistent time sources or conventions, resulting in telemetry correlation and science timing are corrupted. | Mitigate | Use authoritative time services and verify end-to-end timestamp handling. | 20% | 430 | 1416.6667 | 1910 | 283.3333
157 | Spacecraft & Payload Technical | Optical alignment shifts | There is a risk that launch or thermal loads disturb payload alignment, resulting in instrument performance falls below specification. | Avoid | Use stable materials, conduct alignment tests across environments, and provide an in-flight calibration method. | 15% | 560 | 1626.6667 | 2160 | 244
158 | Data & Science Products | Data latency misses user need | There is a risk that processing and distribution take longer than the operational decision window, resulting in products lose practical value. | Mitigate | Measure end-to-end latency and optimize the critical path with near-real-time product tiers. | 20% | 330 | 1270 | 1740 | 254
159 | Mission & Science | Sample return integrity is compromised | There is a risk that the collected sample or science material is altered during handling or return, resulting in scientific value is materially reduced. | Mitigate | Define contamination-control requirements and verify the complete custody and handling chain through rehearsals. | 50% | 130 | 490 | 670 | 245
160 | Regulatory, Environmental & External | Geopolitical relations disrupt partnership | There is a risk that government policy restricts collaboration with a partner or supplier, resulting in data, hardware or services become unavailable. | Accept | Segment critical dependencies and maintain domestic or allied alternatives for essential capabilities. | 40% | 160 | 613.3333 | 840 | 245.3333
161 | Software & Autonomy | Command validation is incomplete | There is a risk that invalid or conflicting commands are not rejected safely, resulting in equipment damage or mission interruption can occur. | Mitigate | Implement layered command checks and test malformed, stale and out-of-sequence commands. | 30% | 270 | 776.6667 | 1030 | 233
162 | Supply Chain & Commercial | Warranty ends before launch | There is a risk that schedule delays consume the warranty period before hardware is used, resulting in repairs and recertification become project costs. | Mitigate | Tie warranty start to acceptance or launch and price extension options. | 30% | 240 | 820 | 1110 | 246
163 | Ground Segment & Operations | Partner ground service is withdrawn | There is a risk that a partner changes priorities or stops providing agreed services, resulting in coverage and data delivery are reduced. | Accept | Formalize service commitments and maintain a commercial or internal backup option. | 20% | 310 | 963.3333 | 1290 | 192.6667
164 | Data & Science Products | Calibration database is corrupted | There is a risk that incorrect constants or versioning enter the operational calibration store, resulting in large volumes of products are processed incorrectly. | Accept | Use versioned immutable calibration records, approvals and automated validity checks. | 20% | 350 | 1050 | 1400 | 210
165 | Data & Science Products | Reprocessing demand is underestimated | There is a risk that calibration or algorithm updates require more compute and labour than planned, resulting in backlogs delay consistent archive releases. | Mitigate | Benchmark full-volume reprocessing and reserve scalable compute and campaign staffing. | 20% | 390 | 1303.3333 | 1760 | 260.6667
166 | Spacecraft & Payload Technical | Payload mass exceeds allocation | There is a risk that payload mass growth consumes spacecraft and launch margins, resulting in redesign or a more expensive launch configuration is required. | Transfer | Track a controlled mass budget, apply phase-appropriate margins, and trigger design trades at predefined thresholds. | 15% | 340 | 1193.3333 | 1620 | 179
167 | Spacecraft & Payload Technical | Mechanism fails to deploy | There is a risk that a solar array, antenna, cover or boom does not fully deploy, resulting in the mission loses power, communications or payload capability. | Mitigate | Use high-heritage mechanisms, test repeated deployments under representative conditions, and add deployment telemetry and contingency logic. | 15% | 390 | 1503.3333 | 2060 | 225.5
168 | Data & Science Products | User demand exceeds service capacity | There is a risk that product portals and APIs receive more traffic than planned, resulting in access slows or fails during major events. | Mitigate | Load-test services, use elastic capacity and prioritize operationally critical users. | 20% | 260 | 1033.3333 | 1420 | 206.6667
169 | Ground Segment & Operations | Control centre outage interrupts service | There is a risk that power, network or facility failure makes the primary centre unavailable, resulting in spacecraft monitoring and commanding are interrupted. | Mitigate | Maintain a tested backup control capability and regularly exercise failover. | 20% | 320 | 1100 | 1490 | 220
170 | Software & Autonomy | Requirements volatility drives rework | There is a risk that software requirements continue changing after architecture definition, resulting in code, tests and documentation require repeated revision. | Mitigate | Establish change control, prototype uncertain functions, and defer discretionary features to later releases. | 30% | 160 | 573.3333 | 780 | 172
171 | Software & Autonomy | Patch capability is inadequate | There is a risk that the mission cannot safely update defective flight software, resulting in known faults persist or require costly operational workarounds. | Mitigate | Design a recoverable dual-bank update process and rehearse upload, rollback and verification. | 30% | 190 | 723.3333 | 990 | 217
172 | Data & Science Products | Metadata are incomplete | There is a risk that products lack consistent provenance, quality and processing metadata, resulting in users cannot interpret or reproduce results. | Mitigate | Adopt controlled metadata standards and validate them automatically at ingestion. | 20% | 270 | 836.6667 | 1120 | 167.3333
173 | Data & Science Products | User requirements are misunderstood | There is a risk that science and operational users need different formats or timeliness than assumed, resulting in products require late redesign. | Accept | Validate prototypes with representative users and baseline product-level requirements. | 20% | 310 | 1056.6667 | 1430 | 211.3333
174 | Mission & Science | Background environment is underestimated | There is a risk that stray light, radiation or environmental background exceeds the assumed level, resulting in signal-to-noise performance is degraded. | Mitigate | Update environmental models, test worst-case backgrounds, and preserve shielding and observing-window options. | 50% | 120 | 366.6667 | 490 | 183.3333
175 | Mission & Science | External observatory coordination fails | There is a risk that coordinated observations from partner facilities are not available, resulting in planned multi-platform investigations lose value. | Accept | Obtain written observing commitments and develop standalone science cases that do not depend on partner availability. | 50% | 140 | 453.3333 | 610 | 226.6667
176 | Supply Chain & Commercial | Contract incentives are misaligned | There is a risk that commercial terms reward delivery speed over quality or lifecycle performance, resulting in defects and downstream costs increase. | Accept | Align incentives with verified technical outcomes and balanced cost, schedule and quality measures. | 30% | 230 | 616.6667 | 810 | 185
177 | Supply Chain & Commercial | Contract change negotiations stall | There is a risk that the parties cannot agree on price or responsibility for required changes, resulting in work pauses or proceeds without cost clarity. | Mitigate | Define change mechanisms, maintain contemporaneous cost records and escalate disputed scope promptly. | 30% | 160 | 726.6667 | 1010 | 218
178 | Ground Segment & Operations | Obsolescence affects long mission | There is a risk that ground hardware or software becomes unsupported during operations, resulting in maintenance and security costs increase. | Mitigate | Use lifecycle roadmaps, virtualized environments and funded technology refresh points. | 20% | 230 | 1050 | 1460 | 210
179 | Spacecraft & Payload Technical | Propellant margin erodes | There is a risk that actual manoeuvre demand or propulsion performance differs from assumptions, resulting in mission life or disposal capability is reduced. | Mitigate | Maintain a probabilistic delta-v budget and protect a management reserve for collision avoidance and disposal. | 15% | 380 | 1146.6667 | 1530 | 172
180 | Data & Science Products | Ground truth is insufficient | There is a risk that representative validation measurements are unavailable, resulting in product accuracy cannot be demonstrated. | Mitigate | Plan ground and airborne campaigns early and secure partner datasets and fallback methods. | 20% | 320 | 860 | 1130 | 172
181 | Software & Autonomy | Third-party software has vulnerabilities | There is a risk that a library or operating-system component contains a serious defect or vulnerability, resulting in certification, patching or redesign delays delivery. | Accept | Maintain a software bill of materials, monitor advisories and qualify controlled replacement versions. | 30% | 180 | 540 | 720 | 162
182 | Ground Segment & Operations | Operator training is inadequate | There is a risk that controllers have insufficient practice with off-nominal scenarios, resulting in incorrect actions worsen anomalies. | Accept | Use certification standards, recurrent simulations and objective proficiency checks. | 20% | 230 | 830 | 1130 | 166
183 | Ground Segment & Operations | Routine software updates introduce faults | There is a risk that a ground-system update changes validated behaviour, resulting in operations are interrupted or commands are generated incorrectly. | Mitigate | Use segregated test environments, regression tests and controlled rollback for every production update. | 20% | 260 | 726.6667 | 960 | 145.3333
184 | Data & Science Products | Data pipeline is delivered late | There is a risk that processing software is not ready when commissioning data arrive, resulting in calibration and product release are delayed. | Mitigate | Develop the pipeline against simulators and precursor data with incremental acceptance releases. | 20% | 200 | 940 | 1310 | 188
185 | Data & Science Products | Checksum failures go unnoticed | There is a risk that stored or transferred files are silently corrupted, resulting in analysis uses invalid data. | Mitigate | Generate and verify checksums at transfer, ingestion, replication and retrieval. | 20% | 230 | 830 | 1130 | 166
186 | Mission & Science | Technology demonstration conflicts with science | There is a risk that technology-demonstration objectives compete with core science for resources, resulting in primary mission objectives receive less observing time or margin. | Mitigate | Rank objectives, ring-fence minimum science resources, and define rules for suspending demonstration activities. | 50% | 80 | 326.6667 | 450 | 163.3333
187 | Spacecraft & Payload Technical | Radiation tolerance is inadequate | There is a risk that parts experience a radiation environment above their qualified tolerance, resulting in single-event effects or cumulative damage cause loss of function. | Transfer | Update radiation analysis, select screened parts, and implement shielding, error correction and fault recovery. | 15% | 250 | 1016.6667 | 1400 | 152.5
188 | Data & Science Products | Data validation lacks independence | There is a risk that the same team develops and approves science products, resulting in systematic errors escape release gates. | Accept | Use independent validation datasets, reviewers and acceptance criteria. | 20% | 240 | 660 | 870 | 132
189 | Software & Autonomy | Flight software delivery is late | There is a risk that flight software maturity trails hardware integration needs, resulting in system tests start late or use unrepresentative stubs. | Mitigate | Use incremental releases, prioritize integration-critical functions, and measure earned functionality at each build. | 30% | 170 | 570 | 770 | 171
190 | Software & Autonomy | Ground and flight protocols diverge | There is a risk that ground software and flight software implement different protocol interpretations, resulting in commands or telemetry fail during integration. | Mitigate | Generate interfaces from controlled schemas and conduct continuous end-to-end compatibility testing. | 30% | 120 | 480 | 660 | 144
191 | Ground Segment & Operations | Operations workload exceeds staffing | There is a risk that routine planning and anomaly load require more effort than estimated, resulting in staff fatigue and contractor costs increase. | Mitigate | Use workload simulations, automate repetitive tasks and cross-train surge staff. | 20% | 260 | 800 | 1070 | 160
192 | Data & Science Products | Science data volume exceeds capacity | There is a risk that actual raw and processed data volume exceeds storage or downlink allocations, resulting in observations are discarded or infrastructure costs rise. | Mitigate | Validate volume with representative scenes and implement prioritization, compression and scalable storage. | 20% | 240 | 753.3333 | 1010 | 150.6667
193 | Data & Science Products | Proprietary dependency blocks reproducibility | There is a risk that critical processing relies on inaccessible tools or licences, resulting in partners and future users cannot reproduce products. | Mitigate | Prefer open interfaces and preserve executable environments and licences for the mission lifecycle. | 20% | 170 | 630 | 860 | 126
194 | Ground Segment & Operations | Operations procedures are incomplete | There is a risk that nominal and contingency procedures are not validated before launch, resulting in operator errors and slow anomaly response increase. | Mitigate | Author procedures early, validate them in simulations and control them as operational baselines. | 20% | 150 | 576.6667 | 790 | 115.3333
195 | Ground Segment & Operations | Anomaly response authority is unclear | There is a risk that teams disagree about who can direct recovery actions, resulting in decisions are delayed during time-critical events. | Accept | Approve an anomaly command structure and rehearse escalation and decision rights. | 20% | 180 | 720 | 990 | 144
196 | Data & Science Products | Archive format becomes obsolete | There is a risk that long-lived products depend on unsupported formats or software, resulting in future users cannot access the mission record. | Mitigate | Use open preservation formats and schedule integrity and migration reviews. | 20% | 170 | 703.3333 | 970 | 140.6667
197 | Data & Science Products | AI-assisted processing introduces bias | There is a risk that training data or model behaviour creates systematic product errors, resulting in some regions or conditions receive unreliable results. | Mitigate | Assess bias across representative conditions and retain monitored, versioned correction and fallback methods. | 20% | 190 | 483.3333 | 630 | 96.6667
198 | Ground Segment & Operations | Flight dynamics products are inaccurate | There is a risk that orbit determination or manoeuvre products contain modelling or data errors, resulting in pointing, contacts or conjunction decisions are wrong. | Mitigate | Use independent checks, calibrated models and formal product approval for critical manoeuvres. | 20% | 170 | 536.6667 | 720 | 107.3333
199 | Data & Science Products | Cloud egress costs are underestimated | There is a risk that users or partners transfer more data than forecast, resulting in operating costs exceed the data budget. | Mitigate | Model access patterns, colocate processing and use controlled distribution tiers and caches. | 20% | 120 | 500 | 690 | 100
200 | Data & Science Products | Duplicate records create inconsistency | There is a risk that multiple repositories hold conflicting versions of products or metadata, resulting in users retrieve non-authoritative results. | Accept | Assign authoritative repositories and unique identifiers with automated synchronization checks. | 20% | 130 | 463.3333 | 630 | 92.6667