## Cover Page
CSA-FIN-RD-0589
Version Draft 1.0
2026-09-21
Cost Analysis Data Requirement (CADRe)
CADRe Part C - Essential Programmatic Inputs
ORCA (Ocean Reconnaissance and Chemistry Analyzer)
Prepared by ORCA Project Team
| Reviewed by [TBD] | TBD

## Table of Contents
ORCA CADRe Part C - Table of Contents
# | Sheet
1 | Cover Page
2 | 1 - Change History
3 | 4d - CBS in JS format
4 | 2 - Phasing Nomenclature
5 | 3 - Phase Durations
6 | PM's sched Scenarios
7 | GR&A
8 | 4 - RAM LoE
9 | 5 - Risk Register
10 | Risk Breakdown Structure
11 | Raw Labour Rates
12 | Labour Rates lookup
13 | Rolodex
14 | Inflation Rate

## 1 - Change History
` Table of Contents
2. Version Control - Baseline Tracker
Purpose: | To track the baseline across time
hold the major and minor releases of the baseline
| Change history and associated files that contain the relevant data |  |  |  |  | Reserved
| File Number | Date | File Version | Author | Changes | Parent Baseline Name | Baseline ID
[6 empty] | ORCA @ PREP1 | 1
[6 empty] | ORCA @ KDP-0 | 2
|  |  |  | MB | Rebaseline: cruise duration increased following updated Jupiter gravity-assist trajectory analysis. | ORCA @ MDR#2 | 3
[6 empty] | ORCA @ PREP2 | 4
[6 empty] | ORCA @ KDP-A | 5
| CSA-FIN-RD-0587 | 2033-12-20 | Draft 1 | MB | Initial document ahead of Phase B | ORCA @ KDP-B | 6
[6 empty] | ORCA @ PDR | 7
[6 empty] | ORCA @ CDR | 8
| CSA-FIN-RD-0590 | 2026-09-21 | Draft 1 | MB | Update ahead of Gate 4: PDR and CDR complete, System Integration Review baseline. | ORCA @ SIR | 9 | <<--- We are here now
[6 empty] | ORCA @ Launch (as flown) | 10
[6 empty] | ORCA @ CR | 11
[6 empty] | ORCA @ KDP-X | 12
[6 empty] | ORCA @ end of life | 13

## 4d - CBS in JS format (hidden)
` Table of Contents
4d. CBS (as self referencing list) for use as a javascript array
Why we we asking:
this page is auto-generated and used for drawing it out
Self referencing list for dtree
UID | Parent ID | Level | Node Name | CBS Code | Depth | Icon | Notes | Javascript Code | Depth
1 | -1 | 1 | Space Missions |  | Taxon 1 | Box.png |  | datatable[0] = new Array("1","-1","Space Missions","1","Box.png"); | Taxon 1
2 | 1 | 2 | EO SAR Missions |  | Taxon 2 | EO.png |  | datatable[1] = new Array("2","1","EO SAR Missions","2","EO.png"); | Taxon 2
3 | 2 | 3 | Radarsat Portfolio |  | Phylum | Pouch.png |  | datatable[2] = new Array("3","2","Radarsat Portfolio","3","Pouch.png"); | Phylum
4 | 0 | 4 | Radarsat 1 |  | Mission | Satellite.png |  | datatable[3] = new Array("4","0","Radarsat 1","4","Satellite.png"); | Mission
5 | 0 | 4 | Radarsat 2 |  | Mission | Satellite.png |  | datatable[4] = new Array("5","0","Radarsat 2","4","Satellite.png"); | Design Reference Mission
6 | 0 | 4 | Radarsat Constellation Mission |  | Mission | Satellite.png |  | datatable[5] = new Array("6","0","Radarsat Constellation Mission","4","Satellite.png"); | Segment
7 | 0 | 4 | Radarsat+ Replenishment | 1 | Mission | Satellite.png |  | datatable[6] = new Array("7","0","Radarsat+ Replenishment","4","Satellite.png"); | System of Systems
8 | 0 | 4 | Radarsat+ Next Generation |  | Mission | Satellite.png |  | datatable[7] = new Array("8","0","Radarsat+ Next Generation","4","Satellite.png"); | System
9 | 2 | 5 | Analysis Scenario 1: RCM Proxy |  | Design Reference Mission | Scenario.png |  | datatable[8] = new Array("9","2","Analysis Scenario 1: RCM Proxy","5","Scenario.png"); | Subsystem
10 | 2 | 5 | Analysis Scenario 2: RCM+ |  | Design Reference Mission | Scenario.png |  | datatable[9] = new Array("10","2","Analysis Scenario 2: RCM+","5","Scenario.png"); | Assembly
11 | 2 | 5 | Analysis Scenario 3: Airbus concept |  | Design Reference Mission | Scenario.png |  | datatable[10] = new Array("11","2","Analysis Scenario 3: Airbus concept","5","Scenario.png"); | Component
12 | 2 | 5 | Analysis Scenario 4: MDA Chorus Data Buy |  | Design Reference Mission | Scenario.png |  | datatable[11] = new Array("12","2","Analysis Scenario 4: MDA Chorus Data Buy","5","Scenario.png");
13 | 2 | 5 | Analysis Scenario 5: MDA Chorus+ |  | Design Reference Mission | Scenario.png |  | datatable[12] = new Array("13","2","Analysis Scenario 5: MDA Chorus+","5","Scenario.png");
14 | 2 | 5 | Analysis Scenario 6: Airbus Sentinel 2 |  | Design Reference Mission | Scenario.png |  | datatable[13] = new Array("14","2","Analysis Scenario 6: Airbus Sentinel 2","5","Scenario.png");
15 | 8 | 6 | Government Overhead and Oversight | 1.1 | Segment | Government.png | This WBS includes all CSA Oversight, OGD salaries, and basic overhead for the care and maintenance of CSA staff | datatable[14] = new Array("15","8","Government Overhead and Oversight","6","Government.png");
16 | 8 | 6 | Space Segment | 1.2 | Segment | Satellite.png | The Space Segment includes things we launch into space | datatable[15] = new Array("16","8","Space Segment","6","Satellite.png");
17 | 8 | 6 | Launch Segment | 1.3 | Segment | Rocket.png | The launch segment includes the launch vehicle and seom support services | datatable[16] = new Array("17","8","Launch Segment","6","Rocket.png");
18 | 8 | 6 | Ground Segment | 1.4 | Segment | Facility.png | The ground segment includes the planning desgin and development of the GS, but not the Ops | datatable[17] = new Array("18","8","Ground Segment","6","Facility.png");
19 | 8 | 6 | Ops Segment | 1.5 | Segment | Ops.png | Ops includes SatOps, Mission Ops, Science Ops - typically contracts | datatable[18] = new Array("19","8","Ops Segment","6","Ops.png");
20 | 8 | 6 | Science Segment | 1.6 | Segment | Science.png | Typically G&C | datatable[19] = new Array("20","8","Science Segment","6","Science.png");
21 | 10 | 7 | Gov't Oversight (Salaries and EBP) | 1.1.1 | System of Systems | Government.png |  | datatable[20] = new Array("21","10","Gov't Oversight (Salaries and EBP)","7","Government.png");
22 | 10 | 7 | Government Overhead | 1.1.2 | System of Systems | Government.png |  | datatable[21] = new Array("22","10","Government Overhead","7","Government.png");
23 | 21 | 8 | CSA Oversight | 1.1.1.1 | System | Government.png |  | datatable[22] = new Array("23","21","CSA Oversight","8","Government.png");
24 | 21 | 8 | OGD Oversight | 1.1.1.2 | System | Government.png |  | datatable[23] = new Array("24","21","OGD Oversight","8","Government.png");
25 | 23 | 9 | CSA Project Team | 1.1.1.1.1 | Subsystem | Government.png | This CBS contains all salaries associated with the RAM of the Project team | datatable[24] = new Array("25","23","CSA Project Team","9","Government.png");
26 | 23 | 9 | CSA Internal Services | 1.1.1.1.2 | Subsystem | Government.png | This CBS contains all salaries associated with CSA internal services (finance, HR, audit, eval, policy, Executives, IM, IT, contracts, shipping, etc) | datatable[25] = new Array("26","23","CSA Internal Services","9","Government.png");
27 | 24 | 9 | OGD Internal Services by MOU | 1.1.1.2.1 | Subsystem | Government.png |  | datatable[26] = new Array("27","24","OGD Internal Services by MOU","9","Government.png");
28 | 24 | 9 | OGD User Departments by MOU (RAM portion) | 1.1.1.2.2 | Subsystem | Government.png |  | datatable[27] = new Array("28","24","OGD User Departments by MOU (RAM portion)","9","Government.png");
29 | 21 | 10 | Shared Services | 1.1.1.2.1.1 | Assembly | Government.png |  | datatable[28] = new Array("29","21","Shared Services","10","Government.png");
30 | 21 | 10 | SPAC | 1.1.1.2.1.2 | Assembly | Government.png |  | datatable[29] = new Array("30","21","SPAC","10","Government.png");
31 | 21 | 10 | Justice Canada | 1.1.1.2.1.3 | Assembly | Government.png |  | datatable[30] = new Array("31","21","Justice Canada","10","Government.png");
32 | 23 | 10 | ECCC | 1.1.1.2.2.1 | Assembly | Government.png |  | datatable[31] = new Array("32","23","ECCC","10","Government.png");
33 | 23 | 10 | NRCAN | 1.1.1.2.2.2 | Assembly | Government.png |  | datatable[32] = new Array("33","23","NRCAN","10","Government.png");
34 | 23 | 10 | DND | 1.1.1.2.2.3 | Assembly | Government.png |  | datatable[33] = new Array("34","23","DND","10","Government.png");
35 | 25 | 11 | RAM per Person per FY and Phase | 1.1.1.1.1.1 | Component | Government.png |  | datatable[34] = new Array("35","25","RAM per Person per FY and Phase","11","Government.png");
36 | 25 | 11 | PSPC Procurement Services | 1.1.1.2.1.2.1 | Component | Government.png |  | datatable[35] = new Array("36","25","PSPC Procurement Services","11","Government.png");
37 | 25 | 11 | PSPC Fairness Monitor | 1.1.1.2.1.2.2 | Component | Government.png |  | datatable[36] = new Array("37","25","PSPC Fairness Monitor","11","Government.png");
38 | 31 | 11 | Legal Services | 1.1.1.2.1.3.1 | Component | Government.png |  | datatable[37] = new Array("38","31","Legal Services","11","Government.png");
39 | 22 | 8 | CSA Overhead | 1.1.2.1 | System | Government.png |  | datatable[38] = new Array("39","22","CSA Overhead","8","Government.png");
40 | 34 | 9 | IS Management Overhead | 1.1.2.1.1 | Subsystem | Government.png |  | datatable[39] = new Array("40","34","IS Management Overhead ","9","Government.png");
41 | 34 | 9 | Management Consulting Services | 1.1.2.1.2 | Subsystem | Government.png |  | datatable[40] = new Array("41","34","Management Consulting Services","9","Government.png");
42 | 34 | 9 | Temporary Help | 1.1.2.1.3 | Subsystem | Government.png |  | datatable[41] = new Array("42","34","Temporary Help","9","Government.png");
43 | 34 | 9 | Students | 1.1.2.1.4 | Subsystem | Government.png | This CBS includes any students, FSWEP or PDF assisint Csa project team | datatable[42] = new Array("43","34","Students","9","Government.png");
44 | 34 | 9 | Government Travel & Living | 1.1.2.1.5 | Subsystem | Government.png | This CBS includes any government Travel and Living expenses | datatable[43] = new Array("44","34","Government Travel & Living","9","Government.png");
45 | 34 | 9 | Translation | 1.1.2.1.6 | Subsystem | Government.png | This CBS includes any translation costs | datatable[44] = new Array("45","34","Translation","9","Government.png");
46 | 34 | 9 | Shipping | 1.1.2.1.7 | Subsystem | Government.png | This CBs includes any shipping cost, but not shipping flight HW which is under space segment | datatable[45] = new Array("46","34","Shipping","9","Government.png");
47 | 34 | 9 | Software Licenses | 1.1.2.1.8 | Subsystem | Government.png | This CBS includes any COTs SW not flight Sw or ground SW | datatable[46] = new Array("47","34","Software Licenses","9","Government.png");
48 | 34 | 9 | Public Outreach and STEM initiatives | 1.1.2.1.9 | Subsystem | Government.png | This CBS includes any public relations and STEM | datatable[47] = new Array("48","34","Public Outreach and STEM initiatives","9","Government.png");
49 | 34 | 9 | Other Overhead (Specify) | 1.1.2.1.10 | Subsystem | Government.png | This CBS includes any other misc fees | datatable[48] = new Array("49","34","Other Overhead (Specify)","9","Government.png");
50 | 36 | 10 | Consultants - Industrial Space Experts | 1.1.2.1.2.1 | Assembly | Government.png |  | datatable[49] = new Array("50","36","Consultants - Industrial Space Experts","10","Government.png");
51 | 36 | 10 | Consultants - Academia | 1.1.2.1.2.2 | Assembly | Government.png |  | datatable[50] = new Array("51","36","Consultants - Academia","10","Government.png");
52 | 36 | 10 | Consultants - Non-Space Experts | 1.1.2.1.2.3 | Assembly | Government.png |  | datatable[51] = new Array("52","36","Consultants - Non-Space Experts","10","Government.png");
53 | 12 | 6 | Mission SEITPM and Support Equipment |  | Segment | SEITPM.png |  | datatable[52] = new Array("53","12","Mission SEITPM and Support Equipment","6","SEITPM.png");
54 | 48 | 7 | Project Management |  | System of Systems | SEITPM.png |  | datatable[53] = new Array("54","48","Project Management","7","SEITPM.png");
55 | 48 | 7 | Systems Engineering |  | System of Systems | SEITPM.png |  | datatable[54] = new Array("55","48","Systems Engineering","7","SEITPM.png");
56 | 48 | 7 | Mission Assurance |  | System of Systems | SEITPM.png |  | datatable[55] = new Array("56","48","Mission Assurance","7","SEITPM.png");
57 | 48 | 7 | Assembly, Integration and Testing |  | System of Systems | SEITPM.png |  | datatable[56] = new Array("57","48","Assembly, Integration and Testing","7","SEITPM.png");
58 | 48 | 7 | Support Equipment |  | System of Systems | SEITPM.png |  | datatable[57] = new Array("58","48","Support Equipment","7","SEITPM.png");
59 | 16 | 7 | Space Vehicle 1 … i |  | System of Systems | Satellite.png |  | datatable[58] = new Array("59","16","Space Vehicle 1 … i","7","Satellite.png");
60 | 59 | 8 | Spacecraft SEITPM and Support Equipment |  | System | SEITPM.png |  | datatable[59] = new Array("60","59","Spacecraft SEITPM and Support Equipment","8","SEITPM.png");
61 | 55 | 9 | Project Management |  | Subsystem | SEITPM.png |  | datatable[60] = new Array("61","55","Project Management","9","SEITPM.png");
62 | 55 | 9 | Systems Engineering |  | Subsystem | SEITPM.png |  | datatable[61] = new Array("62","55","Systems Engineering","9","SEITPM.png");
63 | 55 | 9 | Mission Assurance |  | Subsystem | SEITPM.png |  | datatable[62] = new Array("63","55","Mission Assurance","9","SEITPM.png");
64 | 55 | 9 | Assembly, Integration and Testing |  | Subsystem | SEITPM.png |  | datatable[63] = new Array("64","55","Assembly, Integration and Testing","9","SEITPM.png");
65 | 55 | 9 | Support Equipment |  | Subsystem | SEITPM.png |  | datatable[64] = new Array("65","55","Support Equipment","9","SEITPM.png");
66 | 59 | 8 | Bus/Platform |  | System | Widget.png |  | datatable[65] = new Array("66","59","Bus/Platform","8","Widget.png");
67 | 66 | 9 | Platform SEITPM and Support Equipment |  | Subsystem | SEITPM.png |  | datatable[66] = new Array("67","66","Platform SEITPM and Support Equipment","9","SEITPM.png");
68 | 62 | 10 | Project Management |  | Assembly | SEITPM.png |  | datatable[67] = new Array("68","62","Project Management","10","SEITPM.png");
69 | 62 | 10 | Systems Engineering |  | Assembly | SEITPM.png |  | datatable[68] = new Array("69","62","Systems Engineering","10","SEITPM.png");
70 | 62 | 10 | Mission Assurance |  | Assembly | SEITPM.png |  | datatable[69] = new Array("70","62","Mission Assurance","10","SEITPM.png");
71 | 62 | 10 | Assembly, Integration and Testing |  | Assembly | SEITPM.png |  | datatable[70] = new Array("71","62","Assembly, Integration and Testing","10","SEITPM.png");
72 | 62 | 10 | Support Equipment |  | Assembly | SEITPM.png |  | datatable[71] = new Array("72","62","Support Equipment","10","SEITPM.png");
73 | 61 | 9 | Structures and Mechanisms Subsystem (SMS) |  | Subsystem | Widget.png |  | datatable[72] = new Array("73","61","Structures and Mechanisms Subsystem (SMS)","9","Widget.png");
74 | 68 | 10 | Structures and Mechanisms Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[73] = new Array("74","68","Structures and Mechanisms Subsystem SEITPM","10","SEITPM.png");
75 | 69 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[74] = new Array("75","69","Project Management","11","SEITPM.png");
76 | 69 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[75] = new Array("76","69","Systems Engineering","11","SEITPM.png");
77 | 69 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[76] = new Array("77","69","Mission Assurance","11","SEITPM.png");
78 | 69 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[77] = new Array("78","69","Assembly, Integration and Testing","11","SEITPM.png");
79 | 69 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[78] = new Array("79","69","Support Equipment","11","SEITPM.png");
80 | 68 | 10 | Primary Structures |  | Assembly | Widget.png |  | datatable[79] = new Array("80","68","Primary Structures","10","Widget.png");
81 | 75 | 11 | Load Carrying Shell/Truss |  | Component | Widget.png |  | datatable[80] = new Array("81","75","Load Carrying Shell/Truss","11","Widget.png");
82 | 75 | 11 | Equipment Compartments |  | Component | Widget.png |  | datatable[81] = new Array("82","75","Equipment Compartments","11","Widget.png");
83 | 75 | 11 | Booms |  | Component | Widget.png |  | datatable[82] = new Array("83","75","Booms","11","Widget.png");
84 | 75 | 11 | Adapters |  | Component | Widget.png |  | datatable[83] = new Array("84","75","Adapters","11","Widget.png");
85 | 75 | 11 | Other Structures (Specify) |  | Component | Widget.png |  | datatable[84] = new Array("85","75","Other Structures (Specify)","11","Widget.png");
86 | 68 | 10 | Secondary Structures |  | Assembly | Widget.png |  | datatable[85] = new Array("86","68","Secondary Structures","10","Widget.png");
87 | 81 | 11 | Equipment (Instrument) Mountings |  | Component | Widget.png |  | datatable[86] = new Array("87","81","Equipment (Instrument) Mountings","11","Widget.png");
88 | 81 | 11 | Ballast Mass |  | Component | Widget.png |  | datatable[87] = new Array("88","81","Ballast Mass","11","Widget.png");
89 | 81 | 11 | Other Secondary Structures (Specify) |  | Component | Widget.png |  | datatable[88] = new Array("89","81","Other Secondary Structures (Specify)","11","Widget.png");
90 | 68 | 10 | Mechanisms and Pyrotechnics |  | Assembly | Widget.png |  | datatable[89] = new Array("90","68","Mechanisms and Pyrotechnics","10","Widget.png");
91 | 85 | 11 | Positioning |  | Component | Widget.png |  | datatable[90] = new Array("91","85","Positioning","11","Widget.png");
92 | 85 | 11 | Deployment and Storage Equipment |  | Component | Widget.png |  | datatable[91] = new Array("92","85","Deployment and Storage Equipment","11","Widget.png");
93 | 85 | 11 | Docking Mechanisms |  | Component | Widget.png |  | datatable[92] = new Array("93","85","Docking Mechanisms","11","Widget.png");
94 | 85 | 11 | Other Mechanisms (Specify) |  | Component | Widget.png |  | datatable[93] = new Array("94","85","Other Mechanisms (Specify)","11","Widget.png");
95 | 85 | 11 | Pyrotechnics |  | Component | Widget.png |  | datatable[94] = new Array("95","85","Pyrotechnics","11","Widget.png");
96 | 68 | 10 | SMS Other (Specify) |  | Assembly | Widget.png |  | datatable[95] = new Array("96","68","SMS Other (Specify)","10","Widget.png");
97 | 61 | 9 | Thermal Control Subsystem (TCS) |  | Subsystem | Widget.png |  | datatable[96] = new Array("97","61","Thermal Control Subsystem (TCS)","9","Widget.png");
98 | 92 | 10 | Thermal Control Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[97] = new Array("98","92","Thermal Control Subsystem SEITPM","10","SEITPM.png");
99 | 93 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[98] = new Array("99","93","Project Management","11","SEITPM.png");
100 | 93 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[99] = new Array("100","93","Systems Engineering","11","SEITPM.png");
101 | 93 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[100] = new Array("101","93","Mission Assurance","11","SEITPM.png");
102 | 93 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[101] = new Array("102","93","Assembly, Integration and Testing","11","SEITPM.png");
103 | 93 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[102] = new Array("103","93","Support Equipment","11","SEITPM.png");
104 | 92 | 10 | Active Devices |  | Assembly | Widget.png |  | datatable[103] = new Array("104","92","Active Devices","10","Widget.png");
105 | 99 | 11 | Cryogenic Devices |  | Component | Widget.png |  | datatable[104] = new Array("105","99","Cryogenic Devices","11","Widget.png");
106 | 99 | 11 | Liquid Loops |  | Component | Widget.png |  | datatable[105] = new Array("106","99","Liquid Loops","11","Widget.png");
107 | 99 | 11 | Electric Coolers |  | Component | Widget.png |  | datatable[106] = new Array("107","99","Electric Coolers","11","Widget.png");
108 | 99 | 11 | Heaters, Thermistors, and Thermostats |  | Component | Widget.png |  | datatable[107] = new Array("108","99","Heaters, Thermistors, and Thermostats","11","Widget.png");
109 | 99 | 11 | Other Active Devices (Specify) |  | Component | Widget.png |  | datatable[108] = new Array("109","99","Other Active Devices (Specify)","11","Widget.png");
110 | 92 | 10 | Passive Devices |  | Assembly | Widget.png |  | datatable[109] = new Array("110","92","Passive Devices","10","Widget.png");
111 | 105 | 11 | Radiator Panel/Fins |  | Component | Widget.png |  | datatable[110] = new Array("111","105","Radiator Panel/Fins","11","Widget.png");
112 | 105 | 11 | Coatings |  | Component | Widget.png |  | datatable[111] = new Array("112","105","Coatings","11","Widget.png");
113 | 105 | 11 | Heat Pipes |  | Component | Widget.png |  | datatable[112] = new Array("113","105","Heat Pipes","11","Widget.png");
114 | 105 | 11 | Insulation |  | Component | Widget.png |  | datatable[113] = new Array("114","105","Insulation","11","Widget.png");
115 | 105 | 11 | Conductive Structures |  | Component | Widget.png |  | datatable[114] = new Array("115","105","Conductive Structures","11","Widget.png");
116 | 105 | 11 | Heat Activated Structures |  | Component | Widget.png |  | datatable[115] = new Array("116","105","Heat Activated Structures","11","Widget.png");
117 | 105 | 11 | Sun Shields |  | Component | Widget.png |  | datatable[116] = new Array("117","105","Sun Shields","11","Widget.png");
118 | 105 | 11 | Second Surface Mirrors |  | Component | Widget.png |  | datatable[117] = new Array("118","105","Second Surface Mirrors","11","Widget.png");
119 | 105 | 11 | Shutters and Louvers |  | Component | Widget.png |  | datatable[118] = new Array("119","105","Shutters and Louvers","11","Widget.png");
120 | 105 | 11 | Other Passive Devices (Specify) |  | Component | Widget.png |  | datatable[119] = new Array("120","105","Other Passive Devices (Specify)","11","Widget.png");
121 | 92 | 10 | TCS Other (Specify) |  | Assembly | Widget.png |  | datatable[120] = new Array("121","92","TCS Other (Specify)","10","Widget.png");
122 | 61 | 9 | Electric Power Subsystem (EPS) |  | Subsystem | Widget.png |  | datatable[121] = new Array("122","61","Electric Power Subsystem (EPS)","9","Widget.png");
123 | 117 | 10 | Electric Power Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[122] = new Array("123","117","Electric Power Subsystem SEITPM","10","SEITPM.png");
124 | 118 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[123] = new Array("124","118","Project Management","11","SEITPM.png");
125 | 118 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[124] = new Array("125","118","Systems Engineering","11","SEITPM.png");
126 | 118 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[125] = new Array("126","118","Mission Assurance","11","SEITPM.png");
127 | 118 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[126] = new Array("127","118","Assembly, Integration and Testing","11","SEITPM.png");
128 | 118 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[127] = new Array("128","118","Support Equipment","11","SEITPM.png");
129 | 117 | 10 | Electrical Power Generation |  | Assembly | Widget.png |  | datatable[128] = new Array("129","117","Electrical Power Generation","10","Widget.png");
130 | 124 | 11 | Solar Array |  | Component | Widget.png |  | datatable[129] = new Array("130","124","Solar Array","11","Widget.png");
131 | 124 | 11 | Solar Array Positioner |  | Component | Widget.png |  | datatable[130] = new Array("131","124","Solar Array Positioner","11","Widget.png");
132 | 124 | 11 | Radioisotope Thermionic Generator |  | Component | Widget.png |  | datatable[131] = new Array("132","124","Radioisotope Thermionic Generator","11","Widget.png");
133 | 124 | 11 | Chemical (Fuel Cells) |  | Component | Widget.png |  | datatable[132] = new Array("133","124","Chemical (Fuel Cells)","11","Widget.png");
134 | 124 | 11 | Auxiliary Power Units |  | Component | Widget.png |  | datatable[133] = new Array("134","124","Auxiliary Power Units","11","Widget.png");
135 | 124 | 11 | Other Power Sources |  | Component | Widget.png |  | datatable[134] = new Array("135","124","Other Power Sources","11","Widget.png");
136 | 117 | 10 | Electrical Power Conditioning |  | Assembly | Widget.png |  | datatable[135] = new Array("136","117","Electrical Power Conditioning","10","Widget.png");
137 | 131 | 11 | Power Control Electronics |  | Component | Widget.png |  | datatable[136] = new Array("137","131","Power Control Electronics","11","Widget.png");
138 | 131 | 11 | Power Conversion Electronics |  | Component | Widget.png |  | datatable[137] = new Array("138","131","Power Conversion Electronics","11","Widget.png");
139 | 131 | 11 | Power Dissipation Devices |  | Component | Widget.png |  | datatable[138] = new Array("139","131","Power Dissipation Devices","11","Widget.png");
140 | 131 | 11 | Power Distribution Electronics |  | Component | Widget.png |  | datatable[139] = new Array("140","131","Power Distribution Electronics","11","Widget.png");
141 | 131 | 11 | Power Switching Electronics |  | Component | Widget.png |  | datatable[140] = new Array("141","131","Power Switching Electronics","11","Widget.png");
142 | 131 | 11 | Power Regulation Electronics |  | Component | Widget.png |  | datatable[141] = new Array("142","131","Power Regulation Electronics","11","Widget.png");
143 | 131 | 11 | Other Power Conditioning Devices (Specify) |  | Component | Widget.png |  | datatable[142] = new Array("143","131","Other Power Conditioning Devices (Specify)","11","Widget.png");
144 | 117 | 10 | Electrical Power Storage |  | Assembly | Widget.png |  | datatable[143] = new Array("144","117","Electrical Power Storage","10","Widget.png");
145 | 139 | 11 | Rechargeable Batteries |  | Component | Widget.png |  | datatable[144] = new Array("145","139","Rechargeable Batteries","11","Widget.png");
146 | 139 | 11 | Charge Control Electronics |  | Component | Widget.png |  | datatable[145] = new Array("146","139","Charge Control Electronics","11","Widget.png");
147 | 139 | 11 | Other Electrical Power Storage Devices (Specify) |  | Component | Widget.png |  | datatable[146] = new Array("147","139","Other Electrical Power Storage Devices (Specify)","11","Widget.png");
148 | 117 | 10 | Harnesses and Cables |  | Assembly | Widget.png |  | datatable[147] = new Array("148","117","Harnesses and Cables","10","Widget.png");
149 | 117 | 10 | EPS Other (Specify) |  | Assembly | Widget.png |  | datatable[148] = new Array("149","117","EPS Other (Specify)","10","Widget.png");
150 | 61 | 9 | Attitude Control Subsystem (ACS) |  | Subsystem | Widget.png |  | datatable[149] = new Array("150","61","Attitude Control Subsystem (ACS)","9","Widget.png");
151 | 145 | 10 | Attitude Control Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[150] = new Array("151","145","Attitude Control Subsystem SEITPM","10","SEITPM.png");
152 | 146 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[151] = new Array("152","146","Project Management","11","SEITPM.png");
153 | 146 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[152] = new Array("153","146","Systems Engineering","11","SEITPM.png");
154 | 146 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[153] = new Array("154","146","Mission Assurance","11","SEITPM.png");
155 | 146 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[154] = new Array("155","146","Assembly, Integration and Testing","11","SEITPM.png");
156 | 146 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[155] = new Array("156","146","Support Equipment","11","SEITPM.png");
157 | 145 | 10 | Attitude Determination |  | Assembly | Widget.png |  | datatable[156] = new Array("157","145","Attitude Determination","10","Widget.png");
158 | 152 | 11 | Earth (Horizon) Sensors |  | Component | Widget.png |  | datatable[157] = new Array("158","152","Earth (Horizon) Sensors","11","Widget.png");
159 | 152 | 11 | Sun Sensors |  | Component | Widget.png |  | datatable[158] = new Array("159","152","Sun Sensors","11","Widget.png");
160 | 152 | 11 | Star Tracker/Sensors |  | Component | Widget.png |  | datatable[159] = new Array("160","152","Star Tracker/Sensors","11","Widget.png");
161 | 152 | 11 | Global Positioning System (GPS) Receiver |  | Component | Widget.png |  | datatable[160] = new Array("161","152","Global Positioning System (GPS) Receiver","11","Widget.png");
162 | 152 | 11 | Imagers |  | Component | Widget.png |  | datatable[161] = new Array("162","152","Imagers","11","Widget.png");
163 | 152 | 11 | Magnetometers |  | Component | Widget.png |  | datatable[162] = new Array("163","152","Magnetometers","11","Widget.png");
164 | 152 | 11 | Altimeters |  | Component | Widget.png |  | datatable[163] = new Array("164","152","Altimeters","11","Widget.png");
165 | 152 | 11 | Inertial Reference Unit (IRU)/Inertial Measurement Unit (IMU) |  | Component | Widget.png |  | datatable[164] = new Array("165","152","Inertial Reference Unit (IRU)/Inertial Measurement Unit (IMU)","11","Widget.png");
166 | 152 | 11 | Radar |  | Component | Widget.png |  | datatable[165] = new Array("166","152","Radar","11","Widget.png");
167 | 152 | 11 | Rate Gyros |  | Component | Widget.png |  | datatable[166] = new Array("167","152","Rate Gyros","11","Widget.png");
168 | 152 | 11 | Accelerometers |  | Component | Widget.png |  | datatable[167] = new Array("168","152","Accelerometers","11","Widget.png");
169 | 152 | 11 | Bearing and Power Transfer Assembly |  | Component | Widget.png |  | datatable[168] = new Array("169","152","Bearing and Power Transfer Assembly","11","Widget.png");
170 | 152 | 11 | Other Attitude Determination Devices (Specify) |  | Component | Widget.png |  | datatable[169] = new Array("170","152","Other Attitude Determination Devices (Specify)","11","Widget.png");
171 | 145 | 10 | Attitude Control |  | Assembly | Widget.png |  | datatable[170] = new Array("171","145","Attitude Control","10","Widget.png");
172 | 166 | 11 | Reaction Wheel |  | Component | Widget.png |  | datatable[171] = new Array("172","166","Reaction Wheel","11","Widget.png");
173 | 166 | 11 | Momentum Wheel |  | Component | Widget.png |  | datatable[172] = new Array("173","166","Momentum Wheel","11","Widget.png");
174 | 166 | 11 | Control Moment Gyro |  | Component | Widget.png |  | datatable[173] = new Array("174","166","Control Moment Gyro","11","Widget.png");
175 | 166 | 11 | Other Energy Storage Devices |  | Component | Widget.png |  | datatable[174] = new Array("175","166","Other Energy Storage Devices","11","Widget.png");
176 | 166 | 11 | Magnetic Control Devices |  | Component | Widget.png |  | datatable[175] = new Array("176","166","Magnetic Control Devices","11","Widget.png");
177 | 166 | 11 | Spin Control Devices |  | Component | Widget.png |  | datatable[176] = new Array("177","166","Spin Control Devices","11","Widget.png");
178 | 166 | 11 | Control Electronics |  | Component | Widget.png |  | datatable[177] = new Array("178","166","Control Electronics","11","Widget.png");
179 | 166 | 11 | Other Attitude Control Devices (Specify) |  | Component | Widget.png |  | datatable[178] = new Array("179","166","Other Attitude Control Devices (Specify)","11","Widget.png");
180 | 145 | 10 | ACS Other (Specify) |  | Assembly | Widget.png |  | datatable[179] = new Array("180","145","ACS Other (Specify)","10","Widget.png");
181 | 61 | 9 | Propulsion Subsystem |  | Subsystem | Widget.png |  | datatable[180] = new Array("181","61","Propulsion Subsystem","9","Widget.png");
182 | 176 | 10 | Propulsion Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[181] = new Array("182","176","Propulsion Subsystem SEITPM","10","SEITPM.png");
183 | 177 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[182] = new Array("183","177","Project Management","11","SEITPM.png");
184 | 177 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[183] = new Array("184","177","Systems Engineering","11","SEITPM.png");
185 | 177 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[184] = new Array("185","177","Mission Assurance","11","SEITPM.png");
186 | 177 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[185] = new Array("186","177","Assembly, Integration and Testing","11","SEITPM.png");
187 | 177 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[186] = new Array("187","177","Support Equipment","11","SEITPM.png");
188 | 176 | 10 | Tanks |  | Assembly | Widget.png |  | datatable[187] = new Array("188","176","Tanks","10","Widget.png");
189 | 183 | 11 | Oxidizer Tanks |  | Component | Widget.png |  | datatable[188] = new Array("189","183","Oxidizer Tanks","11","Widget.png");
190 | 183 | 11 | Fuel Tanks |  | Component | Widget.png |  | datatable[189] = new Array("190","183","Fuel Tanks","11","Widget.png");
191 | 183 | 11 | Propellant Tanks |  | Component | Widget.png |  | datatable[190] = new Array("191","183","Propellant Tanks","11","Widget.png");
192 | 183 | 11 | Pressurance Tanks |  | Component | Widget.png |  | datatable[191] = new Array("192","183","Pressurance Tanks","11","Widget.png");
193 | 183 | 11 | Plumbing |  | Component | Widget.png |  | datatable[192] = new Array("193","183","Plumbing","11","Widget.png");
194 | 183 | 11 | Other Tanks (Specify) |  | Component | Widget.png |  | datatable[193] = new Array("194","183","Other Tanks (Specify)","11","Widget.png");
195 | 176 | 10 | Maneuvering Thrusters |  | Assembly | Widget.png |  | datatable[194] = new Array("195","176","Maneuvering Thrusters","10","Widget.png");
196 | 190 | 11 | Bipropellant |  | Component | Widget.png |  | datatable[195] = new Array("196","190","Bipropellant","11","Widget.png");
197 | 190 | 11 | Monopropellant |  | Component | Widget.png |  | datatable[196] = new Array("197","190","Monopropellant","11","Widget.png");
198 | 190 | 11 | Solar Electric |  | Component | Widget.png |  | datatable[197] = new Array("198","190","Solar Electric","11","Widget.png");
199 | 190 | 11 | Ion |  | Component | Widget.png |  | datatable[198] = new Array("199","190","Ion","11","Widget.png");
200 | 190 | 11 | Cold Gas |  | Component | Widget.png |  | datatable[199] = new Array("200","190","Cold Gas","11","Widget.png");
201 | 190 | 11 | Other Maneuvering Thrusters (Specify) |  | Component | Widget.png |  | datatable[200] = new Array("201","190","Other Maneuvering Thrusters (Specify)","11","Widget.png");
202 | 176 | 10 | Translation Thrusters |  | Assembly | Widget.png |  | datatable[201] = new Array("202","176","Translation Thrusters","10","Widget.png");
203 | 197 | 11 | Bipropellant |  | Component | Widget.png |  | datatable[202] = new Array("203","197","Bipropellant","11","Widget.png");
204 | 197 | 11 | Monopropellant |  | Component | Widget.png |  | datatable[203] = new Array("204","197","Monopropellant","11","Widget.png");
205 | 197 | 11 | Solar Electric |  | Component | Widget.png |  | datatable[204] = new Array("205","197","Solar Electric","11","Widget.png");
206 | 197 | 11 | Ion |  | Component | Widget.png |  | datatable[205] = new Array("206","197","Ion","11","Widget.png");
207 | 197 | 11 | Cold Gas |  | Component | Widget.png |  | datatable[206] = new Array("207","197","Cold Gas","11","Widget.png");
208 | 197 | 11 | Other Translation Thrusters (Specify) |  | Component | Widget.png |  | datatable[207] = new Array("208","197","Other Translation Thrusters (Specify)","11","Widget.png");
209 | 176 | 10 | Propellant |  | Assembly | Widget.png |  | datatable[208] = new Array("209","176","Propellant","10","Widget.png");
210 | 204 | 11 | Solid Propellant |  | Component | Widget.png |  | datatable[209] = new Array("210","204","Solid Propellant","11","Widget.png");
211 | 204 | 11 | Liquid Propellant |  | Component | Widget.png |  | datatable[210] = new Array("211","204","Liquid Propellant","11","Widget.png");
212 | 204 | 11 | Prussurant Propellant |  | Component | Widget.png |  | datatable[211] = new Array("212","204","Prussurant Propellant","11","Widget.png");
213 | 204 | 11 | Other Propellant (Specify) |  | Component | Widget.png |  | datatable[212] = new Array("213","204","Other Propellant (Specify)","11","Widget.png");
214 | 176 | 11 | Solid Rocket Motors |  | Component | Widget.png |  | datatable[213] = new Array("214","176","Solid Rocket Motors","11","Widget.png");
215 | 176 | 11 | Power Electronics |  | Component | Widget.png |  | datatable[214] = new Array("215","176","Power Electronics","11","Widget.png");
216 | 176 | 11 | Propulsion Other (Specify) |  | Component | Widget.png |  | datatable[215] = new Array("216","176","Propulsion Other (Specify)","11","Widget.png");
217 | 61 | 9 | Telemetry, Tracking, and Command Subsystem (TT&C) |  | Subsystem | Widget.png |  | datatable[216] = new Array("217","61","Telemetry, Tracking, and Command Subsystem (TT&C)","9","Widget.png");
218 | 212 | 10 | TT&C Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[217] = new Array("218","212","TT&C Subsystem SEITPM","10","SEITPM.png");
219 | 213 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[218] = new Array("219","213","Project Management","11","SEITPM.png");
220 | 213 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[219] = new Array("220","213","Systems Engineering","11","SEITPM.png");
221 | 213 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[220] = new Array("221","213","Mission Assurance","11","SEITPM.png");
222 | 213 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[221] = new Array("222","213","Assembly, Integration and Testing","11","SEITPM.png");
223 | 213 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[222] = new Array("223","213","Support Equipment","11","SEITPM.png");
224 | 212 | 10 | Antennas |  | Assembly | Widget.png |  | datatable[223] = new Array("224","212","Antennas","10","Widget.png");
225 | 219 | 11 | Omnidirectional |  | Component | Widget.png |  | datatable[224] = new Array("225","219","Omnidirectional","11","Widget.png");
226 | 219 | 11 | Spiral |  | Component | Widget.png |  | datatable[225] = new Array("226","219","Spiral","11","Widget.png");
227 | 219 | 11 | Horn |  | Component | Widget.png |  | datatable[226] = new Array("227","219","Horn","11","Widget.png");
228 | 219 | 11 | Patch |  | Component | Widget.png |  | datatable[227] = new Array("228","219","Patch","11","Widget.png");
229 | 219 | 11 | Parabolic |  | Component | Widget.png |  | datatable[228] = new Array("229","219","Parabolic","11","Widget.png");
230 | 219 | 11 | Phased Array |  | Component | Widget.png |  | datatable[229] = new Array("230","219","Phased Array","11","Widget.png");
231 | 219 | 11 | Other Antennas (Specify) |  | Component | Widget.png |  | datatable[230] = new Array("231","219","Other Antennas (Specify)","11","Widget.png");
232 | 212 | 10 | Waveguides/Routers |  | Assembly | Widget.png |  | datatable[231] = new Array("232","212","Waveguides/Routers","10","Widget.png");
233 | 227 | 11 | Diplexers |  | Component | Widget.png |  | datatable[232] = new Array("233","227","Diplexers","11","Widget.png");
234 | 227 | 11 | Triplexers |  | Component | Widget.png |  | datatable[233] = new Array("234","227","Triplexers","11","Widget.png");
235 | 227 | 11 | Multiplexers |  | Component | Widget.png |  | datatable[234] = new Array("235","227","Multiplexers","11","Widget.png");
236 | 227 | 11 | Multicouplers |  | Component | Widget.png |  | datatable[235] = new Array("236","227","Multicouplers","11","Widget.png");
237 | 227 | 11 | Coaxial Switches |  | Component | Widget.png |  | datatable[236] = new Array("237","227","Coaxial Switches","11","Widget.png");
238 | 227 | 11 | RF Switches |  | Component | Widget.png |  | datatable[237] = new Array("238","227","RF Switches","11","Widget.png");
239 | 227 | 11 | Filters |  | Component | Widget.png |  | datatable[238] = new Array("239","227","Filters","11","Widget.png");
240 | 227 | 11 | Waveguides |  | Component | Widget.png |  | datatable[239] = new Array("240","227","Waveguides","11","Widget.png");
241 | 227 | 11 | Other Routers (Specify) |  | Component | Widget.png |  | datatable[240] = new Array("241","227","Other Routers (Specify)","11","Widget.png");
242 | 212 | 10 | Radio Frequency Equipment |  | Assembly | Widget.png |  | datatable[241] = new Array("242","212","Radio Frequency Equipment","10","Widget.png");
243 | 237 | 11 | Amplifiers |  | Component | Widget.png |  | datatable[242] = new Array("243","237","Amplifiers","11","Widget.png");
244 | 237 | 11 | Receivers |  | Component | Widget.png |  | datatable[243] = new Array("244","237","Receivers","11","Widget.png");
245 | 237 | 11 | Transmitters |  | Component | Widget.png |  | datatable[244] = new Array("245","237","Transmitters","11","Widget.png");
246 | 237 | 11 | Transceivers |  | Component | Widget.png |  | datatable[245] = new Array("246","237","Transceivers","11","Widget.png");
247 | 237 | 11 | Transponders |  | Component | Widget.png |  | datatable[246] = new Array("247","237","Transponders","11","Widget.png");
248 | 237 | 11 | Modulators |  | Component | Widget.png |  | datatable[247] = new Array("248","237","Modulators","11","Widget.png");
249 | 237 | 11 | Demodulators |  | Component | Widget.png |  | datatable[248] = new Array("249","237","Demodulators","11","Widget.png");
250 | 237 | 11 | Modems |  | Component | Widget.png |  | datatable[249] = new Array("250","237","Modems","11","Widget.png");
251 | 237 | 11 | Traveling Wave Tube Assemblies |  | Component | Widget.png |  | datatable[250] = new Array("251","237","Traveling Wave Tube Assemblies","11","Widget.png");
252 | 237 | 11 | Solid State Power Amplifiers |  | Component | Widget.png |  | datatable[251] = new Array("252","237","Solid State Power Amplifiers","11","Widget.png");
253 | 237 | 11 | Global Positioning System (GPS) Receiver |  | Component | Widget.png |  | datatable[252] = new Array("253","237","Global Positioning System (GPS) Receiver","11","Widget.png");
254 | 237 | 11 | Downconverters |  | Component | Widget.png |  | datatable[253] = new Array("254","237","Downconverters","11","Widget.png");
255 | 237 | 11 | Upconverters |  | Component | Widget.png |  | datatable[254] = new Array("255","237","Upconverters","11","Widget.png");
256 | 237 | 11 | Other RF Equipment (Specify) |  | Component | Widget.png |  | datatable[255] = new Array("256","237","Other RF Equipment (Specify)","11","Widget.png");
257 | 212 | 10 | Command and Data Handling (C&DH) |  | Assembly | Widget.png |  | datatable[256] = new Array("257","212","Command and Data Handling (C&DH)","10","Widget.png");
258 | 252 | 11 | Processors |  | Component | Widget.png |  | datatable[257] = new Array("258","252","Processors","11","Widget.png");
259 | 252 | 11 | Solid State Memory |  | Component | Widget.png |  | datatable[258] = new Array("259","252","Solid State Memory","11","Widget.png");
260 | 252 | 11 | Decoders |  | Component | Widget.png |  | datatable[259] = new Array("260","252","Decoders","11","Widget.png");
261 | 252 | 11 | Command Units |  | Component | Widget.png |  | datatable[260] = new Array("261","252","Command Units","11","Widget.png");
262 | 252 | 11 | Telemetry Units |  | Component | Widget.png |  | datatable[261] = new Array("262","252","Telemetry Units","11","Widget.png");
263 | 252 | 11 | Command Sequencers |  | Component | Widget.png |  | datatable[262] = new Array("263","252","Command Sequencers","11","Widget.png");
264 | 252 | 11 | Timing Units |  | Component | Widget.png |  | datatable[263] = new Array("264","252","Timing Units","11","Widget.png");
265 | 252 | 11 | Frequency Generators |  | Component | Widget.png |  | datatable[264] = new Array("265","252","Frequency Generators","11","Widget.png");
266 | 252 | 11 | Signal Conditioners |  | Component | Widget.png |  | datatable[265] = new Array("266","252","Signal Conditioners","11","Widget.png");
267 | 252 | 11 | Data Switches |  | Component | Widget.png |  | datatable[266] = new Array("267","252","Data Switches","11","Widget.png");
268 | 252 | 11 | Communication Security |  | Component | Widget.png |  | datatable[267] = new Array("268","252","Communication Security","11","Widget.png");
269 | 252 | 11 | Interface Units |  | Component | Widget.png |  | datatable[268] = new Array("269","252","Interface Units","11","Widget.png");
270 | 252 | 11 | Tape Recorders |  | Component | Widget.png |  | datatable[269] = new Array("270","252","Tape Recorders","11","Widget.png");
271 | 252 | 11 | Disk Recorders |  | Component | Widget.png |  | datatable[270] = new Array("271","252","Disk Recorders","11","Widget.png");
272 | 252 | 11 | Command Sensor or Situational Awareness Sensors |  | Component | Widget.png |  | datatable[271] = new Array("272","252","Command Sensor or Situational Awareness Sensors","11","Widget.png");
273 | 252 | 11 | Other C&DH (Specify) |  | Component | Widget.png |  | datatable[272] = new Array("273","252","Other C&DH (Specify)","11","Widget.png");
274 | 212 | 10 | TT&C Other (Specify) |  | Assembly | Widget.png |  | datatable[273] = new Array("274","212","TT&C Other (Specify)","10","Widget.png");
275 | 61 | 9 | Bus Flight Software |  | Subsystem | Widget.png |  | datatable[274] = new Array("275","61","Bus Flight Software","9","Widget.png");
276 | 275 | 10 | Bus FSW Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[275] = new Array("276","275","Bus FSW Subsystem SEITPM","10","SEITPM.png");
277 | 271 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[276] = new Array("277","271","Project Management","11","SEITPM.png");
278 | 271 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[277] = new Array("278","271","Systems Engineering","11","SEITPM.png");
279 | 271 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[278] = new Array("279","271","Mission Assurance","11","SEITPM.png");
280 | 271 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[279] = new Array("280","271","Assembly, Integration and Testing","11","SEITPM.png");
281 | 271 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[280] = new Array("281","271","Support Equipment","11","SEITPM.png");
282 | 270 | 11 | Thermal Control Software |  | Component | Widget.png |  | datatable[281] = new Array("282","270","Thermal Control Software","11","Widget.png");
283 | 270 | 11 | Electrical Power Software |  | Component | Widget.png |  | datatable[282] = new Array("283","270","Electrical Power Software","11","Widget.png");
284 | 270 | 11 | Attitude Control Software |  | Component | Widget.png |  | datatable[283] = new Array("284","270","Attitude Control Software","11","Widget.png");
285 | 270 | 11 | Telemetry, Tracking, and Command Software |  | Component | Widget.png |  | datatable[284] = new Array("285","270","Telemetry, Tracking, and Command Software","11","Widget.png");
286 | 270 | 11 | Other Flight Software (Specify) |  | Component | Widget.png |  | datatable[285] = new Array("286","270","Other Flight Software (Specify)","11","Widget.png");
287 | 59 | 8 | SEITPM and Support Equipment (If Applicable for Integration of Multiple Payloads) |  | System | SEITPM.png |  | datatable[286] = new Array("287","59","SEITPM and Support Equipment (If Applicable for Integration of Multiple Payloads)","8","SEITPM.png");
288 | 282 | 9 | Project Management |  | Subsystem | SEITPM.png |  | datatable[287] = new Array("288","282","Project Management","9","SEITPM.png");
289 | 282 | 9 | Systems Engineering |  | Subsystem | SEITPM.png |  | datatable[288] = new Array("289","282","Systems Engineering","9","SEITPM.png");
290 | 282 | 9 | Mission Assurance |  | Subsystem | SEITPM.png |  | datatable[289] = new Array("290","282","Mission Assurance","9","SEITPM.png");
291 | 282 | 9 | Assembly, Integration and Testing |  | Subsystem | SEITPM.png |  | datatable[290] = new Array("291","282","Assembly, Integration and Testing","9","SEITPM.png");
292 | 282 | 9 | Support Equipment |  | Subsystem | SEITPM.png |  | datatable[291] = new Array("292","282","Support Equipment","9","SEITPM.png");
293 | 59 | 8 | Payload 1 … n (Specify) |  | System | Widget.png |  | datatable[292] = new Array("293","59","Payload 1 … n (Specify)","8","Widget.png");
294 | 293 | 9 | Payload 1 SEITPM and Support Equipment |  | Subsystem | SEITPM.png |  | datatable[293] = new Array("294","293","Payload 1 SEITPM and Support Equipment","9","SEITPM.png");
295 | 289 | 10 | Project Management |  | Assembly | SEITPM.png |  | datatable[294] = new Array("295","289","Project Management","10","SEITPM.png");
296 | 289 | 10 | Systems Engineering |  | Assembly | SEITPM.png |  | datatable[295] = new Array("296","289","Systems Engineering","10","SEITPM.png");
297 | 289 | 10 | Mission Assurance |  | Assembly | SEITPM.png |  | datatable[296] = new Array("297","289","Mission Assurance","10","SEITPM.png");
298 | 289 | 10 | Assembly, Integration and Testing |  | Assembly | SEITPM.png |  | datatable[297] = new Array("298","289","Assembly, Integration and Testing","10","SEITPM.png");
299 | 289 | 10 | Support Equipment |  | Assembly | SEITPM.png |  | datatable[298] = new Array("299","289","Support Equipment","10","SEITPM.png");
300 | 288 | 9 | Payload 1 Structures and Mechanisms Subsystem |  | Subsystem | Widget.png |  | datatable[299] = new Array("300","288","Payload 1 Structures and Mechanisms Subsystem","9","Widget.png");
301 | 295 | 10 | Structures and Mechanims Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[300] = new Array("301","295","Structures and Mechanims Subsystem SEITPM","10","SEITPM.png");
302 | 296 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[301] = new Array("302","296","Project Management","11","SEITPM.png");
303 | 296 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[302] = new Array("303","296","Systems Engineering","11","SEITPM.png");
304 | 296 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[303] = new Array("304","296","Mission Assurance","11","SEITPM.png");
305 | 296 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[304] = new Array("305","296","Assembly, Integration and Testing","11","SEITPM.png");
306 | 296 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[305] = new Array("306","296","Support Equipment","11","SEITPM.png");
307 | 295 | 10 | Structures |  | Assembly | Widget.png |  | datatable[306] = new Array("307","295","Structures","10","Widget.png");
308 | 295 | 10 | Mechanisms and Pyrotechnics |  | Assembly | Widget.png |  | datatable[307] = new Array("308","295","Mechanisms and Pyrotechnics","10","Widget.png");
309 | 295 | 10 | Structures and Mechanisms Other (Specify) |  | Assembly | Widget.png |  | datatable[308] = new Array("309","295","Structures and Mechanisms Other (Specify)","10","Widget.png");
310 | 288 | 9 | Payload 1 Thermal Control Subsystem |  | Subsystem | Widget.png |  | datatable[309] = new Array("310","288","Payload 1 Thermal Control Subsystem","9","Widget.png");
311 | 310 | 10 | Thermal Control Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[310] = new Array("311","310","Thermal Control Subsystem SEITPM","10","SEITPM.png");
312 | 306 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[311] = new Array("312","306","Project Management","11","SEITPM.png");
313 | 306 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[312] = new Array("313","306","Systems Engineering","11","SEITPM.png");
314 | 306 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[313] = new Array("314","306","Mission Assurance","11","SEITPM.png");
315 | 306 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[314] = new Array("315","306","Assembly, Integration and Testing","11","SEITPM.png");
316 | 306 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[315] = new Array("316","306","Support Equipment","11","SEITPM.png");
317 | 316 | 10 | Cryogenic Devices |  | Assembly | Widget.png |  | datatable[316] = new Array("317","316","Cryogenic Devices","10","Widget.png");
318 | 317 | 10 | Liquid Loops |  | Assembly | Widget.png |  | datatable[317] = new Array("318","317","Liquid Loops","10","Widget.png");
319 | 318 | 10 | Electric Coolers |  | Assembly | Widget.png |  | datatable[318] = new Array("319","318","Electric Coolers","10","Widget.png");
320 | 319 | 10 | Electric heaters, Thermisters, and Thermostats |  | Assembly | Widget.png |  | datatable[319] = new Array("320","319","Electric heaters, Thermisters, and Thermostats","10","Widget.png");
321 | 320 | 10 | Passive Devices |  | Assembly | Widget.png |  | datatable[320] = new Array("321","320","Passive Devices","10","Widget.png");
322 | 321 | 10 | Sun Shields |  | Assembly | Widget.png |  | datatable[321] = new Array("322","321","Sun Shields","10","Widget.png");
323 | 322 | 10 | Thermal Control Other (Specify) |  | Assembly | Widget.png |  | datatable[322] = new Array("323","322","Thermal Control Other (Specify)","10","Widget.png");
324 | 288 | 9 | Payload 1 Electrical Power Subsystem |  | Subsystem | Widget.png |  | datatable[323] = new Array("324","288","Payload 1 Electrical Power Subsystem","9","Widget.png");
325 | 319 | 10 | Electrical Power Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[324] = new Array("325","319","Electrical Power Subsystem SEITPM","10","SEITPM.png");
326 | 320 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[325] = new Array("326","320","Project Management","11","SEITPM.png");
327 | 320 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[326] = new Array("327","320","Systems Engineering","11","SEITPM.png");
328 | 320 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[327] = new Array("328","320","Mission Assurance","11","SEITPM.png");
329 | 320 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[328] = new Array("329","320","Assembly, Integration and Testing","11","SEITPM.png");
330 | 320 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[329] = new Array("330","320","Support Equipment","11","SEITPM.png");
331 | 319 | 10 | Power Sources |  | Assembly | Widget.png |  | datatable[330] = new Array("331","319","Power Sources","10","Widget.png");
332 | 319 | 10 | Power Control, Switching, and Distribution Electronics |  | Assembly | Widget.png |  | datatable[331] = new Array("332","319","Power Control, Switching, and Distribution Electronics","10","Widget.png");
333 | 319 | 10 | Power Conditioning, Conversion, and Regulation |  | Assembly | Widget.png |  | datatable[332] = new Array("333","319","Power Conditioning, Conversion, and Regulation","10","Widget.png");
334 | 319 | 10 | Harnesses and Cables |  | Assembly | Widget.png |  | datatable[333] = new Array("334","319","Harnesses and Cables","10","Widget.png");
335 | 319 | 10 | Electrical Power Other (Specify) |  | Assembly | Widget.png |  | datatable[334] = new Array("335","319","Electrical Power Other (Specify)","10","Widget.png");
336 | 288 | 9 | Payload 1 Pointing, Command, and Control Interface |  | Subsystem | Widget.png |  | datatable[335] = new Array("336","288","Payload 1 Pointing, Command, and Control Interface","9","Widget.png");
337 | 336 | 10 | Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[336] = new Array("337","336","Subsystem SEITPM","10","SEITPM.png");
338 | 332 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[337] = new Array("338","332","Project Management","11","SEITPM.png");
339 | 332 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[338] = new Array("339","332","Systems Engineering","11","SEITPM.png");
340 | 332 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[339] = new Array("340","332","Mission Assurance","11","SEITPM.png");
341 | 332 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[340] = new Array("341","332","Assembly, Integration and Testing","11","SEITPM.png");
342 | 332 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[341] = new Array("342","332","Support Equipment","11","SEITPM.png");
343 | 331 | 10 | Computers and Processors |  | Assembly | Widget.png |  | datatable[342] = new Array("343","331","Computers and Processors","10","Widget.png");
344 | 331 | 10 | Command/Telemetric Units |  | Assembly | Widget.png |  | datatable[343] = new Array("344","331","Command/Telemetric Units","10","Widget.png");
345 | 331 | 10 | Control Electronics |  | Assembly | Widget.png |  | datatable[344] = new Array("345","331","Control Electronics","10","Widget.png");
346 | 331 | 10 | Pointing Sensors |  | Assembly | Widget.png |  | datatable[345] = new Array("346","331","Pointing Sensors","10","Widget.png");
347 | 331 | 10 | Payload Positioners |  | Assembly | Widget.png |  | datatable[346] = new Array("347","331","Payload Positioners","10","Widget.png");
348 | 331 | 10 | Security, Encryption, and Decryption Devices |  | Assembly | Widget.png |  | datatable[347] = new Array("348","331","Security, Encryption, and Decryption Devices","10","Widget.png");
349 | 331 | 10 | Data Storage, handling, and Interface |  | Assembly | Widget.png |  | datatable[348] = new Array("349","331","Data Storage, handling, and Interface","10","Widget.png");
350 | 331 | 10 | Multifunctional Digital Electronic Boxes |  | Assembly | Widget.png |  | datatable[349] = new Array("350","331","Multifunctional Digital Electronic Boxes","10","Widget.png");
351 | 331 | 10 | Pointing, Command, and Control Interface Other (Specify) |  | Assembly | Widget.png |  | datatable[350] = new Array("351","331","Pointing, Command, and Control Interface Other (Specify)","10","Widget.png");
352 | 288 | 9 | Payload Signal Electronics |  | Subsystem | Widget.png |  | datatable[351] = new Array("352","288","Payload Signal Electronics","9","Widget.png");
353 | 347 | 10 | Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[352] = new Array("353","347","Subsystem SEITPM","10","SEITPM.png");
354 | 348 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[353] = new Array("354","348","Project Management","11","SEITPM.png");
355 | 348 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[354] = new Array("355","348","Systems Engineering","11","SEITPM.png");
356 | 348 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[355] = new Array("356","348","Mission Assurance","11","SEITPM.png");
357 | 348 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[356] = new Array("357","348","Assembly, Integration and Testing","11","SEITPM.png");
358 | 348 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[357] = new Array("358","348","Support Equipment","11","SEITPM.png");
359 | 347 | 10 | Passive Signal Flow Control |  | Assembly | Widget.png |  | datatable[358] = new Array("359","347","Passive Signal Flow Control","10","Widget.png");
360 | 347 | 10 | Transmitter/Receiver/Transceiver/Transponder |  | Assembly | Widget.png |  | datatable[359] = new Array("360","347","Transmitter/Receiver/Transceiver/Transponder","10","Widget.png");
361 | 347 | 10 | Modulators/Demodulators/Modems |  | Assembly | Widget.png |  | datatable[360] = new Array("361","347","Modulators/Demodulators/Modems","10","Widget.png");
362 | 347 | 10 | Multiplexers/Demultiplexers |  | Assembly | Widget.png |  | datatable[361] = new Array("362","347","Multiplexers/Demultiplexers","10","Widget.png");
363 | 347 | 10 | Amplifiers |  | Assembly | Widget.png |  | datatable[362] = new Array("363","347","Amplifiers","10","Widget.png");
364 | 347 | 10 | Frequency Upconverters/Downconverters |  | Assembly | Widget.png |  | datatable[363] = new Array("364","347","Frequency Upconverters/Downconverters","10","Widget.png");
365 | 347 | 10 | Frequency and Timing |  | Assembly | Widget.png |  | datatable[364] = new Array("365","347","Frequency and Timing","10","Widget.png");
366 | 347 | 10 | Signal Conditioners |  | Assembly | Widget.png |  | datatable[365] = new Array("366","347","Signal Conditioners","10","Widget.png");
367 | 347 | 10 | Multifunctional Digital Electronic Boxes |  | Assembly | Widget.png |  | datatable[366] = new Array("367","347","Multifunctional Digital Electronic Boxes","10","Widget.png");
368 | 347 | 10 | Signal Electronics Other (Specify) |  | Assembly | Widget.png |  | datatable[367] = new Array("368","347","Signal Electronics Other (Specify)","10","Widget.png");
369 | 288 | 9 | Payload 1 Optical Assembly |  | Subsystem | Widget.png |  | datatable[368] = new Array("369","288","Payload 1 Optical Assembly","9","Widget.png");
370 | 364 | 10 | Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[369] = new Array("370","364","Subsystem SEITPM","10","SEITPM.png");
371 | 365 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[370] = new Array("371","365","Project Management","11","SEITPM.png");
372 | 365 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[371] = new Array("372","365","Systems Engineering","11","SEITPM.png");
373 | 365 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[372] = new Array("373","365","Mission Assurance","11","SEITPM.png");
374 | 365 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[373] = new Array("374","365","Assembly, Integration and Testing","11","SEITPM.png");
375 | 365 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[374] = new Array("375","365","Support Equipment","11","SEITPM.png");
376 | 364 | 10 | Structure/Outerbarrel/Cover |  | Assembly | Widget.png |  | datatable[375] = new Array("376","364","Structure/Outerbarrel/Cover","10","Widget.png");
377 | 364 | 10 | Mirrors/Optics |  | Assembly | Widget.png |  | datatable[376] = new Array("377","364","Mirrors/Optics","10","Widget.png");
378 | 364 | 10 | Aft Optics Assembly |  | Assembly | Widget.png |  | datatable[377] = new Array("378","364","Aft Optics Assembly","10","Widget.png");
379 | 364 | 10 | Alignment and Calibration |  | Assembly | Widget.png |  | datatable[378] = new Array("379","364","Alignment and Calibration","10","Widget.png");
380 | 364 | 10 | Thermal |  | Assembly | Widget.png |  | datatable[379] = new Array("380","364","Thermal","10","Widget.png");
374 | 364 | 10 | Control Electronics |  | Assembly | Widget.png |  | datatable[373] = new Array("374","364","Control Electronics","10","Widget.png");
375 | 364 | 10 | Optical Assembly Other |  | Assembly | Widget.png |  | datatable[374] = new Array("375","364","Optical Assembly Other","10","Widget.png");
376 | 288 | 9 | Payload 1 Sensor |  | Subsystem | Widget.png |  | datatable[375] = new Array("376","288","Payload 1 Sensor","9","Widget.png");
377 | 378 | 10 | Sensor SEITPM |  | Assembly | SEITPM.png |  | datatable[376] = new Array("377","378","Sensor SEITPM","10","SEITPM.png");
378 | 379 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[377] = new Array("378","379","Project Management","11","SEITPM.png");
379 | 379 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[378] = new Array("379","379","Systems Engineering","11","SEITPM.png");
380 | 379 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[379] = new Array("380","379","Mission Assurance","11","SEITPM.png");
381 | 379 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[380] = new Array("381","379","Assembly, Integration and Testing","11","SEITPM.png");
382 | 379 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[381] = new Array("382","379","Support Equipment","11","SEITPM.png");
383 | 378 | 10 | Payload Structure |  | Assembly | Widget.png |  | datatable[382] = new Array("383","378","Payload Structure","10","Widget.png");
384 | 378 | 10 | Focal Plan Array |  | Assembly | Widget.png |  | datatable[383] = new Array("384","378","Focal Plan Array","10","Widget.png");
385 | 378 | 10 | Sensor Positioners |  | Assembly | Widget.png |  | datatable[384] = new Array("385","378","Sensor Positioners","10","Widget.png");
386 | 378 | 10 | Sensor Electronics |  | Assembly | Widget.png |  | datatable[385] = new Array("386","378","Sensor Electronics","10","Widget.png");
387 | 378 | 10 | Alignment and Calibration |  | Assembly | Widget.png |  | datatable[386] = new Array("387","378","Alignment and Calibration","10","Widget.png");
388 | 378 | 10 | Magnetometer |  | Assembly | Widget.png |  | datatable[387] = new Array("388","378","Magnetometer","10","Widget.png");
389 | 378 | 10 | Spectrometer |  | Assembly | Widget.png |  | datatable[388] = new Array("389","378","Spectrometer","10","Widget.png");
390 | 378 | 10 | Radiometer |  | Assembly | Widget.png |  | datatable[389] = new Array("390","378","Radiometer","10","Widget.png");
391 | 378 | 10 | Camera |  | Assembly | Widget.png |  | datatable[390] = new Array("391","378","Camera","10","Widget.png");
392 | 378 | 10 | Sounder |  | Assembly | Widget.png |  | datatable[391] = new Array("392","378","Sounder","10","Widget.png");
393 | 378 | 10 | Flight Sensor Software |  | Assembly | Widget.png |  | datatable[392] = new Array("393","378","Flight Sensor Software","10","Widget.png");
394 | 378 | 10 | Other Sensor Types (Specify) |  | Assembly | Widget.png |  | datatable[393] = new Array("394","378","Other Sensor Types (Specify)","10","Widget.png");
395 | 378 | 10 | Mission Sensor Other (Specify) |  | Assembly | Widget.png |  | datatable[394] = new Array("395","378","Mission Sensor Other (Specify)","10","Widget.png");
396 | 288 | 9 | Payload Flight Software |  | Subsystem | Widget.png |  | datatable[395] = new Array("396","288","Payload Flight Software","9","Widget.png");
397 | 396 | 10 | Payload 1 FSW SEITPM |  | Assembly | SEITPM.png |  | datatable[396] = new Array("397","396","Payload 1 FSW SEITPM","10","SEITPM.png");
398 | 392 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[397] = new Array("398","392","Project Management","11","SEITPM.png");
399 | 392 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[398] = new Array("399","392","Systems Engineering","11","SEITPM.png");
400 | 392 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[399] = new Array("400","392","Mission Assurance","11","SEITPM.png");
401 | 392 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[400] = new Array("401","392","Assembly, Integration and Testing","11","SEITPM.png");
402 | 392 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[401] = new Array("402","392","Support Equipment","11","SEITPM.png");
403 | 396 | 10 | CSCI (Specify) |  | Assembly | Widget.png |  | datatable[402] = new Array("403","396","CSCI (Specify)","10","Widget.png");
404 | 288 | 9 | Payload Antenna 1 … n (Specify) |  | Subsystem | Widget.png |  | datatable[403] = new Array("404","288","Payload Antenna 1 … n (Specify)","9","Widget.png");
405 | 399 | 10 | Payload 1 Antenna SEITPM |  | Assembly | SEITPM.png |  | datatable[404] = new Array("405","399","Payload 1 Antenna SEITPM","10","SEITPM.png");
406 | 400 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[405] = new Array("406","400","Project Management","11","SEITPM.png");
407 | 400 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[406] = new Array("407","400","Systems Engineering","11","SEITPM.png");
408 | 400 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[407] = new Array("408","400","Mission Assurance","11","SEITPM.png");
409 | 400 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[408] = new Array("409","400","Assembly, Integration and Testing","11","SEITPM.png");
410 | 400 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[409] = new Array("410","400","Support Equipment","11","SEITPM.png");
411 | 399 | 10 | Structures and Mechanisms |  | Assembly | Widget.png |  | datatable[410] = new Array("411","399","Structures and Mechanisms","10","Widget.png");
412 | 399 | 10 | Antenna Positioners |  | Assembly | Widget.png |  | datatable[411] = new Array("412","399","Antenna Positioners","10","Widget.png");
413 | 399 | 10 | Reflector/Horn |  | Assembly | Widget.png |  | datatable[412] = new Array("413","399","Reflector/Horn","10","Widget.png");
414 | 399 | 10 | Feed |  | Assembly | Widget.png |  | datatable[413] = new Array("414","399","Feed","10","Widget.png");
415 | 399 | 10 | Waveguide/Coad/Cabling |  | Assembly | Widget.png |  | datatable[414] = new Array("415","399","Waveguide/Coad/Cabling","10","Widget.png");
416 | 399 | 10 | Transmit/Receive Modules |  | Assembly | Widget.png |  | datatable[415] = new Array("416","399","Transmit/Receive Modules","10","Widget.png");
417 | 399 | 10 | Antenna Other (Specify) |  | Assembly | Widget.png |  | datatable[416] = new Array("417","399","Antenna Other (Specify)","10","Widget.png");
418 | 288 | 9 | Payload Other (Specify) |  | Subsystem | Widget.png |  | datatable[417] = new Array("418","288","Payload Other (Specify)","9","Widget.png");
419 | 418 | 10 | Booster Adapter |  | Assembly | Widget.png |  | datatable[418] = new Array("419","418","Booster Adapter","10","Widget.png");
420 | 418 | 10 | Space Vehicle Storage |  | Assembly | Widget.png |  | datatable[419] = new Array("420","418","Space Vehicle Storage","10","Widget.png");
421 | 418 | 10 | Space Vehicle Other (Specify) |  | Assembly | Widget.png |  | datatable[420] = new Array("421","418","Space Vehicle Other (Specify)","10","Widget.png");
422 | 12 | 7 | Launch Systems Integration (LSI) |  |  | Rocket.png |  | datatable[421] = new Array("422","12","Launch Systems Integration (LSI)","7","Rocket.png");
423 | 12 | 7 | Launch Operations |  |  | Rocket.png |  | datatable[422] = new Array("423","12","Launch Operations","7","Rocket.png");
424 | 12 | 7 | Launch Operations Support |  |  | Rocket.png |  | datatable[423] = new Array("424","12","Launch Operations Support","7","Rocket.png");
425 | 12 | 7 | Launch Vehicle Services |  |  | Rocket.png |  | datatable[424] = new Array("425","12","Launch Vehicle Services","7","Rocket.png");
426 | 12 | 7 | Launch Insurance |  |  | Rocket.png |  | datatable[425] = new Array("426","12","Launch Insurance","7","Rocket.png");
427 | 13 | 7 | Ground Segment SEITPM |  | Assembly | SEITPM.png |  | datatable[426] = new Array("427","13","Ground Segment SEITPM","7","SEITPM.png");
428 | 422 | 8 | Project Management |  | Component | SEITPM.png |  | datatable[427] = new Array("428","422","Project Management","8","SEITPM.png");
429 | 422 | 8 | Systems Engineering |  | Component | SEITPM.png |  | datatable[428] = new Array("429","422","Systems Engineering","8","SEITPM.png");
430 | 422 | 8 | Mission Assurance |  | Component | SEITPM.png |  | datatable[429] = new Array("430","422","Mission Assurance","8","SEITPM.png");
431 | 422 | 8 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[430] = new Array("431","422","Assembly, Integration and Testing","8","SEITPM.png");
432 | 422 | 8 | Support Equipment |  | Component | SEITPM.png |  | datatable[431] = new Array("432","422","Support Equipment","8","SEITPM.png");
433 | 13 | 7 | Mission Control Centers |  |  | Facility.png |  | datatable[432] = new Array("433","13","Mission Control Centers","7","Facility.png");
434 | 13 | 7 | Science / Data Ops Centers |  |  | Facility.png |  | datatable[433] = new Array("434","13","Science / Data Ops Centers","7","Facility.png");
435 | 13 | 7 | Terminals and Data Networks – incl Antennas |  |  | Facility.png |  | datatable[434] = new Array("435","13","Terminals and Data Networks – incl Antennas ","7","Facility.png");
436 | 13 | 7 | Data Distribution & Archival |  |  | Facility.png |  | datatable[435] = new Array("436","13","Data Distribution & Archival ","7","Facility.png");
437 | 13 | 7 | Training Facilities |  |  | Facility.png |  | datatable[436] = new Array("437","13","Training Facilities ","7","Facility.png");
438 | 433 | 8 | CSA Mission Control |  |  | Facility.png |  | datatable[437] = new Array("438","433","CSA Mission Control","8","Facility.png");
439 | 438 | 9 | SatOps Mission Control Complex at JHCSC |  |  | Facility.png |  | datatable[438] = new Array("439","438","SatOps Mission Control Complex at JHCSC ","9","Facility.png");
440 | 438 | 9 | ISS Mission Operations Complex |  |  | Facility.png |  | datatable[439] = new Array("440","438","ISS Mission Operations Complex","9","Facility.png");
441 | 433 | 8 | NASA Mission Operations Complex |  |  | Facility.png |  | datatable[440] = new Array("441","433","NASA Mission Operations Complex","8","Facility.png");
442 | 435 | 10 | RMPSR |  |  | Facility.png |  | datatable[441] = new Array("442","435","RMPSR","10","Facility.png");
443 | 435 | 10 | OEC |  |  | Facility.png |  | datatable[442] = new Array("443","435","OEC","10","Facility.png");
444 | 435 | 10 | PTOC |  |  | Facility.png |  | datatable[443] = new Array("444","435","PTOC","10","Facility.png");
445 | 439 | 10 | SatOps Mission control SEITPM |  | Assembly | SEITPM.png |  | datatable[444] = new Array("445","439","SatOps Mission control SEITPM","10","SEITPM.png");
446 | 440 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[445] = new Array("446","440","Project Management","11","SEITPM.png");
447 | 440 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[446] = new Array("447","440","Systems Engineering","11","SEITPM.png");
448 | 440 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[447] = new Array("448","440","Mission Assurance","11","SEITPM.png");
449 | 440 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[448] = new Array("449","440","Assembly, Integration and Testing","11","SEITPM.png");
450 | 440 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[449] = new Array("450","440","Support Equipment","11","SEITPM.png");
451 | 434 | 10 | Hardware Components |  |  | Facility.png |  | datatable[450] = new Array("451","434","Hardware Components","10","Facility.png");
452 | 446 | 11 | Workstations |  |  | Facility.png |  | datatable[451] = new Array("452","446","Workstations","11","Facility.png");
453 | 446 | 11 | Servers |  |  | Facility.png |  | datatable[452] = new Array("453","446","Servers","11","Facility.png");
454 | 446 | 11 | Storage and Archive |  |  | Facility.png |  | datatable[453] = new Array("454","446","Storage and Archive","11","Facility.png");
455 | 446 | 11 | Network Equipment |  |  | Facility.png |  | datatable[454] = new Array("455","446","Network Equipment","11","Facility.png");
456 | 446 | 11 | Interface Equipment |  |  | Facility.png |  | datatable[455] = new Array("456","446","Interface Equipment","11","Facility.png");
457 | 446 | 11 | Security Encryption/Decryption |  |  | Facility.png |  | datatable[456] = new Array("457","446","Security Encryption/Decryption","11","Facility.png");
458 | 446 | 11 | Data Processing |  |  | Facility.png |  | datatable[457] = new Array("458","446","Data Processing","11","Facility.png");
459 | 446 | 11 | COTS Hardware Other (Specify) |  |  | Facility.png |  | datatable[458] = new Array("459","446","COTS Hardware Other (Specify)","11","Facility.png");
460 | 446 | 11 | Pre-Operations Maintenance (Specify) |  |  | Facility.png |  | datatable[459] = new Array("460","446","Pre-Operations Maintenance (Specify)","11","Facility.png");
461 | 446 | 11 | Environments |  |  | Facility.png |  | datatable[460] = new Array("461","446","Environments","11","Facility.png");
462 | 434 | 10 | SatOps GS Software |  |  | Facility.png |  | datatable[461] = new Array("462","434","SatOps GS Software","10","Facility.png");
463 | 462 | 11 | SW CSCI |  |  | Facility.png |  | datatable[462] = new Array("463","462","SW CSCI","11","Facility.png");
464 | 429 | 8 | NASA Science Operations Centers |  |  | Facility.png |  | datatable[463] = new Array("464","429","NASA Science Operations Centers","8","Facility.png");
465 | 429 | 8 | HPC (High Performance Computing) |  |  | Facility.png |  | datatable[464] = new Array("465","429","HPC (High Performance Computing)","8","Facility.png");
466 | 429 | 8 | Geospace Observatory |  |  | Facility.png |  | datatable[465] = new Array("466","429","Geospace Observatory","8","Facility.png");
467 | 429 | 8 | Other SODC (specify) |  |  | Facility.png |  | datatable[466] = new Array("467","429","Other SODC (specify)","8","Facility.png");
468 | 435 | 8 | CSA Terminals and Antennas |  |  | Facility.png |  | datatable[467] = new Array("468","435"," CSA Terminals and Antennas","8","Facility.png");
469 | 463 | 9 | CSA St-Hubert Antenna |  |  | Facility.png |  | datatable[468] = new Array("469","463","CSA St-Hubert Antenna","9","Facility.png");
470 | 463 | 9 | Ferme Yves Bachand Antenna |  |  | Facility.png |  | datatable[469] = new Array("470","463","Ferme Yves Bachand Antenna","9","Facility.png");
471 | 463 | 9 | Ferme Beldor Antenna |  |  | Facility.png |  | datatable[470] = new Array("471","463","Ferme Beldor Antenna","9","Facility.png");
472 | 463 | 9 | Transponder |  |  | Facility.png |  | datatable[471] = new Array("472","463","Transponder","9","Facility.png");
473 | 431 | 8 | Digital Earth Canada |  |  | Facility.png |  | datatable[472] = new Array("473","431","Digital Earth Canada","8","Facility.png");
474 | 431 | 8 | Federal Geospatial Platform (FGP) |  |  | Facility.png |  | datatable[473] = new Array("474","431","Federal Geospatial Platform (FGP)","8","Facility.png");
475 | 431 | 8 | EODMS |  |  | Facility.png |  | datatable[474] = new Array("475","431","EODMS","8","Facility.png");
476 | 431 | 8 | Canadian Astronomy Data Centre |  |  | Facility.png |  | datatable[475] = new Array("476","431","Canadian Astronomy Data Centre","8","Facility.png");
477 | 431 | 8 | NASA Data Distribution & Archival |  |  | Facility.png |  | datatable[476] = new Array("477","431","NASA Data Distribution & Archival","8","Facility.png");
478 | 437 | 8 | MMLC |  |  | Facility.png |  | datatable[477] = new Array("478","437","MMLC","8","Facility.png");
479 | 437 | 8 | MOTS |  |  | Facility.png |  | datatable[478] = new Array("479","437","MOTS","8","Facility.png");
480 | 14 | 7 | CSA Mission Operations |  |  | Ops.png |  | datatable[479] = new Array("480","14","CSA Mission Operations","7","Ops.png");
481 | 475 | 8 | CSA SatOps |  |  | Ops.png |  | datatable[480] = new Array("481","475","CSA SatOps","8","Ops.png");
482 | 475 | 8 | CSA ISS Ops |  |  | Ops.png |  | datatable[481] = new Array("482","475","CSA ISS Ops","8","Ops.png");
483 | 475 | 8 | CSA ISS Sustaining Engineering |  |  | Ops.png |  | datatable[482] = new Array("483","475","CSA ISS Sustaining Engineering","8","Ops.png");
484 | 14 | 7 | NASA Mission Operations |  |  | Ops.png |  | datatable[483] = new Array("484","14","NASA Mission Operations","7","Ops.png");
485 | 14 | 7 | Industry Partners (Specify) |  |  | Ops.png |  | datatable[484] = new Array("485","14","Industry Partners (Specify)","7","Ops.png");
486 | 15 | 7 | Mission Science Support |  |  | Science.png |  | datatable[485] = new Array("486","15","Mission Science Support","7","Science.png");
487 | 481 | 8 | Science Maturation Studies & User Requirements |  |  | Science.png |  | datatable[486] = new Array("487","481","Science Maturation Studies & User Requirements","8","Science.png");
488 | 481 | 8 | Science Support for Mission Development |  |  | Science.png |  | datatable[487] = new Array("488","481","Science Support for Mission Development","8","Science.png");
489 | 481 | 8 | Science Support for Commissioning, Including Cal/Val |  |  | Science.png |  | datatable[488] = new Array("489","481","Science Support for Commissioning, Including Cal/Val","8","Science.png");
490 | 481 | 8 | Science Support for Data Handling |  |  | Science.png |  | datatable[489] = new Array("490","481","Science Support for Data Handling","8","Science.png");
491 | 15 | 7 | Science Utilization & Application Development |  |  | Science.png |  | datatable[490] = new Array("491","15","Science Utilization & Application Development","7","Science.png");

## 2 - Phasing Nomenclature
` Table of Contents
7 - Phasing Nomenclature | [5 empty] | What do you call your phases?
Why we we asking:
1. To normalize the naming convention across all investments.
2. Math Models are based on Costing Sub-Phase.
3. We want to output results in your naming convention and scope.
| Based on IGMF rev E |  |  | Based on CSA-FIN-RPT-0072
Phasing according to |  |  | Phasing according to |  |  | Phasing according to
EPMO |  |  | Costing |  |  | PM
|  |  | PREP | PREP 1 | Prototyping Activities (before Gate 1)
Pre-Project | Option Analysis & Planning Phase | Pre-Phase 0 |  | PREP 2 | Prototyping Activities (during Phase 0/A)
|  | Phase 0 | Phase 0/A | Phase 0 | Concept & Feasibility | Phase 0
Project | Definition Phase | Detailed Project Requirements |  | Phase A | Mission Requirements | Phase A
|  | Preliminary Definition | Phase B/C | Phase B | Preliminary Design | Phase B
|  | Detailed Definition |  | Phase C | Detailed Design | Phase C
| Implementation Phase | Implementation | Phase D | MAIT | Manufacturing, Assembly, Integration and Test of Canadian Subsystems and Components | Phase D
|  |  |  | SAIT | Spacecraft Level Assembly, Test | Phase D
|  |  |  | LEOP | Lauch and early operations | Phase D
Post-Project | Post-Implementation Phase | Operations & Disposal | Phase E | Phase E | Nominal Operations (per design life) | Phase E
|  |  | Phase E (EXT) | Phase X | Extended operations (mission extension)
|  |  | Phase F | Phase F | Disposal (incl. post-mortem audit reports) | Phase F
|  |  | Phase G | Phase G | Post-Mortem science utilization
Specify your labels
here. Repeat text if necessary. Leave blank if not included in your scope
Specify your labels
here. Repeat text if necessary. Leave blank if not included in your scope

## 3 - Phase Durations
` Table of Contents
7b - Phasing Durations
Why we we asking:
1. Durations affect Govt Salaries calculations
2. Durations affect Parametric estimates for Space segment, ground segment, ops
3. Schedule Scenarios are inputs to sensitivity analysis
| Schedule Scenario ID | 1
| Scenario Name | Nominal Schedule Used by Gaby for RAM calculation (PM Nomenclature)
| Scenario Description | Phases 0 through F
| Rationale | ORCA concept-stage schedule, consistent with CADRe Part A section 2.5
| Source Doc | CADRe Part A
| Phase | Expected Start | Expected End | Total D | Total M | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060
| Phase 0 | 2026-01-01 | 2027-12-31 | 729 | 23.9671 | 2.9589 | 12 | 9.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase A | 2028-01-01 | 2029-12-31 | 730 | 24 | 0 | 0 | 2.9918 | 12 | 9.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase B1 | 2030-01-01 | 2030-12-31 | 364 | 11.9671 | 0 | 0 | 0 | 0 | 2.9589 | 9.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase B2 | 2031-01-01 | 2031-12-31 | 364 | 11.9671 | 0 | 0 | 0 | 0 | 0 | 2.9589 | 9.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase C | 2032-01-01 | 2033-12-31 | 730 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9918 | 12 | 9.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase D | 2034-01-01 | 2040-12-31 | 2556 | 84.0329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9589 | 12 | 12.0329 | 12 | 12 | 12 | 12.0329 | 9.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase E | 2041-01-01 | 2055-12-31 | 5477 | 180.0658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9589 | 12 | 12 | 12.0329 | 12 | 12 | 12 | 12.0329 | 12 | 12 | 12 | 12.0329 | 12 | 12 | 12 | 9.0411 | 0 | 0 | 0 | 0
| Phase X | 2056-01-01 | 2059-06-30 | 1276 | 41.9507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9918 | 12 | 12 | 12 | 2.9918
| Phase F | 2059-07-01 | 2059-12-28 | 180 | 5.9178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.9507
| Phase D1-MAIT | 2034-01-01 | 2038-06-30 | 1641 | 53.9507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9589 | 12 | 12.0329 | 12 | 12 | 2.9918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase D2-SAIT | 2038-07-01 | 2040-09-30 | 822 | 27.0247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.0082 | 12.0329 | 6.0164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase D3-LEOP | 2040-10-01 | 2040-12-31 | 91 | 2.9918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B22: Assumption: this template's Phase Durations tab has no separate Cruise row. The ~10-year outbound cruise to Saturn is counted inside Phase E (Nominal Operations), consistent with the design life of at least 15 years including cruise requirement in CADRe Part A. CADRe Part A section 2.5 presents cruise as its own line for narrative clarity; the two are reconciled here for costing purposes.

## PM's sched Scenarios
|  | ORCA Ref. | 2026-01-01
Phase | Milestone | ORCA Baseline | Orbiter Platform (Partner Agency) | ORCA Instrument Suite | Worst case duration | Worst case (+2 mo/phase) | Realistic case duration | Baseline: Realistic case date (1 month delay per phase) | Optimistic case duration | Optimistic case | Comments
Phase 0 | Mission Concept Review (MCR) | 2027-12-31 | N/A | N/A | 25.9198 | 2028-02-29 | 24.9671 | 2028-01-31 | 22.9304 | 2027-11-30 | End of Phase 0; mission concept baseline.
Phase A | System Requirements Review (SRR) | 2029-12-31 | N/A | N/A | 51.9054 | 2030-04-30 | 49.9014 | 2030-02-28 | 45.9593 | 2029-10-31 | End of Phase A.
Phase A | ORCA Concept Rebaseline | 2029-07-01 12:00 | N/A | N/A | 45.9921 | 2029-11-01 | 43.9882 | 2029-09-01 | 39.9474 | 2029-05-01 | Programmatic baseline update within Phase A. | Phases | Duration (months) | Expected start | Expected finish
Phase B | Orbiter Bus / ORCA Instrument Suite Interface Complete | 2031-03-14 09:36 | Interface requirements | Interface requirements | 68.3968 | 2031-09-14 | 65.3745 | 2031-06-14 | 59.3955 | 2030-12-14 | Partner-agency orbiter interface control document (ICD) finalized. | Phase 0 | 23.9671 | 2026-01-01 | 2027-12-31
Phase B | Preliminary Design Review (PDR) | 2031-12-31 | Bus accommodation | Preliminary design | 77.9238 | 2032-06-30 | 74.9343 | 2032-03-31 | 68.9225 | 2031-09-30 | End of Phase B (B1+B2). | Phase A | 24 | 2028-01-01 | 2029-12-31
Phase C | Instrument Suite Environmental Qualification Complete | 2033-03-14 | N/A | Qualification | 94.4152 | 2033-11-14 | 90.3745 | 2033-07-14 | 82.4244 | 2032-11-14 | Vibration / thermal-vacuum qualification of the ORCA instrument suite. | Phase B1 | 11.9671 | 2030-01-01 | 2030-12-31
Phase C | Critical Design Review (CDR) | 2033-12-31 | Bus accommodation | Critical design | 103.9422 | 2034-08-31 | 99.9014 | 2034-04-30 | 91.9514 | 2033-08-31 | End of Phase C. | Phase B2 | 11.9671 | 2031-01-01 | 2031-12-31
MAIT | Manufacturing Readiness Review (MRR) | 2036-03-31 12:00 | N/A | N/A | 132.9829 | 2037-01-31 | 127.9566 | 2036-08-31 | 117.9369 | 2035-10-31 | Mid-MAIT manufacturing readiness checkpoint. | Phase C | 24 | 2032-01-01 | 2033-12-31
MAIT | Pre-Ship Review of Systems to Prime (PSR) | 2040-07-04 | Integration readiness | Integration readiness | 184.0342 | 2041-05-04 | 179.0736 | 2040-12-04 | 169.0867 | 2040-02-04 | ~6 months before launch. | Phase D | 84.0329 | 2034-01-01 | 2040-12-31
SAIT | Integrated Instrument Suite Functional Test Complete | 2040-08-31 | N/A | Functional test | 185.9067 | 2041-06-30 | 180.979 | 2041-01-31 | 170.9264 | 2040-03-31 | Ahead of System Integration Review. | Phase E | 180.0658 | 2041-01-01 | 2055-12-31
SAIT | System Integration Review (SIR) | 2040-09-30 | Bus integration | Instrument integration | 186.8922 | 2041-07-30 | 181.8988 | 2041-02-28 | 171.912 | 2040-04-30 | ORCA integrated onto partner-agency orbiter bus. | Phase X | 41.9507 | 2056-01-01 | 2059-06-30
SAIT | Acceptance Review (AR) | 2040-10-02 | Flight acceptance | Flight acceptance | 186.9908 | 2041-08-02 | 181.9645 | 2041-03-02 | 171.9777 | 2040-05-02 | ~3 months before launch. | Phase F | 5.9178 | 2059-07-01 | 2059-12-28
SAIT | Flight Software and Autonomy Verification Complete | 2040-11-01 | N/A | N/A | 187.9763 | 2041-09-01 | 182.9501 | 2041-04-01 | 172.9632 | 2040-06-01 | Autonomy and fault-management software verified. | Total | 407.8685
LEOP | Pre-Ship Review – Spacecraft to Launch Site | 2040-11-16 | Bus checkout | N/A | 188.4691 | 2041-09-16 | 183.4428 | 2041-04-16 | 173.456 | 2040-06-16 | Before shipment to launch site.
LEOP | Launch | 2040-12-31 | N/A | N/A | 189.9474 | 2041-10-31 | 184.9212 | 2041-05-31 | 174.9343 | 2040-07-31 | End of Phase D; Jupiter gravity-assist trajectory.
LEOP | Commissioning Review (CR) | 2041-01-14 | Bus checkout | Instrument checkout | 190.4074 | 2041-11-14 | 185.3811 | 2041-06-14 | 175.3942 | 2040-08-14 | Post-launch systems checkout, ~2 weeks after launch.
Phase E | Start of Nominal Operations | 2041-01-01 | N/A | Plume sampling begins | 191.9842 | 2042-01-01 | 185.9396 | 2041-07-01 | 173.9488 | 2040-07-01 | Start of Phase E.
Phase E | End of Nominal Operations | 2055-12-31 | N/A | N/A | 371.9448 | 2056-12-31 | 365.9001 | 2056-06-30 | 353.8765 | 2055-06-30 | End of Phase E; 4-year prime science mission.
Phase X | End of Life / Disposal Operations Complete | 2059-06-30 | N/A | N/A | 415.9001 | 2060-08-30 | 408.9028 | 2060-01-30 | 394.908 | 2058-11-30 | End of Phase X; optional mission extension.
ORCA Milestone Reference
| Milestone | Realistic Date |  | Phase | Purpose
| Mission Concept Review (MCR) | 2027-12-31 |  | Phase 0 | Mission concept baseline
| System Requirements Review (SRR) | 2029-12-31 |  | Phase A | Requirements baseline
| ORCA Concept Rebaseline | 2029-07-01 12:00 |  | Phase A | Programmatic baseline update
| Orbiter Bus / ORCA Instrument Suite Interface Complete | 2031-03-14 09:36 |  | Phase B | Interface control document finalized
| Preliminary Design Review (PDR) | 2031-12-31 |  | Phase B | Preliminary design maturity
| Instrument Suite Environmental Qualification Complete | 2033-03-14 |  | Phase C | Instrument suite qualification
| Critical Design Review (CDR) | 2033-12-31 |  | Phase C | Design baseline approval
| Manufacturing Readiness Review (MRR) | 2036-03-31 12:00 |  | MAIT | Manufacturing readiness
| Pre-Ship Review of Systems to Prime (PSR) | 2040-07-04 |  | MAIT | Transfer readiness
| Integrated Instrument Suite Functional Test Complete | 2040-08-31 |  | SAIT | Functional test readiness
| System Integration Review (SIR) | 2040-09-30 |  | SAIT | Integrated system readiness
| Acceptance Review (AR) | 2040-10-02 |  | SAIT | Flight acceptance
| Flight Software and Autonomy Verification Complete | 2040-11-01 |  | SAIT | Software verification
| Pre-Ship Review – Spacecraft to Launch Site | 2040-11-16 |  | LEOP | Launch-site readiness
| Launch | 2040-12-31 |  | LEOP | Launch
| Commissioning Review (CR) | 2041-01-14 |  | LEOP | Commissioning complete
| Start of Nominal Operations | 2041-01-01 |  | Phase E | Plume-sampling operations begin
| End of Nominal Operations | 2055-12-31 |  | Phase E | Nominal mission complete
| End of Life / Disposal Operations Complete | 2059-06-30 |  | Phase X | Mission closeout
Formulas:
ORCA Baseline = [ORCA Baseline, row above]+14
Worst case (+2 mo/phase) = EDATE([ORCA Baseline],2)
Optimistic case = EDATE([ORCA Baseline],-1)

## GR&A (hidden)
Costing CSA Ground Rules & Assumptions template
Last review |  |  | 2025-03-31
ID | Catégorie | Category | Category | Sub-category | Items | GR or A | Title | Description | Phase | CBS # linked to GR&A | Impact on Project | Impact on costing, methodology, models, tools & analysis | Excepted source | Do not delete | Source/Link | Other rational | Waiver deviation
1 | Hypothèses Programmatiques | Strategy Naratives | Objectifs politiques et stratégiques | Alignement sur la stratégie de l’ASC | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Strategy
2 | Hypothèses Programmatiques | Strategy Naratives | Objectifs politiques et stratégiques | Contraintes gouvernementales ou directives de haut niveau | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Strategy
3 | Hypothèses Programmatiques |  | Objectifs politiques et stratégiques | Type de mission : Flagship, LargeSat, SmallSat, NanoSat, Hosted Payload, Data stream partnership, data stream purchase | [8 empty] | CADRE Part A | CADRE Part A ou contants
4 | Hypothèses Programmatiques |  | Objectifs politiques et stratégiques | Disciplines et secteur : SatCom, Astronomie, exploration spatiale,... | [8 empty] | CADRE Part A | CADRE Part A
5 | Hypothèses Programmatiques |  | Objectifs politiques et stratégiques | Dépendances avec d'autres projets/missions | [8 empty] | CADRE Part A | CADRE Part A
6 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Soumission au Conseil du Tésor (TBSub) - But de l'exercice de costing : Budget Ask, Reprofiling,… Définir le nombre de TBSub + échéancier associé aux TBSub | [8 empty] | CADRE Part C onglet Stratégie contractuelle | Strategy
7 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Enveloppe de la masse salariale | [8 empty] | CADRE Part C onglet RAM | Strategy
8 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Enveloppe des frais de gestion et plan de voyages | [8 empty] | CADRE Part C onglet Overhead Costs | Strategy
9 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Méthodologie d'établissement des coûts | [8 empty] | Plan de l’exercice d’établissement des coûts | Costing Plan
10 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Note de réflexion supplémentaire | [9 empty] | Costing Plan
11 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Au moins 2 façon différentes pour chaque incluant RAM | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
12 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analyse de sensibilité | [8 empty] | À compléter par Finance | Costing Plan
13 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Sufficiency Report or Independent Cost Estimate or Independent Cost Review | [8 empty] | À compléter par Finance | Costing Plan
14 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analogie (nearest neighboors), lesquels. | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
15 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analyse paramétrique (True planning, PCEC, NCIM, SEER, Compact). CER Calibration Plan. | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
16 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Soumission de l'industrie et jugement d'expert | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
17 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analyse Monte Carlo (crystal ball) | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
18 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Bottom up, qui le fait et comment | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
19 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Learning curves | [8 empty] | RASCI = qui fait quoi. bottom up = Plan de l’exercice d’établissement des coûts | Costing Plan
20 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Inducteurs de coûts princicaux | [8 empty] | CADRE Part C onglet CER & Tools | Costing Plan
21 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Normalisation ( Stochométrie) - si applicable | [8 empty] | le choix de l'outil dicte CADRE part B qui collecte info pour l'analyse paramétrique | Costing Plan
22 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Tracabilité - accès aux sources - répertoires normalisés -liens | [8 empty] | CADRE Part C onglet CER & Tools | Costing Plan
23 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Stratégie de financement | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Strategy
24 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Limitation des coûts : Par exemple, les sources de financement instables, les contraintes de personnel ou un budget à ne pas dépasser devraient être documentés. | [8 empty] | CADRE Part C onglet Stratégie contractuelle | Strategy
25 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Enveloppe Services internes - O&M et RAM | [8 empty] | CADRE Part C onglet Services internes | Strategy
26 | Hypothèses Programmatiques | OBS | Partenariats (OGD, internationaux, industriels) | Rôles et responsabilités des principaux partenaires (agences spatiales, industriels, universités et autres ministères) | [8 empty] | CADRE Part C onglet OBS | OBS
27 | Hypothèses Programmatiques | OBS | Partenariats (OGD, internationaux, industriels) | Modalités de partage des coûts et des risques | [8 empty] | CADRE Part C onglet OBS - Cost Sharing provisions | OBS
28 | Hypothèses Programmatiques | Strategy Naratives | Partenariats (OGD, internationaux, industriels) | Si applicable, dépenses éligibles de l'OTAN | [8 empty] | À définir ici | Strategy
29 | Hypothèses Programmatiques | 8. Economic Constants and short answers | Gouvernance et autorités | Ordre de grandeur général du projet (petit, moyen, grand, flagship) | [8 empty] | CERCES scale | Constants
30 | Hypothèses Programmatiques | Costign Plan | Gouvernance et autorités | Nature of the costing perimeter (degree of difficulty of costing exercise) | [8 empty] | Plan de l’exercice d’établissement des coûts | Costing Plan
31 | Hypothèses Programmatiques | 8. Economic Constants and short answers | Gouvernance et autorités | Palier/ Tier | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Constants
32 | Hypothèses Programmatiques | 8. Economic Constants and short answers | Gouvernance et autorités | PCRA | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Constants
33 | Hypothèses Programmatiques | Milestone Register | Gouvernance et autorités | Point de décision | [8 empty] | CADRE Part C - onglet Phasing Model | Milestone Register
34 | Hypothèses Programmatiques | Costign Plan | Gouvernance et autorités | Costing Exercise Schedule and associated milestones - Costing Plan, Internal WebReport Dashboard and power BI dashboard for CLAD | [8 empty] | Plan de l’exercice d’établissement des coûts | Costing Plan
35 | Hypothèses Financières | 8. Inflation Model | Indices économiques et inflation | Taux d’inflation annuel, indice utilisé (IPC, indice sectoriel), taux de déflation | [8 empty] | Inflation Model dans son propre document - Oracle db ID | Inflation Model
36 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | Taux EBP 27% | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
37 | Hypothèses Financières | 8. Inflation Model | Indices économiques et inflation | Modèle d'inflation appliqué | [8 empty] | Inflation Model dans son propre document - Oracle db ID | Inflation Model
38 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | Année de base / Base year | [9 empty] | Constants
39 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | SSC 4% | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
40 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | PSPC 13% | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
41 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | Taux du Fairness Monitor | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
42 | Hypothèses Financières | 8. Economic Constants and short answers | Taux de change | Monnaies concernées et valeur de référence (CAD, USD, EUR, etc.) | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
43 | Hypothèses Financières | 8. Economic Constants and short answers | Taux de change | Seuil de variation accepté avant révision budgétaire | [8 empty] | Defined in constnats, used in risk analysis. risk reserve - Risk register | Constants
44 | Hypothèses Financières | 8. Economic Constants and short answers | Contingence et marges de sécurité | Pourcentage de contingence sur le coût total du projet (p. ex. 10 à 20 %) | [8 empty] | Defined in constnats, used in risk analysis. risk register onglet. Unknown-Unknown Risk margin | Constants
45 | Hypothèses Financières | Strategy Naratives | Contingence et marges de sécurité | Barème d’évaluation des risques majeurs pour justifier la marge appliquée (modèle d’analyse de risques) | [8 empty] | À définir ici | Strategy | Je ne comprends pas la question
46 | Hypothèses Financières | Procurement Plan | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Sunk Costs Report (STDP, EOADP, Cap Demo, Stedia FAST, ESA Program, Cubesats, space hub, Pre-Phase 0 etc) | [8 empty] | CADRe part C - Expenditure plan | Procurement Plan
47 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stratégie contractuel Phase 0/A - 1 / 2 contrats | [8 empty] | CADRe Part C - Procurement strategy | Strategy
48 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Note de réflexion supplémentaire | [9 empty] | Strategy
49 | Hypothèses Financières | Procurement Plan | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Nombre de contrats et valeur approximative prévus par phase | [8 empty] | CADRe Part C - Procurement Plan (list) | Procurement Plan
50 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Contrats en parallèle avec des concepts différents et un down select | [8 empty] | CADRe Part C - Procurement strategy | Strategy
51 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Agile ou waterfall | [8 empty] | CADRe Part C - Procurement strategy | Strategy
52 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | STDP ou CapDemo en même temps que la phase 0 ou A | [8 empty] | PREP 2 | Strategy
53 | Hypothèses Financières | OBS | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Les fournisseurs attendus et leur capacite de production | [8 empty] | OBS | OBS
54 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Type de SOW - SOW directif versus une architecture de mission proposée par le fournisseur | [8 empty] | CADRe Part C - Procurement strategy | Strategy
55 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Freedom of Design of Vendor | [8 empty] | CADRE Part C onglet OBS Maturité orgnisationelle du fourniseur | Strategy
56 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Types de contrat – source unique ou compétitif (Contrat dirigé en Phase E ops aura une incidence sur le design du ground segment) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
57 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Types de contrat – cout remboursable ou prix ferme | [8 empty] | CADRe Part C - Procurement strategy | Strategy
| Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Type de contrat: gonogo, options, milestones in April for CAFÉ | [9 empty] | Strategy | Split next line into 2
58 | Hypothèses Financières | 12 - Dispose, Divest, Descope, Delay | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Gestion du scope change et des risques dans chaque situation : cout remboursable (TA, options, gouvernance) ; prix ferme (descope, go no go, qualité du SOW a décrire le scope) | [8 empty] | Descope est dans DDD | DDDD
59 | Hypothèses Financières |  | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | G&C (cassiope ou radarsat 2) nous appartient pas | [8 empty] | Business model (CADRe part A) et le procurement strategy le repete | CADRE Part A
60 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | incitatif commercial (ex. modele de commercialization comme a prior mission) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
61 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Pour chaque phase et sous-systeme majeur - CSA led, industry led, academia led (ex. En Phase E, CSA va mener les operations) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
62 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Competitif - ouvert a l'international | [8 empty] | CADRe Part C - Procurement strategy | Strategy
63 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Competitif - ouvert au Canada | [8 empty] | CADRe Part C - Procurement strategy | Strategy
64 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Fausse competition | [8 empty] | CADRe Part C - Procurement strategy | Strategy
65 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | monopole | [8 empty] | CADRe Part C - Procurement strategy | Strategy
66 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Dependences : Le fournisseur X doit etre le meme fournisseur que le fournisseur Y (Ex. Data processing handled by same supplier) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
67 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Long lead Item - flux de trésorie en capital vs contrat vs échéancier | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Strategy
68 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Contenu Canadien | [8 empty] | CADRe Part C - Procurement strategy | Strategy
69 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Chaque contrat couvre quel partie du travail, liste d'inclusions et exclusions. List of inclusions and exclusions | [8 empty] | CBS Dictionary | Strategy
70 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | GFE and GFS (ex. DFL) | [8 empty] | CBS Dictionary | Strategy
71 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Frais de transport et responsabilité | [8 empty] | CBS Dictionary | Strategy
72 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Frais d'assurance et limitation de responsabilité | [8 empty] | CBS Dictionary | Strategy
73 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Qualité du SOW | [8 empty] | RISK posture | Strategy
74 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stabilité des exigences. Par exemple, des exigences très instables, un nombre standard de demandes de modification technique, des exigences stables avec peu ou pas de changements attendus, etc. | [8 empty] | CADRe Part C - Procurement strategy | Strategy
75 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Résultats du RFI | [8 empty] | Procurement strategy | Strategy
76 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stratégie contractuelle Phase BCD - Concurrentiel, source unique (voir note de réflexion du point 2.4.1) | [8 empty] | Procurement strategy | Strategy
77 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stratégie contractuelle Phase EF - Concurrentiel, source unique (voir note de réflexion du point 2.4.1) | [8 empty] | Procurement strategy | Strategy
78 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Capacité du vendeur dans le marché actuel, surcharge contractuel, effectif disponible | [8 empty] | OBS Maturité orgnisationelle du fourniseur | Strategy
79 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Taux standard pour les ingénieurs, techniciens, gestionnaires, etc. | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
80 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Taux spécifiques pour les consultants ou experts externes | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
81 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Barème pour les appels d’offres et la sous-traitance (plafonds, politiques internes) | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
82 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Taux de frais et de profit appliqué au contrat | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
83 | Hypothèses Financières | Risk Register | Plan de gestion des risques financiers | Existence d’une réserve pour risques identifiés (p. ex. volatilité du marché, retards de paiement) | [8 empty] | Registre de risque | Risk Register
84 | Hypothèses Financières | 12 - Dispose, Divest, Descope, Delay | Plan de gestion des risques financiers | Descope Plan and other strategies to deal with funding shortfalls, | [8 empty] | À définir ici et lié au CADRE Part C - onglet DDDD | DDDD
85 | Hypothèses Financières | Procurement Plan | Plan de gestion des risques financiers | Source of funding for each CBS element and Risk to A-Base | [8 empty] | Expenditure plan | Procurement Plan
86 | Hypothèses Financières | 8. Economic Constants and short answers | Taxes | Pays, province et taux de taxes applicables | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
87 | Hypothèses Techniques (Space & Ground Segment) | TRRA | Technologie et niveau de maturité (TRL) | TRL initial prévu pour les composants clés | [8 empty] | CADRE Part C onglet TRL | TRL
88 | Hypothèses Techniques (Space & Ground Segment) | TRRA | Technologie et niveau de maturité (TRL) | Objectifs de TRL à atteindre pour chaque phase du projet | [8 empty] | CADRE Part C onglet TRL | TRL
89 | Hypothèses Techniques (Space & Ground Segment) | 4a. CBS and CBS Dictionary | Sous-systèmes et architecture globale | Liste et description des principaux sous-systèmes (structure, propulsion, contrôle d’attitude, communication, etc.) | [8 empty] | CBS | CBS
90 | Hypothèses Techniques (Space & Ground Segment) | TRRA | Sous-systèmes et architecture globale | Interfaces critiques (par ex. protocole de communication, alignement mécanique) | [8 empty] | TRL assessment tab - worry list | TRL
91 | Hypothèses Techniques (Space & Ground Segment) | Costign Plan | Sous-systèmes et architecture globale | This ground rule should state, at a high level, what is within scope of the estimate. For example, an estimate may cover the space segment, ground segment, and government oversight during phases B, C and D. Further clarification should be given if required, such as refurbishment of the ground segment rather than complete rebuild. | [8 empty] | Perimeter of costing exercise. Further Claraifications in CBs dictionary | Costing Plan
92 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | Stratégie de validation (modèles d’ingénierie, prototypes, simulations) | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
93 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | Méthodes d’essais en environnement (thermique, vibration, vide, etc.) | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
94 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | This assumption should state the expected build approach for the mission. For example, the bus/platform and payloads could be built in series or parallel. | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
95 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | This assumption should state the cost improvement curve, as a percentile, for any items to be acquired with more than a single unit. If appropriate, items should be marked as Xth unit within a lot, such as the 8th unit, to allow for cost improvement curve theory to be reflected. | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
96 | Hypothèses Techniques (Space & Ground Segment) | Engineering Parameters in CADRe part B | Contraintes techniques spécifiques | Estimation de masse et de volume du système | [8 empty] | CADRE part B | CADRE part B
97 | Hypothèses Techniques (Space & Ground Segment) | Engineering Parameters in CADRe part B | Contraintes techniques spécifiques | Consommation électrique maximale | [8 empty] | CADRE part B | CADRE part B
98 | Hypothèses Techniques (Space & Ground Segment) | Engineering Parameters in CADRe part B | Contraintes techniques spécifiques | Besoins minimaux pour assurer la fiabilité | [8 empty] | CADRE part B | CADRE part B
99 | Hypothèses Qualité, Fiabilité et Sécurité | Strategy Naratives | Normes et standards de qualité | ECSS-Q-ST-20, ISO 9001, etc. | [8 empty] | À définir ici | Strategy
100 | Hypothèses Qualité, Fiabilité et Sécurité | Strategy Naratives | Normes et standards de qualité | Méthodes d’assurance qualité (revues, audits internes et externes) | [8 empty] | À définir ici | Strategy
101 | Hypothèses Qualité, Fiabilité et Sécurité | 8. Economic Constants and short answers | Safety and mission assurance | Classe de Mission | [8 empty] | À définir ici | Constants
102 | Hypothèses Qualité, Fiabilité et Sécurité | Strategy Naratives | Safety and mission assurance | La mesure de la surveillance et de la rigueur appliquées par la CSA | [8 empty] | À définir ici | Strategy
103 | Hypothèses Opérationnelles | RAM | Ressources humaines et expertise | Équipe de base (ETP internes) et besoins en personnel spécialisé externe | [8 empty] | CADRE Part C onglet RAM | RAM
104 | Hypothèses Opérationnelles | Strategy Naratives | Ressources humaines et expertise | Disponibilité du personnel et plan de montée en compétence | [8 empty] | À définir ici | Strategy
105 | Hypothèses Opérationnelles | Milestone Register | Calendrier, jalons et ressources temporelles | Dates clés (ex. PDR – Preliminary Design Review, CDR – Critical Design Review, FRR – Flight Readiness Review) / Project Milestone Register (short report, detailed report) | [8 empty] | milestone Register | Milestone Register
106 | Hypothèses Opérationnelles |  | Calendrier, jalons et ressources temporelles | Diagram of Phase Overlaps and Gaps | [8 empty] | we draw it form phasing | GANTT Charts
107 | Hypothèses Opérationnelles | Schedule Constraints and Dependencies | Calendrier, jalons et ressources temporelles | Marges pour délais | [8 empty] | Phasing Model, phases | Schedule Constraints
108 | Hypothèses Opérationnelles | 12 - Dispose, Divest, Descope, Delay | Calendrier, jalons et ressources temporelles | Gestion des retards : conditions de replanification, procédures d’escalade | [8 empty] | À définir ici et lié au CADRE Part C - onglet DDDD | DDDD
109 | Hypothèses Opérationnelles | Phasing Schedules | Calendrier, jalons et ressources temporelles | Modèle de phase utilisé pour analyse de sensibilité (Phasing Model) | [8 empty] | Phasing model (for risk analysis) | Phasing Schedules
110 | Hypothèses Opérationnelles | Phasing Schedules | Calendrier, jalons et ressources temporelles | Échéancier de l'industrie | [8 empty] | Phasing model (for risk analysis) | Phasing Schedules
111 | Hypothèses Opérationnelles | Phasing Schedules | Calendrier, jalons et ressources temporelles | Schedule Scenarios for sensitivity analysis : Adjust Durations - optimistic, pessimistic and expected | [8 empty] | Phasing model (for risk analysis) | Phasing Schedules
112 | Hypothèses Opérationnelles | Strategy Naratives | Planification des infrastructures et installations | Is DFL being used as GFE | [8 empty] | DFL being used? Strategy | Strategy
112 | Hypothèses Opérationnelles | 4a. CBS and CBS Dictionary | Planification des infrastructures et installations | Lieux de développement, sites d’intégration et de test (chambres à vide, bancs de test) | [8 empty] | CBS Dictionary - Ground Segment - Test facilities | CBS Dictionary
113 | Hypothèses Opérationnelles | Schedule Constraints and Dependencies | Planification des infrastructures et installations | Disponibilité des installations (ex. créneaux de test partagés avec d’autres projets) | [8 empty] | schedule risk = risk register -> pessimistic schedule model | Schedule Constraints
114 | Hypothèses Opérationnelles | Schedule Constraints and Dependencies | Gestion de la logistique et de la chaîne d’approvisionnement | Délai de livraison des composants critiques (satellites, propulseurs, éléments électroniques) | [8 empty] | schedule risk = risk register -> pessimistic schedule model | Schedule Constraints
115 | Hypothèses Opérationnelles | Strategy Naratives | Gestion de la logistique et de la chaîne d’approvisionnement | Plans de contingence en cas de rupture d’approvisionnement | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | Strategy
116 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | Description des opérations prévues : phases de lancement, mise à l’orbite, opérations nominales, etc. | [8 empty] | Cadre part A | CADRE Part A
117 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | Mode de supervision et contrôle (centres de contrôle, horaires, équipes) | [8 empty] | À définir ici | Cadre Part A
118 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | Mission Operation Center | [8 empty] | À définir ici | Cadre Part A
119 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | GoC Science Operation Centers (SOCs) | [8 empty] | À définir ici | Cadre Part A
120 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | External Science Operation Centers (ESOCs) | [8 empty] | À définir ici | Cadre Part A
121 | Hypothèses sur la science | Schedule Constraints and Dependencies | Science et applications | Échéancier lié au volet de science du projet | [9 empty] | Schedule Constraints
122 | Hypothèses sur la science | Strategy Naratives | Science et applications | Expected cost of science utilization related to the mission. | [9 empty] | Strategy
123 | Hypothèses sur la science | Strategy Naratives | Portée de la mission sur le milieu public et académique | Coût en lien avec la portée de la mission | [8 empty] | À définir ici | Strategy
124 | Hypothèses Lancement |  | Véhicule de lancement | Sélection du lanceur (ex. Falcon 9, Ariane, etc.) ou fenêtre de lancement partagée | [8 empty] | Cadre part A | CADRE Part A
125 | Hypothèses Lancement |  | Véhicule de lancement | Capacités du lanceur (masse, volume, orbite cible) | [8 empty] | Cadre part A un petit peu et le reste dans le LV database CM list | CADRE Part A
126 | Hypothèses Lancement | Schedule Constraints and Dependencies | Calendrier de lancement | Fenêtres de lancement disponibles (contraintes de météo, alignement orbital, etc.) | [8 empty] | schedule risk = risk register -> pessimistic schedule model | Schedule assumptions and constraints for JCL Analysis
127 | Hypothèses Lancement | 12 - Dispose, Divest, Descope, Delay | Calendrier de lancement | Contingences pour reports éventuels | [8 empty] | schedule risk = risk register -> pessimistic schedule model | DDDD
128 | Hypothèses Lancement | OBS | Contrat et services associés | Responsabilités du fournisseur de lancement (intégration, tests, qualification) | [8 empty] | OBS (roles et responsiblity) - CSa qui paye ou MDa qui paye | OBS
129 | Hypothèses Lancement | 4a. CBS and CBS Dictionary | Contrat et services associés | Assurances (couverture du satellite, du lanceur, etc.) | [8 empty] | CBS Dictionary - if insurance | CBS Dictionary
130 | Hypothèses Opérations en orbite |  | Mode opératoire | Gestion du satellite ou rover (téléopération vs. autonomie) | [9 empty] | Cadre Part A
131 | Hypothèses Opérations en orbite | Engineering Parameters in CADRe part B | Mode opératoire | Durée et fréquence des communications | [8 empty] | CADRE Part B | CADRE part B
132 | Hypothèses Opérations en orbite |  | Maintenance, réparations et évolutions | Possibilité ou non de mise à jour logicielle en vol (OTA updates) | [8 empty] | CADRE part A - Bus FSW section | CADRE Part A
133 | Hypothèses Opérations en orbite |  | Maintenance, réparations et évolutions | Stratégiques de réparation ou d’assistance robotique | [8 empty] | CADRE part A - does it have any robotic repair interfaces | CADRE Part A
134 | Hypothèses Opérations en orbite | 12 - Dispose, Divest, Descope, Delay | Fin de mission et désorbitation | Scénario de désorbitation contrôlée ou passivation (réservoirs, batteries) | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
135 | Hypothèses Opérations en orbite | 12 - Dispose, Divest, Descope, Delay | Fin de mission et désorbitation | Dépôt sur orbite-cimetière pour le matériel en fin de vie (si admissible) | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
136 | Hypothèses Opérations en orbite | Strategy Naratives | Flux de documentation et reporting | Fréquence des rapports d’avancement (hebdomadaires, mensuels) | [8 empty] | À définir ici | Strategy
137 | Hypothèses Opérations en orbite | Strategy Naratives | Classifications et diffusion | Niveau de confidentialité (projet public, secret défense, propriété intellectuelle) | [8 empty] | À définir ici | Strategy
138 | Hypothèses Opérations en orbite | Strategy Naratives | Classifications et diffusion | Politiques de publication ou de diffusion des résultats | [8 empty] | À définir ici et/ou Business Case | Strategy
139 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Réglementations gouvernementales | Exigences fédérales (agences spatiales, ministères, etc.) | [8 empty] | À définir ici et/ou Business Case | Strategy
140 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Réglementations gouvernementales | Normes internationales (ECSS, ISO, NASA, CSA, etc.) | [8 empty] | À définir ici et/ou Business Case | Strategy
141 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Réglementations gouvernementales | Règles et régulations afférentes | [8 empty] | À définir ici et/ou Business Case | Strategy
142 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Contrôle à l’exportation (ex. ITAR, EAR) | Identification des composants ou technologies soumis à licences | [8 empty] | À définir ici | Strategy
143 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Contrôle à l’exportation (ex. ITAR, EAR) | Implications sur la gestion des fournisseurs et des partenaires étrangers | [8 empty] | À définir ici | Strategy
144 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Sécurité et sûreté | Mesures de cybersécurité (protection des données, des communications, etc.) | [8 empty] | À définir ici | Strategy
145 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Sécurité et sûreté | Exigences de sûreté pour le personnel et les installations (accès restreints, habilitations) | [8 empty] | À définir ici | Strategy
146 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Droit spatial et aspects juridiques | Propriété et exploitation des données spatiales | [8 empty] | À définir ici | Strategy
147 | Hypothèses Légales, Réglementaires et Sécuritaires | 12 - Dispose, Divest, Descope, Delay | Droit spatial et aspects juridiques | Protocole en cas de débris spatiaux, en fin de vie du satellite | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
148 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Propriété intellectuelle | Propriété intellectuel en lien avec le projet - enjeux | [8 empty] | À définir ici et/ou Business Case | Strategy
149 | Hypothèses Environnementales | 12 - Dispose, Divest, Descope, Delay | Gestion des débris spatiaux | Respect des lignes directrices d’atténuation des débris (liaisons, désorbitation en fin de vie) | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
150 | Hypothèses Environnementales | 12 - Dispose, Divest, Descope, Delay | Gestion des débris spatiaux | Méthodes envisagées pour minimiser la pollution orbitale | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
151 | Hypothèses Environnementales | Green space | Impacts environnementaux terrestres | Contrôle des émissions lors du lancement (polluants, bruit, etc.) | [8 empty] | CADRE Part C onglet Green Space | Green Space
152 | Hypothèses Environnementales | Strategy Naratives | Impacts environnementaux terrestres | Politique de recyclage ou de réutilisation des composants | [8 empty] | CADRE Part C onglet Green Space | Strategy
153 | Hypothèses sur le risques | Risk Register | Risques | Risque du Projet Phase A à D | [8 empty] | Registre de risque | Risk Register
154 | Hypothèses sur le risques | Risk Register | Risques | Risque du Projet Phase E | [8 empty] | Registre de risque | Risk Register
155 | Hypothèses sur le risques | Risk Register | Risques | Risque du Projet Phase F | [8 empty] | Registre de risque | Risk Register
156 | Hypothèses sur le risques | Risk Register | Risques | Risque Science | [8 empty] | Registre de risque | Risk Register
157 | Hypothèses sur le risques | Risk Register | Risques | Risque Salaire | [8 empty] | Registre de risque | Risk Register
158 | Hypothèses sur le risques | Risk Register | Risques | Schedule Risk Assessment file (ms project) as input to the Joint Cost and Schedule Confidence Analysis Report | [8 empty] | Registre de risque | Risk Register
159 | Hypothèses sur le risques | Risk Register | Risques | Registre de risque | [8 empty] | Registre de risque | Risk Register
160 | Hypothèses sur le risques | Strategy Naratives | Risques | Aspect critique de la mission et impact si la mission n'est pas respectée | [8 empty] | minimum mission success criteria - DRM - CADRE part C Taxon | Strategy
161 | Hypothèse sur les mesures de performance par la valeur acquise | CADRe part D - EVM | Mesures de performance par la valeur acquise (EVM = Earn Value Management) | Seuil orange et rouge pour EVM justifiant une réduction de la portée, une replanification | [9 empty] | pas dans ce fichier, pas avant PDR
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343

## 4 - RAM LoE
9 - RAM LoE Inputs
Why we are asking:
To capture the ORCA project's Resource Allocation Matrix: every position on the team, its classification, and its Level of Effort (LoE) as a fraction of full-time equivalent (FTE) by mission phase. Rate is looked up from 'Labour Rates lookup' by Classification, and the fiscal-year \$ columns are computed self-contained on this sheet from LoE x rate x schedule-phase-month overlap (see '3 - Phase Durations'). EBP and inflation figures are illustrative placeholders.
| RAM Scenario ID | 1
| Scenario Name | Nominal RAM
| Scenario Description | The baseline RAM used for ORCA's staffing plan.
| Rationale | Derived from the ORCA instrument suite WBS/CBS and the Phase Durations schedule.
| Source Doc | N/A - illustrative, pending confirmed CSA staffing plan
Defaults | [8 empty] | Provided by PM | [6 empty] | LoE as % of one FTE, by phase (PM input) | [6 empty] | Rates tab | FTE per fiscal year, calculated from '3 - Phase Durations' and the phase LoE on the left
Row Num | Agency / Dep't | Team | Skillset Group | Skillset | Title - Role | Additional Labels | Branch | Directorate | Employee Name | Position No | New or Existing | Classification | Echelon | Math Model | Funding Source | Phase 0 | Phase A | Phase B | Phase C | Phase D | Phase E | Phase F | Rate ($) | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | Total (FTE-yrs)
1 | CSA | Project Team | Project Manager | PM | Portfolio Manager | Program Office | Space Exploration | Program Management | Alan Whitfield | ORCA-PM-001 | Existing | EN-ENG-6 | Max Echelon | Labour Rates | FF-CSA | 0% | 0% | 21% | 0% | 42% | 100% | 0% | 165000 | 0 | 0 | 0 | 0 | 0.051781 | 0.21 | 0.15822 | 0 | 0.10356 | 0.42 | 0.42115 | 0.42 | 0.42 | 0.42 | 0.42115 | 0.56301 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 0.24932 | 21.8692
2 | CSA | Project Team | Project Manager | Mission Management | ORCA Mission Manager | Program Office | Space Exploration | Program Management | Marie Tremblay | ORCA-PM-002 | Existing | PC-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 100% | 5% | 10% | 67% | 100% | 0% | 122000 | 0 | 0 | 0.24932 | 1 | 0.76575 | 0.05 | 0.062603 | 0.1 | 0.24055 | 0.67 | 0.67184 | 0.67 | 0.67 | 0.67 | 0.67184 | 0.75137 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 0.24932 | 25.5035
3 | CSA | Project Team | Scientific | Mission Ops | Mission Operations Scientist | Science Segment | Space Exploration | Planetary Science | Devon Okafor | ORCA-SCI-001 | New | PC-3 | Max Echelon | Labour Rates | FF-CSA | 0% | 100% | 100% | 0% | 73% | 0% | 0% | 105000 | 0 | 0 | 0.24932 | 1 | 1 | 1 | 0.75342 | 0 | 0.18 | 0.73 | 0.732 | 0.73 | 0.73 | 0.73 | 0.732 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1167
4 | CSA | Project Team | Project Manager | PM | Lead Project Manager | Program Office | Space Exploration | Program Management | Priya Raman | ORCA-PM-003 | New | EN-ENG-5 | Max Echelon | Labour Rates | FF-CSA | 0% | 100% | 25% | 25% | 27% | 100% | 0% | 145000 | 0 | 0 | 0.24932 | 1 | 0.81507 | 0.25 | 0.25068 | 0.25 | 0.25493 | 0.27 | 0.27074 | 0.27 | 0.27 | 0.27 | 0.27074 | 0.45 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 0.24932 | 23.4018
5 | CSA | Project Team | Project Manager | PM | Deputy Project Manager | Program Office | Space Exploration | Program Management | Étienne Lacroix | ORCA-PM-004 | New | EN-ENG-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 15% | 0% | 0% | 70% | 0% | 0% | 128000 | 0 | 0 | 0.037397 | 0.15 | 0.11301 | 0 | 0 | 0 | 0.1726 | 0.7 | 0.70192 | 0.7 | 0.7 | 0.7 | 0.70192 | 0.5274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2042
6 | CSA | Project Team | Project Manager | Planning | Project Management Engineer | Program Office | Space Exploration | Program Management | Grace Lindqvist | ORCA-PM-005 | New | EN-ENG-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 20% | 10% | 0% | 48% | 10% | 0% | 128000 | 0 | 0 | 0.049863 | 0.2 | 0.17534 | 0.1 | 0.075342 | 0 | 0.11836 | 0.48 | 0.48132 | 0.48 | 0.48 | 0.48 | 0.48132 | 0.3863 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.024932 | 5.8139
7 | CSA | Project Team | Project Manager | Cost & Schedule | Schedule and Cost Management Engineer | Program Office | Space Exploration | Program Management | Samuel Boucher | ORCA-PM-006 | New | EN-ENG-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 100% | 10% | 100% | 45% | 100% | 0% | 128000 | 0 | 0 | 0.24932 | 1 | 0.77808 | 0.1 | 0.32466 | 1 | 0.86438 | 0.45 | 0.45123 | 0.45 | 0.45 | 0.45 | 0.45123 | 0.58562 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 0.24932 | 25.8648
8 | CSA | Project Team | Systems | Systems Engineering | Lead Spacecraft Systems Engineer | Instrument Suite | Space Exploration | Engineering | Naomi Fitzgerald | ORCA-SE-001 | New | EN-ENG-5 | Max Echelon | Labour Rates | FF-CSA | 0% | 30% | 0% | 25% | 37% | 5% | 0% | 145000 | 0 | 0 | 0.074795 | 0.3 | 0.22603 | 0 | 0.062329 | 0.25 | 0.27959 | 0.37 | 0.37101 | 0.37 | 0.37 | 0.37 | 0.37101 | 0.2911 | 0.05 | 0.05 | 0.050137 | 0.05 | 0.05 | 0.05 | 0.050137 | 0.05 | 0.05 | 0.05 | 0.050137 | 0.05 | 0.05 | 0.05 | 0.050137 | 0.05 | 0.05 | 0.05 | 0.012466 | 4.6189
9 | CSA | Project Team | Systems | Systems Engineering | Spacecraft Systems Engineer | Instrument Suite | Space Exploration | Engineering | Kevin Anand | ORCA-SE-002 | New | EN-ENG-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 10% | 5% | 100% | 5% | 21% | 0% | 128000 | 0 | 0 | 0.024932 | 0.1 | 0.087671 | 0.05 | 0.28699 | 1 | 0.76575 | 0.05 | 0.050137 | 0.05 | 0.05 | 0.05 | 0.050137 | 0.089452 | 0.21 | 0.21 | 0.21058 | 0.21 | 0.21 | 0.21 | 0.21058 | 0.21 | 0.21 | 0.21 | 0.21058 | 0.21 | 0.21 | 0.21 | 0.21058 | 0.21 | 0.21 | 0.21 | 0.052356 | 6.5397
10 | CSA | Project Team | Speciality Engineer | GNC | Instrument Pointing / GNC Engineer | Instrument Suite | Space Exploration | Engineering | Isabelle Roy | ORCA-GNC-001 | New | EN-ENG-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 0% | 0% | 0% | 2% | 0% | 0% | 128000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0049315 | 0.02 | 0.020055 | 0.02 | 0.02 | 0.02 | 0.020055 | 0.015068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14011
11 | CSA | Project Team | Speciality Engineer | Robotics | Sampling Arm (ISA) Systems Engineer (Option C) | Instrument Suite | Space Exploration | Engineering | Marcus Delgado | ORCA-ISA-001 | New | EN-ENG-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 0% | 0% | 55% | 7% | 55% | 0% | 128000 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13712 | 0.55 | 0.43164 | 0.07 | 0.070192 | 0.07 | 0.07 | 0.07 | 0.070192 | 0.18836 | 0.55 | 0.55 | 0.55151 | 0.55 | 0.55 | 0.55 | 0.55151 | 0.55 | 0.55 | 0.55 | 0.55151 | 0.55 | 0.55 | 0.55 | 0.55151 | 0.55 | 0.55 | 0.55 | 0.13712 | 11.7707
12 | CSA | Project Team | Speciality Engineer | S&MA | Safety and Mission Assurance Engineer | Instrument Suite | Space Exploration | Engineering | Fatima Haidari | ORCA-SMA-001 | New | EN-ENG-5 | Max Echelon | Labour Rates | FF-CSA | 0% | 30% | 100% | 35% | 37% | 30% | 0% | 145000 | 0 | 0 | 0.074795 | 0.3 | 0.4726 | 1 | 0.84068 | 0.35 | 0.35493 | 0.37 | 0.37101 | 0.37 | 0.37 | 0.37 | 0.37101 | 0.35274 | 0.3 | 0.3 | 0.30082 | 0.3 | 0.3 | 0.3 | 0.30082 | 0.3 | 0.3 | 0.3 | 0.30082 | 0.3 | 0.3 | 0.3 | 0.30082 | 0.3 | 0.3 | 0.3 | 0.074795 | 11.4459
13 | CSA | Project Team | Speciality Engineer | FDIR | Fault Detection, Isolation and Recovery Engineer | Instrument Suite | Space Exploration | Engineering | Robert Cianci | ORCA-FDIR-001 | New | EN-ENG-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 10% | 0% | 5% | 0% | 30% | 0% | 128000 | 0 | 0 | 0.024932 | 0.1 | 0.075342 | 0 | 0.012466 | 0.05 | 0.037671 | 0 | 0 | 0 | 0 | 0 | 0 | 0.073973 | 0.3 | 0.3 | 0.30082 | 0.3 | 0.3 | 0.3 | 0.30082 | 0.3 | 0.3 | 0.3 | 0.30082 | 0.3 | 0.3 | 0.3 | 0.30082 | 0.3 | 0.3 | 0.3 | 0.074795 | 5.8525
14 | CSA | Project Team | Speciality Engineer | SatOps | Mission Operations and Ground Systems Engineer | Ground Segment | Space Exploration | Mission Operations | Simone Bergeron | ORCA-OPS-001 | New | EN-ENG-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 10% | 40% | 0% | 5% | 20% | 0% | 128000 | 0 | 0 | 0.024932 | 0.1 | 0.17397 | 0.4 | 0.30137 | 0 | 0.012329 | 0.05 | 0.050137 | 0.05 | 0.05 | 0.05 | 0.050137 | 0.086986 | 0.2 | 0.2 | 0.20055 | 0.2 | 0.2 | 0.2 | 0.20055 | 0.2 | 0.2 | 0.2 | 0.20055 | 0.2 | 0.2 | 0.2 | 0.20055 | 0.2 | 0.2 | 0.2 | 0.049863 | 5.0519
15 | CSA | Project Team | Speciality Engineer | Instruments | Mass Spectrometer Lead Engineer | Instrument Suite | Space Exploration | Engineering | Yusuf Karimi | ORCA-INS-001 | New | PC-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 10% | 100% | 20% | 33% | 5% | 0% | 122000 | 0 | 0 | 0.024932 | 0.1 | 0.32192 | 1 | 0.80329 | 0.2 | 0.23205 | 0.33 | 0.3309 | 0.33 | 0.33 | 0.33 | 0.3309 | 0.26096 | 0.05 | 0.05 | 0.050137 | 0.05 | 0.05 | 0.05 | 0.050137 | 0.05 | 0.05 | 0.05 | 0.050137 | 0.05 | 0.05 | 0.05 | 0.050137 | 0.05 | 0.05 | 0.05 | 0.012466 | 5.838
16 | CSA | Project Team | Speciality Engineer | Radar | Ice-Penetrating Radar Lead Engineer | Instrument Suite | Space Exploration | Engineering | Charlotte Nadeau | ORCA-INS-002 | New | PC-3 | Max Echelon | Labour Rates | FF-CSA | 0% | 0% | 100% | 65% | 35% | 7% | 0% | 105000 | 0 | 0 | 0 | 0 | 0.24658 | 1 | 0.91548 | 0.65 | 0.57603 | 0.35 | 0.35096 | 0.35 | 0.35 | 0.35 | 0.35096 | 0.28096 | 0.07 | 0.07 | 0.070192 | 0.07 | 0.07 | 0.07 | 0.070192 | 0.07 | 0.07 | 0.07 | 0.070192 | 0.07 | 0.07 | 0.07 | 0.070192 | 0.07 | 0.07 | 0.07 | 0.017452 | 7.0492
17 | CSA | Project Team | Speciality Engineer | EMC/EMI | Electromagnetic Compatibility (EMC/EMI) Specialist | Instrument Suite | Space Exploration | Engineering | Daniel Osei | ORCA-EMC-001 | New | EN-ENG-5 | Max Echelon | Labour Rates | FF-CSA | 0% | 25% | 0% | 20% | 37% | 100% | 0% | 145000 | 0 | 0 | 0.062329 | 0.25 | 0.18836 | 0 | 0.049863 | 0.2 | 0.24192 | 0.37 | 0.37101 | 0.37 | 0.37 | 0.37 | 0.37101 | 0.52534 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 0.24932 | 22.0001
18 | CSA | Project Team | Speciality Engineer | Radiation | Space Environment and Radiation Engineer | Instrument Suite | Space Exploration | Engineering | Vera Kowalski | ORCA-RAD-001 | New | EN-ENG-5 | Max Echelon | Labour Rates | FF-CSA | 0% | 35% | 10% | 10% | 10% | 10% | 0% | 145000 | 0 | 0 | 0.08726 | 0.35 | 0.28836 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.024932 | 3.6525
19 | CSA | Project Team | Speciality Engineer | Structures | Instrument Suite Structures Engineer | Instrument Suite | Space Exploration | Engineering | Thomas Girard | ORCA-STR-001 | New | EN-ENG-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 100% | 25% | 100% | 25% | 5% | 0% | 128000 | 0 | 0 | 0.24932 | 1 | 0.81507 | 0.25 | 0.43767 | 1 | 0.81507 | 0.25 | 0.25068 | 0.25 | 0.25 | 0.25 | 0.25068 | 0.20068 | 0.05 | 0.05 | 0.050137 | 0.05 | 0.05 | 0.05 | 0.050137 | 0.05 | 0.05 | 0.05 | 0.050137 | 0.05 | 0.05 | 0.05 | 0.050137 | 0.05 | 0.05 | 0.05 | 0.012466 | 7.1822
20 | CSA | Project Team | Speciality Engineer | Mechanical | Launch and Mechanical Environment Engineer | Instrument Suite | Space Exploration | Engineering | Aline Petit | ORCA-MEC-001 | New | EN-ENG-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 100% | 0% | 10% | 13% | 100% | 0% | 128000 | 0 | 0 | 0.24932 | 1 | 0.75342 | 0 | 0.024932 | 0.1 | 0.1074 | 0.13 | 0.13036 | 0.13 | 0.13 | 0.13 | 0.13036 | 0.34452 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 1.0027 | 1 | 1 | 1 | 0.24932 | 21.6206
21 | CSA | Project Team | Speciality Engineer | Robotics | Sampling Arm Mechanisms Engineer (Option C) | Instrument Suite | Space Exploration | Engineering | Hassan Malik | ORCA-ISA-002 | New | EN-ENG-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 100% | 30% | 5% | 38% | 10% | 0% | 128000 | 0 | 0 | 0.24932 | 1 | 0.8274 | 0.3 | 0.23849 | 0.05 | 0.13137 | 0.38 | 0.38104 | 0.38 | 0.38 | 0.38 | 0.38104 | 0.31096 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.024932 | 7.2156
22 | CSA | Project Team | Speciality Engineer | GNC | Guidance, Navigation and Control (GNC) Engineer | Instrument Suite | Space Exploration | Engineering | Julie Beaulieu | ORCA-GNC-002 | New | EN-ENG-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 0% | 25% | 10% | 35% | 0% | 0% | 128000 | 0 | 0 | 0 | 0 | 0.061644 | 0.25 | 0.21329 | 0.1 | 0.16164 | 0.35 | 0.35096 | 0.35 | 0.35 | 0.35 | 0.35096 | 0.2637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1522
23 | CSA | Project Team | Speciality Engineer | Thermal | Thermal Control Engineer | Instrument Suite | Space Exploration | Engineering | Owen MacKenzie | ORCA-THM-001 | New | EN-ENG-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 10% | 100% | 0% | 35% | 30% | 0% | 128000 | 0 | 0 | 0.024932 | 0.1 | 0.32192 | 1 | 0.75342 | 0 | 0.086301 | 0.35 | 0.35096 | 0.35 | 0.35 | 0.35 | 0.35096 | 0.33767 | 0.3 | 0.3 | 0.30082 | 0.3 | 0.3 | 0.3 | 0.30082 | 0.3 | 0.3 | 0.3 | 0.30082 | 0.3 | 0.3 | 0.3 | 0.30082 | 0.3 | 0.3 | 0.3 | 0.074795 | 10.2042
24 | CSA | Project Team | Speciality Engineer | Power | RTG / Power Systems Engineer | Instrument Suite | Space Exploration | Engineering | Leila Amini | ORCA-PWR-001 | New | EN-ENG-5 | Max Echelon | Labour Rates | FF-CSA | 0% | 5% | 15% | 100% | 3% | 10% | 0% | 145000 | 0 | 0 | 0.012466 | 0.05 | 0.074658 | 0.15 | 0.36233 | 1 | 0.76082 | 0.03 | 0.030082 | 0.03 | 0.03 | 0.03 | 0.030082 | 0.04726 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.024932 | 4.4637
25 | CSA | Project Team | Speciality Engineer | Software | Flight Software and Autonomy Engineer | Instrument Suite | Space Exploration | Engineering | Nathan Cormier | ORCA-SW-001 | New | EN-ENG-4 | Max Echelon | Labour Rates | FF-CSA | 0% | 100% | 10% | 25% | 42% | 10% | 0% | 128000 | 0 | 0 | 0.24932 | 1 | 0.77808 | 0.1 | 0.13767 | 0.25 | 0.29192 | 0.42 | 0.42115 | 0.42 | 0.42 | 0.42 | 0.42115 | 0.3411 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.10027 | 0.1 | 0.1 | 0.1 | 0.024932 | 7.4964
26 | CSA | CSA Internal Services | Internal Services | Multiple - See Model | Multiple - See Model | Other |  |  |  |  | N/A |  | Standard | IS Model (%) | A-Base | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Partner Agency (NASA/ESA) | Orbiter Interface Liaison | Internal Services | Interface Coordination | Orbiter Bus Interface Liaison | Other |  |  | TBD | N/A | MOU |  | Standard | Partner Agency Model | MOU | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | CSA | Horizontal Services | Internal Services | Infrastructure | Real Property and IT Infrastructure | Other |  |  | N/A | N/A | MOU |  | Standard | IS Model (%) | A-Base | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | PSPC | Horizontal Services | Internal Services | Contracts | Fairness Monitor | Other |  |  | N/A | N/A | MOU |  | Standard | IS Model (%) | A-Base | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Shared Services Canada | Horizontal Services | Internal Services | IT | IT Support | Other |  |  | N/A | N/A | MOU |  | Standard | IS Model (%) | A-Base | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Justice Canada | Horizontal Services | Internal Services | Legal | Legal Services | Other |  |  | N/A | N/A | MOU |  | Standard | IS Model (%) | A-Base | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Total FTE | [10 empty] | 0 | 10.1 | 7.31 | 7.2 | 7.71 | 8.58 | 0 |  | 0 | 0 | 2.5181 | 10.1 | 9.4121 | 7.31 | 7.3026 | 7.2 | 7.3258 | 7.71 | 7.7311 | 7.71 | 7.71 | 7.71 | 7.7311 | 7.9245 | 8.58 | 8.58 | 8.6035 | 8.58 | 8.58 | 8.58 | 8.6035 | 8.58 | 8.58 | 8.58 | 8.6035 | 8.58 | 8.58 | 8.58 | 8.6035 | 8.58 | 8.58 | 8.58 | 2.1391 | 262.0684
[5 empty] | Salary without inflation in "Then Year" | [18 empty] | 0 | 0 | 324471.0959 | 1301450 | 1206567.8082 | 916650 | 925331.9178 | 941400 | 955171.2329 | 997250 | 999982.1918 | 997250 | 997250 | 997250 | 999982.1918 | 1040013.5616 | 1170680 | 1170680 | 1173887.3425 | 1170680 | 1170680 | 1170680 | 1173887.3425 | 1170680 | 1170680 | 1170680 | 1173887.3425 | 1170680 | 1170680 | 1170680 | 1173887.3425 | 1170680 | 1170680 | 1170680 | 291868.1644 | 34976957.5342
[5 empty] | Employee Benefit Plan (EBP) | [17 empty] | 27% | 0 | 0 | 87607.1959 | 351391.5 | 325773.3082 | 247495.5 | 249839.6178 | 254178 | 257896.2329 | 269257.5 | 269995.1918 | 269257.5 | 269257.5 | 269257.5 | 269995.1918 | 280803.6616 | 316083.6 | 316083.6 | 316949.5825 | 316083.6 | 316083.6 | 316083.6 | 316949.5825 | 316083.6 | 316083.6 | 316083.6 | 316949.5825 | 316083.6 | 316083.6 | 316083.6 | 316949.5825 | 316083.6 | 316083.6 | 316083.6 | 78804.4044 | 9443778.5342
[5 empty] | Salary and EBP in "Then Year" | [18 empty] | 0 | 0 | 412078.2918 | 1652841.5 | 1532341.1164 | 1164145.5 | 1175171.5356 | 1195578 | 1213067.4658 | 1266507.5 | 1269977.3836 | 1266507.5 | 1266507.5 | 1266507.5 | 1269977.3836 | 1320817.2233 | 1486763.6 | 1486763.6 | 1490836.9249 | 1486763.6 | 1486763.6 | 1486763.6 | 1490836.9249 | 1486763.6 | 1486763.6 | 1486763.6 | 1490836.9249 | 1486763.6 | 1486763.6 | 1486763.6 | 1490836.9249 | 1486763.6 | 1486763.6 | 1486763.6 | 370672.5688 | 44420736.0685
[5 empty] | Bring historic data into Base Year 2026 | [18 empty] | 0 | 0 | 412078.2918 | 1652841.5 | 1532341.1164 | 1164145.5 | 1175171.5356 | 1195578 | 1213067.4658 | 1266507.5 | 1269977.3836 | 1266507.5 | 1266507.5 | 1266507.5 | 1269977.3836 | 1320817.2233 | 1486763.6 | 1486763.6 | 1490836.9249 | 1486763.6 | 1486763.6 | 1486763.6 | 1490836.9249 | 1486763.6 | 1486763.6 | 1486763.6 | 1490836.9249 | 1486763.6 | 1486763.6 | 1486763.6 | 1490836.9249 | 1486763.6 | 1486763.6 | 1486763.6 | 370672.5688 | 44420736.0685
[5 empty] | Apply inflation to future years | [18 empty] | 0 | 0 | 432939.7553 | 1779929.516 | 1691417.8772 | 1317123.7797 | 1362838.6951 | 1421166.536 | 1478004.9151 | 1581694.3179 | 1625678.4202 | 1661767.5928 | 1703311.7826 | 1745894.5771 | 1794444.7962 | 1912937.1628 | 2207108.9208 | 2262286.6438 | 2325196.8066 | 2376814.9052 | 2436235.2778 | 2497141.1597 | 2566582.2084 | 2623558.9309 | 2689147.9042 | 2756376.6018 | 2833026.5265 | 2895918.1673 | 2968316.1215 | 3042524.0245 | 3127131.1994 | 3196551.8032 | 3276465.5983 | 3358377.2383 | 858226.4025 | 71806136.1648
[5 empty] | Salary and EBP in "Base Year" 2026 with inflation | [18 empty] | 0 | 0 | 432939.7553 | 1779929.516 | 1691417.8772 | 1317123.7797 | 1362838.6951 | 1421166.536 | 1478004.9151 | 1581694.3179 | 1625678.4202 | 1661767.5928 | 1703311.7826 | 1745894.5771 | 1794444.7962 | 1912937.1628 | 2207108.9208 | 2262286.6438 | 2325196.8066 | 2376814.9052 | 2436235.2778 | 2497141.1597 | 2566582.2084 | 2623558.9309 | 2689147.9042 | 2756376.6018 | 2833026.5265 | 2895918.1673 | 2968316.1215 | 3042524.0245 | 3127131.1994 | 3196551.8032 | 3276465.5983 | 3358377.2383 | 858226.4025 | 71806136.1648
Please provide an explanation why positions are required
Method: FTE per fiscal year = sum over phases of (phase LoE % x months of that phase falling in the fiscal year, from '3 - Phase Durations') / 12. Salary = sum of (FTE x Rate), with Rate looked up by Classification from 'Labour Rates lookup'. EBP rate (blue input above) and inflation factors ('Inflation Rate' tab) are illustrative placeholders pending confirmed CSA parameters.

## 5 - Risk Register
` Table of Contents
13 - Risk Register for Costing Purposes
Why we we asking:
EVM needs it, sensitivity analysis needs it
Probability scale: 1 Very Low 10% ¦ 2 Low 30% ¦ 3 Medium 50% ¦ 4 High 70% ¦ 5 Very High 90%. Costs in thousands of CAD ($000). Weighted Exposure = Probability x Most Likely cost. Risk Category / Sub-category follow the 'Risk Breakdown Structure' tab. Figures are illustrative.
| # | ID | Risk Category | Risk Sub-category | Risk Name | Type of Risk | Description | Internal Factors | External Factors | Probability | Mitigation Strategy | Mitigation Strategy Narrative | Cost Impact – Optimistic ($000) | Cost Impact – Most Likely ($000) | Cost Impact – Pessimistic ($000) | Weighted Exposure ($000) | Cost Impact in Phase | Schedule Impact in Phase | Impact on Project | Impact on Analysis
| 1 | R-001 | Programmatic Integration & Execution | Partnership & External Agreements | RTG Fuel Supply Delay | Schedule | Pu-238 production is limited and allocated across multiple missions; ORCA's supply commitment with the international partner is not yet finalized. | RTG procurement depends on the partner; no CSA-held fuel allocation | Limited Pu-238 production; competing mission demand | 50% | Mitigate | Secure a fuel allocation letter through the partner agency before PDR, track fuel-production milestones at every gate, and carry a launch-opportunity reserve. | 1000 | 4000 | 9500 | 2000 | B2–D | C–D | Schedule slip to launch window; possible multi-year wait for the next Jupiter gravity-assist opportunity. | Adds schedule contingency and extended Phase D standing-army LoE to the estimate.
| 2 | R-002 | Technological & Engineering Factors | Technology Readiness & Maturity | Ice-Penetrating Radar TRL Immaturity | Technical | Ice-penetrating radar performance at Enceladus's ice shell has not been demonstrated at flight TRL; ground and airborne analogue testing is still needed. | Immature antenna and processing design; limited ice-analogue test data | Access to analogue test sites; RF component availability | 50% | Mitigate | Fund an airborne and ground analogue campaign in Phases A–B1, set a TRL 6 exit criterion at PDR, and keep a descoped radar mode as a fallback. | 450 | 1800 | 4200 | 900 | B1–C | B2–C | Could require redesign, additional testing, increased costs, and schedule delays. | Adds instrument engineering and test LoE in Phases B and C.
| 3 | R-003 | Technological & Engineering Factors | System Performance & Reliability | Mass Spectrometer Sensitivity Risk | Technical | Detecting biosignature-relevant compounds at parts-per-billion concentrations has not yet been demonstrated in a flight-qualified instrument of this mass and power class. | Detector noise and contamination budget not closed | Detector supplier performance; availability of heritage instrument data | 50% | Mitigate | Demonstrate sensitivity on a breadboard before PDR, hold an end-to-end error budget from inlet to detector, and reserve mass and power margin. | 350 | 1500 | 3500 | 750 | B2–C | C–D | Could require redesign, additional testing, and reduced science return if sensitivity targets are not met. | Adds instrument engineering, calibration and verification LoE.
| 4 | R-004 | External & Environmental Factors | Regulatory & Legal | Export Control Delays | Governance | A Technical Assistance Agreement (TAA) covering instrument-level data exchange with the partner agency has not yet been established. | Late identification of controlled data items | Foreign export-licensing review timelines | 50% | Mitigate | Start the TAA application in Phase A, identify controlled technical data early, and schedule data exchanges around licence approval dates. | 200 | 900 | 2100 | 450 | A–B2 | B1–C | Could delay data exchange, joint testing, and integration activities with the partner agency. | Adds PM and legal coordination LoE plus schedule contingency.
| 5 | R-005 | Programmatic Integration & Execution | Partnership & External Agreements | Partner Schedule Dependency | Programmatic | ORCA's instruments are accommodated payloads on a partner-led spacecraft; ORCA does not control the host mission's own schedule risk. | Limited ORCA-side float before instrument delivery | Host mission development and launch schedule | 50% | Mitigate | Write need dates and interface milestones into the partner agreement and hold ORCA-side float ahead of instrument delivery. | 700 | 3000 | 7000 | 1500 | C–D | C–D | Delays on the partner's side could cascade directly into ORCA's integration and launch readiness dates. | Adds standing-army LoE and storage cost if delivery must wait for the host.
| 6 | R-006 | Programmatic Integration & Execution | Schedule Planning & Control | Launch Window Availability | Schedule | Manifest slots on the required class of launch vehicle are not yet reserved for the ~2041 launch opportunity. | Instrument readiness must support a fixed trajectory window | Launch-provider manifest; gravity-assist geometry | 30% | Accept | Launch procurement is the partner's responsibility; accept the residual exposure but track manifest status and backup trajectory options at each gate. | 800 | 3500 | 8000 | 1050 | D | D–E | Missing the trajectory window could force a multi-year delay to the next viable gravity-assist path. | A missed window adds multi-year storage and standing-army cost.
| 7 | R-007 | Programmatic Integration & Execution | Cost & Budget Management | Early-Stage Cost Uncertainty | Cost | Estimating maturity is consistent with Phase B/C; several subsystem costs are still based on analogous-mission estimates rather than vendor quotes. | Analogy-based estimates; immature WBS | Volatility in supplier quotations | 50% | Mitigate | Refresh bottom-up estimates at PDR and CDR, replace analogy costs with vendor quotes, and reconcile the RAM and CBS at each gate. | 600 | 2500 | 6000 | 1250 | B1–D | B2–D | Could result in cost growth as design matures and vendor quotes replace parametric estimates. | Widens the cost uncertainty range and drives contingency sizing.
| 8 | R-008 | External & Environmental Factors | Geopolitical & Economic | Currency Exchange Exposure | Cost | Major payload contracts and the partner-agency relationship involve non-CAD-denominated costs. | Foreign-denominated subcontracts | Exchange-rate movements | 50% | Transfer | Use CAD-denominated contracts where possible and forward-purchase foreign currency for large milestone payments. | 300 | 1200 | 2800 | 600 | C–D | C–D | Unfavourable exchange-rate movement could increase the CAD cost of foreign-denominated contracts. | Adds FX contingency to foreign-content CBS elements.
| 9 | R-009 | Technological & Engineering Factors | System Performance & Reliability | Deep-Space Radiation/Thermal Margin | Technical | Component qualification levels are based on analogous outer-planet missions and have not yet been validated against ORCA's specific trajectory and RTG thermal design. | Analogy-based qualification levels | Jovian and Saturnian radiation environment; RTG heat output | 30% | Mitigate | Run trajectory-specific radiation and RTG thermal analyses in Phase B and qualify parts to mission-specific levels with margin. | 650 | 2800 | 6500 | 840 | B2–C | C–D | Could require additional shielding, thermal design changes, or component requalification. | Adds shielding mass, parts qualification and thermal test LoE.
| 10 | R-010 | Technological & Engineering Factors | Software & Algorithms | Autonomous Operations Complexity | Technical | The autonomy and fault-management software architecture for the instrument suite has not yet been baselined. | Underestimated software complexity | Light-time delay; host spacecraft FDIR interfaces | 50% | Mitigate | Baseline the autonomy architecture before PDR, prototype fault-management logic early, and run long-duration autonomy simulations. | 400 | 1600 | 3700 | 800 | B2–D | C–D | Increased software development and validation effort could cause cost and schedule growth. | Adds flight software development and V&V LoE.
| 11 | R-011 | Programmatic Integration & Execution | Partnership & External Agreements | DSN Allocation Contention | Programmatic | ORCA's downlink allocation has not yet been negotiated as part of the partnership agreement. | Onboard storage sizing not yet tied to downlink plan | Deep Space Network demand from other missions | 50% | Mitigate | Negotiate a documented downlink allocation in the partner agreement and design onboard data prioritization for flythrough passes. | 200 | 900 | 2100 | 450 | E | E | Insufficient downlink priority could limit science data return during plume flythroughs. | Adds operations planning LoE; mainly reduces science return rather than adding cost.
| 12 | R-012 | Technological & Engineering Factors | Technology Readiness & Maturity | Sampling Arm TRL Immaturity (Option C) | Technical | The ISA (Ice Sampling Arm) concept builds on Canadarm heritage but has not been adapted or tested for the Enceladus surface/plume environment. | Heritage design not adapted to cryogenic environment | Uncertainty in Enceladus surface and plume conditions | 50% | Mitigate | Run a dedicated ISA risk-reduction campaign in Phases A–B1, with a go/no-go decision on Option C at SRR. | 350 | 1400 | 3300 | 700 | A–C | B1–C | Could require a dedicated technology risk-reduction campaign, adding cost and schedule. | Adds robotics engineering and test LoE (Option C only).
| 13 | R-013 | Safety, Assurance & Compliance | Certification & Standards | Planetary Protection Scope | Governance | A formal planetary protection plan has not yet been developed jointly with the partner agency. | Planetary protection requirements not yet flowed down | COSPAR category assignment; partner planetary protection policy | 50% | Mitigate | Develop a joint planetary protection plan with the partner in Phase A and build bioburden controls into the AIT flow. | 250 | 1100 | 2600 | 550 | A–D | C–D | Late-defined planetary protection requirements could drive late design or trajectory changes. | Adds cleanroom, bioburden testing and assurance LoE.
| 14 | R-014 | Organizational & Human Factors | Resource & Staffing Capacity | Workforce Continuity | Programmatic | Program duration spans more than one career stage for most engineering staff; no succession plan is yet in place. | Long mission duration; small specialist pool | Labour-market competition for space specialists | 50% | Mitigate | Establish a succession plan, pair senior and junior staff on key roles, and capture design rationale in controlled documents. | 150 | 700 | 1600 | 350 | 0–F | B1–E | Loss of key personnel could cause knowledge gaps, rework, and schedule delays. | Raises labour-rate and FTE assumptions and adds knowledge-transfer LoE.
| 15 | R-015 | Safety, Assurance & Compliance | Product Assurance & Quality Control | Multi-Party Configuration Management | Technical | A single joint configuration management authority across all contractors and the partner agency has not yet been established. | Multiple baselines across CSA and contractors | Partner configuration-management practices | 50% | Mitigate | Stand up a joint configuration control board with the partner and prime before PDR and audit baselines at each gate. | 200 | 800 | 1900 | 400 | B2–D | C–D | Could lead to interface mismatches, rework, and integration delays. | Adds configuration-management and reconciliation LoE.
| 16 | R-016 | Strategic & Alignment Factors | Strategic Direction & Policy Alignment | Partner Agency Stability | Strategic | The mission concept assumes stable multi-decade support from a single partner agency; this has not been contractually secured. | Single-partner mission architecture | Partner budget and policy changes | 30% | Accept | Accept the residual exposure after securing a binding intergovernmental agreement, and keep a documented descope and re-host option. | 1000 | 4500 | 10500 | 1350 | B1–E | B2–E | Loss of the partner relationship could require a costly architecture change or mission redesign. | A partner exit would require re-estimating the mission architecture.
| 17 | R-017 | Programmatic Integration & Execution | Governance Processes & Controls | Governance Workload | Governance | Gate documentation and decision-note preparation draw on the same technical leads responsible for design closure activities. | Same leads prepare gates and close the design | Departmental review cycles | 50% | Accept | Accept; plan gate-preparation windows into the integrated schedule and assign a dedicated gate coordinator. | 75 | 300 | 700 | 150 | A–C | A–C | Could slow design progress during gate-preparation windows. | Adds PM and governance LoE around gates.
| 18 | R-018 | Programmatic Integration & Execution | Cost & Budget Management | Unallocated Reserve (Unknown-Unknowns) | Cost | Held as management reserve per CSA cost-estimating policy for unknown-unknown risk at Phase B/C maturity. | Estimate maturity at Phase B/C | Risks not yet identified | 50% | Accept | Hold as management reserve and release only through change control. | 400 | 1500 | 3500 | 750 | 0–F | 0–F | Provides cost cover for risks not yet individually identified. | Carried as reserve; not allocated to a CBS element.
| 19 | R-019 | Technological & Engineering Factors | System Performance & Reliability | Instrument Degradation During Cruise | Technical | The ~10-year outbound cruise may degrade detectors, seals or calibration sources before the instruments reach Enceladus. | Limited in-cruise checkout plan; aging consumables | Cruise radiation dose; thermal cycling | 30% | Mitigate | Plan periodic in-cruise instrument checkouts and calibrations, and select parts with lifetime margin. | 350 | 1500 | 3500 | 450 | E | E | May reduce science performance at arrival or require recalibration campaigns. | Adds cruise operations and calibration LoE.
| 20 | R-020 | Technological & Engineering Factors | Design & Development | Plume Sample Contamination | Technical | Terrestrial contamination or spacecraft outgassing may mask low-concentration organics in plume samples. | Contamination control plan not yet baselined | Host spacecraft outgassing; propulsion plume products | 30% | Mitigate | Define contamination budgets early, bake out sample inlets, and carry blank samples for background subtraction. | 300 | 1200 | 2800 | 360 | C–D | D | Could compromise biosignature measurements. | Adds contamination-control and cleanroom LoE.
| 21 | R-021 | Data, Knowledge & Integration | Data Integration & Consistency | Science Data Processing Capacity | Technical | The CSA science operations centre may lack the processing and archive capacity for flythrough data volumes and joint partner data products. | Early data-volume assumptions | Changes to partner data formats | 30% | Mitigate | Size processing and archive capacity from flythrough scenarios and agree data-product formats in the partner ICD. | 250 | 1000 | 2400 | 300 | D–E | D–E | May delay science products after each flythrough. | Adds ground-segment software and operations LoE.
| 22 | R-022 | External & Environmental Factors | Market & Supply Chain | Instrument Supplier Insolvency | Cost | A key instrument subcontractor may exit the market or become insolvent during the long development cycle. | Single-source instrument components | Small space-supplier base; market conditions | 20% | Transfer | Include data-package delivery and escrow clauses in contracts and qualify second sources for critical items. | 400 | 1800 | 4300 | 360 | C–D | C–D | Could force re-procurement and requalification. | Adds procurement and requalification cost.
| 23 | R-023 | Technological & Engineering Factors | Parts, Components & Materials | Long-Lead Radiation-Hardened Parts | Schedule | Radiation-hardened EEE parts and detectors may arrive later than the integration schedule requires. | Late parts list; late purchase orders | Supplier backlog; export-controlled parts | 40% | Mitigate | Release long-lead orders after PDR, track parts at weekly reviews, and qualify alternates. | 250 | 1000 | 2400 | 400 | B2–D | C–D | May delay instrument assembly and environmental testing. | Adds procurement management and schedule contingency.
| 24 | R-024 | Technological & Engineering Factors | Integration & Verification | Instrument Environmental Test Failure | Technical | Instrument-level thermal-vacuum or vibration testing may reveal design or workmanship defects requiring rework and retest. | Limited margin on first-of-kind hardware | Test facility availability | 30% | Mitigate | Test engineering models early, apply workmanship screening, and reserve facility time for retest. | 300 | 1300 | 3000 | 390 | D | D | May delay delivery to the host spacecraft. | Adds rework, retest and facility cost.
| 25 | R-025 | Safety, Assurance & Compliance | Certification & Standards | End-of-Mission Disposal Requirements | Programmatic | Planetary protection disposal requirements for the Saturn system may extend Phase X/F operations or constrain the end-of-mission trajectory. | Disposal concept not yet defined | Partner end-of-mission plan; planetary protection policy | 20% | Accept | Accept; the host spacecraft owns disposal, and ORCA carries only operations-support LoE. | 100 | 500 | 1200 | 100 | X–F | X–F | May extend operations and data archiving. | Adds Phase X/F operations LoE.
[12 empty] | Total ($000) | 10025 | 42300 | 99100 | 17200

## Risk Breakdown Structure
Risk Category | Risk Sub-category | Risk Name | Type of Risk | Description | Internal Factors | External Factors | Cost - Impact in Phase | Schedule - Initial Impact in Phase | Parent CBS
Organizational & Human Factors | Leadership, Governance & Culture | Ineffective Governance and Decision-Making | Governance | Governance structures, roles, and escalation paths are unclear or inconsistently applied, delaying key decisions and creating misalignment across the program. | - Unclear authority - Slow approvals - Inconsistent executive oversight | - Evolving GoC governance expectations - Partner governance incompatibility | All Phases | All Phases
Organizational & Human Factors | Leadership, Governance & Culture | Misaligned Organizational Incentives | Strategic | Incentives prioritize innovation or technical achievement over disciplined cost/schedule performance, reducing accountability. | - Incentives tied to technical milestones - Weak KPIs | - Public/political pressure for innovation | PREP 1 to MAIT | None
Organizational & Human Factors | Leadership, Governance & Culture | Leadership Turnover and Instability | Governance | High turnover in key leadership roles reduces continuity and strategic alignment across program phases. | - Succession gaps - Staffing instability | - Broader public sector mobility pressures | All Phases | All Phases
Organizational & Human Factors | Leadership, Governance & Culture | Risk Governance Culture | Programmatic | Risk processes are inconsistently followed or valued, leading to late identification of major issues. | - Lack of active risk boards - Inconsistent risk scoring | - Changing departmental reporting expectations | PREP 1 to MAIT | PREP 1 to MAIT
Organizational & Human Factors | Communication & Coordination | Internal Miscommunication and Information Silos | Programmatic | Teams lack timely, consistent information sharing, resulting in misaligned decisions and rework. | - Poor knowledge sharing - Unclear reporting paths | - Increased complexity in multi-site or remote collaboration | PREP 1 to MAIT | PREP 1 to MAIT
Organizational & Human Factors | Communication & Coordination | Interface Definition Gaps | Technical | Unclear or incomplete interface definitions lead to integration challenges and design errors. | - Documentation gaps - Inconsistent configuration control | - Partner documentation misalignment | Phase 0 to SAIT | Phase 0 to SAIT
Organizational & Human Factors | Communication & Coordination | International Coordination Challenges | Programmatic | Communication barriers across time zones, cultures, and languages delay critical alignment with partners. | - Limited resources for partner coordination | - Diverse international work practices | All Phases | All Phases
Organizational & Human Factors | Stakeholder Engagement | Unclear or Misaligned Stakeholder Expectations | Strategic | Stakeholder needs are not fully understood or aligned, causing redefinition of scope or priorities. | - Insufficient early engagement | - User community evolution - Science priorities | PREP 1 to Phase C | PREP 1 to Phase C
Organizational & Human Factors | Stakeholder Engagement | Insufficient Executive Sponsorship | Governance | Executive sponsors are not consistently engaged, weakening decision support and program momentum. | - Competing leadership priorities | - Shifts in departmental focus | PREP 1 to Phase C | PREP 1 to Phase C
Organizational & Human Factors | Resource & Staffing Capacity | Skilled Resource Shortages | Programmatic | Lack of experienced personnel delays technical development and increases rework. | - Training gaps - Turnover | - Labour market shortages in space-specialized skills | PREP 1 to Phase C | PREP 1 to Phase C
Organizational & Human Factors | Resource & Staffing Capacity | Knowledge Loss and Continuity Gaps | Programmatic | Loss of key personnel or weak documentation undermines continuity across phases. | - Insufficient knowledge management | - Competitive hiring environment | All Phases | All Phases
Organizational & Human Factors | Resource & Staffing Capacity | Overreliance on Individual Experts | Programmatic | Critical knowledge is concentrated in a few individuals, creating vulnerability if unavailable. | - Limited SME capacity | - Industry-wide SME scarcity | All Phases | All Phases
Technological & Engineering Factors | Technology Readiness & Maturity | Insufficient Technology Readiness Level (TRL) | Technical | Technology maturity is overestimated or not demonstrated early enough, causing downstream delays. | - Over-optimistic internal assessments | - Vendor overstatements of maturity | PREP 1 to Phase C | PREP 1 to Phase C
Technological & Engineering Factors | Technology Readiness & Maturity | Immature or Unproven Materials/Processes | Technical | New materials or manufacturing processes fail to meet requirements or require redesign. | - Limited early testing | - Supplier process immaturity | MAIT | MAIT
Technological & Engineering Factors | Design & Development | Unstable or Incomplete Design Baseline | Technical | Delays in achieving a stable baseline cascade into integration and manufacturing issues. | - Late requirements - Design churn | - Changing partner specifications | PREP 1 to SAIT | PREP 1 to SAIT
Technological & Engineering Factors | Design & Development | Design Complexity Beyond Analytical Capability | Technical | Engineering tools or models cannot fully resolve complex design interactions. | - Tool limitations | - Novel mission or payload architectures | PREP 1 to Phase C | PREP 1 to Phase C
Technological & Engineering Factors | Design & Development | Over-Customization Instead of COTS Adoption | Technical | Excessive customization increases cost, lead time, and risk compared with qualified COTS alternatives. | - Preference for bespoke solutions | - Limited space-qualified COTS availability | PREP 1 to Phase C | PREP 1 to Phase C
Technological & Engineering Factors | Parts, Components & Materials | EEE Part Failure or Obsolescence | Technical | Component failures or discontinuations disrupt design choices and testing schedules. | - Inadequte part screening | - Supply chain obsolescence | MAIT & SAIT | MAIT & SAIT
Technological & Engineering Factors | Parts, Components & Materials | Long-Lead Item Delays | Schedule | Critical components with long procurement cycles delay integration readiness. | - Late ordering | - Supplier backlog or disruption | MAIT & SAIT | MAIT & SAIT
Technological & Engineering Factors | Integration & Verification | Incomplete Integration Planning | Programmatic | Integration sequencing or planning gaps result in late rework and testing conflicts. | - Inadequate early I&T definition | - Partner delays | MAIT & SAIT | MAIT & SAIT
Technological & Engineering Factors | Integration & Verification | Environmental or Vibration Test Failures | Technical | Hardware fails during qualification or environmental tests, requiring redesign or rework. | - Weak margins - Design flaws | - Facility constraints | Phase B to Phase C | Phase B to Phase C
Technological & Engineering Factors | Manufacturing & Assembly | Poor Workmanship or QA Deficiencies | Technical | Manufacturing quality issues result in defects discovered late in testing or integration. | - Insufficient QA processes | - Supplier QA variability | MAIT & SAIT | MAIT & SAIT
Technological & Engineering Factors | Manufacturing & Assembly | Immature Manufacturing Processes | Technical | New or insufficiently validated processes lead to production delays or variability. | - Lac of documentation | - Small-capacity suppliers | MAIT & SAIT | MAIT & SAIT
Technological & Engineering Factors | Software & Algorithms | Underestimated Software Complexity | Technical | Software complexity is underestimated, requiring additional development time and testing. | - Limited early prototyping | - Integration with partner systems | Phase B to SAIT | Phase B to SAIT
Technological & Engineering Factors | Software & Algorithms | Insufficient Software Validation | Technical | Gaps in software validation cause faults discovered late in testing. | - Limited regression testing | - Late partner code deliveries | Phase B to SAIT | Phase B to SAIT
Technological & Engineering Factors | System Performance & Reliability | Insufficient System Margin | Technical | System lacks adequate performance margins, requiring late design changes. | - Underestimated loads | - Evolving partner or payload requirements | Phase B to SAIT | Phase B to SAIT
Technological & Engineering Factors | System Performance & Reliability | Unproven Redundancy or Fail-Safe Design | Technical | Redundant designs are untested or do not function as intended. | - Inadequate model validation | - Supplier delays in providing redundancy analyses | Phase B to SAIT | Phase B to SAIT
Technological & Engineering Factors | Obsolescence & Sustainment | Technology Obsolescence During Development | Technical | Long development timelines result in components or systems becoming outdated before launch. | - Slow decision-making | - Rapid commercial technology cycles | LEOP & ATLO
Technological & Engineering Factors | Obsolescence & Sustainment | Inadequate Sustainment Planning | Programmatic | Lifecycle sustainment needs are not fully planned, risking long-term mission continuity. | - Limited spares strategy | - Supplier discontinuation | Phase E & Phase X
Programmatic Integration & Execution | Cost & Budget Management | Optimistic Cost Baselines | Cost | Early cost estimates underestimate complexity or required effort, resulting in overruns and re-baselining. | - Immature designs - Optimistic modelling - Incomplete scoping | - Vendor underestimation - Inflation volatility | PREP 1 to Phase A
Programmatic Integration & Execution | Cost & Budget Management | Inadequate Contingency and Reserves | Cost | Cost reserves are insufficient to address risks, requirement changes, or technical growth. | - Pressure to reduce contingency - Lack of quantitative risk analysis | - Unpredictable supplier or market cost changes | All Phases
Programmatic Integration & Execution | Cost & Budget Management | Funding Gaps Across Phases | Programmatic | Delays or gaps in funding between phases disrupt schedules and lead to inefficiencies. | - Internal budget reallocations - Fragmented planning | - Treasury Board sequencing - GoC budget cycles | PREP 1 to Phase C | PREP 1 to Phase C
Programmatic Integration & Execution | Cost & Budget Management | Long-Term Cost Unsustainability | Cost | Operational or lifecycle costs exceed long-term funding, jeopardizing mission continuity. | - Underestimated O&M demands | - Shifting fiscal priorities | Phase E & Phase X
Programmatic Integration & Execution | Schedule Planning & Control | Overly Optimistic Schedule Baselines | Schedule | Schedules underestimate duration or complexity of integration, test and partner interactions. | - Underestimated task durations - Limited slack | - Partner timeline dependencies | Phase C, MAIT or SAIT | Phase C, MAIT or SAIT
Programmatic Integration & Execution | Schedule Planning & Control | Insufficient Schedule Margin | Schedule | Lack of adequate float/margin makes the project vulnerable to minor disruptions. | - Compressed internal timelines | - External approvals - Provider availability |  | PREP 1 to SAIT
Programmatic Integration & Execution | Schedule Planning & Control | Poor Schedule Integration Across Teams | Schedule | Schedules are not fully integrated across subsystems or partners, creating conflicting paths. | - Weak configuration control of schedule updates | - Misaligned partner planning cycles |  | PREP 1 to SAIT
Programmatic Integration & Execution | Requirements & Scope Management | Evolving or Unstable Requirements | Technical | Requirements shift during development, prompting redesign and rescheduling. | - Incomplete early requirements - Late discoveries | - Regulatory or partner-driven changes | Phase 0 to Phase C | Phase 0 to Phase C
Programmatic Integration & Execution | Requirements & Scope Management | Scope Creep | Programmatic | Additional features or changes are added without corresponding increases in budget or schedule. | - Internal mission re-design | - Requests from science/user community | Phase 0 to Phase C | Phase 0 to Phase C
Programmatic Integration & Execution | Requirements & Scope Management | Unclear Definition of Deliverables | Programmatic | Deliverables or success criteria are not explicitly defined, resulting in rework and disputes. | - Vague SOW - Weak requirement traceability | - Partner interpretation differences | Phase 0 to Phase C | Phase 0 to Phase C
Programmatic Integration & Execution | Contracting & Procurement | Procurement and Contract Delays | Schedule | Delays in contract awards, evaluations, or negotiations slow project initiation and execution. | - Insufficient procurement staffing | - Federal procurement rules and oversight | PREP 1 & 2, Phase 0 to Phase B, MAIT | PREP 1 & 2, Phase 0 to Phase B, MAIT
Programmatic Integration & Execution | Contracting & Procurement | Misaligned Contract Structures | Governance | Contract types or terms do not support risk-sharing or needed flexibility. | - Inexperienced contracting officers | - Mandatory policy constraints | PREP 1 to MAIT | PREP 1 to MAIT
Programmatic Integration & Execution | Contracting & Procurement | Vendor Performance Issues | Programmatic | Prime or subcontractor performance problems cause rework or schedule delays | - Weak performance oversight | - Supplier instability | PREP 1 to MAIT | PREP 1 to MAIT
Programmatic Integration & Execution | Contracting & Procurement | Waste, Fraud, or Abuse Vulnerabilities | Governance | Inadequate internal controls expose the program to misuse of funds or fraudulent activity. | - Limited review time - Weak monitoring | - Complex multinational supply chains | All Phases
Programmatic Integration & Execution | Industrial Capability & Supplier Performance | Supplier Maturity Limitations | Programmatic | Suppliers lack mature processes, certifications, or capacity to deliver quality components on time. | - Insufficient oversight | - Small national supplier base | MAIT & SAIT | MAIT & SAIT
Programmatic Integration & Execution | Industrial Capability & Supplier Performance | Manufacturing Defects or Quality Issues | Technical | Supplier quality defects result in delays, retesting, or redesign. | - Weak acceptance processes | - Supplier QA inconsistency | MAIT & SAIT | MAIT & SAIT
Programmatic Integration & Execution | Industrial Capability & Supplier Performance | Overstretched SMEs | Programmatic | Small suppliers lack the throughput or staffing required for schedule-critical work. | - Inadequate supplier monitoring | - High demand across space industry | MAIT & SAIT | MAIT & SAIT
Programmatic Integration & Execution | Partnership & External Agreements | Misaligned Partner Schedules or Deliverables | Schedule | International partners operate on different timelines or processes, leading to integration delays. | - Insufficient internal integration planning | - Partner readiness issues | SAIT & ATLO | SAIT & ATLO
Programmatic Integration & Execution | Partnership & External Agreements | Partner Scope or Commitment Changes | Strategic | Changes in partner priorities, scope, or funding affect shared milestones or system architecture. | - Weak MOU/LOA clarity | - Changing political or budgetary environments | PREP 1 to ATLO | PREP 1 to ATLO
Programmatic Integration & Execution | Partnership & External Agreements | Export Control and Licensing Constraints | Governance | Export control requirements (ITAR, TAAs) delay access to components, data, or test facilities. | - Limited early export planning | - Regulatory changes | Phase B to ATLO | Phase B to ATLO
Programmatic Integration & Execution | Governance Processes & Controls | Weak Phase-Gate Discipline | Governance | Phase reviews lack rigor, allowing unresolved issues to carry forward. | - Inconsistent review criteria | - Pressure to meet partner timelines | Phase 0 to ATLO | Phase 0 to ATLO
Programmatic Integration & Execution | Governance Processes & Controls | Fragmented Technical/Cost/Schedule Reporting | Programmatic | Reports are inconsistent or disconnected, obscuring emerging risks. | - Misaligned data system | - Adjusted GoC reporting frameworks | All Phases | All Phases
External & Environmental Factors | Regulatory & Legal | Export Licensing or Regulatory Delays | Governance | Licensing processes delay hardware transfers, testing, or component acquisition. | - Unclear internal responsibilities | - ITAR/Canadian regulations | MAIT, SAIT, ATLO | MAIT, SAIT, ATLO
External & Environmental Factors | Regulatory & Legal | Changes in Laws, Policies, or Standards | Strategic | Domestic or international policy changes impact program scope, design, or compliance obligations. | - Slow adaptation | - New global or national regulations | Phase 0 to Phase C | Phase 0 to Phase C
External & Environmental Factors | Market & Supply Chain | Supplier Insolvency or Instability | Programmatic | Key suppliers face financial or operational challenges that disrupt delivery. | - Dependence on single supplier | - Market volatility | PREP 1 to SAIT | PREP 1 to SAIT
External & Environmental Factors | Market & Supply Chain | Price Escalation or Market Shock | Cost | Unexpected increase in material or component costs exceed planned budgets. | - Long-term fixed-price contracts | - Global supply shocks | MAIT & SAIT | MAIT & SAIT
External & Environmental Factors | Market & Supply Chain | Logistics and Shipping Disruptions | Schedule | Transportation or customs delays impact integration timelines. | - Limited logistics planning | - International border issues | MAIT, SAIT, ATLO | MAIT, SAIT, ATLO
External & Environmental Factors | Geopolitical & Economic | Currency Exchange Volatility | Cost | Foreign-denominated contracts become more expensive due to unstable currency rates. | - High foreign procurement content | - Global economic instability | PREP 1 to SAIT
External & Environmental Factors | Geopolitical & Economic | Inflation Spikes | Cost | Inflation increase labour, materials, and subcontractor prices beyond assumptions. | - Long program timeline | - Global economic trends | PREP 1 to SAIT
External & Environmental Factors | Geopolitical & Economic | Geopolitical Instability or Sanctions | Strategic | Political instability or sanctions disrupt suppliers, partners, or launch providers. | - Limited diversification | - International conflicts or trade actions | PREP 1 to ATLO | PREP 1 to ATLO
External & Environmental Factors | Force Majeure & Environmental Events | Natural Disasters or Environmental Accidents | Schedule | Floods, fires, or contamination events disrupt testing or manufacturing. | - Facility resilience gaps | - Environmental events | MAIT & SAIT | MAIT & SAIT
External & Environmental Factors | Force Majeure & Environmental Events | Space Weather Impacts | Technical | Radiation storms or solar activity necessitate design changes or additional testing. | - Margins underestimated | - Solar activity cycles | PREP 1 to SAIT | PREP 1 to SAIT
Strategic & Alignment Factors | Strategic Direction & Policy Alignment | Shifting GoC or Agency Priorities | Strategic | Changes in federal or departmental priorities alter program direction, scope, or funding. | - Misalignment with strategic planning | - New government mandates | Phase 0 to Phase C | Phase 0 to Phase C
Strategic & Alignment Factors | Strategic Direction & Policy Alignment | Policy-Driven Changes in Agency Focus | Strategic | Agency focus shifts between mission delivery and administrative compliance due to policy changes. | - Leadership turnover | - Political direction | Phase 0 to Phase C | Phase 0 to Phase C
Strategic & Alignment Factors | Value, Stewardship & "Mission vs Resources" Balance | Priority on Technology over Stewardship | Strategic | Culture prioritizes technical success over disciplines resource management, contribution to overruns. | - Incentives tied to innovation | - Public expectations for technological leadership | PREP 1 to ATLO
Strategic & Alignment Factors | Value, Stewardship & "Mission vs Resources" Balance | Unclear Mission Success Criteria | Governance | Lack of clear definition of success undermines tracking, reporting, and accountability. | - Weak KPI framework | - Evolving departmental expectations | PREP 1 to ATLO | PREP 1 to ATLO
Safety, Assurance & Compliance | System Safety & Human Protection | Inadequate Hazard Identification and Mitigation | Safety | Hazards are not fully identified or mitigated, increasing risk during testing or integration. | - Limited safety analysis | - New or updated safety regulations | MAIT & SAIT | MAIT & SAIT
Safety, Assurance & Compliance | System Safety & Human Protection | Safety Procedures Not Followed | Safety | Deviations from safety protocol create risk of injury or system damage. | - Training gaps | - Contractor procedure variance | MAIT & SAIT | MAIT & SAIT
Safety, Assurance & Compliance | Product Assurance & Quality Control | Inadequate QA or Inspection Processes | Technical | Weak QA processes lead to undetected defects in hardware or documentation. | - Insufficient QA staffing | - Supplier quality variability | MAIT & SAIT | MAIT & SAIT
Safety, Assurance & Compliance | Product Assurance & Quality Control | Configuration Management Lapses | Technical | CM issues result in inconsistencies between design, test, and manufacturing data. | - Weak configuration discipline | - Partner CM incompatibility | MAIT & SAIT | MAIT & SAIT
Safety, Assurance & Compliance | Test & Verification | Incomplete or Insufficient Test Plans | Technical | Gaps in test coverage allow defects to be discovered late. | - Inadequate early test planning | - Facility limitations | MAIT, SAIT, LEOP, ATLO, Early Ops, Phase E | MAIT, SAIT, LEOP, ATLO, Early Ops, Phase E
Safety, Assurance & Compliance | Test & Verification | Late Discovery of Non-Compliance | Technical | Key requirements failures are found late in qualification, increasing cost and schedule impact. | - Weak integration testing | - Late partner deliveries | MAIT & SAIT | MAIT & SAIT
Safety, Assurance & Compliance | Certification & Standards | Delayed Safety or Standards Certification | Governance | Delays obtaining required certifications impede integration or launch activities | - Incomplete documentation | - Changing standards | LEOP, ATLO, Cruise Out | LEOP, ATLO, Cruise Out
Data, Knowledge & Integration | Data Integration & Consistency | Misaligned Baselines (Cost, Schedule, Technical) | Programmatic | Cost, schedule, and technical baselines are not consistently aligned, obscuring issues. | - Tool integration gaps | - Partner baseline mismatches | PREP 1 to ATLO | PREP 1 to ATLO
Data, Knowledge & Integration | Data Integration & Consistency | Inconsistent Data Exchange Across Teams | Programmatic | Data is inconsistent or incompatible across engineering, finance, and risk systems. | - Multiple unlinked tools | - Partner data format variability | PREP 1 to ATLO | PREP 1 to ATLO
Data, Knowledge & Integration | Knowledge Management | Knowledge Loss Through Poor Documentation | Programmatic | Documentation gaps cause loss of design rationale and technical context across phases. | - Weak KM discipline | - Staff turnover | Phase 0 to Phase C | Phase 0 to Phase C
Data, Knowledge & Integration | Knowledge Management | Absence of a Knowledge Management Framework | Governance | Lack of organizational KM policy results in inconsistent retention of critical program information. | - No formal KM process | - Cross-agency documentation expectations | PREP 1 to Phase C | PREP 1 to Phase C

## Raw Labour Rates
Raw Labour Rates
Illustrative extract of published Treasury Board of Canada pay-scale bands, top (MAX) step only, for the classification groups used on the ORCA project. Placeholder figures pending confirmed CSA compensation data; not authoritative.
Classification | Classification Name | Step | Salary | Effective Date | Active
AS-1 | Administrative Services 1 | MAX | 55000 | 2026-04-01 | Yes
AS-2 | Administrative Services 2 | MAX | 62000 | 2026-04-01 | Yes
CR-4 | Clerical and Regulatory 4 | MAX | 58000 | 2026-04-01 | Yes
CS-2 | Computer Systems 2 | MAX | 78000 | 2026-04-01 | Yes
EC-1 | Economics and Social Science Services 1 | MAX | 70000 | 2026-04-01 | Yes
EG-6 | Engineering and Scientific Support 6 | MAX | 95000 | 2026-04-01 | Yes
EN-ENG-3 | Engineering 3 | MAX | 110000 | 2026-04-01 | Yes
EN-ENG-4 | Engineering 4 | MAX | 128000 | 2026-04-01 | Yes
EN-ENG-5 | Engineering 5 | MAX | 145000 | 2026-04-01 | Yes
EN-ENG-6 | Engineering 6 | MAX | 165000 | 2026-04-01 | Yes
EX-2 | Executive 2 | MAX | 175000 | 2026-04-01 | Yes
GT-4 | General Technical 4 | MAX | 72000 | 2026-04-01 | Yes
PC-3 | Physical Sciences 3 | MAX | 105000 | 2026-04-01 | Yes
PC-4 | Physical Sciences 4 | MAX | 122000 | 2026-04-01 | Yes
PC-5 | Physical Sciences 5 | MAX | 140000 | 2026-04-01 | Yes

## Labour Rates lookup
Labour Rates lookup
One row per classification actually used on the ORCA RAM, with its top-step (MAX) annual rate pulled from 'Raw Labour Rates' by formula. The RAM sheet's Rate column looks up against this table.
Classification | MaxStep
AS-1 | 55000
AS-2 | 62000
CR-4 | 58000
CS-2 | 78000
EC-1 | 70000
EG-6 | 95000
EN-ENG-3 | 110000
EN-ENG-4 | 128000
EN-ENG-5 | 145000
EN-ENG-6 | 165000
EX-2 | 175000
GT-4 | 72000
PC-3 | 105000
PC-4 | 122000
PC-5 | 140000

## Rolodex
Rolodex
Fictional placeholder directory for the ORCA project team. Names are illustrative and used only to drive the RAM sheet's Classification lookup; no real CSA personnel data is represented here.
Employee Name | Classification | Position Title | Position No | Directorate
Alan Whitfield | EN-ENG-6 | Portfolio Manager | ORCA-PM-001 | Program Management
Marie Tremblay | PC-4 | ORCA Mission Manager | ORCA-PM-002 | Program Management
Devon Okafor | PC-3 | Mission Operations Scientist | ORCA-SCI-001 | Planetary Science
Priya Raman | EN-ENG-5 | Lead Project Manager | ORCA-PM-003 | Program Management
Étienne Lacroix | EN-ENG-4 | Deputy Project Manager | ORCA-PM-004 | Program Management
Grace Lindqvist | EN-ENG-4 | Project Management Engineer | ORCA-PM-005 | Program Management
Samuel Boucher | EN-ENG-4 | Schedule and Cost Management Engineer | ORCA-PM-006 | Program Management
Naomi Fitzgerald | EN-ENG-5 | Lead Spacecraft Systems Engineer | ORCA-SE-001 | Engineering
Kevin Anand | EN-ENG-4 | Spacecraft Systems Engineer | ORCA-SE-002 | Engineering
Isabelle Roy | EN-ENG-4 | Instrument Pointing / GNC Engineer | ORCA-GNC-001 | Engineering
Marcus Delgado | EN-ENG-4 | Sampling Arm (ISA) Systems Engineer (Option C) | ORCA-ISA-001 | Engineering
Fatima Haidari | EN-ENG-5 | Safety and Mission Assurance Engineer | ORCA-SMA-001 | Engineering
Robert Cianci | EN-ENG-4 | Fault Detection, Isolation and Recovery Engineer | ORCA-FDIR-001 | Engineering
Simone Bergeron | EN-ENG-4 | Mission Operations and Ground Systems Engineer | ORCA-OPS-001 | Mission Operations
Yusuf Karimi | PC-4 | Mass Spectrometer Lead Engineer | ORCA-INS-001 | Engineering
Charlotte Nadeau | PC-3 | Ice-Penetrating Radar Lead Engineer | ORCA-INS-002 | Engineering
Daniel Osei | EN-ENG-5 | Electromagnetic Compatibility (EMC/EMI) Specialist | ORCA-EMC-001 | Engineering
Vera Kowalski | EN-ENG-5 | Space Environment and Radiation Engineer | ORCA-RAD-001 | Engineering
Thomas Girard | EN-ENG-4 | Instrument Suite Structures Engineer | ORCA-STR-001 | Engineering
Aline Petit | EN-ENG-4 | Launch and Mechanical Environment Engineer | ORCA-MEC-001 | Engineering
Hassan Malik | EN-ENG-4 | Sampling Arm Mechanisms Engineer (Option C) | ORCA-ISA-002 | Engineering
Julie Beaulieu | EN-ENG-4 | Guidance, Navigation and Control (GNC) Engineer | ORCA-GNC-002 | Engineering
Owen MacKenzie | EN-ENG-4 | Thermal Control Engineer | ORCA-THM-001 | Engineering
Leila Amini | EN-ENG-5 | RTG / Power Systems Engineer | ORCA-PWR-001 | Engineering
Nathan Cormier | EN-ENG-4 | Flight Software and Autonomy Engineer | ORCA-SW-001 | Engineering

## Inflation Rate
Inflation Rate
Base Year 2026
Illustrative escalation table. Historic years use placeholder Bank-of-Canada-style CPI figures; future years assume a flat 2.5% escalation. Not authoritative; pending confirmed CSA/TBS economic parameters.
FY | Inflation Rate | In BY 2026 | Forward Index | Source
2010 | Historical CPI | 1.33 |  | Illustrative - Bank of Canada CPI series
2011 | Historical CPI | 1.31 |  | Illustrative - Bank of Canada CPI series
2012 | Historical CPI | 1.29 |  | Illustrative - Bank of Canada CPI series
2013 | Historical CPI | 1.27 |  | Illustrative - Bank of Canada CPI series
2014 | Historical CPI | 1.25 |  | Illustrative - Bank of Canada CPI series
2015 | Historical CPI | 1.23 |  | Illustrative - Bank of Canada CPI series
2016 | Historical CPI | 1.21 |  | Illustrative - Bank of Canada CPI series
2017 | Historical CPI | 1.19 |  | Illustrative - Bank of Canada CPI series
2018 | Historical CPI | 1.17 |  | Illustrative - Bank of Canada CPI series
2019 | Historical CPI | 1.15 |  | Illustrative - Bank of Canada CPI series
2020 | Historical CPI | 1.13 |  | Illustrative - Bank of Canada CPI series
2021 | Historical CPI | 1.11 |  | Illustrative - Bank of Canada CPI series
2022 | Historical CPI | 1.09 |  | Illustrative - Bank of Canada CPI series
2023 | Historical CPI | 1.07 |  | Illustrative - Bank of Canada CPI series
2024 | Historical CPI | 1.05 |  | Illustrative - Bank of Canada CPI series
2025 | Historical CPI | 1.03 |  | Illustrative - Bank of Canada CPI series
2026 | 0 | 1 | 1 | Base year
2027 | 2.5% |  | 1.025 | Illustrative flat 2.5%/yr escalation
2028 | 2.5% |  | 1.0506 | Illustrative flat 2.5%/yr escalation
2029 | 2.5% |  | 1.0769 | Illustrative flat 2.5%/yr escalation
2030 | 2.5% |  | 1.1038 | Illustrative flat 2.5%/yr escalation
2031 | 2.5% |  | 1.1314 | Illustrative flat 2.5%/yr escalation
2032 | 2.5% |  | 1.1597 | Illustrative flat 2.5%/yr escalation
2033 | 2.5% |  | 1.1887 | Illustrative flat 2.5%/yr escalation
2034 | 2.5% |  | 1.2184 | Illustrative flat 2.5%/yr escalation
2035 | 2.5% |  | 1.2489 | Illustrative flat 2.5%/yr escalation
2036 | 2.5% |  | 1.2801 | Illustrative flat 2.5%/yr escalation
2037 | 2.5% |  | 1.3121 | Illustrative flat 2.5%/yr escalation
2038 | 2.5% |  | 1.3449 | Illustrative flat 2.5%/yr escalation
2039 | 2.5% |  | 1.3785 | Illustrative flat 2.5%/yr escalation
2040 | 2.5% |  | 1.413 | Illustrative flat 2.5%/yr escalation
2041 | 2.5% |  | 1.4483 | Illustrative flat 2.5%/yr escalation
2042 | 2.5% |  | 1.4845 | Illustrative flat 2.5%/yr escalation
2043 | 2.5% |  | 1.5216 | Illustrative flat 2.5%/yr escalation
2044 | 2.5% |  | 1.5597 | Illustrative flat 2.5%/yr escalation
2045 | 2.5% |  | 1.5987 | Illustrative flat 2.5%/yr escalation
2046 | 2.5% |  | 1.6386 | Illustrative flat 2.5%/yr escalation
2047 | 2.5% |  | 1.6796 | Illustrative flat 2.5%/yr escalation
2048 | 2.5% |  | 1.7216 | Illustrative flat 2.5%/yr escalation
2049 | 2.5% |  | 1.7646 | Illustrative flat 2.5%/yr escalation
2050 | 2.5% |  | 1.8087 | Illustrative flat 2.5%/yr escalation
2051 | 2.5% |  | 1.8539 | Illustrative flat 2.5%/yr escalation
2052 | 2.5% |  | 1.9003 | Illustrative flat 2.5%/yr escalation
2053 | 2.5% |  | 1.9478 | Illustrative flat 2.5%/yr escalation
2054 | 2.5% |  | 1.9965 | Illustrative flat 2.5%/yr escalation
2055 | 2.5% |  | 2.0464 | Illustrative flat 2.5%/yr escalation
2056 | 2.5% |  | 2.0976 | Illustrative flat 2.5%/yr escalation
2057 | 2.5% |  | 2.15 | Illustrative flat 2.5%/yr escalation
2058 | 2.5% |  | 2.2038 | Illustrative flat 2.5%/yr escalation
2059 | 2.5% |  | 2.2589 | Illustrative flat 2.5%/yr escalation
2060 | 2.5% |  | 2.3153 | Illustrative flat 2.5%/yr escalation