## Cover Page
CSA-FIN-RD-0589
Version Draft 1.0
2026-09-21
Cost Analysis Data Requirement (CADRe)
CADRe Part D - Additional Programmatic Inputs
ORCA at SIR
Prepared by ORCA Project Team
Reviewed by [TBD]

## Table of contents
Table of Contents
|  | Version control | 1 | Change History | Used to track the evolution of the baseline overtime
|  |  | 2 | CM List | List of documents (title, version, date, number) used in the costing exercise
| ✔️ | Decompositions | 3 | Context : Taxon, Phylum and Design Reference Missions | Provides context of this CADRe in relation to other associated CADRe. A given mission has alternate analysis scenarios (DRMs) and nearest neighbors in the same Taxon
| 🕒 |  | 4 | CBS x WBS = mapping to alternate taxonomy | The CBS is a decomposition used by the costing team. The WBS is a decomposition used by the project team. this tab is used to ma the two for reporting purposes
| 🕒 |  | 5 | Organizational Breakdown Structure (OBS) | The organizational breakdown structure identifies vendors, scientific teams, international partners, OGD clients and suppliers. It help specify their roles and hierarchy
| ✔️ | Phasing and Scheduling | 6 | Phasing Nomenclature | The costing team has prescribed names for engineering phases, and these may differ from the nameing convention of the project team. this tab help us identify what the project team uses as their naming convention
| ✔️ |  | 7 | Phasing durations | This specifies the phase durations for each segment of time, accordnig to the costing definitions
| ✔️ |  | 8 | Milestone Register | List of milestones (governance gates, technical reviews, contract start and end dates, and some interim dates)
| 🕒 |  | 9 | Gantt chart | utility function that draws a gantt chart
|  |  | 10 | Schedule Constraints and Dependencies
|  | Strategies | 11 | Strategy Narratives | Narratives including: Procurement strategy, IP strategy, Open Data Strategy, Cyber strategy, staffing strategy, etc
|  |  | 12 | DDDD - Dispose, Divest, Descope, Delay | Phase F disposal plan, Divestment Plan (After nominal operations), mitigation plans for cost overruns and extended delays (descope and delay)
|  |  | 13 | Procurement Plan | Procurement plan is a list which includes past investments (Sunk Costs), anticipated R&D activities as well as future contracts, MOUs, grants and contributions, and other sources of cunding
|  |  | 14 | Overhead Costs
| 🕒 | Constants | 15 | Economic factors (rates, fees, etc) | This is a default tab, pre-populated with economic constants, labour rates, and other commonly used rates like EBP
| 🕒 |  | 16 | Inflation Model | The inflation model help actualize historic data into the current base year, and helps add inflation on future years. It is specific to the CBS segments, and includes a most likely value as well as a pessimistic value to sensitivity analysis
|  | Math Models | 17 | CERs used and compensation algorithms | List of tools used, their versions and any compensation algorithms aplpied to results
|  |  | 18 | Nearest Neighbors | Description of Legacy or Similar Systems for comparison by analogy
|  |  | 19 | Phasing Curves (Cost distribution functions)
|  |  | 20 | Value Chain | Economic model for job impact analysis
|  | Process Improvement | 21 | Lessons Learned | Past Lessons learned considered, new lessons generated associated with Cost & Schedule Estimation

## 1 - Change history
` Table of Contents
1. Version Control - Baseline Tracker
Purpose: | To track the baseline across time
hold the major and minor releases of the baseline
| Change history and associated files that contain the relevant data |  |  |  |  | Reserved
| File Number | Date | File Version | Author | Changes | Parent Baseline Name | Baseline ID
[6 empty] | ORCA @ PREP1 | 1
[6 empty] | ORCA @ KDP-0 | 2
[6 empty] | ORCA @ MDR#2 | 3
[6 empty] | ORCA @ PREP2 | 4
[6 empty] | ORCA @ KDP-A | 5
[6 empty] | ORCA @ KDP-B | 6
[6 empty] | ORCA @ PDR | 7
[6 empty] | ORCA @ CDR | 8
| CSA-FIN-RD-0591 | 2026-09-21 | Draft 1 | MB | Initial CADRe Part D baseline: schedule scenarios, dependencies, strategies and procurement plan, aligned to the CADRe Part C SIR baseline. | ORCA @ SIR | 9 | <<--- We are here now
[6 empty] | ORCA @ KDP-E | 10
[6 empty] | ORCA @ Launch (as flown) | 11
[6 empty] | ORCA @ CR | 12
[6 empty] | ORCA @ KDP-X | 13
[6 empty] | ORCA @ end of life | 14

## 2 - CM
` Table of Contents
2. Version Control - CM List - Document Tracker
Purpose: | this is a list of useful documents used in costing
Why we are asking for this:
It helps document the source of inputs used in calculations
Reserved
| Internal ID | Category | Document Title | Org | Doc Number | Doc version | Doc date | Phase | Milestone | CDRL | Source | Contract No | LL Data ID | hyperlink | Comments | Used in this CADRe ? | Parent Baseline
| 1.01 | Costing Exercise | ORCA CADRe Part A - Mission Description | CSA | ORC-CAD-A-001 | Rev 1.0 | 2027-04-13 | Phase D | Start of Nominal Operations | A | ORCA CM Repository | ORC-CSA-001 | LL-ORC-001 | https://cm.orca.fake/ORC-CAD-A-001 | Baseline mission description | Yes | ORC-BASE-001
| 1.02 | Costing Exercise | ORCA CADRe Part B - Engineering Parameters | CSA | ORC-CAD-B-001 | Rev 1.0 | 2027-04-13 | Phase D | Start of Nominal Operations | B | ORCA CM Repository | ORC-CSA-001 | LL-ORC-002 | https://cm.orca.fake/ORC-CAD-B-001 | Engineering parameter baseline | Yes | ORC-BASE-001
| 1.03 | Costing Exercise | ORCA CADRe Part C - Essential Programmatics | CSA | ORC-CAD-C-001 | Rev 1.0 | 2027-04-13 | Phase D | Start of Nominal Operations | C | ORCA CM Repository | ORC-CSA-001 | LL-ORC-003 | https://cm.orca.fake/ORC-CAD-C-001 | Programmatic baseline | Yes | ORC-BASE-001
| 1.04 | Costing Exercise | ORCA CADRe Part D - More Programmatics | CSA | ORC-CAD-D-001 | Rev 1.0 | 2027-04-13 | Phase D | Start of Nominal Operations | D | ORCA CM Repository | ORC-CSA-001 | LL-ORC-004 | https://cm.orca.fake/ORC-CAD-D-001 | Current CADRe Part D baseline | Yes | ORC-BASE-001
| 1.05 | Costing Exercise | ORCA PM Cost Report | CSA | ORC-PM-COST-001 | Rev 1.0 | 2027-04-13 | Phase D | Start of Nominal Operations | - | ORCA PMO | ORC-CSA-001 | LL-ORC-005 | https://cm.orca.fake/ORC-PM-COST-001 | Current cost baseline | Yes | ORC-BASE-001
| 1.06 | Costing Exercise | ORCA Cost Model Verification Checklist | CSA | ORC-CM-VER-001 | Rev 1.0 | 2027-04-13 | Phase D | Start of Nominal Operations | - | ORCA PMO | ORC-CSA-001 | LL-ORC-006 | https://cm.orca.fake/ORC-CM-VER-001 | Cost model verification | Yes | ORC-BASE-001
| 1.07 | Costing Exercise | ORCA Risk Cost Adjustment Memo | CSA | ORC-RISK-COST-001 | Rev 1.0 | 2027-04-13 | Phase D | Start of Nominal Operations | - | ORCA PMO | ORC-CSA-001 | LL-ORC-007 | https://cm.orca.fake/ORC-RISK-COST-001 | Risk-adjusted cost inputs | Yes | ORC-BASE-001
| 2.01 | Governance | ORCA Project Charter | CSA | ORC-GOV-001 | Rev 2.0 | 2024-12-12 | Phase C | Critical Design Review | - | ORCA PMO | ORC-CSA-001 | LL-ORC-008 | https://cm.orca.fake/ORC-GOV-001 | Approved project governance baseline | Yes | ORC-BASE-001
| 2.02 | Governance | ORCA KDP-E Decision Package | CSA | ORC-GOV-002 | Rev 1.0 | 2027-04-13 | Phase D | Start of Nominal Operations | - | ORCA PMO | ORC-CSA-001 | LL-ORC-009 | https://cm.orca.fake/ORC-GOV-002 | KDP-E program decision baseline | Yes | ORC-KDPE-001
| 2.03 | Governance | ORCA Phase E Gate Data Package | CSA | ORC-GOV-003 | Rev 1.0 | 2027-04-13 | Phase D | Start of Nominal Operations | - | ORCA PMO | ORC-CSA-001 | LL-ORC-010 | https://cm.orca.fake/ORC-GOV-003 | Phase E evidence package | Yes | ORC-KDPE-001
| 2.04 | Governance | ORCA Configuration Control Board Charter | CSA | ORC-GOV-004 | Rev 1.0 | 2026-09-24 | Phase D | Acceptance Review | - | ORCA PMO | ORC-CSA-001 | LL-ORC-011 | https://cm.orca.fake/ORC-GOV-004 | CM authority and change control | Yes | ORC-BASE-001
| 2.05 | Governance | ORCA KDP-E Baseline Approval Memo | CSA | ORC-GOV-005 | Rev 1.0 | 2027-04-13 | Phase D | Start of Nominal Operations | - | ORCA PMO | ORC-CSA-001 | LL-ORC-012 | https://cm.orca.fake/ORC-GOV-005 | Configuration baseline approval | Yes | ORC-KDPE-001
| 3.01 | Mission Concept | ORCA Mission Concept Document | CSA | ORC-MCD-001 | Rev 1.0 | 2023-10-18 | Phase B | Preliminary Design Review | - | ORCA Systems Engineering | ORC-CSA-001 | LL-ORC-013 | https://cm.orca.fake/ORC-MCD-001 | Single approved mission concept; no alternate mission concepts retained | Yes | ORC-BASE-001
| 4.01 | Mission Requirements | ORCA Mission Requirements Document | CSA | ORC-MRD-001 | Rev 3.0 | 2024-12-12 | Phase C | Critical Design Review | - | ORCA Systems Engineering | ORC-CSA-001 | LL-ORC-014 | https://cm.orca.fake/ORC-MRD-001 | Controlled mission requirements | Yes | ORC-BASE-001
| 4.02 | Mission Requirements | ORCA System Requirements Specification | CSA | ORC-SRS-001 | Rev 2.0 | 2024-12-12 | Phase C | Critical Design Review | - | ORCA Systems Engineering | ORC-CSA-001 | LL-ORC-015 | https://cm.orca.fake/ORC-SRS-001 | System-level requirements | Yes | ORC-BASE-001
| 4.03 | Mission Requirements | NEREID Orbiter Interface Control Document | CSA | ORC-KAR-SRS-001 | Rev 2.0 | 2024-12-12 | Phase C | Critical Design Review | - | ORCA Systems Engineering | ORC-CSA-001 | LL-ORC-016 | https://cm.orca.fake/ORC-KAR-SRS-001 | Bus requirements | Yes | ORC-BASE-001
| 4.04 | Mission Requirements | ORCA Instrument Suite Requirements Specification | CSA | ORC-RCP-SRS-001 | Rev 2.0 | 2024-12-12 | Phase C | Critical Design Review | - | ORCA Payload Engineering | ORC-CSA-001 | LL-ORC-017 | https://cm.orca.fake/ORC-RCP-SRS-001 | Instrument suite requirements | Yes | ORC-BASE-001
| 4.05 | Mission Requirements | ORCA Verification and Validation Requirements Matrix | CSA | ORC-VVRM-001 | Rev 2.0 | 2026-09-24 | Phase D | Acceptance Review | - | ORCA Systems Engineering | ORC-CSA-001 | LL-ORC-018 | https://cm.orca.fake/ORC-VVRM-001 | Verification closure baseline | Yes | ORC-BASE-001
| 5.01 | Ops Plan | ORCA Mission Operations Plan | CSA | ORC-OPS-001 | Rev 2.0 | 2027-04-13 | Phase D | Start of Nominal Operations | - | ORCA Mission Operations | ORC-CSA-001 | LL-ORC-019 | https://cm.orca.fake/ORC-OPS-001 | Nominal operations baseline | Yes | ORC-KDPE-001
| 5.02 | Ops Plan | ORCA Enceladus Flyby and Sampling Operations Plan | CSA | ORC-OPS-002 | Rev 2.0 | 2027-04-13 | Phase D | Start of Nominal Operations | - | ORCA Mission Operations | ORC-CSA-001 | LL-ORC-020 | https://cm.orca.fake/ORC-OPS-002 | Plume-transit and sampling procedures | Yes | ORC-KDPE-001
| 5.03 | Ops Plan | ORCA End-of-Mission Disposal Plan | CSA | ORC-OPS-003 | Rev 1.0 | 2027-04-13 | Phase D | Start of Nominal Operations | - | ORCA Mission Operations | ORC-CSA-001 | LL-ORC-021 | https://cm.orca.fake/ORC-OPS-003 | End-of-mission disposal sequence | Yes | ORC-KDPE-001
| 6.01 | Vendor's Decompositions | NEREID Orbiter Accommodation Breakdown | CSA | ORC-KAR-PBS-001 | Rev 2.0 | 2024-12-12 | Phase C | Critical Design Review | - | ORCA Systems Engineering | ORC-CSA-001 | LL-ORC-022 | https://cm.orca.fake/ORC-KAR-PBS-001 | Bus decomposition | Yes | ORC-BASE-001
| 6.02 | Vendor's Decompositions | ORCA Instrument Suite Breakdown | CSA | ORC-RCP-PBS-001 | Rev 2.0 | 2024-12-12 | Phase C | Critical Design Review | - | ORCA Payload Engineering | ORC-CSA-001 | LL-ORC-023 | https://cm.orca.fake/ORC-RCP-PBS-001 | Payload decomposition | Yes | ORC-BASE-001
| 6.03 | PM's Decompositions | ORCA Work Breakdown Structure | CSA | ORC-WBS-001 | Rev 2.0 | 2024-12-12 | Phase C | Critical Design Review | - | ORCA PMO | ORC-CSA-001 | LL-ORC-024 | https://cm.orca.fake/ORC-WBS-001 | Program WBS baseline | Yes | ORC-BASE-001
| 6.04 | Costing Decomposition | ORCA Cost Breakdown Structure | CSA | ORC-CBS-001 | Rev 2.0 | 2024-12-12 | Phase C | Critical Design Review | - | ORCA PMO | ORC-CSA-001 | LL-ORC-025 | https://cm.orca.fake/ORC-CBS-001 | Cost structure baseline | Yes | ORC-BASE-001
| 7.01 | Vendor's TRRA | ORCA Technology Development Plan | CSA | ORC-TRRA-001 | Rev 2.0 | 2024-06-15 | Phase B | Preliminary Design Review | - | ORCA Systems Engineering | ORC-CSA-001 | LL-ORC-026 | https://cm.orca.fake/ORC-TRRA-001 | Technology maturity plan | Yes | ORC-BASE-001
| 7.02 | Vendor's TRRA | ORCA Critical Technology Element Assessment | CSA | ORC-TRRA-002 | Rev 2.0 | 2024-12-12 | Phase C | Critical Design Review | - | ORCA Systems Engineering | ORC-CSA-001 | LL-ORC-027 | https://cm.orca.fake/ORC-TRRA-002 | Instrument accommodation and autonomous plume-transit maturity | Yes | ORC-BASE-001
| 7.03 | Vendor's TRRA | ORCA Technology Maturation Roadmap | CSA | ORC-TRRA-003 | Rev 2.0 | 2025-06-24 | Phase D | Manufacturing Readiness Review | - | ORCA Systems Engineering | ORC-CSA-001 | LL-ORC-028 | https://cm.orca.fake/ORC-TRRA-003 | Technology maturation closure | Yes | ORC-BASE-001
| 7.04 | Vendor's TRRA | ORCA TRRA Summary Report | CSA | ORC-TRRA-004 | Rev 1.0 | 2026-09-24 | Phase D | Acceptance Review | - | ORCA Systems Engineering | ORC-CSA-001 | LL-ORC-029 | https://cm.orca.fake/ORC-TRRA-004 | Final technology readiness summary | Yes | ORC-BASE-001
| 8.01 | Risk Register | ORCA Engineering Risk Register | CSA | ORC-RISK-001 | Rev 4.0 | 2027-04-13 | Phase D | Start of Nominal Operations | - | ORCA PMO | ORC-CSA-001 | LL-ORC-030 | https://cm.orca.fake/ORC-RISK-001 | Technical and programmatic risks | Yes | ORC-KDPE-001
| 8.02 | Risk Register | ORCA Mission Operations Risk Register | CSA | ORC-RISK-002 | Rev 1.0 | 2027-04-13 | Phase D | Start of Nominal Operations | - | ORCA Mission Operations | ORC-CSA-001 | LL-ORC-031 | https://cm.orca.fake/ORC-RISK-002 | Operational and proximity-operation risks | Yes | ORC-KDPE-001
| 8.03 | Risk Register | ORCA Cost Risk Register | CSA | ORC-RISK-003 | Rev 2.0 | 2027-04-13 | Phase D | Start of Nominal Operations | - | ORCA PMO | ORC-CSA-001 | LL-ORC-032 | https://cm.orca.fake/ORC-RISK-003 | Cost uncertainty and reserves | Yes | ORC-KDPE-001
| 9.01 | Vendor Quotes | Host Orbiter Interface Hardware Estimate | CSA | ORC-VQ-001 | Rev 1.0 | 2024-10-01 | Phase C | Critical Design Review | - | ORCA Procurement | ORC-CSA-001 | LL-ORC-033 | https://quotes.orca.fake/ORC-VQ-001 | Fictional supplier estimate | Yes | ORC-BASE-001
| 9.02 | Vendor Quotes | ORCA Sampling Arm Procurement Estimate | CSA | ORC-VQ-002 | Rev 1.0 | 2024-10-15 | Phase C | Critical Design Review | - | ORCA Procurement | ORC-CSA-001 | LL-ORC-034 | https://quotes.orca.fake/ORC-VQ-002 | Fictional supplier estimate | Yes | ORC-BASE-001
| 9.03 | Vendor Quotes | Ice-Penetrating Radar Sensor Procurement Estimate | CSA | ORC-VQ-003 | Rev 1.0 | 2024-11-01 | Phase C | Critical Design Review | - | ORCA Procurement | ORC-CSA-001 | LL-ORC-035 | https://quotes.orca.fake/ORC-VQ-003 | Fictional supplier estimate | Yes | ORC-BASE-001
| 9.04 | Vendor Quotes | Flight Computer and Avionics Procurement Estimate | CSA | ORC-VQ-004 | Rev 1.0 | 2024-11-15 | Phase C | Critical Design Review | - | ORCA Procurement | ORC-CSA-001 | LL-ORC-036 | https://quotes.orca.fake/ORC-VQ-004 | Fictional supplier estimate | Yes | ORC-BASE-001

## 3 - Taxon
` Table of Contents
3. Context (TAXON, Phylum , DRM)
Purpose: | Provides context of this CADRe in relation to other associated CADRe. A given mission has alternate analysis scenarios (DRMs) and nearest neighbors in the same Taxon
The DRM is used to express different mission concepts, or different analysis options like AIS (on-off), mission class (B-C)
The taxon is used to classify missions into similar neighborhoods.
TAXON 1 | TAXON 2 | PHYLUM | Generation | Missions | Mission Description | Analysis Scenarios | Analysis Scenarios desc | DRM
Space Mission | Orbital Sustainability Missions | On-Orbit Debris Removal | 1 | DELTARA | Single-target mission that captures an inactive satellite and lowers its orbit for atmospheric re-entry. | Single-Pass Sampling Scenario |  | DRM-VAN-001
|  |  | 2 | NEXORA | Multi-target debris-removal mission using autonomous orbital transfers between inactive LEO satellites. | Multi-Pass Sampling Scenario |  | DRM-NEX-001
|  |  | 3 | SENTRA | Active debris-removal mission using a robotic capture arm to rendezvous with and deorbit inactive LEO satellites. | SENTRA Baseline Mission |  | DRM-SEN-001: Multi-target rendezvous, robotic capture, and deorbit of inactive LEO satellites
[5 empty] | Space situational awareness mission | Option 1 | MDA concept at Phase 0
[6 empty] | Option 2 | Airbus concept at Phase 0
[6 empty] | Option 3 | Boeing Mission Concept at Phase 0
[6 empty] | Option 4 | PPP option by Company X
[6 empty] | Baseline at KDP-B | Comdev is the mission baseline starting at Phase B
|  | On_orbit Servicing | 1 | VANTERA | Robotic inspection of inactive LEO spacecraft. | Inspection Scenario
|  |  | 2 | ORVEX | Robotic capture and servicing of cooperative spacecraft. | Servicing Scenario
[7 empty] | Remote sensing of the Enceladus plume and surface. | Inspection Scenario
[7 empty] | In-situ sampling and analysis of plume ejecta. | Servicing Scenario
Space Mission | Deep Space Science Missions | Outer-Planet In-Situ Instrument Missions | 1 | LUMEN | CSA-led space telescope instrument contribution to a partner-agency observatory mission. | LUMEN Baseline Mission |  | DRM-LUM-001
|  |  | 2 | BOREALIS | CSA-led remote-sensing instrument contribution to a partner-agency deep-space mission. | Borealis Baseline Mission |  | DRM-BOR-001
|  |  | 3 | ORCA | CSA-led instrument suite (ice-penetrating radar, mass spectrometer and sampling arm) hosted on the NEREID orbiter (NASA-led, ESA-contributed platform) to transit Enceladus's plume and characterize its composition and sub-surface ocean chemistry. | ORCA Baseline Mission |  | DRM-ORC-001: Enceladus plume transit, in-situ sampling, and sub-surface ocean chemistry characterization
|  | On-Orbit Servicing | 1 | VANTERA | Robotic inspection of inactive LEO spacecraft. | Inspection Scenario |  | DRM-VAN-001
|  |  | 2 | ORVEX | Robotic capture and servicing of cooperative spacecraft. | Servicing Scenario |  | DRM-ORV-001

## 4- WBS Mapping
4. CBS to WBS Traceability Table — ORCA
Purpose: | The ORCA WBS translates the project CBS into the mission team's planning and reporting structure, covering the NEREID Orbiter, instrument accommodation payload, launch, ground segment, integration, and mission operations.
WBS | WBS Element | Phase A | Phase B/C | MAIT | SAIT | LEOP | Phase E/X
1 | ORCA Mission Program | 1.1, 1.2 | 1.1, 1.2, 1.3 | 1.1 | 1.1 | 1.1 | 1.1
1.1 | Project Management & Mission Control | 1.1 | 1.1 | 1.1 | 1.1 | 1.1 | 1.1
1.1.1 | Project Management & Controls | 1.1.1 | 1.1.1 | 1.1.1 | 1.1.1 | 1.1.1 | 1.1.1
1.1.2 | Cost, Schedule & Configuration Management | 1.1.2 | 1.1.2 | 1.1.2 | 1.1.2 | 1.1.2 | 1.1.2
1.1.3 | Reviews, Governance & Mission Reporting | 1.1.3 | 1.1.3 | 1.1.3 | 1.1.3 | 1.1.3 | 1.1.3
1.2 | Safety & Mission Assurance | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2
1.3 | Host Orbiter Interface & Accommodation (Partner-Provided Platform) | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
1.3.1 | Power Interface & Energy Budget Coordination | 1.3.1 | 1.3.1 | 1.3.1 | 1.3.1 | 1.3.1 | 1.3.1
1.3.2 | Pointing & Accommodation Requirements | 1.3.2 | 1.3.2 | 1.3.2 | 1.3.2 | 1.3.2 | 1.3.2
1.3.3 | Command & Data Handling Interface | 1.3.3 | 1.3.3 | 1.3.3 | 1.3.3 | 1.3.3 | 1.3.3
1.3.4 | Communications Relay Interface | 1.3.4 | 1.3.4 | 1.3.4 | 1.3.4 | 1.3.4 | 1.3.4
1.3.5 | Interface Verification & Testing | 1.3.5 | 1.3.5 | 1.3.5 | 1.3.5 | 1.3.5 | 1.3.5
1.3.6 | Structural & Thermal Interface | 1.3.6 | 1.3.6 | 1.3.6 | 1.3.6 | 1.3.6 | 1.3.6
1.4 | ORCA Instrument Suite | 1.4 | 1.4 | 1.4 | 1.4 | 1.4 | 1.4
1.4.1 | Sampling Arm & End-Effector | 1.4.1 | 1.4.1 | 1.4.1 | 1.4.1 | 1.4.1 | 1.4.1
1.4.2 | Ice-Penetrating Radar Subsystem | 1.4.2 | 1.4.2 | 1.4.2 | 1.4.2 | 1.4.2 | 1.4.2
1.4.3 | Mass Spectrometer & Instrument Electronics | 1.4.3 | 1.4.3 | 1.4.3 | 1.4.3 | 1.4.3 | 1.4.3
1.5 | Launch Support (Partner-Procured) | 1.5 | 1.5 | 1.5 | 1.5
1.5.1 | Instrument Suite Launch Readiness |  | 1.5.1 | 1.5.1 | 1.5.1
1.5.2 | Launch Campaign Support |  |  | 1.5.2 | 1.5.2 | 1.5.2
1.6 | Ground Segment | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6
1.6.1 | Mission Control & Telemetry | 1.6.1 | 1.6.1 | 1.6.1 | 1.6.1 | 1.6.1 | 1.6.1
1.6.2 | Mission Planning & Science Data Database | 1.6.2 | 1.6.2 | 1.6.2 | 1.6.2 | 1.6.2 | 1.6.2
1.7 | Mission Operations | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7
1.7.1 | Plume Transit & Sampling Operations |  | 1.7.1 | 1.7.1 | 1.7.1 | 1.7.1 | 1.7.1
1.7.2 | Sample Acquisition & Science Data Operations |  |  | 1.7.2 | 1.7.2 | 1.7.2 | 1.7.2
1.8 | System Integration, Assembly, Test & Verification |  | 1.8 | 1.8 | 1.8 | 1.8
1.8.1 | Engineering Model Integration & Test |  | 1.8.1 | 1.8.1
1.8.2 | Qualification & Environmental Testing |  | 1.8.2 | 1.8.2 | 1.8.2
1.8.3 | Flight Acceptance & End-to-End Testing |  |  |  | 1.8.3 | 1.8.3
1.9 | Commissioning |  |  |  |  | 1.9 | 1.9
1.9.1 | Host Orbiter Interface Commissioning |  |  |  |  | 1.9.1 | 1.9.1
1.9.2 | Instrument Suite Commissioning |  |  |  |  | 1.9.2 | 1.9.2

## 4d - CBS in JS format (hidden)
` Table of Contents
4d. CBS (as self referencing list) for use as a javascript array
Why we we asking:
this page is auto-generated and used for drawing it out
Self referencing list for dtree
UID | Parent ID | Level | Node Name | CBS Code | Depth | Icon | Notes | Javascript Code | Depth
1 | -1 | 1 | Space Missions |  | Taxon 1 | Box.png |  | datatable[0] = new Array("1","-1","Space Missions","1","Box.png"); | Taxon 1
2 | 1 | 2 | EO SAR Missions |  | Taxon 2 | EO.png |  | datatable[1] = new Array("2","1","EO SAR Missions","2","EO.png"); | Taxon 2
3 | 2 | 3 | Radarsat Portfolio |  | Phylum | Pouch.png |  | datatable[2] = new Array("3","2","Radarsat Portfolio","3","Pouch.png"); | Phylum
4 | 0 | 4 | Radarsat 1 |  | Mission | Satellite.png |  | datatable[3] = new Array("4","0","Radarsat 1","4","Satellite.png"); | Mission
5 | 0 | 4 | Radarsat 2 |  | Mission | Satellite.png |  | datatable[4] = new Array("5","0","Radarsat 2","4","Satellite.png"); | Design Reference Mission
6 | 0 | 4 | Radarsat Constellation Mission |  | Mission | Satellite.png |  | datatable[5] = new Array("6","0","Radarsat Constellation Mission","4","Satellite.png"); | Segment
7 | 0 | 4 | Radarsat+ Replenishment | 1 | Mission | Satellite.png |  | datatable[6] = new Array("7","0","Radarsat+ Replenishment","4","Satellite.png"); | System of Systems
8 | 0 | 4 | Radarsat+ Next Generation |  | Mission | Satellite.png |  | datatable[7] = new Array("8","0","Radarsat+ Next Generation","4","Satellite.png"); | System
9 | 2 | 5 | Analysis Scenario 1: RCM Proxy |  | Design Reference Mission | Scenario.png |  | datatable[8] = new Array("9","2","Analysis Scenario 1: RCM Proxy","5","Scenario.png"); | Subsystem
10 | 2 | 5 | Analysis Scenario 2: RCM+ |  | Design Reference Mission | Scenario.png |  | datatable[9] = new Array("10","2","Analysis Scenario 2: RCM+","5","Scenario.png"); | Assembly
11 | 2 | 5 | Analysis Scenario 3: Airbus concept |  | Design Reference Mission | Scenario.png |  | datatable[10] = new Array("11","2","Analysis Scenario 3: Airbus concept","5","Scenario.png"); | Component
12 | 2 | 5 | Analysis Scenario 4: MDA Chorus Data Buy |  | Design Reference Mission | Scenario.png |  | datatable[11] = new Array("12","2","Analysis Scenario 4: MDA Chorus Data Buy","5","Scenario.png");
13 | 2 | 5 | Analysis Scenario 5: MDA Chorus+ |  | Design Reference Mission | Scenario.png |  | datatable[12] = new Array("13","2","Analysis Scenario 5: MDA Chorus+","5","Scenario.png");
14 | 2 | 5 | Analysis Scenario 6: Airbus Sentinel 2 |  | Design Reference Mission | Scenario.png |  | datatable[13] = new Array("14","2","Analysis Scenario 6: Airbus Sentinel 2","5","Scenario.png");
15 | 8 | 6 | Government Overhead and Oversight | 1.1 | Segment | Government.png | This WBS includes all CSA Oversight, OGD salaries, and basic overhead for the care and maintenance of CSA staff | datatable[14] = new Array("15","8","Government Overhead and Oversight","6","Government.png");
16 | 8 | 6 | Space Segment | 1.2 | Segment | Satellite.png | The Space Segment includes things we launch into space | datatable[15] = new Array("16","8","Space Segment","6","Satellite.png");
17 | 8 | 6 | Launch Segment | 1.3 | Segment | Rocket.png | The launch segment includes the launch vehicle and seom support services | datatable[16] = new Array("17","8","Launch Segment","6","Rocket.png");
18 | 8 | 6 | Ground Segment | 1.4 | Segment | Facility.png | The ground segment includes the planning desgin and development of the GS, but not the Ops | datatable[17] = new Array("18","8","Ground Segment","6","Facility.png");
19 | 8 | 6 | Ops Segment | 1.5 | Segment | Ops.png | Ops includes SatOps, Mission Ops, Science Ops - typically contracts | datatable[18] = new Array("19","8","Ops Segment","6","Ops.png");
20 | 8 | 6 | Science Segment | 1.6 | Segment | Science.png | Typically G&C | datatable[19] = new Array("20","8","Science Segment","6","Science.png");
21 | 10 | 7 | Gov't Oversight (Salaries and EBP) | 1.1.1 | System of Systems | Government.png |  | datatable[20] = new Array("21","10","Gov't Oversight (Salaries and EBP)","7","Government.png");
22 | 10 | 7 | Government Overhead | 1.1.2 | System of Systems | Government.png |  | datatable[21] = new Array("22","10","Government Overhead","7","Government.png");
23 | 21 | 8 | CSA Oversight | 1.1.1.1 | System | Government.png |  | datatable[22] = new Array("23","21","CSA Oversight","8","Government.png");
24 | 21 | 8 | OGD Oversight | 1.1.1.2 | System | Government.png |  | datatable[23] = new Array("24","21","OGD Oversight","8","Government.png");
25 | 23 | 9 | CSA Project Team | 1.1.1.1.1 | Subsystem | Government.png | This CBS contains all salaries associated with the RAM of the Project team | datatable[24] = new Array("25","23","CSA Project Team","9","Government.png");
26 | 23 | 9 | CSA Internal Services | 1.1.1.1.2 | Subsystem | Government.png | This CBS contains all salaries associated with CSA internal services (finance, HR, audit, eval, policy, Executives, IM, IT, contracts, shipping, etc) | datatable[25] = new Array("26","23","CSA Internal Services","9","Government.png");
27 | 24 | 9 | OGD Internal Services by MOU | 1.1.1.2.1 | Subsystem | Government.png |  | datatable[26] = new Array("27","24","OGD Internal Services by MOU","9","Government.png");
28 | 24 | 9 | OGD User Departments by MOU (RAM portion) | 1.1.1.2.2 | Subsystem | Government.png |  | datatable[27] = new Array("28","24","OGD User Departments by MOU (RAM portion)","9","Government.png");
29 | 21 | 10 | Shared Services | 1.1.1.2.1.1 | Assembly | Government.png |  | datatable[28] = new Array("29","21","Shared Services","10","Government.png");
30 | 21 | 10 | SPAC | 1.1.1.2.1.2 | Assembly | Government.png |  | datatable[29] = new Array("30","21","SPAC","10","Government.png");
31 | 21 | 10 | Justice Canada | 1.1.1.2.1.3 | Assembly | Government.png |  | datatable[30] = new Array("31","21","Justice Canada","10","Government.png");
32 | 23 | 10 | ECCC | 1.1.1.2.2.1 | Assembly | Government.png |  | datatable[31] = new Array("32","23","ECCC","10","Government.png");
33 | 23 | 10 | NRCAN | 1.1.1.2.2.2 | Assembly | Government.png |  | datatable[32] = new Array("33","23","NRCAN","10","Government.png");
34 | 23 | 10 | DND | 1.1.1.2.2.3 | Assembly | Government.png |  | datatable[33] = new Array("34","23","DND","10","Government.png");
35 | 25 | 11 | RAM per Person per FY and Phase | 1.1.1.1.1.1 | Component | Government.png |  | datatable[34] = new Array("35","25","RAM per Person per FY and Phase","11","Government.png");
36 | 25 | 11 | PSPC Procurement Services | 1.1.1.2.1.2.1 | Component | Government.png |  | datatable[35] = new Array("36","25","PSPC Procurement Services","11","Government.png");
37 | 25 | 11 | PSPC Fairness Monitor | 1.1.1.2.1.2.2 | Component | Government.png |  | datatable[36] = new Array("37","25","PSPC Fairness Monitor","11","Government.png");
38 | 31 | 11 | Legal Services | 1.1.1.2.1.3.1 | Component | Government.png |  | datatable[37] = new Array("38","31","Legal Services","11","Government.png");
39 | 22 | 8 | CSA Overhead | 1.1.2.1 | System | Government.png |  | datatable[38] = new Array("39","22","CSA Overhead","8","Government.png");
40 | 34 | 9 | IS Management Overhead | 1.1.2.1.1 | Subsystem | Government.png |  | datatable[39] = new Array("40","34","IS Management Overhead ","9","Government.png");
41 | 34 | 9 | Management Consulting Services | 1.1.2.1.2 | Subsystem | Government.png |  | datatable[40] = new Array("41","34","Management Consulting Services","9","Government.png");
42 | 34 | 9 | Temporary Help | 1.1.2.1.3 | Subsystem | Government.png |  | datatable[41] = new Array("42","34","Temporary Help","9","Government.png");
43 | 34 | 9 | Students | 1.1.2.1.4 | Subsystem | Government.png | This CBS includes any students, FSWEP or PDF assisint Csa project team | datatable[42] = new Array("43","34","Students","9","Government.png");
44 | 34 | 9 | Government Travel & Living | 1.1.2.1.5 | Subsystem | Government.png | This CBS includes any government Travel and Living expenses | datatable[43] = new Array("44","34","Government Travel & Living","9","Government.png");
45 | 34 | 9 | Translation | 1.1.2.1.6 | Subsystem | Government.png | This CBS includes any translation costs | datatable[44] = new Array("45","34","Translation","9","Government.png");
46 | 34 | 9 | Shipping | 1.1.2.1.7 | Subsystem | Government.png | This CBs includes any shipping cost, but not shipping flight HW which is under space segment | datatable[45] = new Array("46","34","Shipping","9","Government.png");
47 | 34 | 9 | Software Licenses | 1.1.2.1.8 | Subsystem | Government.png | This CBS includes any COTs SW not flight Sw or ground SW | datatable[46] = new Array("47","34","Software Licenses","9","Government.png");
48 | 34 | 9 | Public Outreach and STEM initiatives | 1.1.2.1.9 | Subsystem | Government.png | This CBS includes any public relations and STEM | datatable[47] = new Array("48","34","Public Outreach and STEM initiatives","9","Government.png");
49 | 34 | 9 | Other Overhead (Specify) | 1.1.2.1.10 | Subsystem | Government.png | This CBS includes any other misc fees | datatable[48] = new Array("49","34","Other Overhead (Specify)","9","Government.png");
50 | 36 | 10 | Consultants - Industrial Space Experts | 1.1.2.1.2.1 | Assembly | Government.png |  | datatable[49] = new Array("50","36","Consultants - Industrial Space Experts","10","Government.png");
51 | 36 | 10 | Consultants - Academia | 1.1.2.1.2.2 | Assembly | Government.png |  | datatable[50] = new Array("51","36","Consultants - Academia","10","Government.png");
52 | 36 | 10 | Consultants - Non-Space Experts | 1.1.2.1.2.3 | Assembly | Government.png |  | datatable[51] = new Array("52","36","Consultants - Non-Space Experts","10","Government.png");
53 | 12 | 6 | Mission SEITPM and Support Equipment |  | Segment | SEITPM.png |  | datatable[52] = new Array("53","12","Mission SEITPM and Support Equipment","6","SEITPM.png");
54 | 48 | 7 | Project Management |  | System of Systems | SEITPM.png |  | datatable[53] = new Array("54","48","Project Management","7","SEITPM.png");
55 | 48 | 7 | Systems Engineering |  | System of Systems | SEITPM.png |  | datatable[54] = new Array("55","48","Systems Engineering","7","SEITPM.png");
56 | 48 | 7 | Mission Assurance |  | System of Systems | SEITPM.png |  | datatable[55] = new Array("56","48","Mission Assurance","7","SEITPM.png");
57 | 48 | 7 | Assembly, Integration and Testing |  | System of Systems | SEITPM.png |  | datatable[56] = new Array("57","48","Assembly, Integration and Testing","7","SEITPM.png");
58 | 48 | 7 | Support Equipment |  | System of Systems | SEITPM.png |  | datatable[57] = new Array("58","48","Support Equipment","7","SEITPM.png");
59 | 16 | 7 | Space Vehicle 1 … i |  | System of Systems | Satellite.png |  | datatable[58] = new Array("59","16","Space Vehicle 1 … i","7","Satellite.png");
60 | 59 | 8 | Spacecraft SEITPM and Support Equipment |  | System | SEITPM.png |  | datatable[59] = new Array("60","59","Spacecraft SEITPM and Support Equipment","8","SEITPM.png");
61 | 55 | 9 | Project Management |  | Subsystem | SEITPM.png |  | datatable[60] = new Array("61","55","Project Management","9","SEITPM.png");
62 | 55 | 9 | Systems Engineering |  | Subsystem | SEITPM.png |  | datatable[61] = new Array("62","55","Systems Engineering","9","SEITPM.png");
63 | 55 | 9 | Mission Assurance |  | Subsystem | SEITPM.png |  | datatable[62] = new Array("63","55","Mission Assurance","9","SEITPM.png");
64 | 55 | 9 | Assembly, Integration and Testing |  | Subsystem | SEITPM.png |  | datatable[63] = new Array("64","55","Assembly, Integration and Testing","9","SEITPM.png");
65 | 55 | 9 | Support Equipment |  | Subsystem | SEITPM.png |  | datatable[64] = new Array("65","55","Support Equipment","9","SEITPM.png");
66 | 59 | 8 | Bus/Platform |  | System | Widget.png |  | datatable[65] = new Array("66","59","Bus/Platform","8","Widget.png");
67 | 66 | 9 | Platform SEITPM and Support Equipment |  | Subsystem | SEITPM.png |  | datatable[66] = new Array("67","66","Platform SEITPM and Support Equipment","9","SEITPM.png");
68 | 62 | 10 | Project Management |  | Assembly | SEITPM.png |  | datatable[67] = new Array("68","62","Project Management","10","SEITPM.png");
69 | 62 | 10 | Systems Engineering |  | Assembly | SEITPM.png |  | datatable[68] = new Array("69","62","Systems Engineering","10","SEITPM.png");
70 | 62 | 10 | Mission Assurance |  | Assembly | SEITPM.png |  | datatable[69] = new Array("70","62","Mission Assurance","10","SEITPM.png");
71 | 62 | 10 | Assembly, Integration and Testing |  | Assembly | SEITPM.png |  | datatable[70] = new Array("71","62","Assembly, Integration and Testing","10","SEITPM.png");
72 | 62 | 10 | Support Equipment |  | Assembly | SEITPM.png |  | datatable[71] = new Array("72","62","Support Equipment","10","SEITPM.png");
73 | 61 | 9 | Structures and Mechanisms Subsystem (SMS) |  | Subsystem | Widget.png |  | datatable[72] = new Array("73","61","Structures and Mechanisms Subsystem (SMS)","9","Widget.png");
74 | 68 | 10 | Structures and Mechanisms Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[73] = new Array("74","68","Structures and Mechanisms Subsystem SEITPM","10","SEITPM.png");
75 | 69 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[74] = new Array("75","69","Project Management","11","SEITPM.png");
76 | 69 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[75] = new Array("76","69","Systems Engineering","11","SEITPM.png");
77 | 69 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[76] = new Array("77","69","Mission Assurance","11","SEITPM.png");
78 | 69 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[77] = new Array("78","69","Assembly, Integration and Testing","11","SEITPM.png");
79 | 69 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[78] = new Array("79","69","Support Equipment","11","SEITPM.png");
80 | 68 | 10 | Primary Structures |  | Assembly | Widget.png |  | datatable[79] = new Array("80","68","Primary Structures","10","Widget.png");
81 | 75 | 11 | Load Carrying Shell/Truss |  | Component | Widget.png |  | datatable[80] = new Array("81","75","Load Carrying Shell/Truss","11","Widget.png");
82 | 75 | 11 | Equipment Compartments |  | Component | Widget.png |  | datatable[81] = new Array("82","75","Equipment Compartments","11","Widget.png");
83 | 75 | 11 | Booms |  | Component | Widget.png |  | datatable[82] = new Array("83","75","Booms","11","Widget.png");
84 | 75 | 11 | Adapters |  | Component | Widget.png |  | datatable[83] = new Array("84","75","Adapters","11","Widget.png");
85 | 75 | 11 | Other Structures (Specify) |  | Component | Widget.png |  | datatable[84] = new Array("85","75","Other Structures (Specify)","11","Widget.png");
86 | 68 | 10 | Secondary Structures |  | Assembly | Widget.png |  | datatable[85] = new Array("86","68","Secondary Structures","10","Widget.png");
87 | 81 | 11 | Equipment (Instrument) Mountings |  | Component | Widget.png |  | datatable[86] = new Array("87","81","Equipment (Instrument) Mountings","11","Widget.png");
88 | 81 | 11 | Ballast Mass |  | Component | Widget.png |  | datatable[87] = new Array("88","81","Ballast Mass","11","Widget.png");
89 | 81 | 11 | Other Secondary Structures (Specify) |  | Component | Widget.png |  | datatable[88] = new Array("89","81","Other Secondary Structures (Specify)","11","Widget.png");
90 | 68 | 10 | Mechanisms and Pyrotechnics |  | Assembly | Widget.png |  | datatable[89] = new Array("90","68","Mechanisms and Pyrotechnics","10","Widget.png");
91 | 85 | 11 | Positioning |  | Component | Widget.png |  | datatable[90] = new Array("91","85","Positioning","11","Widget.png");
92 | 85 | 11 | Deployment and Storage Equipment |  | Component | Widget.png |  | datatable[91] = new Array("92","85","Deployment and Storage Equipment","11","Widget.png");
93 | 85 | 11 | Docking Mechanisms |  | Component | Widget.png |  | datatable[92] = new Array("93","85","Docking Mechanisms","11","Widget.png");
94 | 85 | 11 | Other Mechanisms (Specify) |  | Component | Widget.png |  | datatable[93] = new Array("94","85","Other Mechanisms (Specify)","11","Widget.png");
95 | 85 | 11 | Pyrotechnics |  | Component | Widget.png |  | datatable[94] = new Array("95","85","Pyrotechnics","11","Widget.png");
96 | 68 | 10 | SMS Other (Specify) |  | Assembly | Widget.png |  | datatable[95] = new Array("96","68","SMS Other (Specify)","10","Widget.png");
97 | 61 | 9 | Thermal Control Subsystem (TCS) |  | Subsystem | Widget.png |  | datatable[96] = new Array("97","61","Thermal Control Subsystem (TCS)","9","Widget.png");
98 | 92 | 10 | Thermal Control Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[97] = new Array("98","92","Thermal Control Subsystem SEITPM","10","SEITPM.png");
99 | 93 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[98] = new Array("99","93","Project Management","11","SEITPM.png");
100 | 93 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[99] = new Array("100","93","Systems Engineering","11","SEITPM.png");
101 | 93 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[100] = new Array("101","93","Mission Assurance","11","SEITPM.png");
102 | 93 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[101] = new Array("102","93","Assembly, Integration and Testing","11","SEITPM.png");
103 | 93 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[102] = new Array("103","93","Support Equipment","11","SEITPM.png");
104 | 92 | 10 | Active Devices |  | Assembly | Widget.png |  | datatable[103] = new Array("104","92","Active Devices","10","Widget.png");
105 | 99 | 11 | Cryogenic Devices |  | Component | Widget.png |  | datatable[104] = new Array("105","99","Cryogenic Devices","11","Widget.png");
106 | 99 | 11 | Liquid Loops |  | Component | Widget.png |  | datatable[105] = new Array("106","99","Liquid Loops","11","Widget.png");
107 | 99 | 11 | Electric Coolers |  | Component | Widget.png |  | datatable[106] = new Array("107","99","Electric Coolers","11","Widget.png");
108 | 99 | 11 | Heaters, Thermistors, and Thermostats |  | Component | Widget.png |  | datatable[107] = new Array("108","99","Heaters, Thermistors, and Thermostats","11","Widget.png");
109 | 99 | 11 | Other Active Devices (Specify) |  | Component | Widget.png |  | datatable[108] = new Array("109","99","Other Active Devices (Specify)","11","Widget.png");
110 | 92 | 10 | Passive Devices |  | Assembly | Widget.png |  | datatable[109] = new Array("110","92","Passive Devices","10","Widget.png");
111 | 105 | 11 | Radiator Panel/Fins |  | Component | Widget.png |  | datatable[110] = new Array("111","105","Radiator Panel/Fins","11","Widget.png");
112 | 105 | 11 | Coatings |  | Component | Widget.png |  | datatable[111] = new Array("112","105","Coatings","11","Widget.png");
113 | 105 | 11 | Heat Pipes |  | Component | Widget.png |  | datatable[112] = new Array("113","105","Heat Pipes","11","Widget.png");
114 | 105 | 11 | Insulation |  | Component | Widget.png |  | datatable[113] = new Array("114","105","Insulation","11","Widget.png");
115 | 105 | 11 | Conductive Structures |  | Component | Widget.png |  | datatable[114] = new Array("115","105","Conductive Structures","11","Widget.png");
116 | 105 | 11 | Heat Activated Structures |  | Component | Widget.png |  | datatable[115] = new Array("116","105","Heat Activated Structures","11","Widget.png");
117 | 105 | 11 | Sun Shields |  | Component | Widget.png |  | datatable[116] = new Array("117","105","Sun Shields","11","Widget.png");
118 | 105 | 11 | Second Surface Mirrors |  | Component | Widget.png |  | datatable[117] = new Array("118","105","Second Surface Mirrors","11","Widget.png");
119 | 105 | 11 | Shutters and Louvers |  | Component | Widget.png |  | datatable[118] = new Array("119","105","Shutters and Louvers","11","Widget.png");
120 | 105 | 11 | Other Passive Devices (Specify) |  | Component | Widget.png |  | datatable[119] = new Array("120","105","Other Passive Devices (Specify)","11","Widget.png");
121 | 92 | 10 | TCS Other (Specify) |  | Assembly | Widget.png |  | datatable[120] = new Array("121","92","TCS Other (Specify)","10","Widget.png");
122 | 61 | 9 | Electric Power Subsystem (EPS) |  | Subsystem | Widget.png |  | datatable[121] = new Array("122","61","Electric Power Subsystem (EPS)","9","Widget.png");
123 | 117 | 10 | Electric Power Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[122] = new Array("123","117","Electric Power Subsystem SEITPM","10","SEITPM.png");
124 | 118 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[123] = new Array("124","118","Project Management","11","SEITPM.png");
125 | 118 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[124] = new Array("125","118","Systems Engineering","11","SEITPM.png");
126 | 118 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[125] = new Array("126","118","Mission Assurance","11","SEITPM.png");
127 | 118 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[126] = new Array("127","118","Assembly, Integration and Testing","11","SEITPM.png");
128 | 118 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[127] = new Array("128","118","Support Equipment","11","SEITPM.png");
129 | 117 | 10 | Electrical Power Generation |  | Assembly | Widget.png |  | datatable[128] = new Array("129","117","Electrical Power Generation","10","Widget.png");
130 | 124 | 11 | Solar Array |  | Component | Widget.png |  | datatable[129] = new Array("130","124","Solar Array","11","Widget.png");
131 | 124 | 11 | Solar Array Positioner |  | Component | Widget.png |  | datatable[130] = new Array("131","124","Solar Array Positioner","11","Widget.png");
132 | 124 | 11 | Radioisotope Thermionic Generator |  | Component | Widget.png |  | datatable[131] = new Array("132","124","Radioisotope Thermionic Generator","11","Widget.png");
133 | 124 | 11 | Chemical (Fuel Cells) |  | Component | Widget.png |  | datatable[132] = new Array("133","124","Chemical (Fuel Cells)","11","Widget.png");
134 | 124 | 11 | Auxiliary Power Units |  | Component | Widget.png |  | datatable[133] = new Array("134","124","Auxiliary Power Units","11","Widget.png");
135 | 124 | 11 | Other Power Sources |  | Component | Widget.png |  | datatable[134] = new Array("135","124","Other Power Sources","11","Widget.png");
136 | 117 | 10 | Electrical Power Conditioning |  | Assembly | Widget.png |  | datatable[135] = new Array("136","117","Electrical Power Conditioning","10","Widget.png");
137 | 131 | 11 | Power Control Electronics |  | Component | Widget.png |  | datatable[136] = new Array("137","131","Power Control Electronics","11","Widget.png");
138 | 131 | 11 | Power Conversion Electronics |  | Component | Widget.png |  | datatable[137] = new Array("138","131","Power Conversion Electronics","11","Widget.png");
139 | 131 | 11 | Power Dissipation Devices |  | Component | Widget.png |  | datatable[138] = new Array("139","131","Power Dissipation Devices","11","Widget.png");
140 | 131 | 11 | Power Distribution Electronics |  | Component | Widget.png |  | datatable[139] = new Array("140","131","Power Distribution Electronics","11","Widget.png");
141 | 131 | 11 | Power Switching Electronics |  | Component | Widget.png |  | datatable[140] = new Array("141","131","Power Switching Electronics","11","Widget.png");
142 | 131 | 11 | Power Regulation Electronics |  | Component | Widget.png |  | datatable[141] = new Array("142","131","Power Regulation Electronics","11","Widget.png");
143 | 131 | 11 | Other Power Conditioning Devices (Specify) |  | Component | Widget.png |  | datatable[142] = new Array("143","131","Other Power Conditioning Devices (Specify)","11","Widget.png");
144 | 117 | 10 | Electrical Power Storage |  | Assembly | Widget.png |  | datatable[143] = new Array("144","117","Electrical Power Storage","10","Widget.png");
145 | 139 | 11 | Rechargeable Batteries |  | Component | Widget.png |  | datatable[144] = new Array("145","139","Rechargeable Batteries","11","Widget.png");
146 | 139 | 11 | Charge Control Electronics |  | Component | Widget.png |  | datatable[145] = new Array("146","139","Charge Control Electronics","11","Widget.png");
147 | 139 | 11 | Other Electrical Power Storage Devices (Specify) |  | Component | Widget.png |  | datatable[146] = new Array("147","139","Other Electrical Power Storage Devices (Specify)","11","Widget.png");
148 | 117 | 10 | Harnesses and Cables |  | Assembly | Widget.png |  | datatable[147] = new Array("148","117","Harnesses and Cables","10","Widget.png");
149 | 117 | 10 | EPS Other (Specify) |  | Assembly | Widget.png |  | datatable[148] = new Array("149","117","EPS Other (Specify)","10","Widget.png");
150 | 61 | 9 | Attitude Control Subsystem (ACS) |  | Subsystem | Widget.png |  | datatable[149] = new Array("150","61","Attitude Control Subsystem (ACS)","9","Widget.png");
151 | 145 | 10 | Attitude Control Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[150] = new Array("151","145","Attitude Control Subsystem SEITPM","10","SEITPM.png");
152 | 146 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[151] = new Array("152","146","Project Management","11","SEITPM.png");
153 | 146 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[152] = new Array("153","146","Systems Engineering","11","SEITPM.png");
154 | 146 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[153] = new Array("154","146","Mission Assurance","11","SEITPM.png");
155 | 146 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[154] = new Array("155","146","Assembly, Integration and Testing","11","SEITPM.png");
156 | 146 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[155] = new Array("156","146","Support Equipment","11","SEITPM.png");
157 | 145 | 10 | Attitude Determination |  | Assembly | Widget.png |  | datatable[156] = new Array("157","145","Attitude Determination","10","Widget.png");
158 | 152 | 11 | Earth (Horizon) Sensors |  | Component | Widget.png |  | datatable[157] = new Array("158","152","Earth (Horizon) Sensors","11","Widget.png");
159 | 152 | 11 | Sun Sensors |  | Component | Widget.png |  | datatable[158] = new Array("159","152","Sun Sensors","11","Widget.png");
160 | 152 | 11 | Star Tracker/Sensors |  | Component | Widget.png |  | datatable[159] = new Array("160","152","Star Tracker/Sensors","11","Widget.png");
161 | 152 | 11 | Global Positioning System (GPS) Receiver |  | Component | Widget.png |  | datatable[160] = new Array("161","152","Global Positioning System (GPS) Receiver","11","Widget.png");
162 | 152 | 11 | Imagers |  | Component | Widget.png |  | datatable[161] = new Array("162","152","Imagers","11","Widget.png");
163 | 152 | 11 | Magnetometers |  | Component | Widget.png |  | datatable[162] = new Array("163","152","Magnetometers","11","Widget.png");
164 | 152 | 11 | Altimeters |  | Component | Widget.png |  | datatable[163] = new Array("164","152","Altimeters","11","Widget.png");
165 | 152 | 11 | Inertial Reference Unit (IRU)/Inertial Measurement Unit (IMU) |  | Component | Widget.png |  | datatable[164] = new Array("165","152","Inertial Reference Unit (IRU)/Inertial Measurement Unit (IMU)","11","Widget.png");
166 | 152 | 11 | Radar |  | Component | Widget.png |  | datatable[165] = new Array("166","152","Radar","11","Widget.png");
167 | 152 | 11 | Rate Gyros |  | Component | Widget.png |  | datatable[166] = new Array("167","152","Rate Gyros","11","Widget.png");
168 | 152 | 11 | Accelerometers |  | Component | Widget.png |  | datatable[167] = new Array("168","152","Accelerometers","11","Widget.png");
169 | 152 | 11 | Bearing and Power Transfer Assembly |  | Component | Widget.png |  | datatable[168] = new Array("169","152","Bearing and Power Transfer Assembly","11","Widget.png");
170 | 152 | 11 | Other Attitude Determination Devices (Specify) |  | Component | Widget.png |  | datatable[169] = new Array("170","152","Other Attitude Determination Devices (Specify)","11","Widget.png");
171 | 145 | 10 | Attitude Control |  | Assembly | Widget.png |  | datatable[170] = new Array("171","145","Attitude Control","10","Widget.png");
172 | 166 | 11 | Reaction Wheel |  | Component | Widget.png |  | datatable[171] = new Array("172","166","Reaction Wheel","11","Widget.png");
173 | 166 | 11 | Momentum Wheel |  | Component | Widget.png |  | datatable[172] = new Array("173","166","Momentum Wheel","11","Widget.png");
174 | 166 | 11 | Control Moment Gyro |  | Component | Widget.png |  | datatable[173] = new Array("174","166","Control Moment Gyro","11","Widget.png");
175 | 166 | 11 | Other Energy Storage Devices |  | Component | Widget.png |  | datatable[174] = new Array("175","166","Other Energy Storage Devices","11","Widget.png");
176 | 166 | 11 | Magnetic Control Devices |  | Component | Widget.png |  | datatable[175] = new Array("176","166","Magnetic Control Devices","11","Widget.png");
177 | 166 | 11 | Spin Control Devices |  | Component | Widget.png |  | datatable[176] = new Array("177","166","Spin Control Devices","11","Widget.png");
178 | 166 | 11 | Control Electronics |  | Component | Widget.png |  | datatable[177] = new Array("178","166","Control Electronics","11","Widget.png");
179 | 166 | 11 | Other Attitude Control Devices (Specify) |  | Component | Widget.png |  | datatable[178] = new Array("179","166","Other Attitude Control Devices (Specify)","11","Widget.png");
180 | 145 | 10 | ACS Other (Specify) |  | Assembly | Widget.png |  | datatable[179] = new Array("180","145","ACS Other (Specify)","10","Widget.png");
181 | 61 | 9 | Propulsion Subsystem |  | Subsystem | Widget.png |  | datatable[180] = new Array("181","61","Propulsion Subsystem","9","Widget.png");
182 | 176 | 10 | Propulsion Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[181] = new Array("182","176","Propulsion Subsystem SEITPM","10","SEITPM.png");
183 | 177 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[182] = new Array("183","177","Project Management","11","SEITPM.png");
184 | 177 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[183] = new Array("184","177","Systems Engineering","11","SEITPM.png");
185 | 177 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[184] = new Array("185","177","Mission Assurance","11","SEITPM.png");
186 | 177 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[185] = new Array("186","177","Assembly, Integration and Testing","11","SEITPM.png");
187 | 177 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[186] = new Array("187","177","Support Equipment","11","SEITPM.png");
188 | 176 | 10 | Tanks |  | Assembly | Widget.png |  | datatable[187] = new Array("188","176","Tanks","10","Widget.png");
189 | 183 | 11 | Oxidizer Tanks |  | Component | Widget.png |  | datatable[188] = new Array("189","183","Oxidizer Tanks","11","Widget.png");
190 | 183 | 11 | Fuel Tanks |  | Component | Widget.png |  | datatable[189] = new Array("190","183","Fuel Tanks","11","Widget.png");
191 | 183 | 11 | Propellant Tanks |  | Component | Widget.png |  | datatable[190] = new Array("191","183","Propellant Tanks","11","Widget.png");
192 | 183 | 11 | Pressurance Tanks |  | Component | Widget.png |  | datatable[191] = new Array("192","183","Pressurance Tanks","11","Widget.png");
193 | 183 | 11 | Plumbing |  | Component | Widget.png |  | datatable[192] = new Array("193","183","Plumbing","11","Widget.png");
194 | 183 | 11 | Other Tanks (Specify) |  | Component | Widget.png |  | datatable[193] = new Array("194","183","Other Tanks (Specify)","11","Widget.png");
195 | 176 | 10 | Maneuvering Thrusters |  | Assembly | Widget.png |  | datatable[194] = new Array("195","176","Maneuvering Thrusters","10","Widget.png");
196 | 190 | 11 | Bipropellant |  | Component | Widget.png |  | datatable[195] = new Array("196","190","Bipropellant","11","Widget.png");
197 | 190 | 11 | Monopropellant |  | Component | Widget.png |  | datatable[196] = new Array("197","190","Monopropellant","11","Widget.png");
198 | 190 | 11 | Solar Electric |  | Component | Widget.png |  | datatable[197] = new Array("198","190","Solar Electric","11","Widget.png");
199 | 190 | 11 | Ion |  | Component | Widget.png |  | datatable[198] = new Array("199","190","Ion","11","Widget.png");
200 | 190 | 11 | Cold Gas |  | Component | Widget.png |  | datatable[199] = new Array("200","190","Cold Gas","11","Widget.png");
201 | 190 | 11 | Other Maneuvering Thrusters (Specify) |  | Component | Widget.png |  | datatable[200] = new Array("201","190","Other Maneuvering Thrusters (Specify)","11","Widget.png");
202 | 176 | 10 | Translation Thrusters |  | Assembly | Widget.png |  | datatable[201] = new Array("202","176","Translation Thrusters","10","Widget.png");
203 | 197 | 11 | Bipropellant |  | Component | Widget.png |  | datatable[202] = new Array("203","197","Bipropellant","11","Widget.png");
204 | 197 | 11 | Monopropellant |  | Component | Widget.png |  | datatable[203] = new Array("204","197","Monopropellant","11","Widget.png");
205 | 197 | 11 | Solar Electric |  | Component | Widget.png |  | datatable[204] = new Array("205","197","Solar Electric","11","Widget.png");
206 | 197 | 11 | Ion |  | Component | Widget.png |  | datatable[205] = new Array("206","197","Ion","11","Widget.png");
207 | 197 | 11 | Cold Gas |  | Component | Widget.png |  | datatable[206] = new Array("207","197","Cold Gas","11","Widget.png");
208 | 197 | 11 | Other Translation Thrusters (Specify) |  | Component | Widget.png |  | datatable[207] = new Array("208","197","Other Translation Thrusters (Specify)","11","Widget.png");
209 | 176 | 10 | Propellant |  | Assembly | Widget.png |  | datatable[208] = new Array("209","176","Propellant","10","Widget.png");
210 | 204 | 11 | Solid Propellant |  | Component | Widget.png |  | datatable[209] = new Array("210","204","Solid Propellant","11","Widget.png");
211 | 204 | 11 | Liquid Propellant |  | Component | Widget.png |  | datatable[210] = new Array("211","204","Liquid Propellant","11","Widget.png");
212 | 204 | 11 | Prussurant Propellant |  | Component | Widget.png |  | datatable[211] = new Array("212","204","Prussurant Propellant","11","Widget.png");
213 | 204 | 11 | Other Propellant (Specify) |  | Component | Widget.png |  | datatable[212] = new Array("213","204","Other Propellant (Specify)","11","Widget.png");
214 | 176 | 11 | Solid Rocket Motors |  | Component | Widget.png |  | datatable[213] = new Array("214","176","Solid Rocket Motors","11","Widget.png");
215 | 176 | 11 | Power Electronics |  | Component | Widget.png |  | datatable[214] = new Array("215","176","Power Electronics","11","Widget.png");
216 | 176 | 11 | Propulsion Other (Specify) |  | Component | Widget.png |  | datatable[215] = new Array("216","176","Propulsion Other (Specify)","11","Widget.png");
217 | 61 | 9 | Telemetry, Tracking, and Command Subsystem (TT&C) |  | Subsystem | Widget.png |  | datatable[216] = new Array("217","61","Telemetry, Tracking, and Command Subsystem (TT&C)","9","Widget.png");
218 | 212 | 10 | TT&C Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[217] = new Array("218","212","TT&C Subsystem SEITPM","10","SEITPM.png");
219 | 213 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[218] = new Array("219","213","Project Management","11","SEITPM.png");
220 | 213 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[219] = new Array("220","213","Systems Engineering","11","SEITPM.png");
221 | 213 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[220] = new Array("221","213","Mission Assurance","11","SEITPM.png");
222 | 213 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[221] = new Array("222","213","Assembly, Integration and Testing","11","SEITPM.png");
223 | 213 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[222] = new Array("223","213","Support Equipment","11","SEITPM.png");
224 | 212 | 10 | Antennas |  | Assembly | Widget.png |  | datatable[223] = new Array("224","212","Antennas","10","Widget.png");
225 | 219 | 11 | Omnidirectional |  | Component | Widget.png |  | datatable[224] = new Array("225","219","Omnidirectional","11","Widget.png");
226 | 219 | 11 | Spiral |  | Component | Widget.png |  | datatable[225] = new Array("226","219","Spiral","11","Widget.png");
227 | 219 | 11 | Horn |  | Component | Widget.png |  | datatable[226] = new Array("227","219","Horn","11","Widget.png");
228 | 219 | 11 | Patch |  | Component | Widget.png |  | datatable[227] = new Array("228","219","Patch","11","Widget.png");
229 | 219 | 11 | Parabolic |  | Component | Widget.png |  | datatable[228] = new Array("229","219","Parabolic","11","Widget.png");
230 | 219 | 11 | Phased Array |  | Component | Widget.png |  | datatable[229] = new Array("230","219","Phased Array","11","Widget.png");
231 | 219 | 11 | Other Antennas (Specify) |  | Component | Widget.png |  | datatable[230] = new Array("231","219","Other Antennas (Specify)","11","Widget.png");
232 | 212 | 10 | Waveguides/Routers |  | Assembly | Widget.png |  | datatable[231] = new Array("232","212","Waveguides/Routers","10","Widget.png");
233 | 227 | 11 | Diplexers |  | Component | Widget.png |  | datatable[232] = new Array("233","227","Diplexers","11","Widget.png");
234 | 227 | 11 | Triplexers |  | Component | Widget.png |  | datatable[233] = new Array("234","227","Triplexers","11","Widget.png");
235 | 227 | 11 | Multiplexers |  | Component | Widget.png |  | datatable[234] = new Array("235","227","Multiplexers","11","Widget.png");
236 | 227 | 11 | Multicouplers |  | Component | Widget.png |  | datatable[235] = new Array("236","227","Multicouplers","11","Widget.png");
237 | 227 | 11 | Coaxial Switches |  | Component | Widget.png |  | datatable[236] = new Array("237","227","Coaxial Switches","11","Widget.png");
238 | 227 | 11 | RF Switches |  | Component | Widget.png |  | datatable[237] = new Array("238","227","RF Switches","11","Widget.png");
239 | 227 | 11 | Filters |  | Component | Widget.png |  | datatable[238] = new Array("239","227","Filters","11","Widget.png");
240 | 227 | 11 | Waveguides |  | Component | Widget.png |  | datatable[239] = new Array("240","227","Waveguides","11","Widget.png");
241 | 227 | 11 | Other Routers (Specify) |  | Component | Widget.png |  | datatable[240] = new Array("241","227","Other Routers (Specify)","11","Widget.png");
242 | 212 | 10 | Radio Frequency Equipment |  | Assembly | Widget.png |  | datatable[241] = new Array("242","212","Radio Frequency Equipment","10","Widget.png");
243 | 237 | 11 | Amplifiers |  | Component | Widget.png |  | datatable[242] = new Array("243","237","Amplifiers","11","Widget.png");
244 | 237 | 11 | Receivers |  | Component | Widget.png |  | datatable[243] = new Array("244","237","Receivers","11","Widget.png");
245 | 237 | 11 | Transmitters |  | Component | Widget.png |  | datatable[244] = new Array("245","237","Transmitters","11","Widget.png");
246 | 237 | 11 | Transceivers |  | Component | Widget.png |  | datatable[245] = new Array("246","237","Transceivers","11","Widget.png");
247 | 237 | 11 | Transponders |  | Component | Widget.png |  | datatable[246] = new Array("247","237","Transponders","11","Widget.png");
248 | 237 | 11 | Modulators |  | Component | Widget.png |  | datatable[247] = new Array("248","237","Modulators","11","Widget.png");
249 | 237 | 11 | Demodulators |  | Component | Widget.png |  | datatable[248] = new Array("249","237","Demodulators","11","Widget.png");
250 | 237 | 11 | Modems |  | Component | Widget.png |  | datatable[249] = new Array("250","237","Modems","11","Widget.png");
251 | 237 | 11 | Traveling Wave Tube Assemblies |  | Component | Widget.png |  | datatable[250] = new Array("251","237","Traveling Wave Tube Assemblies","11","Widget.png");
252 | 237 | 11 | Solid State Power Amplifiers |  | Component | Widget.png |  | datatable[251] = new Array("252","237","Solid State Power Amplifiers","11","Widget.png");
253 | 237 | 11 | Global Positioning System (GPS) Receiver |  | Component | Widget.png |  | datatable[252] = new Array("253","237","Global Positioning System (GPS) Receiver","11","Widget.png");
254 | 237 | 11 | Downconverters |  | Component | Widget.png |  | datatable[253] = new Array("254","237","Downconverters","11","Widget.png");
255 | 237 | 11 | Upconverters |  | Component | Widget.png |  | datatable[254] = new Array("255","237","Upconverters","11","Widget.png");
256 | 237 | 11 | Other RF Equipment (Specify) |  | Component | Widget.png |  | datatable[255] = new Array("256","237","Other RF Equipment (Specify)","11","Widget.png");
257 | 212 | 10 | Command and Data Handling (C&DH) |  | Assembly | Widget.png |  | datatable[256] = new Array("257","212","Command and Data Handling (C&DH)","10","Widget.png");
258 | 252 | 11 | Processors |  | Component | Widget.png |  | datatable[257] = new Array("258","252","Processors","11","Widget.png");
259 | 252 | 11 | Solid State Memory |  | Component | Widget.png |  | datatable[258] = new Array("259","252","Solid State Memory","11","Widget.png");
260 | 252 | 11 | Decoders |  | Component | Widget.png |  | datatable[259] = new Array("260","252","Decoders","11","Widget.png");
261 | 252 | 11 | Command Units |  | Component | Widget.png |  | datatable[260] = new Array("261","252","Command Units","11","Widget.png");
262 | 252 | 11 | Telemetry Units |  | Component | Widget.png |  | datatable[261] = new Array("262","252","Telemetry Units","11","Widget.png");
263 | 252 | 11 | Command Sequencers |  | Component | Widget.png |  | datatable[262] = new Array("263","252","Command Sequencers","11","Widget.png");
264 | 252 | 11 | Timing Units |  | Component | Widget.png |  | datatable[263] = new Array("264","252","Timing Units","11","Widget.png");
265 | 252 | 11 | Frequency Generators |  | Component | Widget.png |  | datatable[264] = new Array("265","252","Frequency Generators","11","Widget.png");
266 | 252 | 11 | Signal Conditioners |  | Component | Widget.png |  | datatable[265] = new Array("266","252","Signal Conditioners","11","Widget.png");
267 | 252 | 11 | Data Switches |  | Component | Widget.png |  | datatable[266] = new Array("267","252","Data Switches","11","Widget.png");
268 | 252 | 11 | Communication Security |  | Component | Widget.png |  | datatable[267] = new Array("268","252","Communication Security","11","Widget.png");
269 | 252 | 11 | Interface Units |  | Component | Widget.png |  | datatable[268] = new Array("269","252","Interface Units","11","Widget.png");
270 | 252 | 11 | Tape Recorders |  | Component | Widget.png |  | datatable[269] = new Array("270","252","Tape Recorders","11","Widget.png");
271 | 252 | 11 | Disk Recorders |  | Component | Widget.png |  | datatable[270] = new Array("271","252","Disk Recorders","11","Widget.png");
272 | 252 | 11 | Command Sensor or Situational Awareness Sensors |  | Component | Widget.png |  | datatable[271] = new Array("272","252","Command Sensor or Situational Awareness Sensors","11","Widget.png");
273 | 252 | 11 | Other C&DH (Specify) |  | Component | Widget.png |  | datatable[272] = new Array("273","252","Other C&DH (Specify)","11","Widget.png");
274 | 212 | 10 | TT&C Other (Specify) |  | Assembly | Widget.png |  | datatable[273] = new Array("274","212","TT&C Other (Specify)","10","Widget.png");
275 | 61 | 9 | Bus Flight Software |  | Subsystem | Widget.png |  | datatable[274] = new Array("275","61","Bus Flight Software","9","Widget.png");
276 | 275 | 10 | Bus FSW Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[275] = new Array("276","275","Bus FSW Subsystem SEITPM","10","SEITPM.png");
277 | 271 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[276] = new Array("277","271","Project Management","11","SEITPM.png");
278 | 271 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[277] = new Array("278","271","Systems Engineering","11","SEITPM.png");
279 | 271 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[278] = new Array("279","271","Mission Assurance","11","SEITPM.png");
280 | 271 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[279] = new Array("280","271","Assembly, Integration and Testing","11","SEITPM.png");
281 | 271 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[280] = new Array("281","271","Support Equipment","11","SEITPM.png");
282 | 270 | 11 | Thermal Control Software |  | Component | Widget.png |  | datatable[281] = new Array("282","270","Thermal Control Software","11","Widget.png");
283 | 270 | 11 | Electrical Power Software |  | Component | Widget.png |  | datatable[282] = new Array("283","270","Electrical Power Software","11","Widget.png");
284 | 270 | 11 | Attitude Control Software |  | Component | Widget.png |  | datatable[283] = new Array("284","270","Attitude Control Software","11","Widget.png");
285 | 270 | 11 | Telemetry, Tracking, and Command Software |  | Component | Widget.png |  | datatable[284] = new Array("285","270","Telemetry, Tracking, and Command Software","11","Widget.png");
286 | 270 | 11 | Other Flight Software (Specify) |  | Component | Widget.png |  | datatable[285] = new Array("286","270","Other Flight Software (Specify)","11","Widget.png");
287 | 59 | 8 | SEITPM and Support Equipment (If Applicable for Integration of Multiple Payloads) |  | System | SEITPM.png |  | datatable[286] = new Array("287","59","SEITPM and Support Equipment (If Applicable for Integration of Multiple Payloads)","8","SEITPM.png");
288 | 282 | 9 | Project Management |  | Subsystem | SEITPM.png |  | datatable[287] = new Array("288","282","Project Management","9","SEITPM.png");
289 | 282 | 9 | Systems Engineering |  | Subsystem | SEITPM.png |  | datatable[288] = new Array("289","282","Systems Engineering","9","SEITPM.png");
290 | 282 | 9 | Mission Assurance |  | Subsystem | SEITPM.png |  | datatable[289] = new Array("290","282","Mission Assurance","9","SEITPM.png");
291 | 282 | 9 | Assembly, Integration and Testing |  | Subsystem | SEITPM.png |  | datatable[290] = new Array("291","282","Assembly, Integration and Testing","9","SEITPM.png");
292 | 282 | 9 | Support Equipment |  | Subsystem | SEITPM.png |  | datatable[291] = new Array("292","282","Support Equipment","9","SEITPM.png");
293 | 59 | 8 | Payload 1 … n (Specify) |  | System | Widget.png |  | datatable[292] = new Array("293","59","Payload 1 … n (Specify)","8","Widget.png");
294 | 293 | 9 | Payload 1 SEITPM and Support Equipment |  | Subsystem | SEITPM.png |  | datatable[293] = new Array("294","293","Payload 1 SEITPM and Support Equipment","9","SEITPM.png");
295 | 289 | 10 | Project Management |  | Assembly | SEITPM.png |  | datatable[294] = new Array("295","289","Project Management","10","SEITPM.png");
296 | 289 | 10 | Systems Engineering |  | Assembly | SEITPM.png |  | datatable[295] = new Array("296","289","Systems Engineering","10","SEITPM.png");
297 | 289 | 10 | Mission Assurance |  | Assembly | SEITPM.png |  | datatable[296] = new Array("297","289","Mission Assurance","10","SEITPM.png");
298 | 289 | 10 | Assembly, Integration and Testing |  | Assembly | SEITPM.png |  | datatable[297] = new Array("298","289","Assembly, Integration and Testing","10","SEITPM.png");
299 | 289 | 10 | Support Equipment |  | Assembly | SEITPM.png |  | datatable[298] = new Array("299","289","Support Equipment","10","SEITPM.png");
300 | 288 | 9 | Payload 1 Structures and Mechanisms Subsystem |  | Subsystem | Widget.png |  | datatable[299] = new Array("300","288","Payload 1 Structures and Mechanisms Subsystem","9","Widget.png");
301 | 295 | 10 | Structures and Mechanims Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[300] = new Array("301","295","Structures and Mechanims Subsystem SEITPM","10","SEITPM.png");
302 | 296 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[301] = new Array("302","296","Project Management","11","SEITPM.png");
303 | 296 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[302] = new Array("303","296","Systems Engineering","11","SEITPM.png");
304 | 296 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[303] = new Array("304","296","Mission Assurance","11","SEITPM.png");
305 | 296 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[304] = new Array("305","296","Assembly, Integration and Testing","11","SEITPM.png");
306 | 296 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[305] = new Array("306","296","Support Equipment","11","SEITPM.png");
307 | 295 | 10 | Structures |  | Assembly | Widget.png |  | datatable[306] = new Array("307","295","Structures","10","Widget.png");
308 | 295 | 10 | Mechanisms and Pyrotechnics |  | Assembly | Widget.png |  | datatable[307] = new Array("308","295","Mechanisms and Pyrotechnics","10","Widget.png");
309 | 295 | 10 | Structures and Mechanisms Other (Specify) |  | Assembly | Widget.png |  | datatable[308] = new Array("309","295","Structures and Mechanisms Other (Specify)","10","Widget.png");
310 | 288 | 9 | Payload 1 Thermal Control Subsystem |  | Subsystem | Widget.png |  | datatable[309] = new Array("310","288","Payload 1 Thermal Control Subsystem","9","Widget.png");
311 | 310 | 10 | Thermal Control Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[310] = new Array("311","310","Thermal Control Subsystem SEITPM","10","SEITPM.png");
312 | 306 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[311] = new Array("312","306","Project Management","11","SEITPM.png");
313 | 306 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[312] = new Array("313","306","Systems Engineering","11","SEITPM.png");
314 | 306 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[313] = new Array("314","306","Mission Assurance","11","SEITPM.png");
315 | 306 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[314] = new Array("315","306","Assembly, Integration and Testing","11","SEITPM.png");
316 | 306 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[315] = new Array("316","306","Support Equipment","11","SEITPM.png");
317 | 316 | 10 | Cryogenic Devices |  | Assembly | Widget.png |  | datatable[316] = new Array("317","316","Cryogenic Devices","10","Widget.png");
318 | 317 | 10 | Liquid Loops |  | Assembly | Widget.png |  | datatable[317] = new Array("318","317","Liquid Loops","10","Widget.png");
319 | 318 | 10 | Electric Coolers |  | Assembly | Widget.png |  | datatable[318] = new Array("319","318","Electric Coolers","10","Widget.png");
320 | 319 | 10 | Electric heaters, Thermisters, and Thermostats |  | Assembly | Widget.png |  | datatable[319] = new Array("320","319","Electric heaters, Thermisters, and Thermostats","10","Widget.png");
321 | 320 | 10 | Passive Devices |  | Assembly | Widget.png |  | datatable[320] = new Array("321","320","Passive Devices","10","Widget.png");
322 | 321 | 10 | Sun Shields |  | Assembly | Widget.png |  | datatable[321] = new Array("322","321","Sun Shields","10","Widget.png");
323 | 322 | 10 | Thermal Control Other (Specify) |  | Assembly | Widget.png |  | datatable[322] = new Array("323","322","Thermal Control Other (Specify)","10","Widget.png");
324 | 288 | 9 | Payload 1 Electrical Power Subsystem |  | Subsystem | Widget.png |  | datatable[323] = new Array("324","288","Payload 1 Electrical Power Subsystem","9","Widget.png");
325 | 319 | 10 | Electrical Power Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[324] = new Array("325","319","Electrical Power Subsystem SEITPM","10","SEITPM.png");
326 | 320 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[325] = new Array("326","320","Project Management","11","SEITPM.png");
327 | 320 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[326] = new Array("327","320","Systems Engineering","11","SEITPM.png");
328 | 320 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[327] = new Array("328","320","Mission Assurance","11","SEITPM.png");
329 | 320 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[328] = new Array("329","320","Assembly, Integration and Testing","11","SEITPM.png");
330 | 320 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[329] = new Array("330","320","Support Equipment","11","SEITPM.png");
331 | 319 | 10 | Power Sources |  | Assembly | Widget.png |  | datatable[330] = new Array("331","319","Power Sources","10","Widget.png");
332 | 319 | 10 | Power Control, Switching, and Distribution Electronics |  | Assembly | Widget.png |  | datatable[331] = new Array("332","319","Power Control, Switching, and Distribution Electronics","10","Widget.png");
333 | 319 | 10 | Power Conditioning, Conversion, and Regulation |  | Assembly | Widget.png |  | datatable[332] = new Array("333","319","Power Conditioning, Conversion, and Regulation","10","Widget.png");
334 | 319 | 10 | Harnesses and Cables |  | Assembly | Widget.png |  | datatable[333] = new Array("334","319","Harnesses and Cables","10","Widget.png");
335 | 319 | 10 | Electrical Power Other (Specify) |  | Assembly | Widget.png |  | datatable[334] = new Array("335","319","Electrical Power Other (Specify)","10","Widget.png");
336 | 288 | 9 | Payload 1 Pointing, Command, and Control Interface |  | Subsystem | Widget.png |  | datatable[335] = new Array("336","288","Payload 1 Pointing, Command, and Control Interface","9","Widget.png");
337 | 336 | 10 | Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[336] = new Array("337","336","Subsystem SEITPM","10","SEITPM.png");
338 | 332 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[337] = new Array("338","332","Project Management","11","SEITPM.png");
339 | 332 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[338] = new Array("339","332","Systems Engineering","11","SEITPM.png");
340 | 332 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[339] = new Array("340","332","Mission Assurance","11","SEITPM.png");
341 | 332 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[340] = new Array("341","332","Assembly, Integration and Testing","11","SEITPM.png");
342 | 332 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[341] = new Array("342","332","Support Equipment","11","SEITPM.png");
343 | 331 | 10 | Computers and Processors |  | Assembly | Widget.png |  | datatable[342] = new Array("343","331","Computers and Processors","10","Widget.png");
344 | 331 | 10 | Command/Telemetric Units |  | Assembly | Widget.png |  | datatable[343] = new Array("344","331","Command/Telemetric Units","10","Widget.png");
345 | 331 | 10 | Control Electronics |  | Assembly | Widget.png |  | datatable[344] = new Array("345","331","Control Electronics","10","Widget.png");
346 | 331 | 10 | Pointing Sensors |  | Assembly | Widget.png |  | datatable[345] = new Array("346","331","Pointing Sensors","10","Widget.png");
347 | 331 | 10 | Payload Positioners |  | Assembly | Widget.png |  | datatable[346] = new Array("347","331","Payload Positioners","10","Widget.png");
348 | 331 | 10 | Security, Encryption, and Decryption Devices |  | Assembly | Widget.png |  | datatable[347] = new Array("348","331","Security, Encryption, and Decryption Devices","10","Widget.png");
349 | 331 | 10 | Data Storage, handling, and Interface |  | Assembly | Widget.png |  | datatable[348] = new Array("349","331","Data Storage, handling, and Interface","10","Widget.png");
350 | 331 | 10 | Multifunctional Digital Electronic Boxes |  | Assembly | Widget.png |  | datatable[349] = new Array("350","331","Multifunctional Digital Electronic Boxes","10","Widget.png");
351 | 331 | 10 | Pointing, Command, and Control Interface Other (Specify) |  | Assembly | Widget.png |  | datatable[350] = new Array("351","331","Pointing, Command, and Control Interface Other (Specify)","10","Widget.png");
352 | 288 | 9 | Payload Signal Electronics |  | Subsystem | Widget.png |  | datatable[351] = new Array("352","288","Payload Signal Electronics","9","Widget.png");
353 | 347 | 10 | Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[352] = new Array("353","347","Subsystem SEITPM","10","SEITPM.png");
354 | 348 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[353] = new Array("354","348","Project Management","11","SEITPM.png");
355 | 348 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[354] = new Array("355","348","Systems Engineering","11","SEITPM.png");
356 | 348 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[355] = new Array("356","348","Mission Assurance","11","SEITPM.png");
357 | 348 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[356] = new Array("357","348","Assembly, Integration and Testing","11","SEITPM.png");
358 | 348 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[357] = new Array("358","348","Support Equipment","11","SEITPM.png");
359 | 347 | 10 | Passive Signal Flow Control |  | Assembly | Widget.png |  | datatable[358] = new Array("359","347","Passive Signal Flow Control","10","Widget.png");
360 | 347 | 10 | Transmitter/Receiver/Transceiver/Transponder |  | Assembly | Widget.png |  | datatable[359] = new Array("360","347","Transmitter/Receiver/Transceiver/Transponder","10","Widget.png");
361 | 347 | 10 | Modulators/Demodulators/Modems |  | Assembly | Widget.png |  | datatable[360] = new Array("361","347","Modulators/Demodulators/Modems","10","Widget.png");
362 | 347 | 10 | Multiplexers/Demultiplexers |  | Assembly | Widget.png |  | datatable[361] = new Array("362","347","Multiplexers/Demultiplexers","10","Widget.png");
363 | 347 | 10 | Amplifiers |  | Assembly | Widget.png |  | datatable[362] = new Array("363","347","Amplifiers","10","Widget.png");
364 | 347 | 10 | Frequency Upconverters/Downconverters |  | Assembly | Widget.png |  | datatable[363] = new Array("364","347","Frequency Upconverters/Downconverters","10","Widget.png");
365 | 347 | 10 | Frequency and Timing |  | Assembly | Widget.png |  | datatable[364] = new Array("365","347","Frequency and Timing","10","Widget.png");
366 | 347 | 10 | Signal Conditioners |  | Assembly | Widget.png |  | datatable[365] = new Array("366","347","Signal Conditioners","10","Widget.png");
367 | 347 | 10 | Multifunctional Digital Electronic Boxes |  | Assembly | Widget.png |  | datatable[366] = new Array("367","347","Multifunctional Digital Electronic Boxes","10","Widget.png");
368 | 347 | 10 | Signal Electronics Other (Specify) |  | Assembly | Widget.png |  | datatable[367] = new Array("368","347","Signal Electronics Other (Specify)","10","Widget.png");
369 | 288 | 9 | Payload 1 Optical Assembly |  | Subsystem | Widget.png |  | datatable[368] = new Array("369","288","Payload 1 Optical Assembly","9","Widget.png");
370 | 364 | 10 | Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[369] = new Array("370","364","Subsystem SEITPM","10","SEITPM.png");
371 | 365 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[370] = new Array("371","365","Project Management","11","SEITPM.png");
372 | 365 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[371] = new Array("372","365","Systems Engineering","11","SEITPM.png");
373 | 365 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[372] = new Array("373","365","Mission Assurance","11","SEITPM.png");
374 | 365 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[373] = new Array("374","365","Assembly, Integration and Testing","11","SEITPM.png");
375 | 365 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[374] = new Array("375","365","Support Equipment","11","SEITPM.png");
376 | 364 | 10 | Structure/Outerbarrel/Cover |  | Assembly | Widget.png |  | datatable[375] = new Array("376","364","Structure/Outerbarrel/Cover","10","Widget.png");
377 | 364 | 10 | Mirrors/Optics |  | Assembly | Widget.png |  | datatable[376] = new Array("377","364","Mirrors/Optics","10","Widget.png");
378 | 364 | 10 | Aft Optics Assembly |  | Assembly | Widget.png |  | datatable[377] = new Array("378","364","Aft Optics Assembly","10","Widget.png");
379 | 364 | 10 | Alignment and Calibration |  | Assembly | Widget.png |  | datatable[378] = new Array("379","364","Alignment and Calibration","10","Widget.png");
380 | 364 | 10 | Thermal |  | Assembly | Widget.png |  | datatable[379] = new Array("380","364","Thermal","10","Widget.png");
374 | 364 | 10 | Control Electronics |  | Assembly | Widget.png |  | datatable[373] = new Array("374","364","Control Electronics","10","Widget.png");
375 | 364 | 10 | Optical Assembly Other |  | Assembly | Widget.png |  | datatable[374] = new Array("375","364","Optical Assembly Other","10","Widget.png");
376 | 288 | 9 | Payload 1 Sensor |  | Subsystem | Widget.png |  | datatable[375] = new Array("376","288","Payload 1 Sensor","9","Widget.png");
377 | 378 | 10 | Sensor SEITPM |  | Assembly | SEITPM.png |  | datatable[376] = new Array("377","378","Sensor SEITPM","10","SEITPM.png");
378 | 379 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[377] = new Array("378","379","Project Management","11","SEITPM.png");
379 | 379 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[378] = new Array("379","379","Systems Engineering","11","SEITPM.png");
380 | 379 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[379] = new Array("380","379","Mission Assurance","11","SEITPM.png");
381 | 379 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[380] = new Array("381","379","Assembly, Integration and Testing","11","SEITPM.png");
382 | 379 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[381] = new Array("382","379","Support Equipment","11","SEITPM.png");
383 | 378 | 10 | Payload Structure |  | Assembly | Widget.png |  | datatable[382] = new Array("383","378","Payload Structure","10","Widget.png");
384 | 378 | 10 | Focal Plan Array |  | Assembly | Widget.png |  | datatable[383] = new Array("384","378","Focal Plan Array","10","Widget.png");
385 | 378 | 10 | Sensor Positioners |  | Assembly | Widget.png |  | datatable[384] = new Array("385","378","Sensor Positioners","10","Widget.png");
386 | 378 | 10 | Sensor Electronics |  | Assembly | Widget.png |  | datatable[385] = new Array("386","378","Sensor Electronics","10","Widget.png");
387 | 378 | 10 | Alignment and Calibration |  | Assembly | Widget.png |  | datatable[386] = new Array("387","378","Alignment and Calibration","10","Widget.png");
388 | 378 | 10 | Magnetometer |  | Assembly | Widget.png |  | datatable[387] = new Array("388","378","Magnetometer","10","Widget.png");
389 | 378 | 10 | Spectrometer |  | Assembly | Widget.png |  | datatable[388] = new Array("389","378","Spectrometer","10","Widget.png");
390 | 378 | 10 | Radiometer |  | Assembly | Widget.png |  | datatable[389] = new Array("390","378","Radiometer","10","Widget.png");
391 | 378 | 10 | Camera |  | Assembly | Widget.png |  | datatable[390] = new Array("391","378","Camera","10","Widget.png");
392 | 378 | 10 | Sounder |  | Assembly | Widget.png |  | datatable[391] = new Array("392","378","Sounder","10","Widget.png");
393 | 378 | 10 | Flight Sensor Software |  | Assembly | Widget.png |  | datatable[392] = new Array("393","378","Flight Sensor Software","10","Widget.png");
394 | 378 | 10 | Other Sensor Types (Specify) |  | Assembly | Widget.png |  | datatable[393] = new Array("394","378","Other Sensor Types (Specify)","10","Widget.png");
395 | 378 | 10 | Mission Sensor Other (Specify) |  | Assembly | Widget.png |  | datatable[394] = new Array("395","378","Mission Sensor Other (Specify)","10","Widget.png");
396 | 288 | 9 | Payload Flight Software |  | Subsystem | Widget.png |  | datatable[395] = new Array("396","288","Payload Flight Software","9","Widget.png");
397 | 396 | 10 | Payload 1 FSW SEITPM |  | Assembly | SEITPM.png |  | datatable[396] = new Array("397","396","Payload 1 FSW SEITPM","10","SEITPM.png");
398 | 392 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[397] = new Array("398","392","Project Management","11","SEITPM.png");
399 | 392 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[398] = new Array("399","392","Systems Engineering","11","SEITPM.png");
400 | 392 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[399] = new Array("400","392","Mission Assurance","11","SEITPM.png");
401 | 392 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[400] = new Array("401","392","Assembly, Integration and Testing","11","SEITPM.png");
402 | 392 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[401] = new Array("402","392","Support Equipment","11","SEITPM.png");
403 | 396 | 10 | CSCI (Specify) |  | Assembly | Widget.png |  | datatable[402] = new Array("403","396","CSCI (Specify)","10","Widget.png");
404 | 288 | 9 | Payload Antenna 1 … n (Specify) |  | Subsystem | Widget.png |  | datatable[403] = new Array("404","288","Payload Antenna 1 … n (Specify)","9","Widget.png");
405 | 399 | 10 | Payload 1 Antenna SEITPM |  | Assembly | SEITPM.png |  | datatable[404] = new Array("405","399","Payload 1 Antenna SEITPM","10","SEITPM.png");
406 | 400 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[405] = new Array("406","400","Project Management","11","SEITPM.png");
407 | 400 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[406] = new Array("407","400","Systems Engineering","11","SEITPM.png");
408 | 400 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[407] = new Array("408","400","Mission Assurance","11","SEITPM.png");
409 | 400 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[408] = new Array("409","400","Assembly, Integration and Testing","11","SEITPM.png");
410 | 400 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[409] = new Array("410","400","Support Equipment","11","SEITPM.png");
411 | 399 | 10 | Structures and Mechanisms |  | Assembly | Widget.png |  | datatable[410] = new Array("411","399","Structures and Mechanisms","10","Widget.png");
412 | 399 | 10 | Antenna Positioners |  | Assembly | Widget.png |  | datatable[411] = new Array("412","399","Antenna Positioners","10","Widget.png");
413 | 399 | 10 | Reflector/Horn |  | Assembly | Widget.png |  | datatable[412] = new Array("413","399","Reflector/Horn","10","Widget.png");
414 | 399 | 10 | Feed |  | Assembly | Widget.png |  | datatable[413] = new Array("414","399","Feed","10","Widget.png");
415 | 399 | 10 | Waveguide/Coad/Cabling |  | Assembly | Widget.png |  | datatable[414] = new Array("415","399","Waveguide/Coad/Cabling","10","Widget.png");
416 | 399 | 10 | Transmit/Receive Modules |  | Assembly | Widget.png |  | datatable[415] = new Array("416","399","Transmit/Receive Modules","10","Widget.png");
417 | 399 | 10 | Antenna Other (Specify) |  | Assembly | Widget.png |  | datatable[416] = new Array("417","399","Antenna Other (Specify)","10","Widget.png");
418 | 288 | 9 | Payload Other (Specify) |  | Subsystem | Widget.png |  | datatable[417] = new Array("418","288","Payload Other (Specify)","9","Widget.png");
419 | 418 | 10 | Booster Adapter |  | Assembly | Widget.png |  | datatable[418] = new Array("419","418","Booster Adapter","10","Widget.png");
420 | 418 | 10 | Space Vehicle Storage |  | Assembly | Widget.png |  | datatable[419] = new Array("420","418","Space Vehicle Storage","10","Widget.png");
421 | 418 | 10 | Space Vehicle Other (Specify) |  | Assembly | Widget.png |  | datatable[420] = new Array("421","418","Space Vehicle Other (Specify)","10","Widget.png");
422 | 12 | 7 | Launch Systems Integration (LSI) |  |  | Rocket.png |  | datatable[421] = new Array("422","12","Launch Systems Integration (LSI)","7","Rocket.png");
423 | 12 | 7 | Launch Operations |  |  | Rocket.png |  | datatable[422] = new Array("423","12","Launch Operations","7","Rocket.png");
424 | 12 | 7 | Launch Operations Support |  |  | Rocket.png |  | datatable[423] = new Array("424","12","Launch Operations Support","7","Rocket.png");
425 | 12 | 7 | Launch Vehicle Services |  |  | Rocket.png |  | datatable[424] = new Array("425","12","Launch Vehicle Services","7","Rocket.png");
426 | 12 | 7 | Launch Insurance |  |  | Rocket.png |  | datatable[425] = new Array("426","12","Launch Insurance","7","Rocket.png");
427 | 13 | 7 | Ground Segment SEITPM |  | Assembly | SEITPM.png |  | datatable[426] = new Array("427","13","Ground Segment SEITPM","7","SEITPM.png");
428 | 422 | 8 | Project Management |  | Component | SEITPM.png |  | datatable[427] = new Array("428","422","Project Management","8","SEITPM.png");
429 | 422 | 8 | Systems Engineering |  | Component | SEITPM.png |  | datatable[428] = new Array("429","422","Systems Engineering","8","SEITPM.png");
430 | 422 | 8 | Mission Assurance |  | Component | SEITPM.png |  | datatable[429] = new Array("430","422","Mission Assurance","8","SEITPM.png");
431 | 422 | 8 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[430] = new Array("431","422","Assembly, Integration and Testing","8","SEITPM.png");
432 | 422 | 8 | Support Equipment |  | Component | SEITPM.png |  | datatable[431] = new Array("432","422","Support Equipment","8","SEITPM.png");
433 | 13 | 7 | Mission Control Centers |  |  | Facility.png |  | datatable[432] = new Array("433","13","Mission Control Centers","7","Facility.png");
434 | 13 | 7 | Science / Data Ops Centers |  |  | Facility.png |  | datatable[433] = new Array("434","13","Science / Data Ops Centers","7","Facility.png");
435 | 13 | 7 | Terminals and Data Networks – incl Antennas |  |  | Facility.png |  | datatable[434] = new Array("435","13","Terminals and Data Networks – incl Antennas ","7","Facility.png");
436 | 13 | 7 | Data Distribution & Archival |  |  | Facility.png |  | datatable[435] = new Array("436","13","Data Distribution & Archival ","7","Facility.png");
437 | 13 | 7 | Training Facilities |  |  | Facility.png |  | datatable[436] = new Array("437","13","Training Facilities ","7","Facility.png");
438 | 433 | 8 | CSA Mission Control |  |  | Facility.png |  | datatable[437] = new Array("438","433","CSA Mission Control","8","Facility.png");
439 | 438 | 9 | SatOps Mission Control Complex at JHCSC |  |  | Facility.png |  | datatable[438] = new Array("439","438","SatOps Mission Control Complex at JHCSC ","9","Facility.png");
440 | 438 | 9 | ISS Mission Operations Complex |  |  | Facility.png |  | datatable[439] = new Array("440","438","ISS Mission Operations Complex","9","Facility.png");
441 | 433 | 8 | NASA Mission Operations Complex |  |  | Facility.png |  | datatable[440] = new Array("441","433","NASA Mission Operations Complex","8","Facility.png");
442 | 435 | 10 | RMPSR |  |  | Facility.png |  | datatable[441] = new Array("442","435","RMPSR","10","Facility.png");
443 | 435 | 10 | OEC |  |  | Facility.png |  | datatable[442] = new Array("443","435","OEC","10","Facility.png");
444 | 435 | 10 | PTOC |  |  | Facility.png |  | datatable[443] = new Array("444","435","PTOC","10","Facility.png");
445 | 439 | 10 | SatOps Mission control SEITPM |  | Assembly | SEITPM.png |  | datatable[444] = new Array("445","439","SatOps Mission control SEITPM","10","SEITPM.png");
446 | 440 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[445] = new Array("446","440","Project Management","11","SEITPM.png");
447 | 440 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[446] = new Array("447","440","Systems Engineering","11","SEITPM.png");
448 | 440 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[447] = new Array("448","440","Mission Assurance","11","SEITPM.png");
449 | 440 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[448] = new Array("449","440","Assembly, Integration and Testing","11","SEITPM.png");
450 | 440 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[449] = new Array("450","440","Support Equipment","11","SEITPM.png");
451 | 434 | 10 | Hardware Components |  |  | Facility.png |  | datatable[450] = new Array("451","434","Hardware Components","10","Facility.png");
452 | 446 | 11 | Workstations |  |  | Facility.png |  | datatable[451] = new Array("452","446","Workstations","11","Facility.png");
453 | 446 | 11 | Servers |  |  | Facility.png |  | datatable[452] = new Array("453","446","Servers","11","Facility.png");
454 | 446 | 11 | Storage and Archive |  |  | Facility.png |  | datatable[453] = new Array("454","446","Storage and Archive","11","Facility.png");
455 | 446 | 11 | Network Equipment |  |  | Facility.png |  | datatable[454] = new Array("455","446","Network Equipment","11","Facility.png");
456 | 446 | 11 | Interface Equipment |  |  | Facility.png |  | datatable[455] = new Array("456","446","Interface Equipment","11","Facility.png");
457 | 446 | 11 | Security Encryption/Decryption |  |  | Facility.png |  | datatable[456] = new Array("457","446","Security Encryption/Decryption","11","Facility.png");
458 | 446 | 11 | Data Processing |  |  | Facility.png |  | datatable[457] = new Array("458","446","Data Processing","11","Facility.png");
459 | 446 | 11 | COTS Hardware Other (Specify) |  |  | Facility.png |  | datatable[458] = new Array("459","446","COTS Hardware Other (Specify)","11","Facility.png");
460 | 446 | 11 | Pre-Operations Maintenance (Specify) |  |  | Facility.png |  | datatable[459] = new Array("460","446","Pre-Operations Maintenance (Specify)","11","Facility.png");
461 | 446 | 11 | Environments |  |  | Facility.png |  | datatable[460] = new Array("461","446","Environments","11","Facility.png");
462 | 434 | 10 | SatOps GS Software |  |  | Facility.png |  | datatable[461] = new Array("462","434","SatOps GS Software","10","Facility.png");
463 | 462 | 11 | SW CSCI |  |  | Facility.png |  | datatable[462] = new Array("463","462","SW CSCI","11","Facility.png");
464 | 429 | 8 | NASA Science Operations Centers |  |  | Facility.png |  | datatable[463] = new Array("464","429","NASA Science Operations Centers","8","Facility.png");
465 | 429 | 8 | HPC (High Performance Computing) |  |  | Facility.png |  | datatable[464] = new Array("465","429","HPC (High Performance Computing)","8","Facility.png");
466 | 429 | 8 | Geospace Observatory |  |  | Facility.png |  | datatable[465] = new Array("466","429","Geospace Observatory","8","Facility.png");
467 | 429 | 8 | Other SODC (specify) |  |  | Facility.png |  | datatable[466] = new Array("467","429","Other SODC (specify)","8","Facility.png");
468 | 435 | 8 | CSA Terminals and Antennas |  |  | Facility.png |  | datatable[467] = new Array("468","435"," CSA Terminals and Antennas","8","Facility.png");
469 | 463 | 9 | CSA St-Hubert Antenna |  |  | Facility.png |  | datatable[468] = new Array("469","463","CSA St-Hubert Antenna","9","Facility.png");
470 | 463 | 9 | Ferme Yves Bachand Antenna |  |  | Facility.png |  | datatable[469] = new Array("470","463","Ferme Yves Bachand Antenna","9","Facility.png");
471 | 463 | 9 | Ferme Beldor Antenna |  |  | Facility.png |  | datatable[470] = new Array("471","463","Ferme Beldor Antenna","9","Facility.png");
472 | 463 | 9 | Transponder |  |  | Facility.png |  | datatable[471] = new Array("472","463","Transponder","9","Facility.png");
473 | 431 | 8 | Digital Earth Canada |  |  | Facility.png |  | datatable[472] = new Array("473","431","Digital Earth Canada","8","Facility.png");
474 | 431 | 8 | Federal Geospatial Platform (FGP) |  |  | Facility.png |  | datatable[473] = new Array("474","431","Federal Geospatial Platform (FGP)","8","Facility.png");
475 | 431 | 8 | EODMS |  |  | Facility.png |  | datatable[474] = new Array("475","431","EODMS","8","Facility.png");
476 | 431 | 8 | Canadian Astronomy Data Centre |  |  | Facility.png |  | datatable[475] = new Array("476","431","Canadian Astronomy Data Centre","8","Facility.png");
477 | 431 | 8 | NASA Data Distribution & Archival |  |  | Facility.png |  | datatable[476] = new Array("477","431","NASA Data Distribution & Archival","8","Facility.png");
478 | 437 | 8 | MMLC |  |  | Facility.png |  | datatable[477] = new Array("478","437","MMLC","8","Facility.png");
479 | 437 | 8 | MOTS |  |  | Facility.png |  | datatable[478] = new Array("479","437","MOTS","8","Facility.png");
480 | 14 | 7 | CSA Mission Operations |  |  | Ops.png |  | datatable[479] = new Array("480","14","CSA Mission Operations","7","Ops.png");
481 | 475 | 8 | CSA SatOps |  |  | Ops.png |  | datatable[480] = new Array("481","475","CSA SatOps","8","Ops.png");
482 | 475 | 8 | CSA ISS Ops |  |  | Ops.png |  | datatable[481] = new Array("482","475","CSA ISS Ops","8","Ops.png");
483 | 475 | 8 | CSA ISS Sustaining Engineering |  |  | Ops.png |  | datatable[482] = new Array("483","475","CSA ISS Sustaining Engineering","8","Ops.png");
484 | 14 | 7 | NASA Mission Operations |  |  | Ops.png |  | datatable[483] = new Array("484","14","NASA Mission Operations","7","Ops.png");
485 | 14 | 7 | Industry Partners (Specify) |  |  | Ops.png |  | datatable[484] = new Array("485","14","Industry Partners (Specify)","7","Ops.png");
486 | 15 | 7 | Mission Science Support |  |  | Science.png |  | datatable[485] = new Array("486","15","Mission Science Support","7","Science.png");
487 | 481 | 8 | Science Maturation Studies & User Requirements |  |  | Science.png |  | datatable[486] = new Array("487","481","Science Maturation Studies & User Requirements","8","Science.png");
488 | 481 | 8 | Science Support for Mission Development |  |  | Science.png |  | datatable[487] = new Array("488","481","Science Support for Mission Development","8","Science.png");
489 | 481 | 8 | Science Support for Commissioning, Including Cal/Val |  |  | Science.png |  | datatable[488] = new Array("489","481","Science Support for Commissioning, Including Cal/Val","8","Science.png");
490 | 481 | 8 | Science Support for Data Handling |  |  | Science.png |  | datatable[489] = new Array("490","481","Science Support for Data Handling","8","Science.png");
491 | 15 | 7 | Science Utilization & Application Development |  |  | Science.png |  | datatable[490] = new Array("491","15","Science Utilization & Application Development","7","Science.png");

## 5- OBS
` Table of Contents
5. OBS
Purpose: | The organizational breakdown structure identifies vendors, scientific teams, international partners, OGD clients and suppliers. It help specify their roles and hierarchy
Why we are asking for this:
This information helps us understand the procurement strategy.
It also helps map SAP claims against cost elements
Type | Sub-Type | Name | Description | Cost sharing Provisions, who pays? | How are WPD defined? | Oversight | Overhead | Mission Level SEITPM | Space Segment | Launch Segment | Ground Segment | Ops Segment | Science Segment
Government | Mission Owner / Project Office | Canadian Orbital Mission Directorate (COMD) | Fictional government organization representing the ORCA mission owner and program authority. | Government mission appropriation | Mission workplan / SOW | x | x | x
Industry | Prime Space Systems Integrator | Asterion Orbital Integration Ltd. | Fictional prime contractor supporting spacecraft-level integration, verification, and technical coordination. | CSA-style fiscal framework | Contract SOW / CWBS |  |  | x | x
Industry | Radar Subsystem Supplier | Northstar Orbital Technologies | Fictional supplier providing the ice-penetrating radar subsystem for ORCA. | Contract funding | Contract SOW / CWBS |  |  | x | x
Industry | Sampling Arm Supplier | Aetheris Space Robotics | Fictional supplier providing the sampling arm, end-effector, actuators, and sample-handling mechanisms. | Contract funding | Contract SOW / CWBS |  |  | x | x
Industry | Avionics Supplier | Polarion Avionics Corporation | Fictional supplier providing flight-computing, payload electronics, and avionics support. | Contract funding | Contract SOW / CWBS |  |  | x | x
Industry | Context Imaging Supplier | Borealis Vision Systems | Fictional supplier providing plume-context imaging cameras and optical calibration equipment. | Contract funding | Contract SOW / CWBS |  |  | x | x
Industry | Communications Supplier | Canterra Space Communications | Fictional supplier providing instrument command & data-handling electronics and data-interface hardware to the NEREID orbiter. | Contract funding | Contract SOW / CWBS |  |  | x |  | x | x
Industry | Thermal & Structures Supplier | Arcturon Space Structures | Fictional supplier supporting spacecraft structures, thermal hardware, and payload mounting interfaces. | Contract funding | Contract SOW / CWBS |  |  | x | x
Industry | Launch Coordination (Partner-Procured) | Peregrine Launch Services | Fictional launch-campaign coordination role; the launch vehicle and services are procured by the partner agency (NASA). | Launch services contract | Launch SOW / ICD |  |  |  |  | x
Industry | Ground Systems Supplier | Meridian Ground Technologies | Fictional supplier providing mission-control interfaces, telemetry processing, and ground-system equipment. | Contract funding | Ground SOW / ICD |  |  |  |  | x |  | x
Academia | Orbital Mechanics Team | Northern Institute of Space Engineering | Fictional university team supporting trajectory analysis, orbital mechanics, and plume-transit navigation research. | Research agreement | Research SOW / workplan | [6 empty] | x | x
Academia | Robotics Research Team | Laurentia University of Aerospace Technology | Fictional university team supporting sampling-arm dynamics, end-effector testing, and sample-acquisition simulations. | Research agreement | Research SOW / test plan |  |  | x |  |  | x | x
Academia | Space Environment Team | Boreal Technical University | Fictional university team supporting deep-space radiation-environment analysis and mission sustainability studies. | Research agreement | Research SOW / workplan | [6 empty] | x | x
Int'l partners | European Technical Partner | ESA | International partner (ESA) contributing to the host orbiter and providing plume-transit trajectory analysis support. | Partner contribution | MOU / PIP | x | x | x | x |  | x | x | x
Int'l partners | American Host-Platform Partner | NASA | International partner (NASA) providing and operating the NEREID orbiter host platform, including launch. | Partner contribution | MOU / PIP | x | x | x | x |  |  | x | x
Government | Space Environment OGD | Canadian Orbital Safety Directorate (COSD) | Fictional government organization supporting export-control compliance, planetary-protection oversight, and deep-space mission assurance. | Government service | MOU / service agreement | x |  | x |  |  | x | x
Government | Space Weather OGD | Canadian Space Environment Office (CSEO) | Fictional government organization providing space-weather and orbital-environment information. | Government service | MOU / service agreement | x |  | x |  |  | x | x
Government | Technical Assurance OGD | National Aerospace Research Directorate (NARD) | Fictional government organization providing independent engineering review, testing support, and technical assurance. | Government service | MOU / workplan | x |  | x | x |  | x | x

## 6 - Phase Name
` Table of Contents
7 - Phasing Nomenclature | [5 empty] | What do you call your phases?
Why we we asking:
1. To normalize the naming convention across all investments.
2. Math Models are based on Costing Sub-Phase.
3. We want to output results in your naming convention and scope.
| Based on IGMF rev E |  |  | Based on CSA-FIN-RPT-0072
Phasing according to |  |  | Phasing according to |  |  | Phasing according to
EPMO |  |  | Costing |  |  | PM
|  |  | PREP | PREP 1 | Prototyping Activities (before Gate 1)
Pre-Project | Option Analysis & Planning Phase | Pre-Phase 0 |  | PREP 2 | Prototyping Activities (during Phase 0/A)
|  | Phase 0 | Phase 0/A | Phase 0 | Concept & Feasibility | Phase 0
Project | Definition Phase | Detailed Project Requirements |  | Phase A | Mission Requirements | Phase A
|  | Preliminary Definition | Phase B/C | Phase B | Preliminary Design | Phase B
|  | Detailed Definition |  | Phase C | Detailed Design | Phase C
| Implementation Phase | Implementation | Phase D | MAIT | Manufacturing, Assembly, Integration and Test of Canadian Subsystems and Components | Phase D
|  |  |  | SAIT | Spacecraft Level Assembly, Test | Phase D
|  |  |  | LEOP | Lauch and early operations | Phase D
Post-Project | Post-Implementation Phase | Operations & Disposal | Phase E | Phase E | Nominal Operations (per design life) | Phase E
|  |  | Phase E (EXT) | Phase X | Extended operations (mission extension)
|  |  | Phase F | Phase F | Disposal (incl. post-mortem audit reports) | Phase F
|  |  | Phase G | Phase G | Post-Mortem science utilization

## 7 - Phase Durations
` Table of Contents
7b - Phasing Durations
Why we we asking:
1. Durations affect Govt Salaries calculations
2. Durations affect Parametric estimates for Space segment, ground segment, ops
3. Schedule Scenarios are inputs to sensitivity analysis
| Schedule Scenario ID | 1 | [9 empty] | Click to draw
| Scenario Name | ORCA Nominal / Baseline Schedule
| Scenario Description | Baseline ORCA schedule used for primary planning, salary calculations and parametric estimation.
| Rationale | Uses the ORCA Phase 0 through Phase X dates established in CADRe Part C (§7 Phase Durations).
| Source Doc | ORCA CADRe Part A — Project Phase Schedule
| Phase | Expected Start | Expected End | Total D | Total M | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062 | 2063 | 2064 | 2065 | 2066 | 2067 | 2068 | 2069 | 2070 | 2071 | 2072 | 2073 | 2074 | 2075 | 2076 | 2077 | 2078 | 2079 | 2080 | 2081 | 2082 | 2083 | 2084 | 2085 | 2086 | 2087 | 2088 | 2089 | 2090 | 2091 | 2092 | 2093
Phase 0 | 2026-01-01 | 2027-12-31 | 730 | 24 | 9.9 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 12 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase A | 2028-01-01 | 2029-12-31 | 731 | 24 | 10.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 12 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase B | 2030-01-01 | 2031-12-31 | 730 | 24 | 10.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 12 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase C | 2032-01-01 | 2033-12-31 | 731 | 24 | 13.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 12 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase D | 2034-01-01 | 2040-12-31 | 2557 | 84.1 | 26.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 12 | 12 | 12 | 12 | 12 | 12 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase E | 2041-01-01 | 2055-12-31 | 5478 | 180.1 | 12.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase X | 2056-01-01 | 2059-06-30 | 1277 | 42 | 41.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 12 | 12 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Schedule Scenario ID | 2 | [8 empty] | Click to draw
| Scenario Name | ORCA Optimistic Schedule
| Scenario Description | Accelerated schedule used for sensitivity analysis, assuming efficient design maturation, procurement and integration.
| Rationale | Phase durations are reduced ~15% relative to the nominal schedule while retaining the ORCA phase structure.
| Source Doc | ORCA CADRe Part A — Project Phase Schedule; sensitivity scenario
| Phase | Expected Start | Expected End | Total D | Total M | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062 | 2063 | 2064 | 2065 | 2066 | 2067 | 2068 | 2069 | 2070 | 2071 | 2072 | 2073 | 2074 | 2075 | 2076 | 2077 | 2078 | 2079 | 2080 | 2081 | 2082 | 2083 | 2084 | 2085 | 2086 | 2087 | 2088 | 2089 | 2090 | 2091 | 2092 | 2093
Phase 0 | 2026-01-01 | 2027-09-13 | 621 | 20.4 | 8.9 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 12 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase A | 2027-09-14 | 2029-05-26 | 621 | 20.4 | 9.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6 | 12 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase B | 2029-05-27 | 2031-02-06 | 621 | 20.4 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2 | 10.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase C | 2031-02-07 | 2032-10-19 | 621 | 20.4 | 11.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7 | 12 | 6.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase D | 2032-10-20 | 2038-10-02 | 2174 | 71.5 | 23.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.4 | 12 | 12 | 12 | 12 | 12 | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase E | 2038-10-03 | 2051-07-02 | 4656 | 153.1 | 11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.9 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase X | 2051-07-03 | 2054-06-22 | 1086 | 35.7 | 37.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 12 | 12 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Schedule Scenario ID | 3 | [8 empty] | Click to draw
| Scenario Name | ORCA Pessimistic Schedule
| Scenario Description | Delayed schedule used for sensitivity analysis, assuming additional design, test, procurement and integration delays.
| Rationale | Phase durations are increased ~20% relative to the nominal schedule to represent schedule-risk sensitivity.
| Source Doc | ORCA CADRe Part A — Project Phase Schedule; sensitivity scenario
| PM | Expected Start | Expected End | Total D | Total M | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062 | 2063 | 2064 | 2065 | 2066 | 2067 | 2068 | 2069 | 2070 | 2071 | 2072 | 2073 | 2074 | 2075 | 2076 | 2077 | 2078 | 2079 | 2080 | 2081 | 2082 | 2083 | 2084 | 2085 | 2086 | 2087 | 2088 | 2089 | 2090 | 2091 | 2092 | 2093
Phase 0 | 2026-01-01 | 2028-05-25 | 876 | 28.8 | 11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 12 | 12 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase A | 2028-05-26 | 2030-10-19 | 877 | 28.8 | 11.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2 | 12 | 6.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase B | 2030-10-20 | 2033-03-13 | 876 | 28.8 | 12.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.4 | 12 | 11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase C | 2033-03-14 | 2035-08-07 | 877 | 28.8 | 15.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 12 | 12 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase D | 2035-08-08 | 2043-12-31 | 3068 | 100.9 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase E | 2044-01-01 | 2061-12-29 | 6573 | 216.1 | 14.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phase X | 2061-12-30 | 2066-03-10 | 1532 | 50.4 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 12 | 12 | 12 | 11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 8 - Milestones
` Table of Contents
8 - Milestone Register
Why we we asking:
to double check your schedule
based in IGMF rev F
| ID | Phase | Milestone | Description | Specify Date | Actual or Planned? | Type | Milestone Description | Used in Analysis?
| M1 | Prep 1 | Primus | First Gate 0 of first dollar spent |  |  | Governance |  | Used to calculate sunk costs
| M2 |  | Contract Award | First R&D contract, grant or contribution signed |  |  | Contract |  | Used to calculate sunk costs
| M3 |  | Final Review | Last R&D contract, grant or contribution before Mission Gate 0 is Completed |  |  | Contract |  | Used to calculate sunk costs
| M4 | Prep 2 | Secundus | Gate 0 which will lead to an R&D contract during Phase 0/A. Could be same as Mission Gate 0 but not always |  |  | Governance |  | not used in costing, used only for graphics on Gantt Chart
| M5 |  | Contract Award | First R&D contract signed after Mission Gate 1 |  |  | Contract |  | Used for parametric analysis
| M6 |  | Final Review | Last R&D contract ends after Mission Gate 1 |  |  | Contract |  | Used for parametric analysis
| M7 | Phase 0 | Phase 0 Start | RAM Effort to prepare Gate 0 or Gate 1 Begins |  |  | RAM |  | Used to compute CSA Salaries
| M8 |  | Gate 0 | Policy cover (possibly though a Strategic Retreat) |  |  | Governance |  | not used in costing, used only for graphics on Gantt Chart
| M9 |  | KDP-0 / Gate 1 | Key Decision Point in CSA Governance Framework |  |  | Governance |  | not used in costing, used only for graphics on Gantt Chart
| M10 |  | R1 | Identification of Investment Options |  |  | Governance |  | not used in costing, used only for graphics on Gantt Chart
| M11 |  | Contract Award | Phase 0 Contract Award |  |  | Contract |  | Used for parametric analysis
| M12 |  | PL-MCR | Mission Concept Review |  |  | Major Milestone | MCR is conducted early in the mission planning process to assess the feasibility and viability of the mission concept. | Major Milestones used to compute durations in paramateric and analogy
| M13 |  | PL-MRR | Mission Requirements Review |  |  | Major Milestone | MRR is conducted to establish and validate the specific requirements that the mission must meet to achieve its objectives. | Major Milestones used to compute durations in paramateric and analogy
| M14 |  | MDR | Mission Definition Review |  |  | Interim Milestone | MDR is conducted to refine the mission concept and requirements further and to establish a more detailed plan for mission implementation. | Minor Milestones are sometimes used to infer Major Milestones when those have not been specified
| M15 |  | FR | Contractor Phase 0 Final Review |  |  | Contract |  | Used for parametric analysis
| M16 |  | R2 | Investment Option Recommendation |  |  | Governance |  | not used in costing, used only for graphics on Gantt Chart
| M17 |  | Phase 0 End | RAM Effort for Phase 0 Ends |  |  | RAM |  | Used to compute CSA Salaries
| M18 | Phase A | Phase A Start | RAM Effort to prepare Gate 2 Begins |  |  | RAM |  | Used to compute CSA Salaries
| M19 |  | KDP-A / Gate 2 | Key Decision Point in CSA Governance Framework |  |  | Governance |  | not used in costing, used only for graphics on Gantt Chart
| M20 |  | Contract Award | Phase A Contract Award |  |  | Contract |  | Used for parametric analysis
| M21 |  | PL-SRR | 2029-12-17 |  | Planned | Major Milestone | SRR is conducted to establish and validate the high-level requirements that the system must meet to achieve its mission objectives. | Minor Milestones are sometimes used to infer Major Milestones when those have not been specified
| M24 |  | M-SRR | 2029-12-31 |  | Planned | External Dependency |  | Major Milestones used to compute durations in paramateric and analogy
|  |  | M-SDR | 2029-09-01 |  | Planned | External Dependency
| M27 |  | Final Review | Contractor Phase A Final Review |  |  | Contract |  | Used for parametric analysis
| M28 |  | Phase A End | RAM Effort for Phase A Ends |  |  | RAM |  | Used to compute CSA Salaries
| M29 | Phase B | Phase B Start | RAM Effort to prepare Phase B Begins |  |  | RAM |  | Used to compute CSA Salaries
| M30 |  | KDP-B / Review R3 | Key Decision Point in CSA Governance Framework |  |  | Governance |  | not used in costing, used only for graphics on Gantt Chart
| M31 |  | Contract Award | Phase B Contract Award |  |  | Contract |  | Used for parametric analysis
| M32 |  | PL-PDR | 2031-11-16 |  | Planned | Major Milestone | The main purpose of PDR is to assess and evaluate the preliminary design of the spacecraft or system. | Minor Milestones are sometimes used to infer Major Milestones when those have not been specified
| M35 |  | M-PDR | 2031-12-31 |  | Planned | External Dependency |  | Major Milestones used to compute durations in paramateric and analogy
| M36 |  | Final Review | Contractor Phase B Final Review |  |  | Contract |  | Used for parametric analysis
| M37 |  | Phase B End | RAM Effort for Phase B Ends |  |  | RAM |  | Used to compute CSA Salaries
| M38 | Phase C | Phase C Start | RAM Effort to prepare Phase B Begins |  |  | RAM |  | Used to compute CSA Salaries
| M39 |  | KDP-C / Review R4 | Key Decision Point in CSA Governance Framework |  |  | Governance |  | not used in costing, used only for graphics on Gantt Chart
| M40 |  | Contract Award | Phase C Contract Award or PDR |  |  | Contract |  | Used for parametric analysis
| M41 |  | PL-CDR | 2033-10-31 |  | Planned | Major Milestone | CDR serves as a critical milestone to evaluate and approve the detailed design of the spacecraft or system. | Minor Milestones are sometimes used to infer Major Milestones when those have not been specified
| M44 |  | M-CDR | 2033-12-31 |  | Planned | External Dependency |  | Major Milestones used to compute durations in paramateric and analogy
| M45 |  | Final Review | Contractor Phase C Final Review |  |  | Contract |  | Used for parametric analysis
| M46 |  | Phase C End | RAM Effort for Phase C Ends |  |  | RAM |  | Used to compute CSA Salaries
| M47 | MAIT | Phase D Start | RAM Effort to prepare Phase D Begins |  |  | RAM |  | Used to compute CSA Salaries
| M48 |  | KDP-D / Gate 3 / Review R5 | Key Decision Point in CSA Governance Framework |  |  | Governance |  | not used in costing, used only for graphics on Gantt Chart
| M49 |  | Contract Award | Phase D Contract Award or CDR |  |  | Contract |  | Used for parametric analysis
| M50 |  | Subsystem Integration | Sub-System Integration Review (SIR) |  |  | External Dependency | SIR evaluates the integration of all subsystems and components to ensure they function together as a cohesive system. | Major Milestones used to compute durations in paramateric and analogy
| M51 |  | PL-PSR | 2040-07-04 |  | Planned | Major Milestone |  | Minor Milestones are sometimes used to infer Major Milestones when those have not been specified
| M56 | SAIT | Arrive date at Prime | ORCA space segment arrives at Prime (EDA) for spacecraft integration |  |  | Interim Milestone |  | Minor Milestones are sometimes used to infer Major Milestones when those have not been specified
| M57 |  | SIR | System Integration Review (SIR) |  |  | Interim Milestone |  | Minor Milestones are sometimes used to infer Major Milestones when those have not been specified
| M59 |  | PSR to LV | Pre-Ship Review (PSR) (to LV) |  |  | External Dependency |  | Major Milestones used to compute durations in paramateric and analogy
| M60 | LEOP | Arrive date to LV | Space Segment arrives at Launch provider for integration with LV |  |  | Interim Milestone |  | Minor Milestones are sometimes used to infer Major Milestones when those have not been specified
| M61 |  | FRR | Flight Readiness Review (FRR) |  |  | Interim Milestone | FRR evaluates the readiness of the spacecraft, launch vehicle, and ground support systems for launch. | Minor Milestones are sometimes used to infer Major Milestones when those have not been specified
| M62 |  | ORR | Ops Readiness Review (ORR) |  |  | Interim Milestone | ORR evaluates the readiness of mission operations personnel, procedures, and facilities for mission execution. | Minor Milestones are sometimes used to infer Major Milestones when those have not been specified
| M63 |  | Launch | 2040-12-31 |  | Planned | External Dependency | Launch marks the initiation of the space mission, with the primary goal of placing the spacecraft into its designated orbit or trajectory. | Major Milestones used to compute durations in paramateric and analogy
| M64 |  | Orbit-Insertion Start | Start of orbit-raising / transit to the Enceladus science orbit |  |  | Interim Milestone |  | Minor Milestones are sometimes used to infer Major Milestones when those have not been specified
| M65 |  | Orbit Insertion | Orbital insertion into the Enceladus science orbit |  |  | Interim Milestone | Orbit insertion maneuvers adjust the NEREID orbiter's trajectory to place ORCA into its intended science orbit around Enceladus. | Minor Milestones are sometimes used to infer Major Milestones when those have not been specified
| M69 |  | CR | Commissioning Review (CR) |  |  | Interim Milestone | CR evaluates the initial performance of the spacecraft and its systems after deployment or landing. | Minor Milestones are sometimes used to infer Major Milestones when those have not been specified
| M71 | Phase E | Phase E Start | RAM Effort to prepare Phase E Begins |  |  | RAM |  | Used to compute CSA Salaries
| M72 |  | KDP-E / Gate 4 | Key Decision Point in CSA Governance Framework |  |  | Governance |  | not used in costing, used only for graphics on Gantt Chart
| M74 |  | Phase E Start | Start of nominal Ops or CR |  |  | Major Milestone |  | Major Milestones used to compute durations in paramateric and analogy
| M75 |  | End of Nominal Ops | End of Nominal Ops |  |  | Major Milestone |  | Major Milestones used to compute durations in paramateric and analogy
| M76 |  | End of operations | End of Extended Operations |  |  | Major Milestone |  | Major Milestones used to compute durations in paramateric and analogy
| M77 |  | Final Review | Contractor Final Review after extended Ops |  |  | Contract |  | Used for parametric analysis
| M78 | Phase X | RAM Effort to prepare Phase X (Extended Operations & Disposal) Begins | RAM Effort to prepare Phase X (Disposal & Disposal) Begins |  |  | RAM |  | Used to compute CSA Salaries
| M79 |  | KDP-X / Gate 5 | Key Decision Point in CSA Governance Framework (IGMF Gate 5) |  |  | Governance |  | not used in costing, used only for graphics on Gantt Chart
| M80 |  | DR | Decommissioning & Disposal Review (disposal of NEREID Orbiter) |  |  | Interim Milestone | The Decommissioning Review marks the transition from operations to the disposal phase of mission assets | Minor Milestones are sometimes used to infer Major Milestones when those have not been specified
| M81 |  | Final Review | Contractor Final Review for Phase X |  |  | Contract |  | Used for parametric analysis

## 9 - Sched Dependencies
` Table of Contents
10 - Schedule Constraints and dependencies
Why we are asking
To conduct a JCL analysis
Critical Path Analysis
| 2025-01-01 |  | ORCA concept & science maturation studies initiated
| 2026-01-01 |  | Phase 0 Start — Gate 0 / KDP-0 (first dollar spent)
| 2027-12-31 | M-MCR | Mission Concept Review (MCR)
| 2028-01-01 |  | Phase A Start — KDP-A / Gate 2
| 2029-07-01 |  | ORCA Concept Rebaseline
| 2029-12-31 | M-SRR | System Requirements Review (SRR)
| 2030-01-01 |  | Phase B Start — KDP-B / Review R3
| 2031-03-14 |  | Orbiter / ORCA Instrument Suite Interface Complete
| 2031-12-31 | M-PDR | Preliminary Design Review (PDR) — Phase B End
| 2032-01-01 |  | Phase C Start — KDP-C / Review R4
| 2033-03-14 |  | Instrument Suite Environmental Qualification Complete
| 2033-12-31 | M-CDR | Critical Design Review (CDR) — Phase C End
| 2034-01-01 |  | Phase D Start — KDP-D / Gate 3 / R5 (MAIT/SAIT)
| 2036-03-31 | M-MRR | Manufacturing Readiness Review (MRR)
| 2040-07-04 | L-6mo | Pre-Ship Review of Systems to Prime (PSR) — flight units ship to Prime (EDA)
| 2040-08-31 |  | Integrated Instrument Suite Functional Test Complete
| 2040-09-30 | M-SIR | System Integration Review (SIR)
| 2040-10-02 | M-AR | Acceptance Review (AR) — Flight Acceptance
| 2040-11-01 |  | Flight Software and Autonomy Verification Complete
| 2040-11-16 | L-45d | Pre-Ship Review — Spacecraft to Launch Site
| 2040-12-31 | L | Launch (NASA / host orbiter NEREID) — Phase E Start
| 2041-01-01 | L+1d | Orbital insertion into Enceladus science orbit; commissioning start
| 2041-01-14 | M-CR | Commissioning Review (CR) — start of nominal Ops
| 2055-12-31 |  | End of Nominal Ops (Phase E End); Phase X disposal through 2059-06-30
Assumption | dependencies | CSA instrument flight units must be delivered to the Prime (EDA) ahead of Mission CDR to support host-orbiter integration
Assumption | Phase 0 | CSA conducted a Phase 0 previously; it is assumed to have been sufficient to meet the exit criteria of a real Phase 0
Assumption | Phase A | The CSA Phase A must be completed before Mission SRR
Assumption | Phase B | The Orbiter/Instrument Suite Interface Control Document must be complete before PDR
Assumption | Phase C | Instrument suite environmental qualification must be complete ~9 months before CDR
Assumption | Phase MAIT | The Manufacturing Readiness Review (MRR) precedes the CSA flight-hardware build by ~4 years, reflecting long-lead radiation-hardened parts
Assumption | SAIT | The CSA flight-hardware ship date (Pre-Ship Review) is ~6 months before Launch
Assumption | SAIT | Mission CDR is planned for Dec 2033 in the ORCA Scenario 1 baseline
Assumption | SAIT | The assumed duration between Mission CDR and Launch is ~84 months (Scenario 1), driven by the host orbiter's (NASA-led) integration and launch-window schedule
Assumption | LEOP | ORCA Scenario 1 assumes a launch date of Dec 31 2040 on the NEREID orbiter (NASA-led launch)
Assumption | LEOP | Interplanetary cruise to Enceladus (via Jupiter gravity assist) is carried on the NEREID orbiter; no CSA-specific cruise operations are costed
Assumption | LEOP | Post-orbit-insertion checkout of the ORCA instrument suite is assumed ~30 days (20 days optimistic, 50 days pessimistic)
Assumption | LEOP | Commissioning: approximately 1-3 months in the Enceladus science orbit before nominal ops
Assumption | Phase E | Nominal operations life is ~15 years (Scenario 1 Phase E ≈ 180 months), reflecting the long-duration Enceladus science campaign
Assumption | Phase X | Phase X covers extended operations plus the disposal campaign; Scenario 1 duration ≈ 42 months (~3.5 years)
Assumption | Phase X | Disposal is achieved per the partner agency's planetary-protection plan for the NEREID orbiter
Assumption | Phase X | End of Phase X (mission close-out / final disposal) occurs on 2059-06-30 in Scenario 1
Brainstorming Questions about Schedule GR&A
Schedule constraints and Dependencies
Assumption 01 | Mission Milestones are external dependencies for the CSA activities. Per the ORCA Scenario 1 baseline, these dates are:
|  | Mission Milestone | Planned Date |  | CSA Dependency | CSA Planned Date
Assumption 02 |  | Mission SRR | 2029-12-31 | ---> | CSA PL SRR (M-SRR-14d) | 2029-12-17
Assumption 03 |  | Mission SDR | 2029-09-01 | ---> | CSA PDR preparation start | 2029-09-01
Assumption 04 |  | Mission PDR | 2031-12-31 | ---> | CSA PL-PDR (M-PDR-30d) | 2031-12-01
Assumption 05 |  | Mission CDR | 2033-12-31 | ---> | CSA PL-CDR (M-CDR-61d) | 2033-10-31
Assumption 06 |  | Launch | 2040-12-31 | ---> | CSA PSR (L-88d) | 2040-10-04
Schedule Assumptions for Long Lead Items
Assumption 07 |  | Long-lead items (sampling-arm actuators, radiation-hardened electronics, long-lead detector components) — when is the list ready? When are they procured and paid?
Schedule Assumptions for Integrated Testing (Assembly at Mission Level) - SAIT
Is the Prime (EDA) expecting delivery at a given date?
Assuming the Prime (EDA) will handle spacecraft assembly, integration and test during SAIT. The Prime need date for flight units is driven by the Mission CDR schedule. The CSA must ship the flight units ahead of Mission CDR (see Assumption 05).
How long is SAIT expected to last?
In the ORCA Scenario 1 baseline, MAIT/SAIT / Phase D spans ~84 months (Jan 2034 - Dec 2040), reflecting long-lead radiation-hardened parts and the host-orbiter integration schedule.
Any extended long term storage planned? No
Schedule Assumptions for Launch & Early Ops
ORCA's interplanetary cruise to Enceladus (via Jupiter gravity assist) is carried on the NEREID orbiter. Post-orbit-insertion checkout of the ORCA instrument suite is assumed ~30 days (20-50 day range).
how much time for commissioning? 1 -3 months
Any launch window constraints? The launch window is set by planetary alignment for the Jupiter gravity assist and is a hard constraint (host orbiter, NASA-led).
Schedule Assumptions for Ground Segment
Ground-segment dependency: instrument telemetry and commands are relayed via the NEREID orbiter's (NASA-led) Deep Space Network downlink; CSA operates its own Mission Operations Centre and processes instrument science data.
Schedule Assumptions for Ops Segment
Nominal Phase E operations ≈ 180 months (~15 years) in Scenario 1, reflecting the long-duration Enceladus science campaign
Assumed total operating life including extended ops & disposal (Phase E + Phase X) ≈ 18.5 years (Scenario 1)
Schedule Assumptions for Science Segment
Did Science activities (science maturation studies) occur before Phase 0? Yes
Did Science team participate in Phase 0/A to refine requirements? Yes
Did Science team participate in Phase BCD to assist in mission design? Yes
Will science team condut any calibration, validation activities (ex. Sub-orbital capaign) before end of commissioning?
Will science team condut any calibration, validation activities (ex. Sub-orbital capaign) after commissioning?
How long after the space segment ends will the collected data still be considered useful (duration of Phase X)?
Formulas:
CSA Planned Date = [Planned Date]-14
CSA Planned Date = [Planned Date]

## GR&A (hidden)
Costing CSA Ground Rules & Assumptions template
Last review |  |  | 2025-03-31
ID | Catégorie | Category | Category | Sub-category | Items | GR or A | Title | Description | Phase | CBS # linked to GR&A | Impact on Project | Impact on costing, methodology, models, tools & analysis | Excepted source | Do not delete - Mireille | Source/Link | Other rational | Waiver deviation
1 | Hypothèses Programmatiques | Strategy Naratives | Objectifs politiques et stratégiques | Alignement sur la stratégie de l’ASC | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Strategy
2 | Hypothèses Programmatiques | Strategy Naratives | Objectifs politiques et stratégiques | Contraintes gouvernementales ou directives de haut niveau | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Strategy
3 | Hypothèses Programmatiques |  | Objectifs politiques et stratégiques | Type de mission : Flagship, LargeSat, SmallSat, NanoSat, Hosted Payload, Data stream partnership, data stream purchase | [8 empty] | CADRE Part A | CADRE Part A ou contants
4 | Hypothèses Programmatiques |  | Objectifs politiques et stratégiques | Disciplines et secteur : SatCom, Astronomie, exploration spatiale,... | [8 empty] | CADRE Part A | CADRE Part A
5 | Hypothèses Programmatiques |  | Objectifs politiques et stratégiques | Dépendances avec d'autres projets/missions | [8 empty] | CADRE Part A | CADRE Part A
6 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Soumission au Conseil du Tésor (TBSub) - But de l'exercice de costing : Budget Ask, Reprofiling,… Définir le nombre de TBSub + échéancier associé aux TBSub | [8 empty] | CADRE Part C onglet Stratégie contractuelle | Strategy
7 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Enveloppe de la masse salariale | [8 empty] | CADRE Part C onglet RAM | Strategy
8 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Enveloppe des frais de gestion et plan de voyages | [8 empty] | CADRE Part C onglet Overhead Costs | Strategy
9 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Méthodologie d'établissement des coûts | [8 empty] | Plan de l’exercice d’établissement des coûts | Costing Plan
10 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Note de réflexion supplémentaire | [9 empty] | Costing Plan
11 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Au moins 2 façon différentes pour chaque incluant RAM | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
12 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analyse de sensibilité | [8 empty] | À compléter par Finance | Costing Plan
13 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Sufficiency Report or Independent Cost Estimate or Independent Cost Review | [8 empty] | À compléter par Finance | Costing Plan
14 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analogie (nearest neighboors), lesquels. | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
15 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analyse paramétrique (True planning, PCEC, NCIM, SEER, Compact). CER Calibration Plan. | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
16 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Soumission de l'industrie et jugement d'expert | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
17 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analyse Monte Carlo (crystal ball) | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
18 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Bottom up, qui le fait et comment | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
19 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Learning curves | [8 empty] | RASCI = qui fait quoi. bottom up = Plan de l’exercice d’établissement des coûts | Costing Plan
20 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Inducteurs de coûts princicaux | [8 empty] | CADRE Part C onglet CER & Tools | Costing Plan
21 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Normalisation ( Stochométrie) - si applicable | [8 empty] | le choix de l'outil dicte CADRE part B qui collecte info pour l'analyse paramétrique | Costing Plan
22 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Tracabilité - accès aux sources - répertoires normalisés -liens | [8 empty] | CADRE Part C onglet CER & Tools | Costing Plan
23 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Stratégie de financement | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Strategy
24 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Limitation des coûts : Par exemple, les sources de financement instables, les contraintes de personnel ou un budget à ne pas dépasser devraient être documentés. | [8 empty] | CADRE Part C onglet Stratégie contractuelle | Strategy
25 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Enveloppe Services internes - O&M et RAM | [8 empty] | CADRE Part C onglet Services internes | Strategy
26 | Hypothèses Programmatiques | OBS | Partenariats (OGD, internationaux, industriels) | Rôles et responsabilités des principaux partenaires (agences spatiales, industriels, universités et autres ministères) | [8 empty] | CADRE Part C onglet OBS | OBS
27 | Hypothèses Programmatiques | OBS | Partenariats (OGD, internationaux, industriels) | Modalités de partage des coûts et des risques | [8 empty] | CADRE Part C onglet OBS - Cost Sharing provisions | OBS
28 | Hypothèses Programmatiques | Strategy Naratives | Partenariats (OGD, internationaux, industriels) | Si applicable, dépenses éligibles de l'OTAN | [8 empty] | À définir ici | Strategy
29 | Hypothèses Programmatiques | 8. Economic Constants and short answers | Gouvernance et autorités | Ordre de grandeur général du projet (petit, moyen, grand, flagship) | [8 empty] | CERCES scale | Constants
30 | Hypothèses Programmatiques | Costign Plan | Gouvernance et autorités | Nature of the costing perimeter (degree of difficulty of costing exercise) | [8 empty] | Plan de l’exercice d’établissement des coûts | Costing Plan
31 | Hypothèses Programmatiques | 8. Economic Constants and short answers | Gouvernance et autorités | Palier/ Tier | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Constants
32 | Hypothèses Programmatiques | 8. Economic Constants and short answers | Gouvernance et autorités | PCRA | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Constants
33 | Hypothèses Programmatiques | Milestone Register | Gouvernance et autorités | Point de décision | [8 empty] | CADRE Part C - onglet Phasing Model | Milestone Register
34 | Hypothèses Programmatiques | Costign Plan | Gouvernance et autorités | Costing Exercise Schedule and associated milestones - Costing Plan, Internal WebReport Dashboard and power BI dashboard for CLAD | [8 empty] | Plan de l’exercice d’établissement des coûts | Costing Plan
35 | Hypothèses Financières | 8. Inflation Model | Indices économiques et inflation | Taux d’inflation annuel, indice utilisé (IPC, indice sectoriel), taux de déflation | [8 empty] | Inflation Model dans son propre document - Oracle db ID | Inflation Model
36 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | Taux EBP 27% | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
37 | Hypothèses Financières | 8. Inflation Model | Indices économiques et inflation | Modèle d'inflation appliqué | [8 empty] | Inflation Model dans son propre document - Oracle db ID | Inflation Model
38 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | Année de base / Base year | [9 empty] | Constants
39 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | SSC 4% | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
40 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | PSPC 13% | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
41 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | Taux du Fairness Monitor | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
42 | Hypothèses Financières | 8. Economic Constants and short answers | Taux de change | Monnaies concernées et valeur de référence (CAD, USD, EUR, etc.) | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
43 | Hypothèses Financières | 8. Economic Constants and short answers | Taux de change | Seuil de variation accepté avant révision budgétaire | [8 empty] | Defined in constnats, used in risk analysis. risk reserve - Risk register | Constants
44 | Hypothèses Financières | 8. Economic Constants and short answers | Contingence et marges de sécurité | Pourcentage de contingence sur le coût total du projet (p. ex. 10 à 20 %) | [8 empty] | Defined in constnats, used in risk analysis. risk register onglet. Unknown-Unknown Risk margin | Constants
45 | Hypothèses Financières | Strategy Naratives | Contingence et marges de sécurité | Barème d’évaluation des risques majeurs pour justifier la marge appliquée (modèle d’analyse de risques) | [8 empty] | À définir ici | Strategy | Je ne comprends pas la question
46 | Hypothèses Financières | Procurement Plan | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Sunk Costs Report (STDP, EOADP, Cap Demo, Stedia FAST, ESA Program, Cubesats, space hub, Pre-Phase 0 etc) | [8 empty] | CADRe part C - Expenditure plan | Procurement Plan
47 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stratégie contractuel Phase 0/A - 1 / 2 contrats | [8 empty] | CADRe Part C - Procurement strategy | Strategy
48 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Note de réflexion supplémentaire | [9 empty] | Strategy
49 | Hypothèses Financières | Procurement Plan | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Nombre de contrats et valeur approximative prévus par phase | [8 empty] | CADRe Part C - Procurement Plan (list) | Procurement Plan
50 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Contrats en parallèle avec des concepts différents et un down select | [8 empty] | CADRe Part C - Procurement strategy | Strategy
51 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Agile ou waterfall | [8 empty] | CADRe Part C - Procurement strategy | Strategy
52 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | STDP ou CapDemo en même temps que la phase 0 ou A | [8 empty] | PREP 2 | Strategy
53 | Hypothèses Financières | OBS | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Les fournisseurs attendus et leur capacite de production | [8 empty] | OBS | OBS
54 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Type de SOW - SOW directif versus une architecture de mission proposée par le fournisseur | [8 empty] | CADRe Part C - Procurement strategy | Strategy
55 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Freedom of Design of Vendor | [8 empty] | CADRE Part C onglet OBS Maturité orgnisationelle du fourniseur | Strategy
56 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Types de contrat – source unique ou compétitif (Contrat dirigé en Phase E ops aura une incidence sur le design du ground segment) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
57 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Types de contrat – cout remboursable ou prix ferme | [8 empty] | CADRe Part C - Procurement strategy | Strategy
| Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Type de contrat: gonogo, options, milestones in April for CAFÉ | [9 empty] | Strategy | Split next line into 2
58 | Hypothèses Financières | 12 - Dispose, Divest, Descope, Delay | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Gestion du scope change et des risques dans chaque situation : cout remboursable (TA, options, gouvernance) ; prix ferme (descope, go no go, qualité du SOW a décrire le scope) | [8 empty] | Descope est dans DDD | DDDD
59 | Hypothèses Financières |  | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | G&C (cassiope ou radarsat 2) nous appartient pas | [8 empty] | Business model (CADRe part A) et le procurement strategy le repete | CADRE Part A
60 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | incitatif commercial (ex. modele de commercialization comme WFS) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
61 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Pour chaque phase et sous-systeme majeur - CSA led, industry led, academia led (ex. En Phase E, CSA va mener les operations) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
62 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Competitif - ouvert a l'international | [8 empty] | CADRe Part C - Procurement strategy | Strategy
63 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Competitif - ouvert au Canada | [8 empty] | CADRe Part C - Procurement strategy | Strategy
64 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Fausse competition | [8 empty] | CADRe Part C - Procurement strategy | Strategy
65 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | monopole | [8 empty] | CADRe Part C - Procurement strategy | Strategy
66 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Dependences : Le fournisseur X doit etre le meme fournisseur que le fournisseur Y (Ex. Data processing handled by same supplier) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
67 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Long lead Item - flux de trésorie en capital vs contrat vs échéancier | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Strategy
68 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Contenu Canadien | [8 empty] | CADRe Part C - Procurement strategy | Strategy
69 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Chaque contrat couvre quel partie du travail, liste d'inclusions et exclusions. List of inclusions and exclusions | [8 empty] | CBS Dictionary | Strategy
70 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | GFE and GFS (ex. DFL) | [8 empty] | CBS Dictionary | Strategy
71 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Frais de transport et responsabilité | [8 empty] | CBS Dictionary | Strategy
72 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Frais d'assurance et limitation de responsabilité | [8 empty] | CBS Dictionary | Strategy
73 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Qualité du SOW | [8 empty] | RISK posture | Strategy
74 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stabilité des exigences. Par exemple, des exigences très instables, un nombre standard de demandes de modification technique, des exigences stables avec peu ou pas de changements attendus, etc. | [8 empty] | CADRe Part C - Procurement strategy | Strategy
75 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Résultats du RFI | [8 empty] | Procurement strategy | Strategy
76 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stratégie contractuelle Phase BCD - Concurrentiel, source unique (voir note de réflexion du point 2.4.1) | [8 empty] | Procurement strategy | Strategy
77 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stratégie contractuelle Phase EF - Concurrentiel, source unique (voir note de réflexion du point 2.4.1) | [8 empty] | Procurement strategy | Strategy
78 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Capacité du vendeur dans le marché actuel, surcharge contractuel, effectif disponible | [8 empty] | OBS Maturité orgnisationelle du fourniseur | Strategy
79 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Taux standard pour les ingénieurs, techniciens, gestionnaires, etc. | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
80 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Taux spécifiques pour les consultants ou experts externes | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
81 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Barème pour les appels d’offres et la sous-traitance (plafonds, politiques internes) | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
82 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Taux de frais et de profit appliqué au contrat | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
83 | Hypothèses Financières | Risk Register | Plan de gestion des risques financiers | Existence d’une réserve pour risques identifiés (p. ex. volatilité du marché, retards de paiement) | [8 empty] | Registre de risque | Risk Register
84 | Hypothèses Financières | 12 - Dispose, Divest, Descope, Delay | Plan de gestion des risques financiers | Descope Plan and other strategies to deal with funding shortfalls, | [8 empty] | À définir ici et lié au CADRE Part C - onglet DDDD | DDDD
85 | Hypothèses Financières | Procurement Plan | Plan de gestion des risques financiers | Source of funding for each CBS element and Risk to A-Base | [8 empty] | Expenditure plan | Procurement Plan
86 | Hypothèses Financières | 8. Economic Constants and short answers | Taxes | Pays, province et taux de taxes applicables | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
87 | Hypothèses Techniques (Space & Ground Segment) | TRRA | Technologie et niveau de maturité (TRL) | TRL initial prévu pour les composants clés | [8 empty] | CADRE Part C onglet TRL | TRL
88 | Hypothèses Techniques (Space & Ground Segment) | TRRA | Technologie et niveau de maturité (TRL) | Objectifs de TRL à atteindre pour chaque phase du projet | [8 empty] | CADRE Part C onglet TRL | TRL
89 | Hypothèses Techniques (Space & Ground Segment) | 4a. CBS and CBS Dictionary | Sous-systèmes et architecture globale | Liste et description des principaux sous-systèmes (structure, propulsion, contrôle d’attitude, communication, etc.) | [8 empty] | CBS | CBS
90 | Hypothèses Techniques (Space & Ground Segment) | TRRA | Sous-systèmes et architecture globale | Interfaces critiques (par ex. protocole de communication, alignement mécanique) | [8 empty] | TRL assessment tab - worry list | TRL
91 | Hypothèses Techniques (Space & Ground Segment) | Costign Plan | Sous-systèmes et architecture globale | This ground rule should state, at a high level, what is within scope of the estimate. For example, an estimate may cover the space segment, ground segment, and government oversight during phases B, C and D. Further clarification should be given if required, such as refurbishment of the ground segment rather than complete rebuild. | [8 empty] | Perimeter of costing exercise. Further Claraifications in CBs dictionary | Costing Plan
92 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | Stratégie de validation (modèles d’ingénierie, prototypes, simulations) | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
93 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | Méthodes d’essais en environnement (thermique, vibration, vide, etc.) | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
94 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | This assumption should state the expected build approach for the mission. For example, the bus/platform and payloads could be built in series or parallel. | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
95 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | This assumption should state the cost improvement curve, as a percentile, for any items to be acquired with more than a single unit. If appropriate, items should be marked as Xth unit within a lot, such as the 8th unit, to allow for cost improvement curve theory to be reflected. | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
96 | Hypothèses Techniques (Space & Ground Segment) | Engineering Parameters in CADRe part B | Contraintes techniques spécifiques | Estimation de masse et de volume du système | [8 empty] | CADRE part B | CADRE part B
97 | Hypothèses Techniques (Space & Ground Segment) | Engineering Parameters in CADRe part B | Contraintes techniques spécifiques | Consommation électrique maximale | [8 empty] | CADRE part B | CADRE part B
98 | Hypothèses Techniques (Space & Ground Segment) | Engineering Parameters in CADRe part B | Contraintes techniques spécifiques | Besoins minimaux pour assurer la fiabilité | [8 empty] | CADRE part B | CADRE part B
99 | Hypothèses Qualité, Fiabilité et Sécurité | Strategy Naratives | Normes et standards de qualité | ECSS-Q-ST-20, ISO 9001, etc. | [8 empty] | À définir ici | Strategy
100 | Hypothèses Qualité, Fiabilité et Sécurité | Strategy Naratives | Normes et standards de qualité | Méthodes d’assurance qualité (revues, audits internes et externes) | [8 empty] | À définir ici | Strategy
101 | Hypothèses Qualité, Fiabilité et Sécurité | 8. Economic Constants and short answers | Safety and mission assurance | Classe de Mission | [8 empty] | À définir ici | Constants
102 | Hypothèses Qualité, Fiabilité et Sécurité | Strategy Naratives | Safety and mission assurance | La mesure de la surveillance et de la rigueur appliquées par la CSA | [8 empty] | À définir ici | Strategy
103 | Hypothèses Opérationnelles | RAM | Ressources humaines et expertise | Équipe de base (ETP internes) et besoins en personnel spécialisé externe | [8 empty] | CADRE Part C onglet RAM | RAM
104 | Hypothèses Opérationnelles | Strategy Naratives | Ressources humaines et expertise | Disponibilité du personnel et plan de montée en compétence | [8 empty] | À définir ici | Strategy
105 | Hypothèses Opérationnelles | Milestone Register | Calendrier, jalons et ressources temporelles | Dates clés (ex. PDR – Preliminary Design Review, CDR – Critical Design Review, FRR – Flight Readiness Review) / Project Milestone Register (short report, detailed report) | [8 empty] | milestone Register | Milestone Register
106 | Hypothèses Opérationnelles |  | Calendrier, jalons et ressources temporelles | Diagram of Phase Overlaps and Gaps | [8 empty] | we draw it form phasing | GANTT Charts
107 | Hypothèses Opérationnelles | Schedule Constraints and Dependencies | Calendrier, jalons et ressources temporelles | Marges pour délais | [8 empty] | Phasing Model, phases | Schedule Constraints
108 | Hypothèses Opérationnelles | 12 - Dispose, Divest, Descope, Delay | Calendrier, jalons et ressources temporelles | Gestion des retards : conditions de replanification, procédures d’escalade | [8 empty] | À définir ici et lié au CADRE Part C - onglet DDDD | DDDD
109 | Hypothèses Opérationnelles | Phasing Schedules | Calendrier, jalons et ressources temporelles | Modèle de phase utilisé pour analyse de sensibilité (Phasing Model) | [8 empty] | Phasing model (for risk analysis) | Phasing Schedules
110 | Hypothèses Opérationnelles | Phasing Schedules | Calendrier, jalons et ressources temporelles | Échéancier de l'industrie | [8 empty] | Phasing model (for risk analysis) | Phasing Schedules
111 | Hypothèses Opérationnelles | Phasing Schedules | Calendrier, jalons et ressources temporelles | Schedule Scenarios for sensitivity analysis : Adjust Durations - optimistic, pessimistic and expected | [8 empty] | Phasing model (for risk analysis) | Phasing Schedules
112 | Hypothèses Opérationnelles | Strategy Naratives | Planification des infrastructures et installations | Is DFL being used as GFE | [8 empty] | DFL being used? Strategy | Strategy
112 | Hypothèses Opérationnelles | 4a. CBS and CBS Dictionary | Planification des infrastructures et installations | Lieux de développement, sites d’intégration et de test (chambres à vide, bancs de test) | [8 empty] | CBS Dictionary - Ground Segment - Test facilities | CBS Dictionary
113 | Hypothèses Opérationnelles | Schedule Constraints and Dependencies | Planification des infrastructures et installations | Disponibilité des installations (ex. créneaux de test partagés avec d’autres projets) | [8 empty] | schedule risk = risk register -> pessimistic schedule model | Schedule Constraints
114 | Hypothèses Opérationnelles | Schedule Constraints and Dependencies | Gestion de la logistique et de la chaîne d’approvisionnement | Délai de livraison des composants critiques (satellites, propulseurs, éléments électroniques) | [8 empty] | schedule risk = risk register -> pessimistic schedule model | Schedule Constraints
115 | Hypothèses Opérationnelles | Strategy Naratives | Gestion de la logistique et de la chaîne d’approvisionnement | Plans de contingence en cas de rupture d’approvisionnement | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | Strategy
116 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | Description des opérations prévues : phases de lancement, mise à l’orbite, opérations nominales, etc. | [8 empty] | Cadre part A | CADRE Part A
117 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | Mode de supervision et contrôle (centres de contrôle, horaires, équipes) | [8 empty] | À définir ici | Cadre Part A
118 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | Mission Operation Center | [8 empty] | À définir ici | Cadre Part A
119 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | GoC Science Operation Centers (SOCs) | [8 empty] | À définir ici | Cadre Part A
120 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | External Science Operation Centers (ESOCs) | [8 empty] | À définir ici | Cadre Part A
121 | Hypothèses sur la science | Schedule Constraints and Dependencies | Science et applications | Échéancier lié au volet de science du projet | [9 empty] | Schedule Constraints
122 | Hypothèses sur la science | Strategy Naratives | Science et applications | Expected cost of science utilization related to the mission. | [9 empty] | Strategy
123 | Hypothèses sur la science | Strategy Naratives | Portée de la mission sur le milieu public et académique | Coût en lien avec la portée de la mission | [8 empty] | À définir ici | Strategy
124 | Hypothèses Lancement |  | Véhicule de lancement | Sélection du lanceur (ex. Falcon 9, Ariane, etc.) ou fenêtre de lancement partagée | [8 empty] | Cadre part A | CADRE Part A
125 | Hypothèses Lancement |  | Véhicule de lancement | Capacités du lanceur (masse, volume, orbite cible) | [8 empty] | Cadre part A un petit peu et le reste dans le LV database CM list | CADRE Part A
126 | Hypothèses Lancement | Schedule Constraints and Dependencies | Calendrier de lancement | Fenêtres de lancement disponibles (contraintes de météo, alignement orbital, etc.) | [8 empty] | schedule risk = risk register -> pessimistic schedule model | Schedule assumptions and constraints for JCL Analysis
127 | Hypothèses Lancement | 12 - Dispose, Divest, Descope, Delay | Calendrier de lancement | Contingences pour reports éventuels | [8 empty] | schedule risk = risk register -> pessimistic schedule model | DDDD
128 | Hypothèses Lancement | OBS | Contrat et services associés | Responsabilités du fournisseur de lancement (intégration, tests, qualification) | [8 empty] | OBS (roles et responsiblity) - CSa qui paye ou MDa qui paye | OBS
129 | Hypothèses Lancement | 4a. CBS and CBS Dictionary | Contrat et services associés | Assurances (couverture du satellite, du lanceur, etc.) | [8 empty] | CBS Dictionary - if insurance | CBS Dictionary
130 | Hypothèses Opérations en orbite |  | Mode opératoire | Gestion du satellite ou rover (téléopération vs. autonomie) | [9 empty] | Cadre Part A
131 | Hypothèses Opérations en orbite | Engineering Parameters in CADRe part B | Mode opératoire | Durée et fréquence des communications | [8 empty] | CADRE Part B | CADRE part B
132 | Hypothèses Opérations en orbite |  | Maintenance, réparations et évolutions | Possibilité ou non de mise à jour logicielle en vol (OTA updates) | [8 empty] | CADRE part A - Bus FSW section | CADRE Part A
133 | Hypothèses Opérations en orbite |  | Maintenance, réparations et évolutions | Stratégiques de réparation ou d’assistance robotique | [8 empty] | CADRE part A - does it have any robotic repair interfaces | CADRE Part A
134 | Hypothèses Opérations en orbite | 12 - Dispose, Divest, Descope, Delay | Fin de mission et désorbitation | Scénario de désorbitation contrôlée ou passivation (réservoirs, batteries) | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
135 | Hypothèses Opérations en orbite | 12 - Dispose, Divest, Descope, Delay | Fin de mission et désorbitation | Dépôt sur orbite-cimetière pour le matériel en fin de vie (si admissible) | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
136 | Hypothèses Opérations en orbite | Strategy Naratives | Flux de documentation et reporting | Fréquence des rapports d’avancement (hebdomadaires, mensuels) | [8 empty] | À définir ici | Strategy
137 | Hypothèses Opérations en orbite | Strategy Naratives | Classifications et diffusion | Niveau de confidentialité (projet public, secret défense, propriété intellectuelle) | [8 empty] | À définir ici | Strategy
138 | Hypothèses Opérations en orbite | Strategy Naratives | Classifications et diffusion | Politiques de publication ou de diffusion des résultats | [8 empty] | À définir ici et/ou Business Case | Strategy
139 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Réglementations gouvernementales | Exigences fédérales (agences spatiales, ministères, etc.) | [8 empty] | À définir ici et/ou Business Case | Strategy
140 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Réglementations gouvernementales | Normes internationales (ECSS, ISO, NASA, CSA, etc.) | [8 empty] | À définir ici et/ou Business Case | Strategy
141 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Réglementations gouvernementales | Règles et régulations afférentes | [8 empty] | À définir ici et/ou Business Case | Strategy
142 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Contrôle à l’exportation (ex. ITAR, EAR) | Identification des composants ou technologies soumis à licences | [8 empty] | À définir ici | Strategy
143 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Contrôle à l’exportation (ex. ITAR, EAR) | Implications sur la gestion des fournisseurs et des partenaires étrangers | [8 empty] | À définir ici | Strategy
144 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Sécurité et sûreté | Mesures de cybersécurité (protection des données, des communications, etc.) | [8 empty] | À définir ici | Strategy
145 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Sécurité et sûreté | Exigences de sûreté pour le personnel et les installations (accès restreints, habilitations) | [8 empty] | À définir ici | Strategy
146 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Droit spatial et aspects juridiques | Propriété et exploitation des données spatiales | [8 empty] | À définir ici | Strategy
147 | Hypothèses Légales, Réglementaires et Sécuritaires | 12 - Dispose, Divest, Descope, Delay | Droit spatial et aspects juridiques | Protocole en cas de débris spatiaux, en fin de vie du satellite | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
148 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Propriété intellectuelle | Propriété intellectuel en lien avec le projet - enjeux | [8 empty] | À définir ici et/ou Business Case | Strategy
149 | Hypothèses Environnementales | 12 - Dispose, Divest, Descope, Delay | Gestion des débris spatiaux | Respect des lignes directrices d’atténuation des débris (liaisons, désorbitation en fin de vie) | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
150 | Hypothèses Environnementales | 12 - Dispose, Divest, Descope, Delay | Gestion des débris spatiaux | Méthodes envisagées pour minimiser la pollution orbitale | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
151 | Hypothèses Environnementales | Green space | Impacts environnementaux terrestres | Contrôle des émissions lors du lancement (polluants, bruit, etc.) | [8 empty] | CADRE Part C onglet Green Space | Green Space
152 | Hypothèses Environnementales | Strategy Naratives | Impacts environnementaux terrestres | Politique de recyclage ou de réutilisation des composants | [8 empty] | CADRE Part C onglet Green Space | Strategy
153 | Hypothèses sur le risques | Risk Register | Risques | Risque du Projet Phase A à D | [8 empty] | Registre de risque | Risk Register
154 | Hypothèses sur le risques | Risk Register | Risques | Risque du Projet Phase E | [8 empty] | Registre de risque | Risk Register
155 | Hypothèses sur le risques | Risk Register | Risques | Risque du Projet Phase F | [8 empty] | Registre de risque | Risk Register
156 | Hypothèses sur le risques | Risk Register | Risques | Risque Science | [8 empty] | Registre de risque | Risk Register
157 | Hypothèses sur le risques | Risk Register | Risques | Risque Salaire | [8 empty] | Registre de risque | Risk Register
158 | Hypothèses sur le risques | Risk Register | Risques | Schedule Risk Assessment file (ms project) as input to the Joint Cost and Schedule Confidence Analysis Report | [8 empty] | Registre de risque | Risk Register
159 | Hypothèses sur le risques | Risk Register | Risques | Registre de risque | [8 empty] | Registre de risque | Risk Register
160 | Hypothèses sur le risques | Strategy Naratives | Risques | Aspect critique de la mission et impact si la mission n'est pas respectée | [8 empty] | minimum mission success criteria - DRM - CADRE part C Taxon | Strategy
161 | Hypothèse sur les mesures de performance par la valeur acquise | CADRe part D - EVM | Mesures de performance par la valeur acquise (EVM = Earn Value Management) | Seuil orange et rouge pour EVM justifiant une réduction de la portée, une replanification | [9 empty] | pas dans ce fichier, pas avant PDR
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343

## 10 - Strategies
` Table of Contents
11 - Strategy Narratives
Why we we asking:
Part of GRA
This page is full of essays, tell us what you have in mind
Section 1 - Strategic Direction
|  | ID | Category | Question | Expected Response | Classification | Status | Response / Narrative | Basis / Source | Owner | Confidence | Cost / Schedule / Risk Impact
|  | STR-01 | Policy alignment | What policy outcome or strategic objective is the mission intended to advance? | Narrative with references | Ground rule | Drafted | ORCA advances Canada's Space Policy Framework commitment to Canadian leadership in planetary science by contributing instruments to an international flagship mission to characterize Enceladus's sub-surface ocean and plume chemistry. | GC Space Policy Framework; ORCA CADRe Part A §2.3 | Marie Tremblay (ORCA Mission Manager) | High | Strategic driver; defines ADR demonstration scope. Low direct cost impact.
|  | STR-02 | CSA alignment | How does the mission align with CSA priorities, programs, and expected results? | Narrative with references | Assumption | Drafted | Aligns with CSA priorities in planetary exploration, astrobiology-relevant science, and Canadian instrument leadership, building on heritage radar and in-situ sampling technologies. | CSA program priorities; Part A §2.2-2.3 | Alan Whitfield (Portfolio Manager) | High | Reinforces robotics workforce investment.
|  | STR-03 | Government direction | What government decisions, mandates, commitments, or high-level directives constrain the mission? | List and implications | Ground rule | Drafted | CSA-owned and -operated mission, executed by the Canadian Orbital Mission Directorate (COMD) project office; must stay within the approved envelope and comply with GC procurement and Canadian-content direction. | TB submission / GC direction (assumed) | Alan Whitfield (Portfolio Manager) | Medium | Constrains procurement approach and gate schedule.
|  | STR-04 | Success criteria | What strategic outcomes define mission success, and how will they be measured? | Outcomes and measures | Ground rule | Drafted | Success = ORCA instrument suite delivered to the host orbiter on schedule, successful commissioning at Enceladus, and at least the primary plume-transit science passes completed to specification. | Part A §2.4 mission requirements | Naomi Fitzgerald (Lead Spacecraft Systems Engineer) | High | Defines verification scope; drives test cost.
|  | STR-05 | Priority and trade-offs | When cost, schedule, scope, performance, and risk conflict, what is the order of priority? | Ranked priorities | Ground rule | Drafted | Priority order: (1) safety / planetary protection, (2) performance (successful plume sampling and analysis), (3) schedule (host-orbiter launch window), (4) cost, (5) extended scope. | SMA Class B posture (Part A §6.4) | Marie Tremblay (ORCA Mission Manager) | Medium | Guides reserve release and descope decisions.
Section 2 - Funding and Affordability
|  | ID | Category | Question | Expected Response | Classification | Status | Response / Narrative | Basis / Source | Owner | Confidence | Cost / Schedule / Risk Impact
|  | FND-01 | Funding strategy | What is the planned source and timing of funding by mission phase? | Funding profile by phase | Assumption | Drafted | A-base CSA appropriation phased across Phase 0-X (FY2020-FY2032), weighted to the Phase C/D build (FY2024-FY2027). | ORCA Scenario 1 phasing (Part D §7) | Samuel Boucher (Schedule and Cost Management Engineer) | Medium | Funding profile matches Scenario 1 durations.
|  | FND-02 | Affordability limit | Is there a cost ceiling, target, annual limit, or approval threshold that must not be exceeded? | Amounts, years, and basis | Ground rule | Drafted | A not-to-exceed program ceiling is set at TB approval, with annual cash-flow limits by fiscal year. | TB authority (assumed) | Samuel Boucher (Schedule and Cost Management Engineer) | Low | Cost ceiling drives descope triggers.
|  | FND-03 | Funding stability | How stable is the expected funding profile, and what changes or interruptions should be assumed? | Scenario or constraints | Assumption | Drafted | Assume stable A-base funding with risk of single-year deferrals; a one-year slip is carried in the Pessimistic schedule. | Scenario 3 sensitivity (Part D §7) | Samuel Boucher (Schedule and Cost Management Engineer) | Medium | Slip drives salary and escalation growth.
|  | FND-04 | Cost responsibility | Which organization will fund each phase, segment, major subsystem, and in-kind contribution? | Responsibility matrix | Assumption | Drafted | CSA funds all phases and segments; no partner cost-share. Partner contributions (ESA, NASA) and academic support are in-kind only. | CSA-owned mission (Part D §5 OBS) | Samuel Boucher (Schedule and Cost Management Engineer) | High | Limited external funding offset.
|  | FND-05 | Contingency and reserves | Who holds cost and schedule contingency, at what level, and under what release authority? | Reserve approach | Ground rule | Drafted | CSA holds project-level cost and schedule reserve, released by the ORCA Project Board at gates. | IGMF governance | Priya Raman (Lead Project Manager) | Medium | Reserve sized for Class B risk.
|  | FND-06 | Eligible expenditures | Are any costs eligible for NATO or other special funding, reimbursement, or cost-sharing arrangements? | Eligibility and conditions | Assumption | Drafted | No NATO or special eligible-cost arrangements; standard CSA appropriation only. | Mission classification | Samuel Boucher (Schedule and Cost Management Engineer) | High | None.
Section 3 - Delivery and Acquisition
|  | ID | Category | Question | Expected Response | Classification | Status | Response / Narrative | Basis / Source | Owner | Confidence | Cost / Schedule / Risk Impact
|  | DEL-01 | Delivery model | For each phase and major element, will delivery be CSA-led, industry-led, partner-led, or academia-led? | Responsibility by phase/element | Ground rule | Drafted | Phase 0/A CSA-led studies; Phase B-D industry-led under the Prime (Asterion Orbital Integration Ltd.); Phase E-X CSA-led operations with Prime support. | OBS (Part D §5) | Priya Raman (Lead Project Manager) | Medium | Sets contract boundaries by phase.
|  | DEL-02 | Development approach | Will the work use waterfall, agile, incremental, spiral, or a hybrid approach? | Approach by workstream | Ground rule | Drafted | Hybrid: waterfall for flight hardware (gated reviews) and agile for flight software and autonomy. | Class B / GOLD Rules (Part A §6.5) | Naomi Fitzgerald (Lead Spacecraft Systems Engineer) | Medium | Affects test cadence and integration.
|  | DEL-03 | Concept competition | Will multiple concepts or parallel contracts be funded before a down-selection? | Number, duration, and down-select point | Assumption | Drafted | Two parallel Phase 0 concept studies are funded, with down-select at Gate 2 (KDP-A). | Acquisition assumption | Étienne Lacroix (Deputy Project Manager) | Low | Adds Phase 0 cost, reduces Phase B risk.
|  | DEL-04 | Procurement packaging | How will the mission be divided into contracts, and what are the approximate number and value of contracts by phase? | Contract map by phase | Assumption | Drafted | ~7 industry contracts for the ORCA instrument suite: prime/integration (Asterion), Ice-Penetrating Radar (Northstar Orbital Technologies), Sampling Arm (Aetheris Space Robotics), instrument avionics (Polarion Avionics), context imaging (Borealis Vision Systems), instrument data interface (Canterra Space Communications), and structures/thermal (Arcturon Space Structures); plus academic research agreements. Launch and the NEREID orbiter itself are procured by the partner agencies, not CSA. | OBS (Part D §5) | Étienne Lacroix (Deputy Project Manager) | Medium | Contract count drives oversight cost.
|  | DEL-05 | Statement of work | Will requirements be prescriptive, performance-based, or allow the supplier to propose the mission architecture? | SOW approach and rationale | Ground rule | Drafted | Performance-based for the Prime, with prescriptive interface and safety requirements for the sampling-arm subsystem and for the host-orbiter interface control document. | Ground rule | Naomi Fitzgerald (Lead Spacecraft Systems Engineer) | Medium | Balances innovation against safety rigor.
|  | DEL-06 | Competition strategy | For each major procurement, will the approach be competitive, directed, or sole-source? | Approach and rationale by procurement | Ground rule | Drafted | Competitive for prime and ground systems; the sampling-arm subsystem may be directed to the heritage supplier (Aetheris Space Robotics). | Market assessment | Étienne Lacroix (Deputy Project Manager) | Low | Sole-source premium on sampling-arm subsystem.
|  | DEL-07 | Market access | Will competitions be open to Canadian suppliers only or to international suppliers? | Eligibility by procurement | Ground rule | Drafted | Prime and major subcontracts favour Canadian suppliers per content targets; the host orbiter and launch services are provided by the international partner agencies (ESA, NASA). | Canadian-content direction; OBS | Étienne Lacroix (Deputy Project Manager) | Medium | Mixed domestic/international eligibility.
|  | DEL-08 | Market conditions | Are there monopoly, limited-competition, incumbent, or vendor-lock-in conditions that affect price or schedule? | Market assessment | Assumption | Drafted | Limited domestic competition for the sampling-arm subsystem (near-incumbent Aetheris Space Robotics); vendor lock-in risk monitored. | RFI findings (assumed) | Étienne Lacroix (Deputy Project Manager) | Low | Price risk on sampling-arm subsystem.
|  | DEL-09 | Contract pricing | Will contracts use firm price, cost-reimbursable, time-and-materials, incentive-based, or mixed pricing? | Pricing basis by phase/contract | Ground rule | Drafted | Firm price for ground systems; cost-reimbursable with incentive fee for Prime integration and sampling-arm development. | Ground rule | Étienne Lacroix (Deputy Project Manager) | Medium | Cost risk concentrated on development items.
|  | DEL-10 | Commercial incentives | Will revenue sharing, commercialization, service purchases, or other commercial incentives be used? | Model and cost implications | Assumption | Drafted | No revenue-share or commercialization; single government-owned instrument suite hosted on an international partner orbiter. | Acquisition assumption | Samuel Boucher (Schedule and Cost Management Engineer) | High | None.
|  | DEL-11 | Supplier dependencies | Must any elements be supplied, integrated, or operated by the same organization? | Dependencies and rationale | Assumption | Drafted | The Prime (Asterion) integrates the NEREID orbiter and the ORCA instrument suite; Aetheris Space Robotics supports SAIT and early operations. | Acquisition assumption | Naomi Fitzgerald (Lead Spacecraft Systems Engineer) | Medium | Integration continuity requirement.
|  | DEL-12 | Canadian content | What Canadian-content, industrial-benefit, regional, or socioeconomic requirements apply? | Requirements and targets | Ground rule | Drafted | Target >=60% Canadian content across prime, instrument suite, avionics and sensors. | GC industrial-benefit policy | Étienne Lacroix (Deputy Project Manager) | Medium | Constrains supplier selection.
|  | DEL-13 | Market evidence | What RFI, industry engagement, benchmarks, or supplier feedback support the acquisition assumptions? | Findings and references | Assumption | Drafted | RFI and industry days held in Phase 0 with domestic space-robotics suppliers support the acquisition assumptions. | Industry engagement (assumed) | Étienne Lacroix (Deputy Project Manager) | Low | Supports acquisition basis.
|  | DEL-14 | Phase transition | Will the Phase B–D contractor be expected or required to support Phase E–F operations? | Continuity strategy | Ground rule | Drafted | The Phase B-D Prime is required to support Phase E operations and the Phase X disposal campaign under an options clause. | Ground rule | Priya Raman (Lead Project Manager) | Medium | Operations-continuity cost.
Section 4 - Partnerships
|  | ID | Category | Question | Expected Response | Classification | Status | Response / Narrative | Basis / Source | Owner | Confidence | Cost / Schedule / Risk Impact
|  | PAR-01 | Partner roles | Which federal, international, industry, academic, or other partners will participate, and what will each provide? | Roles and contributions | Assumption | Drafted | Industry: Asterion Orbital Integration (prime), Northstar Orbital Technologies (radar), Aetheris Space Robotics (sampling arm), Polarion Avionics, Borealis Vision Systems (context imaging), Canterra Space Communications, Arcturon Space Structures, Meridian Ground Technologies. Academia: Northern Institute of Space Engineering, Laurentia University of Aerospace Technology, Boreal Technical University. International: ESA (host-orbiter contribution) and NASA (host-orbiter lead and launch). OGDs: COSD, CSEO, NARD. | OBS (Part D §5) | Marie Tremblay (ORCA Mission Manager) | High | Defines interfaces and governance load.
|  | PAR-02 | Decision authority | How are decision rights, governance, configuration control, and dispute resolution shared among partners? | Governance model | Ground rule | Drafted | CSA (COMD project office) retains full decision, configuration-control and dispute authority; partners contribute under MOUs; the Prime holds delegated design authority within the approved baseline. | IGMF governance; OBS | Marie Tremblay (ORCA Mission Manager) | High | Clear authority reduces schedule risk.
|  | PAR-03 | Dependencies | What partner deliverables, approvals, facilities, data, or schedules are mission dependencies? | Dependency register | Assumption | Drafted | The NEREID orbiter's launch slot and interface schedule (NASA-led), the sampling-arm delivery from Aetheris, and ESA technical inputs are the key external dependencies. | Sched Dependencies (Part D §10) | Naomi Fitzgerald (Lead Spacecraft Systems Engineer) | Medium | Schedule risk if any slips.
|  | PAR-04 | Contribution valuation | How will in-kind contributions, shared assets, and partner-provided services be valued in the estimate? | Valuation method | Ground rule | Drafted | International-partner (ESA/NASA) contributions are valued as in-kind under MOU; academic research agreements at cost; CSA in-kind at standard rates. | Costing GR&A | Samuel Boucher (Schedule and Cost Management Engineer) | Medium | Adds in-kind value to the estimate.
Section 5 - Governance and Oversight and Assurance
|  | ID | Category | Question | Expected Response | Classification | Status | Response / Narrative | Basis / Source | Owner | Confidence | Cost / Schedule / Risk Impact
|  | GOV-01 | Governance | What governance bodies, decision gates, reviews, and approval authorities apply? | Governance and gate map | Ground rule | Drafted | CSA IGMF gates apply (Gate 0/SR, Gate 1, Gate 2/KDP-A, R3, R4, Gate 3/KDP-D, Gate 4/KDP-E, Gate 5/KDP-X), administered by the COMD project office. | IGMF rev F; Part D §8 | Priya Raman (Lead Project Manager) | High | Defines review cost and cadence.
|  | GOV-02 | CSA oversight | What level of CSA technical, programmatic, financial, and contractual oversight is required? | Oversight model and staffing | Ground rule | Drafted | Full technical, programmatic, financial and contractual oversight, with an embedded CSA systems-engineering and project office through Phase D. | Ground rule | Priya Raman (Lead Project Manager) | Medium | CSA staffing cost through build.
|  | GOV-03 | Reporting | What reporting products, data requirements, and reporting frequency are required? | Reporting calendar | Ground rule | Drafted | Monthly cost/performance reports, quarterly Project Board, and milestone reviews at each gate. | IGMF reporting | Ethan Parker (Project Management Engineer) | Medium | Reporting workload.
|  | GOV-04 | Change control | How will changes to scope, requirements, baseline, schedule, and funding be approved and documented? | Change-control process | Ground rule | Drafted | Baseline changes go through the CSA Configuration Control Board; the Prime submits engineering change requests; TB-threshold changes escalate. | IGMF change control | Ethan Parker (Project Management Engineer) | Medium | Change discipline protects baseline.
|  | ASM-01 | Applicable standards | Which CSA, ECSS, ISO, NASA, engineering, quality, safety, and mission-assurance standards apply? | Tailored standards list | Ground rule | Drafted | Tailored CSA/ECSS standards with GSFC GOLD Rules for Class B, and ISO 9001 quality. | Part A §6.5 | Fatima Haidari (Safety and Mission Assurance Engineer) | High | Sets verification rigor.
|  | ASM-02 | Quality assurance | What reviews, inspections, audits, independent assessments, and acceptance evidence are required? | Assurance plan | Ground rule | Drafted | Gate reviews, a unit/subsystem/system test campaign, independent SMA audits (supported by NARD), and acceptance data packages. | Part A §6.5; OBS | Fatima Haidari (Safety and Mission Assurance Engineer) | Medium | Drives test and audit cost.
|  | ASM-03 | Mission class and rigor | What mission class, risk tolerance, redundancy, qualification, and verification rigor should be assumed? | Classification and tailoring | Ground rule | Drafted | Class B, selective redundancy on critical systems, and a protoflight approach (EM/QM/PFM). | Part A §6.4-6.5 | Fatima Haidari (Safety and Mission Assurance Engineer) | High | Drives redundancy and qualification cost.
Section 6 - Workforce and Facilities
|  | ID | Category | Question | Expected Response | Classification | Status | Response / Narrative | Basis / Source | Owner | Confidence | Cost / Schedule / Risk Impact
|  | RES-01 | Workforce availability | What workforce availability constraints, capability gaps, recruitment challenges, or dependencies on external expertise should be assumed beyond the information documented in the RAM? | Staffing profile and constraints | Assumption | Drafted | Space-robotics and autonomy talent is scarce; assume reliance on Prime/Aetheris specialists and the CSA robotics group beyond the RAM baseline. | RAM (Part C §5) + assumption | Priya Raman (Lead Project Manager) | Low | Recruitment risk to schedule.
|  | RES-02 | Capability development | What recruitment, training, knowledge-transfer, or competency-development effort is required? | Capability plan | Assumption | Drafted | Training and knowledge transfer for autonomous instrument operations and plume-sampling sequencing; the ops team is stood up in Phase C/D. | Assumption | Simone Bergeron (Mission Operations and Ground Systems Engineer) | Medium | Training cost in Phase C/D.
|  | RES-03 | Facilities and tools | What facilities, laboratories, ground infrastructure, software, licenses, and development environments are required? | Asset list and ownership | Assumption | Drafted | CSA integration and test facilities, a robotics testbed (with Laurentia University support), the MOC, and a flight-software development environment are assumed CSA-owned. | Assumption; OBS academia | Naomi Fitzgerald (Lead Spacecraft Systems Engineer) | Medium | Facility availability constraint.
Section 7 - Operations and Sustainment
|  | ID | Category | Question | Expected Response | Classification | Status | Response / Narrative | Basis / Source | Owner | Confidence | Cost / Schedule / Risk Impact
|  | OPS-01 | Operations concept | Who will lead mission operations, and what control centres, coverage hours, staffing, and support model are assumed? | Operations concept by phase | Ground rule | Drafted | CSA-led operations from the CSA MOC (ground systems by Meridian Ground Technologies): 24/7 coverage during plume-transit science passes and business hours otherwise, with the Prime on call during early ops. | Part A §5; OBS | Simone Bergeron (Mission Operations and Ground Systems Engineer) | Medium | Operations staffing profile.
|  | OPS-02 | Mission duration | What commissioning, nominal operations, extension, disposal, and close-out durations should be costed? | Durations and dates | Ground rule | Drafted | Commissioning ~1-3 months; nominal Phase E ~180 months (15 years, per ORCA Scenario 1); extended ops plus disposal (Phase X) ~42 months; close-out ends 2059-12-28. | Scenario 1 (Part D §7) | Simone Bergeron (Mission Operations and Ground Systems Engineer) | High | Sets operations cost duration.
|  | OPS-03 | Service levels | What availability, responsiveness, latency, throughput, and continuity targets apply to operations? | Service-level targets | Ground rule | Drafted | Target >=95% command availability during science-pass windows; disposal maneuvers planned with margin. | Ground rule | Simone Bergeron (Mission Operations and Ground Systems Engineer) | Low | Ground-segment sizing.
|  | OPS-04 | Spares and obsolescence | What strategy applies to spares, replenishment, maintenance, obsolescence, and technology refresh? | Sustainment strategy | Assumption | Drafted | No on-orbit spares (single spacecraft); ground spares held for the MOC; obsolescence managed to end of Phase X. | Assumption | Simone Bergeron (Mission Operations and Ground Systems Engineer) | Medium | Sustainment cost.
Section 8 - Legal and Regulatory
|  | ID | Category | Question | Expected Response | Classification | Status | Response / Narrative | Basis / Source | Owner | Confidence | Cost / Schedule / Risk Impact
|  | REG-01 | Regulatory requirements | Which federal, provincial, international, licensing, spectrum, orbital, environmental, or other regulatory requirements apply? | Requirements and authorities | Ground rule | Drafted | Canadian remote-sensing/space licensing, ITU spectrum filing, export-control (technology transfer) approvals, and planetary-protection approvals apply. | Ground rule | Étienne Lacroix (Deputy Project Manager) | Medium | Licensing lead time.
|  | REG-02 | Export controls | What ITAR, EAR, Controlled Goods, sanctions, or other export-control restrictions affect suppliers and partners? | Restrictions and mitigations | Ground rule | Drafted | Controlled Goods Program applies; ITAR/EAR exposure is managed at the international-partner (ESA, NASA) and launch-provider interfaces, with the Canadian-content strategy limiting exposure. | Ground rule; OBS | Étienne Lacroix (Deputy Project Manager) | Medium | Supplier and partner constraints.
|  | REG-03 | Liability and insurance | What liability, indemnification, insurance, launch, or third-party risk provisions should be assumed? | Legal allocation and cost basis | Assumption | Drafted | Launch liability is carried under the partner agency (NASA) launch arrangement; the Crown self-insures its own instrument hardware on-orbit; re-entry casualty risk is assessed for the host orbiter disposal. | Assumption | Étienne Lacroix (Deputy Project Manager) | Low | Insurance/liability cost.
|  | REG-04 | Space and data law | Who may own, access, distribute, commercialize, or restrict mission data and derived products? | Rights and restrictions | Ground rule | Drafted | CSA owns ORCA instrument data and derived science products; distribution follows the mission's international data-rights agreement and is coordinated with the partner agencies. | Ground rule; OBS | Devon Okafor (Mission Operations Scientist) | Medium | Data rights defined.
|  | REG-05 | Intellectual property | Who will own background and foreground IP, and what licensing or reuse rights are required? | IP allocation | Ground rule | Drafted | CSA holds a licence to foreground IP; contractors retain background IP; sampling-arm mechanism IP licensing with Aetheris is negotiated. | Ground rule | Étienne Lacroix (Deputy Project Manager) | Medium | IP negotiation effort.
Section 9 - Security and Information
|  | ID | Category | Question | Expected Response | Classification | Status | Response / Narrative | Basis / Source | Owner | Confidence | Cost / Schedule / Risk Impact
|  | SEC-01 | Security classification | What security category or classification applies to the mission, systems, information, and contracts? | Classification by asset | Ground rule | Drafted | Mission baseline is Protected B; certain instrument performance and export-controlled technical data are Protected or classified. | Ground rule | Étienne Lacroix (Deputy Project Manager) | Medium | Contract security cost.
|  | SEC-02 | Cybersecurity | What cybersecurity, accreditation, monitoring, data-protection, and communications-security controls apply? | Control baseline | Ground rule | Drafted | ITSG-33 controls, command-link authentication/COMSEC, and ground-system accreditation apply. | Ground rule | Étienne Lacroix (Deputy Project Manager) | Medium | Cybersecurity cost.
|  | SEC-03 | Personnel and facilities | What clearances, access restrictions, controlled facilities, and physical-security measures are required? | Security requirements | Ground rule | Drafted | Secret-cleared key personnel, a controlled integration facility, and physical security per Controlled Goods requirements. | Ground rule | Étienne Lacroix (Deputy Project Manager) | Medium | Clearance schedule.
|  | SEC-04 | Information sharing | What publication, disclosure, data-residency, records-management, and information-sharing restrictions apply? | Rules by information type | Ground rule | Drafted | Publication review for sensitive ConOps, data residency in Canada, and records management per CSA IM policy. | Ground rule | Étienne Lacroix (Deputy Project Manager) | Medium | Disclosure controls.
Section 10 - Science and Data Utilization
|  | ID | Category | Question | Expected Response | Classification | Status | Response / Narrative | Basis / Source | Owner | Confidence | Cost / Schedule / Risk Impact
|  | SCI-01 | Science utilization scope | What science planning, calibration, validation, analysis, archiving, user support, and exploitation activities are included? | Included activities and duration | Ground rule | Drafted | Primarily science data: radar sounding and mass-spectrometry analysis, plume-chemistry validation, and a lessons-learned archive; deep-space radiation-environment studies supported by Boreal Technical University. | Part A §2.1; OBS | Devon Okafor (Mission Operations Scientist) | Medium | Modest science scope.
|  | SCI-02 | Science cost responsibility | Who funds and performs science utilization, and are grants, calls for proposals, or partner contributions expected? | Funding and delivery model | Assumption | Drafted | CSA funds and performs data analysis in-house with academic support; no external grants or calls for proposals are assumed. | Assumption | Devon Okafor (Mission Operations Scientist) | Medium | Low cost impact.
|  | SCI-03 | Data products | What data products, processing levels, archives, access services, and retention periods must be delivered? | Product and service scope | Ground rule | Drafted | Level 0-2 telemetry and instrument science data, plume-composition products, and a mission archive retained to end of Phase X + 5 years. | Ground rule | Devon Okafor (Mission Operations Scientist) | Medium | Archive cost.
Section 11 - Risk and Resilience
|  | ID | Category | Question | Expected Response | Classification | Status | Response / Narrative | Basis / Source | Owner | Confidence | Cost / Schedule / Risk Impact
|  | RSK-01 | Supply chain | Which critical suppliers, materials, components, or services have supply-chain risk? | Critical-item assessment | Assumption | Drafted | Critical items: robotic actuators/end-effector (Aetheris Space Robotics), the radar subsystem (Northstar Orbital Technologies), and imaging/proximity sensors (Borealis Vision Systems). | Assumption; OBS | Naomi Fitzgerald (Lead Spacecraft Systems Engineer) | Medium | Long-lead supply risk.
|  | RSK-02 | Delay response | What contingency plans, alternate suppliers, schedule margin, or advance purchases are assumed for supply-chain delays? | Mitigation and cost treatment | Assumption | Drafted | Schedule margin held in Phase C/D, an alternate sensor source qualified, and advance purchase of long-lead propulsion from Northstar. | Assumption | Samuel Boucher (Schedule and Cost Management Engineer) | Low | Margin and advance-buy cost.
|  | RSK-03 | Foreign exchange and escalation | What inflation, escalation, exchange-rate, tariff, and commodity-price assumptions apply? | Rates, dates, and sources | Assumption | Drafted | CAD-base estimate; assume 2.5%/yr escalation, limited USD exposure on launch and some components, FY2024 economic base. | Costing GR&A (Part C) | Samuel Boucher (Schedule and Cost Management Engineer) | Medium | Escalation on multi-year build.
|  | RSK-04 | Schedule constraints | What fixed dates, launch windows, partner milestones, seasonal constraints, or long-lead items drive the schedule? | Constraints and margins | Ground rule | Drafted | Launch window is fixed by planetary alignment for the Jupiter gravity assist (host orbiter, NASA-led); long-lead sampling-arm hardware drives the ORCA-side critical path. | Sched Dependencies (Part D §10) | Naomi Fitzgerald (Lead Spacecraft Systems Engineer) | Medium | Critical-path driver.
|  | RSK-05 | Fallback strategy | What scope, performance, schedule, or acquisition alternatives are available if affordability or feasibility targets are not met? | Off-ramps and decision triggers | Ground rule | Drafted | Off-ramps: reduce plume-pass count from multi- to single-pass, defer extended ops (Phase X), or descope autonomy to ground-in-the-loop. | Ground rule | Marie Tremblay (ORCA Mission Manager) | Medium | Descope levers protect affordability.
Section 12 - Planetary Protection and End-of-Mission Disposal
|  | ID | Category | Question | Expected Response | Classification | Status | Response / Narrative | Basis / Source | Owner | Confidence | Cost / Schedule / Risk Impact
|  | SUS-01 | Disposal compliance | How will ORCA comply with post-mission disposal and planetary-protection guidelines? | Compliance approach | Ground rule | Drafted | Controlled disposal of the NEREID orbiter and its science payload complement to atmospheric re-entry within guideline timelines; compliant with COSPAR Planetary Protection Policy and NASA/ESA Enceladus contamination-control requirements, and Canadian direction. | COSPAR / NASA-ESA planetary-protection requirements; Part A §2.1 | Naomi Fitzgerald (Lead Spacecraft Systems Engineer) | High | Central mission objective; drives disposal-plan coordination.
|  | SUS-02 | Planetary-protection assurance | How is planetary-protection compliance during plume sampling verified? | Verification approach | Ground rule | Drafted | Plume-sampling ConOps designed for controlled instrument operation with abort-to-safe if sampling parameters fall outside limits; verified in SAIT and operational rehearsals. | Part A §3.2 payload safety | Fatima Haidari (Safety and Mission Assurance Engineer) | Medium | Adds test and rehearsal cost.
|  | SUS-03 | Re-entry safety | What re-entry casualty-risk and public-safety analysis is required? | Risk analysis and threshold | Ground rule | Drafted | Controlled re-entry targeted over an uninhabited ocean corridor; casualty risk assessed below the 1e-4 per-event threshold. | Safety/SMA assumption | Fatima Haidari (Safety and Mission Assurance Engineer) | Low | Analysis effort; constrains disposal ops.
|  | SUS-04 | Orbital coordination | How are conjunction and orbital-traffic coordination handled during plume transit? | Coordination approach | Assumption | Drafted | Planetary-protection and export-control compliance coordination with the Canadian Orbital Safety Directorate (COSD); deep-space radiation and thermal-environment inputs from CSEO; trajectory and communications-window coordination pre-planned for each Enceladus plume pass. | Ops assumption; Part D §5 OBS | Simone Bergeron (Mission Operations and Ground Systems Engineer) | Medium | Ground-segment and ops workload.

## 11 - DDDD
` Table of Contents
12 - Dispose, Divest, Descope, Delay (DDDD)
Why we we asking:
This section helps assess program risk, maturity, and readiness for Earned Value Management (EVM). It explores how you would respond to cost overruns, schedule delays, and end-of-life considerations.
Q1. COST OVERRUNS
If the cost exceeds the approved allocation, what mitigation strategies would you consider? ☐ Descope ☐ Request additional funding ☐ Delay ☐ Cannibalize from the A-Base ☐ Other (specify) | Selected: [x] Descope [x] Delay [x] Request additional funding. Primary response is to descope (reduce plume-pass count) before seeking new funds; cannibalizing the A-Base is a last resort.
If you have a Descope Plan, please describe it. | Yes. Tiered descope: (1) reduce plume-pass count from multi- to single-pass; (2) defer extended operations / disposal (Phase X); (3) descope onboard autonomy to ground-in-the-loop operations. Each ties to a KDP off-ramp.
If you would request more funding, would this be an A-Base pressure or a Fiscal Framework Ask ? | A Fiscal Framework Ask for material growth; minor pressures absorbed as an A-Base pressure within the CSA envelope.
If an A-Base pressure, which other investment would be most at risk of cannibalization? | If A-Base, the CSA space-robotics technology development line would be most at risk of cannibalization.
Do you have a Scope Management Strategy in place? | Yes - baseline is held under the CSA Configuration Control Board; a RID (Review Item Disposition) process runs at each gate; scope changes above the TB threshold escalate.
Who is your Systems Engineer, and what is their approach to RIDs and scope escalation? | Lead Spacecraft Systems Engineer: Naomi Fitzgerald. RIDs are dispositioned at each gate review; scope escalation is controlled via ECR to the CCB with a cost/schedule impact assessment.
How well is the scope defined? What level of uncertainty exists in the scope? | Scope is well defined for the ORCA instrument suite but carries moderate uncertainty in the sampling-arm and autonomy elements (TRL 6). Overall Mission Class B.
Do you have a vendor exit strategy, such as go/no-go milestones? | Yes - go/no-go at Gate 2 (down-select of the two Phase 0 concepts) and at each subsequent gate; option clauses allow an off-ramp before the Phase D commitment.
What thresholds would trigger a replanning or a rebaseline? | Rebaseline if cost variance exceeds +15% of the approved envelope, or schedule variance exceeds 6 months at a gate.
Q2. DELAYS
If the mission extends beyond nominal operations, do you have a Divestiture Plan? Who would you divest to? Are there any financial interests involved in the divestiture? | No divestiture - ORCA is a single-use CSA science payload. Extended operations run under Phase X until end-of-life, then controlled disposal. No third-party financial interest.
What would be the impacts of a significant launch delay? | A launch slip on the host orbiter (NASA-led) delays science-data return, extends CSA salary/O&M carrying cost, and may miss the Jupiter gravity-assist window entirely. Roughly $0.3-0.5M per month of standing-army cost (the Pessimistic scenario carries a 1-year slip).
Do you have contingency plans for schedule delays? | Yes - schedule margin is held in Phase C/D, an alternate sensor source is qualified, and long-lead sampling-arm hardware is advance-purchased. Three schedule scenarios (Nominal / Optimistic / Pessimistic) bound the risk.
What schedule delays would trigger a replanning or a rebaseline? | A slip greater than 6 months against the Scenario 1 baseline at any gate triggers replanning; greater than 12 months triggers a formal rebaseline.
Q3. END OF LIFE
Do you have a general idea of the Disposal Plan for Phase F? | Disposal is handled in Phase X (Phase F/G collapsed into Phase X for ORCA): controlled disposal of the NEREID orbiter and its science payload complement per the partner agency plan, compliant with COSPAR / NASA-ESA planetary-protection requirements.
Are you planning an Audit after launch? | Yes - a post-launch / close-out audit and a lessons-learned review are planned at the end of Phase X.
What are your plans for retiring the space segment after nominal operations? Do you plan to divest any components? If so, how? And to whom? | The space segment is disposed of per the partner agency's end-of-mission plan, not retired for reuse; no components are divested. Ground assets (the MOC) revert to CSA sustaining use.
Do you plan to de-orbit the spacecraft or transfer it to a parking orbit? What is your strategy for managing space debris? | Controlled end-of-mission disposal per the partner agency's planetary-protection plan - never left in an uncontrolled state. The mission is planetary-protection compliant (controlled instrument operations with abort-to-safe).
What is the source of funds for a potential Phase E Extension? | A-Base O&M appropriation funds nominal Phase E; any extension (Phase X) is funded through a subsequent Fiscal Framework Ask or reprofiled A-Base.

## 12 - Procurement Plan
` Table of Contents
13 - Procurement Plan
Why we we asking:
Part of GRA
List all contracts and G&C and MOUs
| Segment | Phase | Type | Vendor | PO Number | Contract Title | Sub-contractor | CWBS | Color of Money
| Space Segment | PREP1 | Contract | Aetheris Space Robotics | 9F063-190007 | Instrument Accommodation Risk-Reduction Prototype |  | CWBS 3 | STDP Contribution
| Space Segment | PREP1 | Contract | Asterion Orbital Integration | 9F063-190012 | Plume Transit & Sampling Ops Risk-Reduction Study |  | CWBS 2 | STDP O&M Contract
| Space Segment | PREP2 | Contract | Northstar Orbital Technologies | 9F063-200019 | Host Orbiter Interface Concept Prototyping |  | CWBS 4 | STDP Contribution
| Space Segment | PREP2 | Contract | Aetheris Space Robotics | 9F063-200024 | Sampling Arm End-Effector Breadboard |  | CWBS 3 | STDP O&M Contract
| Mission SEITPM | Phase 0 | Contract | Asterion Orbital Integration | 9F063-200031 | ORCA Phase 0 Concept Study A |  | CWBS 1 | O&M Contract
| Mission SEITPM | Phase 0 | Contract | Northstar Orbital Technologies | 9F063-200033 | ORCA Phase 0 Concept Study B |  | CWBS 1 | O&M Contract
| Mission SEITPM | Phase A | Contract | Asterion Orbital Integration | 9F063-220045 | ORCA Phase A Definition |  | CWBS 1 | None
| Space Segment | Phase BCD | Contract | Asterion Orbital Integration | 9F063-230061 | ORCA Phase B-D Space Segment (Prime) | Northstar / Aetheris / Polarion / Borealis / Arcturon | CWBS 2-8 | Capital Contract
| Ground Segment | Phase BCD | Contract | Meridian Ground Technologies | 9F063-230064 | ORCA Ground Segment | Canterra Space Communications | CWBS 9 | Capital Contract
| Overhead & Oversight | Phase BCD | MOU | NASA |  | MOU with NASA - launch of the NEREID orbiter and the ORCA instrument suite (partner-procured, no CSA launch contract) |  |  | Capital Contract
| Science Segment | Phase 0 | Contract | Northern Institute of Space Engineering | 9F063-200052 | Science Support during Phase 0 |  | CWBS 11 | O&M Contract
| Science Segment | Phase A | Contract | Laurentia University of Aerospace Technology | 9F063-220057 | Science Support during Phase A |  | CWBS 11 | Capital Contract
| Science Segment | Phase BCD | Contract | Boreal Technical University | 9F063-230059 | Science Support during Phase B-D |  | CWBS 11 | Capital Contract
| Science Segment | Phase E | G&C | Northern Institute of Space Engineering | 9F063-270081 | Science Utilization Grant |  | CWBS 11 | Grants
| Overhead & Oversight | Phase 0 | MOU | COSD |  | MOU with Canadian Orbital Safety Directorate (COSD)
| Overhead & Oversight | Phase A | MOU | COSD |  | MOU with COSD
| Overhead & Oversight | Phase BCD | MOU | CSEO |  | MOU with Canadian Space Environment Office (CSEO)
| Overhead & Oversight | Phase E | MOU | COSD |  | MOU with COSD
| Overhead & Oversight | Phase 0 | MOU | NARD |  | MOU with National Aerospace Research Directorate (NARD)
| Overhead & Oversight | Phase BCD | MOU | NARD |  | MOU with NARD
| Overhead & Oversight | Phase BCD | MOU | ESA |  | MOU with ESA - plume-transit trajectory analysis
| Overhead & Oversight | Phase BCD | MOU | NASA |  | MOU with NASA - host-orbiter interface expertise
| Overhead & Oversight | Phase 0 | RAM | CSA |  | RAM |  |  | O&M Salary
| Overhead & Oversight | Phase A | RAM | CSA |  | RAM |  |  | Capital Salary
| Overhead & Oversight | Phase BCD | RAM | CSA |  | RAM |  |  | Capital Salary
| Overhead & Oversight | Phase E | RAM | CSA |  | RAM |  |  | O&M Salary
Charter of Accounts
CBS x OBS

## 13 - Govt Overhead
` Table of Contents
14. Overhead costs
Why we we asking:
|  |  | RO | GL | ballpark
| IS Management Overhead | This is a % tax based on project size and complexity | multiple | multiple | 1%
| Management Consulting Services | Contracts with management consultants
| Consultants - Industrial Space Experts | Technomics support at KDP-0 | RO-14.1 |  | 10000
|  | Technomics support at KDP-A | RO-14.1 |  | 2000
|  | Technomics support at KDP-B | RO-14.1 |  | 1000
|  | Technomics support at KDP-C | RO-14.1 |  | 1000
|  | Technomics support at KDP-D | RO-14.1 |  | 1000
| Consultants - Academia | Northern Institute of Space Engineering | RO-14.1 |  | 50000
| Consultants - Non-Space Experts | N/A |  |  | 0
| Temporary Help | N/A |  |  | 0
| Students | Student Term 1 |  |  | 16000
|  | Student Term 2 |  |  | 16000
|  | Student Term 3 |  |  | 16000
|  | Student Term 4 |  |  | 16000
| Government Travel & Living | T&L Phase 0 |  |  | 25000 | Should be linked to Travel Plan roll-up
|  | T&L Phase A |  |  | 25000
|  | T&L Phase B |  |  | 25000
|  | T&L Phase C |  |  | 25000
|  | T&L Phase D |  |  | 25000
|  | T&L Phase E |  |  | 25000
| Translation | Phase 0 Docs |  |  | 2000
|  | Phase A Docs |  |  | 5000
|  | Phase BCD Docs |  |  | 5000
| Shipping |  |  |  | 0
| Software Licenses | Matlab, STK, etc |  |  | 50000
| Public Outreach and STEM initiatives |  |  |  | 20000
Other Overhead (Specify)

## 14 - Constants
` Table of Contents
15 - Economic Constants and short answers
This tab contains one word or one number answers
Parameter | Value | Description
EBP Rate | 27% | The Employee Benefit Payments (EBP) rate for federal government initiatives is currently calculated at 27% of total salary costs for new initiatives, according to the Treasury Board Secretariat (TBS).
Shared Services Rate | 4% | Shared Services Canada (SSC) charges federal government departments for IT services; this equal 4% of FTE salary costs to align with the actual cost of providing services.
PSPC Rate | 13% | PSPC accommodation premium is set at 13% and is calculated as a percentage of personnel costs.
PSPC Fairness Monitor Rate | 300000 | The Fairness Monitoring Program of Public Services and Procurement Canada (PSPC) ensures independent assurance that procurement activities are fair, open, and transparent. It involves a third-party fairness monitor who assesses the fairness, openness, and transparency of the monitored activity.
Labour Rates | 205$/hr | As per recent Asterion Orbital Integration quote; estimated contractor rate per hour.
Vendor Fee Rate % | 11% | As per recent Asterion Orbital Integration quote; contractor general fee applied before tax.
Costing Complexity | Medium | Low, Medium, High
Palier/ Tier | Tier 2 | Gated investments are classified into Tiers. Tier determination is made based on the estimated project cost; the use of Tiers enables the implementation of a tailored approach, whereby authority level, reporting, and deliverables are proportionate to the investment materiality, risk, and complexity.
PCRA | PCRA 3 | In accordance with the Standard for Project Complexity and Risk Assessment.
Classe de Mission | Class B | Classification system to group space missions according to their budget size, technical complexity, scientific goals, and acceptable levels of risk.
Investment Type | Space Mission | space mission, real property, software solutions
Mission Type | Hosted Payload | Flagship, LargeSat, SmallSat, NanoSat, Hosted Payload, Data stream partnership, data stream purchase
Discipline | planetary exploration | SatCom, Earth Observation, Atmospheric science, Solar Terrestrial Science, Space surveillance, Astronomy, planetary exploration, human space flight, health and life science, space robotics, platform technologies
Mission Name | ORCA
Current Phase | Phase D (MAIT/SAIT)
Next KDP | KDP-E / Gate 4 | Key decision point
Base year | 2026 | Base year is the reference year used as a benchmark for comparing costs, prices, or other economic indicators over time.
Exchange Rate USD | 1.36 | Exchange rate is the rate at which the USD currency can be exchanged for the Canadian currency at a specific point in time.
Exchange Rate Euro | 1.49 | Exchange rate is the rate at which the Euro currency can be exchanged for the Canadian currency at a specific point in time.
Unknown-Unknown Risk Margin | 10%
tax rates | 14.97% | Assuming the 5% for Goods and Services Tax (GST) and 9.975% for the Quebec Sales Tax (QST).

## 15 - Inflation
` Table of Contents
16 - Inflation Model
Inflation | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | 31/32 | 32/33 | 33/34 | 34/35 | 35/36 | 36/37 | 37/38 | 38/39 | 39/40 | 40/41 | 41/42 | 42/43 | 43/44 | 44/45 | Justification
Csa Salaries |  | 4.75% | 3.5% | 2.5% | 2.3% | 2.3% | 2.3% | 2.3% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | Convention collective des ingénieurs signées jusqu'en octobre 2025 (plus grosse partie du salaire) Hypothèse de 2.3% jusqu'en 2030 et par la suite 2% |  | This section of the sheet should not be modified by the user
CSA Mgt |  | 6.32% | 3.7% | 2.4% | 2.2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | Inflation moyenne de 2% utilisée
Contract Labor | 2.5% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | Hypothèse de 3% annuellement donnée par différents contracteurs dans d'autres projets
Contract Non Labor |  | 3.789% | 4.046% | 2.5% | 2.4% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.259% | 2.259% | 2.259% | 2.259% | 2.259% | 2.259% | 2.259% | 2.259% | 2.259% | 2.259% | 2.259% | 2.259% | Hypothèse que l'inflation va se rapprocher de 2.1%- 2.2% dans les prochaines années
Risk | [24 empty] | Hypothèse de 3% annuellement donnée par différents contracteurs dans d'autres projets | bar: 22/23 to 44/45
No Inflation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Not use | 1 | Inf. GL | FY of Source Cost | Inf. GL - FY of Source Cost (Unique ID) | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | 31/32 | 32/33 | 33/34 | 34/35 | 35/36 | 36/37 | 37/38 | 38/39 | 39/40 | 40/41 | 41/42 | 42/43 | 43/44 | 44/45 | 45/46 |  | DND V1 R&D Near Term Adjusted
Salary Funding Rate |  | 4.75% | 3.5% | 2.25% | 2.25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | Pour onglet 35a et 35b concernant les nouveaux FTE. Financement 4 ans de la 1ere tranche des conventions collectives et les renouvellements subséquents seront financés via le SCT pour les prochaines conventions collectives comme à l'habitude. Le risque ici dans les 1ere années est lorsque le SCT prendra la photo des effectifs à une date X, il est fort possible que les nouveaux employés ne seront pas prises en compte dans les effectifs et l'ASC n'aura pas le financement de l'augmentation pour les nouveaux postes. | 2 | Csa Salaries | 22/23 | Csa Salaries - 22/23 |  | 1 | 1.035 | 1.0609 | 1.0853 | 1.1102 | 1.1358 | 1.1619 | 1.1851 | 1.2088 | 1.233 | 1.2577 | 1.2828 | 1.3085 | 1.3347 | 1.3613 | 1.3886 | 1.4163 | 1.4447 | 1.4736 | 1.503 | 1.5331 | 1.5638 | 1.595 |  |  | Fiscal Year | Annual Inflation | Raw Index | Weighted Index |  | FY | Fiscal Year | Annual Inflation | Raw Index | Weighted Index
Ground segment | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | NR CAN | 3 | Csa Salaries | 23/24 | Csa Salaries - 23/24 |  | 0.95465 | 1 | 1.025 | 1.0486 | 1.0727 | 1.0974 | 1.1226 | 1.1451 | 1.168 | 1.1913 | 1.2151 | 1.2394 | 1.2642 | 1.2895 | 1.3153 | 1.3416 | 1.3684 | 1.3958 | 1.4237 | 1.4522 | 1.4813 | 1.5109 | 1.5411 |  | 1 | 1990 | 5.3% | 0.60277 | 0.62029 |  | 21/22 | 2021 | 0.7% | 1 | 1.0198
DND Table | 0.7% | 3.4% | 6.9% | 4.2% | 2.4% | 2.109% | 2.109% | 2.109% | 2.109% | 2.109% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | 2.077% | Fournit par Technomics | 4 | Csa Salaries | 24/25 | Csa Salaries - 24/25 |  | 0.92237 | 0.96618 | 1 | 1.023 | 1.0465 | 1.0706 | 1.0952 | 1.1171 | 1.1395 | 1.1623 | 1.1855 | 1.2092 | 1.2334 | 1.2581 | 1.2832 | 1.3089 | 1.3351 | 1.3618 | 1.389 | 1.4168 | 1.4451 | 1.474 | 1.5035 |  | 2 | 1991 | 4.8% | 0.63171 | 0.64478 |  | 22/23 | 2022 | 3.4% | 1.034 | 1.0544
Inflation 1,5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% |  | 5 | Csa Salaries | 25/26 | Csa Salaries - 25/26 |  | 0.89987 | 0.94262 | 0.97561 | 1 | 1.023 | 1.0465 | 1.0706 | 1.092 | 1.1139 | 1.1361 | 1.1589 | 1.182 | 1.2057 | 1.2298 | 1.2544 | 1.2795 | 1.3051 | 1.3312 | 1.3578 | 1.3849 | 1.4126 | 1.4409 | 1.4697 |  | 3 | 1992 | 1.8% | 0.64308 | 0.65554 |  | 23/24 | 2023 | 6.9% | 1.1053 | 1.1271
Inflation 8% | 8% | 8% | 8% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% |  | 6 | Csa Salaries | 26/27 | Csa Salaries - 26/27 |  | 0.87964 | 0.92143 | 0.95368 | 0.97752 | 1 | 1.023 | 1.0465 | 1.0675 | 1.0888 | 1.1106 | 1.1328 | 1.1555 | 1.1786 | 1.2021 | 1.2262 | 1.2507 | 1.2757 | 1.3012 | 1.3273 | 1.3538 | 1.3809 | 1.4085 | 1.4367 |  | 4 | 1993 | 2.9% | 0.66173 | 0.67264 |  | 24/25 | 2024 | 4.2% | 1.1518 | 1.1745
[26 empty] | 7 | Csa Salaries | 27/28 | Csa Salaries - 27/28 |  | 0.85987 | 0.90071 | 0.93223 | 0.95554 | 0.97752 | 1 | 1.023 | 1.0435 | 1.0643 | 1.0856 | 1.1073 | 1.1295 | 1.1521 | 1.1751 | 1.1986 | 1.2226 | 1.247 | 1.272 | 1.2974 | 1.3234 | 1.3498 | 1.3768 | 1.4044 |  | 5 | 1994 | -1.4% | 0.65246 | 0.66501 |  | 25/26 | 2025 | 2.4% | 1.1794 | 1.2024
[26 empty] | 8 | Csa Salaries | 28/29 | Csa Salaries - 28/29 |  | 0.84053 | 0.88046 | 0.91127 | 0.93406 | 0.95554 | 0.97752 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 1.3459 | 1.3728 |  | 6 | 1995 | 0% | 0.65246 | 0.66527 |  | 26/27 | 2026 | 2.109% | 1.2043 | 1.2272
Cellule BG7 | pour inflation DND | [24 empty] | 9 | Csa Salaries | 29/30 | Csa Salaries - 29/30 |  | 0.82164 | 0.86066 | 0.89079 | 0.91306 | 0.93406 | 0.95554 | 0.97752 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 1.3459 |  | 7 | 1996 | 1.109% | 0.6597 | 0.67278 |  | 27/28 | 2027 | 2.109% | 1.2297 | 1.2528
[26 empty] | 10 | Csa Salaries | 30/31 | Csa Salaries - 30/31 |  | 0.80553 | 0.84379 | 0.87332 | 0.89515 | 0.91574 | 0.9368 | 0.95835 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 |  | 8 | 1997 | 1.1% | 0.66696 | 0.67984 |  | 28/29 | 2028 | 2.109% | 1.2556 | 1.2782
[26 empty] | 11 | Csa Salaries | 31/32 | Csa Salaries - 31/32 |  | 0.78973 | 0.82724 | 0.8562 | 0.8776 | 0.89779 | 0.91843 | 0.93956 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 |  | 9 | 1998 | 1.8% | 0.67896 | 0.69265 |  | 29/30 | 2029 | 2.109% | 1.2821 | 1.3022
[26 empty] | 12 | Csa Salaries | 32/33 | Csa Salaries - 32/33 |  | 0.77425 | 0.81102 | 0.83941 | 0.86039 | 0.88018 | 0.90043 | 0.92114 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 |  | 10 | 1999 | -0.3324% | 0.67671 | 0.69153 |  | 30/31 | 2030 | 2.109% | 1.3091 | 1.3297
[26 empty] | 13 | Csa Salaries | 33/34 | Csa Salaries - 33/34 |  | 0.75906 | 0.79512 | 0.82295 | 0.84352 | 0.86292 | 0.88277 | 0.90307 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 |  | 11 | 2000 | 2.7% | 0.69498 | 0.70759 |  | 31/32 | 2031 | 2.077% | 1.3363 | 1.3574
[26 empty] | 14 | Csa Salaries | 34/35 | Csa Salaries - 34/35 |  | 0.74418 | 0.77953 | 0.80681 | 0.82698 | 0.846 | 0.86546 | 0.88537 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 |  | 12 | 2001 | 4.84% | 0.72861 | 0.73704 |  | 32/33 | 2032 | 2.077% | 1.3641 | 1.3855
[26 empty] | 15 | Csa Salaries | 35/36 | Csa Salaries - 35/36 |  | 0.72959 | 0.76424 | 0.79099 | 0.81077 | 0.82942 | 0.84849 | 0.86801 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 |  | 13 | 2002 | 2.156% | 0.74432 | 0.75155 |  | 33/34 | 2033 | 2.077% | 1.3924 | 1.4142
[26 empty] | 16 | Csa Salaries | 36/37 | Csa Salaries - 36/37 |  | 0.71528 | 0.74926 | 0.77548 | 0.79487 | 0.81315 | 0.83185 | 0.85099 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 |  | 14 | 2003 | -1.334% | 0.73439 | 0.74498 |  | 34/35 | 2034 | 2.077% | 1.4213 | 1.4438
[26 empty] | 17 | Csa Salaries | 37/38 | Csa Salaries - 37/38 |  | 0.70126 | 0.73457 | 0.76028 | 0.77928 | 0.79721 | 0.81554 | 0.8343 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 |  | 15 | 2004 | -1.58% | 0.72279 | 0.73393 |  | 35/36 | 2035 | 2.077% | 1.4509 | 1.4737
[26 empty] | 18 | Csa Salaries | 38/39 | Csa Salaries - 38/39 |  | 0.68751 | 0.72016 | 0.74537 | 0.764 | 0.78158 | 0.79955 | 0.81794 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 |  | 16 | 2005 | 0.05001% | 0.72315 | 0.7342 |  | 36/37 | 2036 | 2.077% | 1.481 | 1.5043
[26 empty] | 19 | Csa Salaries | 39/40 | Csa Salaries - 39/40 |  | 0.67403 | 0.70604 | 0.73076 | 0.74902 | 0.76625 | 0.78388 | 0.8019 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 |  | 17 | 2006 | 0.7365% | 0.72847 | 0.74265 |  | 37/38 | 2037 | 2.077% | 1.5118 | 1.5356
[26 empty] | 20 | Csa Salaries | 40/41 | Csa Salaries - 40/41 |  | 0.66081 | 0.6922 | 0.71643 | 0.73434 | 0.75123 | 0.76851 | 0.78618 | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 |  | 18 | 2007 | 2.466% | 0.74644 | 0.75695 |  | 38/39 | 2038 | 2.077% | 1.5432 | 1.5675
[26 empty] | 21 | Csa Salaries | 41/42 | Csa Salaries - 41/42 |  | 0.64785 | 0.67863 | 0.70238 | 0.71994 | 0.7365 | 0.75344 | 0.77077 | 0.78849 | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 |  | 19 | 2008 | 4.789% | 0.78219 | 0.79016 |  | 39/40 | 2039 | 2.077% | 1.5752 | 1.6
[26 empty] | 22 | CSA Mgt | 22/23 | CSA Mgt - 22/23 |  | 1 | 1.037 | 1.0619 | 1.0852 | 1.107 | 1.1291 | 1.1517 | 1.1747 | 1.1982 | 1.2222 | 1.2466 | 1.2715 | 1.297 | 1.3229 | 1.3494 | 1.3764 | 1.4039 | 1.432 | 1.4606 | 1.4898 |  |  |  |  | 20 | 2009 | 4.071% | 0.81403 | 0.82098 |  | 40/41 | 2040 | 2.077% | 1.608 | 1.6332
[26 empty] | 23 | CSA Mgt | 23/24 | CSA Mgt - 23/24 |  | 0.94056 | 1 | 1.024 | 1.0465 | 1.0675 | 1.0888 | 1.1106 | 1.1328 | 1.1555 | 1.1786 | 1.2021 | 1.2262 | 1.2507 | 1.2757 | 1.3012 | 1.3273 | 1.3538 | 1.3809 | 1.4085 | 1.4367 | 1.4654 | 1.4947 | 1.5246 | 1.5246 | 21 | 2010 | -1.9% | 0.79856 | 0.80576 |  | 41/42 | 2041 | 2.077% | 1.6414 | 1.6671
[26 empty] | 24 | CSA Mgt | 24/25 | CSA Mgt - 24/25 |  | 0.907 | 0.96432 | 1 | 1.022 | 1.0424 | 1.0633 | 1.0846 | 1.1062 | 1.1284 | 1.1509 | 1.174 | 1.1974 | 1.2214 | 1.2458 | 1.2707 | 1.2961 | 1.3221 | 1.3485 | 1.3755 | 1.403 |  |  |  |  | 22 | 2011 | 4.5% | 0.8345 | 0.84054 |  | 42/43 | 2042 | 2.077% | 1.6755 | 1.7018
[26 empty] | 25 | CSA Mgt | 25/26 | CSA Mgt - 25/26 |  | 0.88574 | 0.94172 | 0.97656 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 1.3459 | 1.3728 |  |  |  |  | 23 | 2012 | 1.663% | 0.84838 | 0.85542 |  | 43/44 | 2043 | 2.077% | 1.7103 | 1.7373
[26 empty] | 26 | CSA Mgt | 26/27 | CSA Mgt - 26/27 |  | 0.86667 | 0.92145 | 0.95554 | 0.97847 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 1.3459 |  |  |  |  | 24 | 2013 | 9.075% | 0.92537 | 0.93538 |  | 44/45 | 2044 | 2.077% | 1.7458 | 1.7733
[26 empty] | 27 | CSA Mgt | 27/28 | CSA Mgt - 27/28 |  | 0.84968 | 0.90338 | 0.9368 | 0.95929 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 |  |  |  |  | 25 | 2014 | -3.13% | 0.8964 | 0.90805
[26 empty] | 28 | CSA Mgt | 28/29 | CSA Mgt - 28/29 |  | 0.83302 | 0.88567 | 0.91844 | 0.94048 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 |  |  |  |  | 26 | 2015 | 3.639% | 0.92902 | 0.94018
[26 empty] | 29 | CSA Mgt | 29/30 | CSA Mgt - 29/30 |  | 0.81669 | 0.8683 | 0.90043 | 0.92204 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 |  |  |  |  | 27 | 2016 | 0.4839% | 0.93352 | 0.94593
[26 empty] | 30 | CSA Mgt | 30/31 | CSA Mgt - 30/31 |  | 0.80067 | 0.85127 | 0.88277 | 0.90396 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 |  |  |  |  | 28 | 2017 | 0.3887% | 0.93715 | 0.95381
[26 empty] | 31 | CSA Mgt | 31/32 | CSA Mgt - 31/32 |  | 0.78497 | 0.83458 | 0.86546 | 0.88623 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 |  |  |  |  | 29 | 2018 | 1.381% | 0.95008 | 0.96493
[26 empty] | 32 | CSA Mgt | 32/33 | CSA Mgt - 32/33 |  | 0.76958 | 0.81822 | 0.84849 | 0.86886 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 |  |  |  |  | 30 | 2019 | 2.525% | 0.97407 | 0.99017
[26 empty] | 33 | CSA Mgt | 33/34 | CSA Mgt - 33/34 |  | 0.75449 | 0.80218 | 0.83186 | 0.85182 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 |  |  |  |  | 31 | 2020 | 1.948% | 0.99305 | 1.012
[26 empty] | 34 | CSA Mgt | 34/35 | CSA Mgt - 34/35 |  | 0.7397 | 0.78645 | 0.81554 | 0.83512 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 |  |  |  |  | 32 | 2021 | 0.7% | 1 | 1.0198 | 21/22
[26 empty] | 35 | CSA Mgt | 35/36 | CSA Mgt - 35/36 |  | 0.72519 | 0.77103 | 0.79955 | 0.81874 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 |  |  |  |  | 33 | 2022 | 3.4% | 1.034 | 1.0544 | 22/23
[26 empty] | 36 | CSA Mgt | 36/37 | CSA Mgt - 36/37 |  | 0.71097 | 0.75591 | 0.78388 | 0.80269 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 |  |  |  |  | 34 | 2023 | 6.9% | 1.1053 | 1.1271 | 23/24
[26 empty] | 37 | CSA Mgt | 37/38 | CSA Mgt - 37/38 |  | 0.69703 | 0.74109 | 0.76851 | 0.78695 | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 |  |  |  |  | 35 | 2024 | 4.2% | 1.1518 | 1.1745 | 24/25
[26 empty] | 38 | CSA Mgt | 38/39 | CSA Mgt - 38/39 |  | 0.68337 | 0.72655 | 0.75344 | 0.77152 | 0.78849 | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 |  |  |  |  | 36 | 2025 | 2.4% | 1.1794 | 1.2024 | 25/26
[26 empty] | 39 | CSA Mgt | 39/40 | CSA Mgt - 39/40 |  | 0.66997 | 0.71231 | 0.73866 | 0.75639 | 0.77303 | 0.78849 | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 |  |  |  |  | 37 | 2026 | 2.109% | 1.2043 | 1.2272 | 26/27
[26 empty] | 40 | CSA Mgt | 40/41 | CSA Mgt - 40/41 |  | 0.65683 | 0.69834 | 0.72418 | 0.74156 | 0.75788 | 0.77303 | 0.78849 | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 |  |  |  |  | 38 | 2027 | 2.109% | 1.2297 | 1.2528 | 27/28
[26 empty] | 41 | CSA Mgt | 41/42 | CSA Mgt - 41/42 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  |  |  |  | 39 | 2028 | 2.109% | 1.2556 | 1.2782 | 28/29
[26 empty] | 42 | Contract Labor | 21/22 | Contract Labor - 22/23 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 | 1.5126 | 1.558 | 1.6047 | 1.6528 | 1.7024 | 1.7535 | 1.8061 |  |  |  |  | 40 | 2029 | 2.109% | 1.2821 | 1.3022 | 29/30
[26 empty] | 43 | Contract Labor | 22/23 | Contract Labor - 22/23 | 0.97561 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 | 1.5126 | 1.558 | 1.6047 | 1.6528 | 1.7024 | 1.7535 |  |  |  |  | 41 | 2030 | 2.109% | 1.3091 | 1.3297 | 30/31
[26 empty] | 44 | Contract Labor | 23/24 | Contract Labor - 23/24 | 0.94719 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 | 1.5126 | 1.558 | 1.6047 | 1.6528 | 1.7024 |  |  |  |  | 42 | 2031 | 2.077% | 1.3363 | 1.3574 | 31/32
[26 empty] | 45 | Contract Labor | 24/25 | Contract Labor - 24/25 | 0.91961 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 | 1.5126 | 1.558 | 1.6047 | 1.6528 |  |  |  |  | 43 | 2032 | 2.077% | 1.3641 | 1.3855 | 32/33
[26 empty] | 46 | Contract Labor | 25/26 | Contract Labor - 25/26 | 0.89282 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 | 1.5126 | 1.558 | 1.6047 |  |  |  |  | 44 | 2033 | 2.077% | 1.3924 | 1.4142 | 33/34
[26 empty] | 47 | Contract Labor | 26/27 | Contract Labor - 26/27 | 0.86682 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 | 1.5126 | 1.558 |  |  |  |  | 45 | 2034 | 2.077% | 1.4213 | 1.4438 | 34/35
[26 empty] | 48 | Contract Labor | 27/28 | Contract Labor - 27/28 | 0.84157 | 0.86261 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 | 1.5126 |  |  |  |  | 46 | 2035 | 2.077% | 1.4509 | 1.4737 | 35/36
[26 empty] | 49 | Contract Labor | 28/29 | Contract Labor - 28/29 | 0.81706 | 0.83748 | 0.86261 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 |  |  |  |  | 47 | 2036 | 2.077% | 1.481 | 1.5043 | 36/37
[26 empty] | 50 | Contract Labor | 29/30 | Contract Labor - 29/30 | 0.79326 | 0.81309 | 0.83748 | 0.86261 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 |  |  |  |  | 48 | 2037 | 2.077% | 1.5118 | 1.5356 | 37/38
[26 empty] | 51 | Contract Labor | 30/31 | Contract Labor - 30/31 | 0.77016 | 0.78941 | 0.81309 | 0.83748 | 0.86261 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 |  |  |  |  | 49 | 2038 | 2.077% | 1.5432 | 1.5675 | 38/39
[26 empty] | 52 | Contract Labor | 31/32 | Contract Labor - 31/32 | 0.74772 | 0.76642 | 0.78941 | 0.81309 | 0.83748 | 0.86261 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 |  |  |  |  | 50 | 2039 | 2.077% | 1.5752 | 1.6 | 39/40
[26 empty] | 53 | Contract Labor | 32/33 | Contract Labor - 32/33 | 0.72595 | 0.74409 | 0.76642 | 0.78941 | 0.81309 | 0.83748 | 0.86261 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 |  |  |  |  | 51 | 2040 | 2.077% | 1.608 | 1.6332 | 40/41
[26 empty] | 54 | Contract Labor | 33/34 | Contract Labor - 33/34 | 0.7048 | 0.72242 | 0.74409 | 0.76642 | 0.78941 | 0.81309 | 0.83748 | 0.86261 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 |  |  |  |  | 52 | 2041 | 2.077% | 1.6414 | 1.6671 | 41/42
[26 empty] | 55 | Contract Labor | 34/35 | Contract Labor - 34/35 | 0.68427 | 0.70138 | 0.72242 | 0.74409 | 0.76642 | 0.78941 | 0.81309 | 0.83748 | 0.86261 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 |  |  |  |  | 53 | 2042 | 2.077% | 1.6755 | 1.7018 | 42/43
[26 empty] | 56 | Contract Labor | 35/36 | Contract Labor - 35/36 | 0.66434 | 0.68095 | 0.70138 | 0.72242 | 0.74409 | 0.76642 | 0.78941 | 0.81309 | 0.83748 | 0.86261 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 |  |  |  |  | 54 | 2043 | 2.077% | 1.7103 | 1.7373 | 43/44
[26 empty] | 57 | Contract Labor | 36/37 | Contract Labor - 36/37 | 0.64499 | 0.66112 | 0.68095 | 0.70138 | 0.72242 | 0.74409 | 0.76642 | 0.78941 | 0.81309 | 0.83748 | 0.86261 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 |  |  |  |  | 55 | 2044 | 2.077% | 1.7458 | 1.7733 | 44/45
[26 empty] | 58 | Contract Labor | 37/38 | Contract Labor - 37/38 | 0.62621 | 0.64186 | 0.66112 | 0.68095 | 0.70138 | 0.72242 | 0.74409 | 0.76642 | 0.78941 | 0.81309 | 0.83748 | 0.86261 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 |  |  |  |  | 56 | 2045 | 2.077% | 1.7821 | 1.8101
[26 empty] | 59 | Contract Labor | 38/39 | Contract Labor - 38/39 | 0.60797 | 0.62317 | 0.64186 | 0.66112 | 0.68095 | 0.70138 | 0.72242 | 0.74409 | 0.76642 | 0.78941 | 0.81309 | 0.83748 | 0.86261 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 | 1.0927 |  |  |  |  | 57 | 2046 | 2.077% | 1.8191 | 1.8477
[26 empty] | 60 | Contract Labor | 39/40 | Contract Labor - 39/40 | 0.59026 | 0.60502 | 0.62317 | 0.64186 | 0.66112 | 0.68095 | 0.70138 | 0.72242 | 0.74409 | 0.76642 | 0.78941 | 0.81309 | 0.83748 | 0.86261 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 | 1.0609 |  |  |  |  | 58 | 2047 | 2.077% | 1.8569 | 1.8861
[26 empty] | 61 | Contract Labor | 40/41 | Contract Labor - 40/41 | 0.57307 | 0.58739 | 0.60502 | 0.62317 | 0.64186 | 0.66112 | 0.68095 | 0.70138 | 0.72242 | 0.74409 | 0.76642 | 0.78941 | 0.81309 | 0.83748 | 0.86261 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 | 1.03 |  |  |  |  | 59 | 2048 | 2.077% | 1.8954 | 1.9253
[26 empty] | 62 | Contract Labor | 41/42 | Contract Labor - 41/42 | 0.55638 | 0.57029 | 0.58739 | 0.60502 | 0.62317 | 0.64186 | 0.66112 | 0.68095 | 0.70138 | 0.72242 | 0.74409 | 0.76642 | 0.78941 | 0.81309 | 0.83748 | 0.86261 | 0.88849 | 0.91514 | 0.9426 | 0.97087 | 1 |  |  |  |  | 60 | 2049 | 2.077% | 1.9348 | 1.9652
[26 empty] | 63 | Contract Non Labor | 22/23 | Contract Non Labor - 22/23 |  | 1 | 1.0405 | 1.0665 | 1.0921 | 1.1161 | 1.1406 | 1.1657 | 1.1914 | 1.2176 | 1.2444 | 1.2718 | 1.3005 | 1.3299 | 1.3599 | 1.3906 | 1.422 | 1.4541 | 1.487 | 1.5206 | 1.5549 |  |  |  |  | 61 | 2050 | 2.077% | 1.975 | 2.0061
[26 empty] | 64 | Contract Non Labor | 23/24 | Contract Non Labor - 23/24 |  | 0.9635 | 1 | 1.025 | 1.0496 | 1.0727 | 1.0963 | 1.1204 | 1.1451 | 1.1702 | 1.196 | 1.2223 | 1.2499 | 1.2781 | 1.307 | 1.3365 | 1.3667 | 1.3976 | 1.4292 | 1.4614 | 1.4945 | 1.5282 | 1.5627 | 1.598 | 1.598 | 62 | 2051 | 2.077% | 2.016 | 2.0477
[26 empty] | 65 | Contract Non Labor | 24/25 | Contract Non Labor - 24/25 |  | 0.92603 | 0.96111 | 1 | 1.024 | 1.0465 | 1.0696 | 1.0931 | 1.1171 | 1.1417 | 1.1668 | 1.1925 | 1.2194 | 1.247 | 1.2751 | 1.3039 | 1.3334 | 1.3635 | 1.3943 | 1.4258 | 1.458 |  |  |  |  | 63 | 2052 | 2.077% | 2.0579 | 2.0904
[26 empty] | 66 | Contract Non Labor | 25/26 | Contract Non Labor - 25/26 |  | 0.90344 | 0.93767 | 0.97561 | 1 | 1.022 | 1.0445 | 1.0675 | 1.0909 | 1.1149 | 1.1395 | 1.1645 | 1.1908 | 1.2177 | 1.2453 | 1.2734 | 1.3021 | 1.3316 | 1.3616 | 1.3924 | 1.4238 |  |  |  |  | 64 | 2053 | 2.077% | 2.1007 | 2.1337
[26 empty] | 67 | Contract Non Labor | 26/27 | Contract Non Labor - 26/27 |  | 0.88227 | 0.91569 | 0.95274 | 0.97656 | 1 | 1.022 | 1.0445 | 1.0675 | 1.0909 | 1.1149 | 1.1395 | 1.1652 | 1.1915 | 1.2184 | 1.246 | 1.2741 | 1.3029 | 1.3323 | 1.3624 | 1.3932 |  |  |  |  | 65 | 2054 | 2.077% | 2.1443 | 2.1781
[26 empty] | 68 | Contract Non Labor | 27/28 | Contract Non Labor - 27/28 |  | 0.86328 | 0.89598 | 0.93223 | 0.95554 | 0.97847 | 1 | 1.022 | 1.0445 | 1.0675 | 1.0909 | 1.1149 | 1.1401 | 1.1659 | 1.1922 | 1.2191 | 1.2467 | 1.2748 | 1.3036 | 1.3331 | 1.3632 |  |  |  |  | 66 | 2055 | 2.077% | 2.1888 | 2.2233
[26 empty] | 69 | Contract Non Labor | 28/29 | Contract Non Labor - 28/29 |  | 0.84469 | 0.8767 | 0.91217 | 0.93497 | 0.95741 | 0.97847 | 1 | 1.022 | 1.0445 | 1.0675 | 1.0909 | 1.1156 | 1.1408 | 1.1666 | 1.1929 | 1.2198 | 1.2474 | 1.2756 | 1.3044 | 1.3338 |  |  |  |  | 67 | 2056 | 2.077% | 2.2343 | 2.2695
[26 empty] | 70 | Contract Non Labor | 29/30 | Contract Non Labor - 29/30 |  | 0.82651 | 0.85782 | 0.89253 | 0.91484 | 0.9368 | 0.95741 | 0.97847 | 1 | 1.022 | 1.0445 | 1.0675 | 1.0916 | 1.1162 | 1.1414 | 1.1672 | 1.1936 | 1.2205 | 1.2481 | 1.2763 | 1.3051 |  |  |  |  | 68 | 2057 | 2.077% | 2.2807 | 0
[26 empty] | 71 | Contract Non Labor | 30/31 | Contract Non Labor - 30/31 |  | 0.80872 | 0.83936 | 0.87332 | 0.89515 | 0.91663 | 0.9368 | 0.95741 | 0.97847 | 1 | 1.022 | 1.0445 | 1.0681 | 1.0922 | 1.1169 | 1.1421 | 1.1679 | 1.1943 | 1.2212 | 1.2488 | 1.277 |  |  |  |  | 69 | 2058 | 2.077% | 2.3281 | 0
[26 empty] | 72 | Contract Non Labor | 31/32 | Contract Non Labor - 31/32 |  | 0.79131 | 0.82129 | 0.85452 | 0.87588 | 0.8969 | 0.91663 | 0.9368 | 0.95741 | 0.97847 | 1 | 1.022 | 1.0451 | 1.0687 | 1.0928 | 1.1175 | 1.1428 | 1.1686 | 1.195 | 1.2219 | 1.2495 |  |  |  |  | 70 | 2059 | 2.077% | 2.3765 | 0
[26 empty] | 73 | Contract Non Labor | 32/33 | Contract Non Labor - 32/33 |  | 0.77427 | 0.80361 | 0.83612 | 0.85703 | 0.8776 | 0.8969 | 0.91663 | 0.9368 | 0.95741 | 0.97847 | 1 | 1.0226 | 1.0457 | 1.0693 | 1.0935 | 1.1182 | 1.1434 | 1.1692 | 1.1956 | 1.2227 |  |  |  |  | 71 | 2060 | 2.077% | 2.4258 | 0
[26 empty] | 74 | Contract Non Labor | 33/34 | Contract Non Labor - 33/34 |  | 0.75761 | 0.78631 | 0.81813 | 0.83858 | 0.8587 | 0.8776 | 0.8969 | 0.91663 | 0.9368 | 0.95741 | 0.97847 | 1 | 1.0226 | 1.0457 | 1.0693 | 1.0935 | 1.1182 | 1.1434 | 1.1692 | 1.1956
[26 empty] | 75 | Contract Non Labor | 34/35 | Contract Non Labor - 34/35 |  | 0.74087 | 0.76894 | 0.80005 | 0.82006 | 0.83974 | 0.85821 | 0.87709 | 0.89639 | 0.91611 | 0.93626 | 0.95686 | 0.97791 | 1 | 1.0226 | 1.0457 | 1.0693 | 1.0935 | 1.1182 | 1.1434 | 1.1692
[26 empty] | 76 | Contract Non Labor | 35/36 | Contract Non Labor - 35/36 |  | 0.72451 | 0.75196 | 0.78238 | 0.80194 | 0.82119 | 0.83926 | 0.85772 | 0.87659 | 0.89587 | 0.91558 | 0.93573 | 0.95631 | 0.97791 | 1 | 1.0226 | 1.0457 | 1.0693 | 1.0935 | 1.1182 | 1.1434
[26 empty] | 77 | Contract Non Labor | 36/37 | Contract Non Labor - 36/37 |  | 0.70851 | 0.73535 | 0.7651 | 0.78423 | 0.80305 | 0.82072 | 0.83877 | 0.85723 | 0.87609 | 0.89536 | 0.91506 | 0.93519 | 0.95631 | 0.97791 | 1 | 1.0226 | 1.0457 | 1.0693 | 1.0935 | 1.1182
[26 empty] | 78 | Contract Non Labor | 37/38 | Contract Non Labor - 37/38 |  | 0.69286 | 0.71911 | 0.7482 | 0.76691 | 0.78531 | 0.80259 | 0.82025 | 0.83829 | 0.85673 | 0.87558 | 0.89485 | 0.91453 | 0.93519 | 0.95631 | 0.97791 | 1 | 1.0226 | 1.0457 | 1.0693 | 1.0935
[26 empty] | 79 | Contract Non Labor | 38/39 | Contract Non Labor - 38/39 |  | 0.67755 | 0.70322 | 0.73168 | 0.74997 | 0.76797 | 0.78486 | 0.80213 | 0.81978 | 0.83781 | 0.85624 | 0.87508 | 0.89433 | 0.91453 | 0.93519 | 0.95631 | 0.97791 | 1 | 1.0226 | 1.0457 | 1.0693
[26 empty] | 80 | Contract Non Labor | 39/40 | Contract Non Labor - 39/40 |  | 0.66259 | 0.68769 | 0.71551 | 0.7334 | 0.751 | 0.76753 | 0.78441 | 0.80167 | 0.81931 | 0.83733 | 0.85575 | 0.87458 | 0.89433 | 0.91453 | 0.93519 | 0.95631 | 0.97791 | 1 | 1.0226 | 1.0457
[26 empty] | 81 | Contract Non Labor | 40/41 | Contract Non Labor - 40/41 |  | 0.64795 | 0.6725 | 0.69971 | 0.7172 | 0.73442 | 0.75057 | 0.76709 | 0.78396 | 0.80121 | 0.81883 | 0.83685 | 0.85526 | 0.87458 | 0.89433 | 0.91453 | 0.93519 | 0.95631 | 0.97791 | 1 | 1.0226
[26 empty] | 82 | Contract Non Labor | 41/42 | Contract Non Labor - 41/42 |  | 0.63364 | 0.65765 | 0.68425 | 0.70136 | 0.71819 | 0.73399 | 0.75014 | 0.76664 | 0.78351 | 0.80075 | 0.81836 | 0.83637 | 0.85526 | 0.87458 | 0.89433 | 0.91453 | 0.93519 | 0.95631 | 0.97791 | 1
[26 empty] | 83 | Risk | 22/23 | Risk - 22/23 | bar: 22/23
[26 empty] | 84 | Risk | 23/24 | Risk - 23/24 | 23/24: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 85 | Risk | 24/25 | Risk - 24/25 | 24/25: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 86 | Risk | 25/26 | Risk - 25/26 | 25/26: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 87 | Risk | 26/27 | Risk - 26/27 | 26/27: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 88 | Risk | 27/28 | Risk - 27/28 | 27/28: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 89 | Risk | 28/29 | Risk - 28/29 | 28/29: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 90 | Risk | 29/30 | Risk - 29/30 | 29/30: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 91 | Risk | 30/31 | Risk - 30/31 | 30/31: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 92 | Risk | 31/32 | Risk - 31/32 | 31/32: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 93 | Risk | 32/33 | Risk - 32/33 | 32/33: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 94 | Risk | 33/34 | Risk - 33/34 | 33/34: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 95 | Risk | 34/35 | Risk - 34/35 | 34/35: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 96 | Risk | 35/36 | Risk - 35/36 | 35/36: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 97 | Risk | 36/37 | Risk - 36/37 | 36/37: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 98 | Risk | 37/38 | Risk - 37/38 | 37/38: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 99 | Risk | 38/39 | Risk - 38/39 | 38/39: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 100 | Risk | 39/40 | Risk - 39/40 | 39/40: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 101 | Risk | 40/41 | Risk - 40/41 | 40/41: 1; 42/43: 0; 43/44: 0; 44/45: 0; 45/46: 0
[26 empty] | 102 | Risk | 41/42 | Risk - 41/42 | 41/42: 1; 42/43: 1.03; 43/44: 1.0609; 44/45: 1.0927; 45/46: 1.0927
[26 empty] | 103 | Anaylse de sensibilité 2% | 21/22 | 2% | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 1.3459 | 1.3728 | 1.4002 | 1.4282 | 1.4568 | 1.4859
[26 empty] | 104 | Anaylse de sensibilité 2% | 22/23 |  | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 1.3459 | 1.3728 | 1.4002 | 1.4282 | 1.4568
[26 empty] | 105 | Anaylse de sensibilité 2% | 23/24 |  | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 1.3459 | 1.3728 | 1.4002 | 1.4282
[26 empty] | 106 | Anaylse de sensibilité 2% | 24/25 |  | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 1.3459 | 1.3728 | 1.4002
[26 empty] | 107 | Anaylse de sensibilité 2% | 25/26 |  | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 1.3459 | 1.3728
[26 empty] | 108 | Anaylse de sensibilité 2% | 26/27 |  | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 1.3459
[26 empty] | 109 | Anaylse de sensibilité 2% | 27/28 |  | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195
[26 empty] | 110 | Anaylse de sensibilité 2% | 28/29 |  | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936
[26 empty] | 111 | Anaylse de sensibilité 2% | 29/30 |  | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682
[26 empty] | 112 | Anaylse de sensibilité 2% | 30/31 |  | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434
[26 empty] | 113 | Anaylse de sensibilité 2% | 31/32 |  | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219
[26 empty] | 114 | Anaylse de sensibilité 2% | 32/33 |  | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951
[26 empty] | 115 | Anaylse de sensibilité 2% | 33/34 |  | 0.78849 | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717
[26 empty] | 116 | Anaylse de sensibilité 2% | 34/35 |  | 0.77303 | 0.78849 | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487
[26 empty] | 117 | Anaylse de sensibilité 2% | 35/36 |  | 0.75788 | 0.77303 | 0.78849 | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262
[26 empty] | 118 | Anaylse de sensibilité 2% | 36/37 |  | 0.74301 | 0.75788 | 0.77303 | 0.78849 | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041
[26 empty] | 119 | Anaylse de sensibilité 2% | 37/38 |  | 0.72845 | 0.74301 | 0.75788 | 0.77303 | 0.78849 | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824
[26 empty] | 120 | Anaylse de sensibilité 2% | 38/39 |  | 0.71416 | 0.72845 | 0.74301 | 0.75788 | 0.77303 | 0.78849 | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404 | 1.0612
[26 empty] | 121 | Anaylse de sensibilité 2% | 39/40 |  | 0.70016 | 0.71416 | 0.72845 | 0.74301 | 0.75788 | 0.77303 | 0.78849 | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02 | 1.0404
[26 empty] | 122 | Anaylse de sensibilité 2% | 40/41 |  | 0.68643 | 0.70016 | 0.71416 | 0.72845 | 0.74301 | 0.75788 | 0.77303 | 0.78849 | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1 | 1.02
[26 empty] | 123 | Anaylse de sensibilité 2% | 41/42 |  | 0.67297 | 0.68643 | 0.70016 | 0.71416 | 0.72845 | 0.74301 | 0.75788 | 0.77303 | 0.78849 | 0.80426 | 0.82035 | 0.83676 | 0.85349 | 0.87056 | 0.88797 | 0.90573 | 0.92385 | 0.94232 | 0.96117 | 0.98039 | 1
[26 empty] | 124 | Anaylse de sensibilité 4% | 21/22 | 4% | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686 | 1.4233 | 1.4802 | 1.5395 | 1.601 | 1.6651 | 1.7317 | 1.8009 | 1.873 | 1.9479 | 2.0258 | 2.1068 | 2.1911
[26 empty] | 125 | Anaylse de sensibilité 4% | 22/23 |  | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686 | 1.4233 | 1.4802 | 1.5395 | 1.601 | 1.6651 | 1.7317 | 1.8009 | 1.873 | 1.9479 | 2.0258 | 2.1068
[26 empty] | 126 | Anaylse de sensibilité 4% | 23/24 |  | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686 | 1.4233 | 1.4802 | 1.5395 | 1.601 | 1.6651 | 1.7317 | 1.8009 | 1.873 | 1.9479 | 2.0258
[26 empty] | 127 | Anaylse de sensibilité 4% | 24/25 |  | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686 | 1.4233 | 1.4802 | 1.5395 | 1.601 | 1.6651 | 1.7317 | 1.8009 | 1.873 | 1.9479
[26 empty] | 128 | Anaylse de sensibilité 4% | 25/26 |  | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686 | 1.4233 | 1.4802 | 1.5395 | 1.601 | 1.6651 | 1.7317 | 1.8009 | 1.873
[26 empty] | 129 | Anaylse de sensibilité 4% | 26/27 |  | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686 | 1.4233 | 1.4802 | 1.5395 | 1.601 | 1.6651 | 1.7317 | 1.8009
[26 empty] | 130 | Anaylse de sensibilité 4% | 27/28 |  | 0.79031 | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686 | 1.4233 | 1.4802 | 1.5395 | 1.601 | 1.6651 | 1.7317
[26 empty] | 131 | Anaylse de sensibilité 4% | 28/29 |  | 0.75992 | 0.79031 | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686 | 1.4233 | 1.4802 | 1.5395 | 1.601 | 1.6651
[26 empty] | 132 | Anaylse de sensibilité 4% | 29/30 |  | 0.73069 | 0.75992 | 0.79031 | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686 | 1.4233 | 1.4802 | 1.5395 | 1.601
[26 empty] | 133 | Anaylse de sensibilité 4% | 30/31 |  | 0.70259 | 0.73069 | 0.75992 | 0.79031 | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686 | 1.4233 | 1.4802 | 1.5395
[26 empty] | 134 | Anaylse de sensibilité 4% | 31/32 |  | 0.67556 | 0.70259 | 0.73069 | 0.75992 | 0.79031 | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686 | 1.4233 | 1.4802
[26 empty] | 135 | Anaylse de sensibilité 4% | 32/33 |  | 0.64958 | 0.67556 | 0.70259 | 0.73069 | 0.75992 | 0.79031 | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686 | 1.4233
[26 empty] | 136 | Anaylse de sensibilité 4% | 33/34 |  | 0.6246 | 0.64958 | 0.67556 | 0.70259 | 0.73069 | 0.75992 | 0.79031 | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686
[26 empty] | 137 | Anaylse de sensibilité 4% | 34/35 |  | 0.60057 | 0.6246 | 0.64958 | 0.67556 | 0.70259 | 0.73069 | 0.75992 | 0.79031 | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159
[26 empty] | 138 | Anaylse de sensibilité 4% | 35/36 |  | 0.57748 | 0.60057 | 0.6246 | 0.64958 | 0.67556 | 0.70259 | 0.73069 | 0.75992 | 0.79031 | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653
[26 empty] | 139 | Anaylse de sensibilité 4% | 36/37 |  | 0.55526 | 0.57748 | 0.60057 | 0.6246 | 0.64958 | 0.67556 | 0.70259 | 0.73069 | 0.75992 | 0.79031 | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167
[26 empty] | 140 | Anaylse de sensibilité 4% | 37/38 |  | 0.53391 | 0.55526 | 0.57748 | 0.60057 | 0.6246 | 0.64958 | 0.67556 | 0.70259 | 0.73069 | 0.75992 | 0.79031 | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699
[26 empty] | 141 | Anaylse de sensibilité 4% | 38/39 |  | 0.51337 | 0.53391 | 0.55526 | 0.57748 | 0.60057 | 0.6246 | 0.64958 | 0.67556 | 0.70259 | 0.73069 | 0.75992 | 0.79031 | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816 | 1.1249
[26 empty] | 142 | Anaylse de sensibilité 4% | 39/40 |  | 0.49363 | 0.51337 | 0.53391 | 0.55526 | 0.57748 | 0.60057 | 0.6246 | 0.64958 | 0.67556 | 0.70259 | 0.73069 | 0.75992 | 0.79031 | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04 | 1.0816
[26 empty] | 143 | Anaylse de sensibilité 4% | 40/41 |  | 0.47464 | 0.49363 | 0.51337 | 0.53391 | 0.55526 | 0.57748 | 0.60057 | 0.6246 | 0.64958 | 0.67556 | 0.70259 | 0.73069 | 0.75992 | 0.79031 | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1 | 1.04
[26 empty] | 144 | Anaylse de sensibilité 4% | 41/42 |  | 0.45639 | 0.47464 | 0.49363 | 0.51337 | 0.53391 | 0.55526 | 0.57748 | 0.60057 | 0.6246 | 0.64958 | 0.67556 | 0.70259 | 0.73069 | 0.75992 | 0.79031 | 0.82193 | 0.8548 | 0.889 | 0.92456 | 0.96154 | 1
[26 empty] | 145 | DND Table | 21/22 |  | 1 | 1.034 | 1.1053 | 1.1518 | 1.1794 | 1.2043 | 1.2297 | 1.2556 | 1.2821 | 1.3091 | 1.3363 | 1.3641 | 1.3924 | 1.4213 | 1.4509 | 1.481 | 1.5118 | 1.5432 | 1.5752 | 1.608 | 1.6414
[26 empty] | 146 |  | 22/23 |  | 0.99305 | 1 | 1.069 | 1.1139 | 1.1406 | 1.1647 | 1.1892 | 1.2143 | 1.2399 | 1.2661 | 1.2924 | 1.3192 | 1.3466 | 1.3746 | 1.4032 | 1.4323 | 1.4621 | 1.4924 | 1.5234 | 1.5551 | 1.5874
[26 empty] | 147 |  | 23/24 |  | 0.9604 | 0.96712 | 1 | 1.042 | 1.067 | 1.0895 | 1.1125 | 1.1359 | 1.1599 | 1.1844 | 1.209 | 1.2341 | 1.2597 | 1.2859 | 1.3126 | 1.3399 | 1.3677 | 1.3961 | 1.4251 | 1.4547 | 1.4849
[26 empty] | 148 |  | 24/25 |  | 0.89841 | 0.90469 | 0.93545 | 1 | 1.024 | 1.0456 | 1.0676 | 1.0902 | 1.1132 | 1.1366 | 1.1602 | 1.1843 | 1.2089 | 1.2341 | 1.2597 | 1.2859 | 1.3126 | 1.3398 | 1.3677 | 1.3961 | 1.4251
[26 empty] | 149 |  | 25/26 |  | 0.86219 | 0.86823 | 0.89775 | 0.95969 | 1 | 1.0211 | 1.0426 | 1.0646 | 1.0871 | 1.11 | 1.133 | 1.1566 | 1.1806 | 1.2051 | 1.2302 | 1.2557 | 1.2818 | 1.3084 | 1.3356 | 1.3634 | 1.3917
[26 empty] | 150 |  | 26/27 |  | 0.84199 | 0.84788 | 0.87671 | 0.9372 | 0.97656 | 1 | 1.0211 | 1.0426 | 1.0646 | 1.0871 | 1.1096 | 1.1327 | 1.1562 | 1.1802 | 1.2048 | 1.2298 | 1.2553 | 1.2814 | 1.308 | 1.3352 | 1.3629
[26 empty] | 151 |  | 27/28 |  | 0.8246 | 0.83037 | 0.8586 | 0.91784 | 0.95639 | 0.97935 | 1 | 1.0211 | 1.0426 | 1.0646 | 1.0867 | 1.1093 | 1.1323 | 1.1559 | 1.1799 | 1.2044 | 1.2294 | 1.2549 | 1.281 | 1.3076 | 1.3348
[26 empty] | 152 |  | 28/29 |  | 0.80756 | 0.81322 | 0.84087 | 0.89889 | 0.93664 | 0.95912 | 0.97935 | 1 | 1.0211 | 1.0426 | 1.0643 | 1.0864 | 1.109 | 1.132 | 1.1555 | 1.1795 | 1.204 | 1.229 | 1.2546 | 1.2806 | 1.3072
[26 empty] | 153 |  | 29/30 |  | 0.79089 | 0.79642 | 0.8235 | 0.88032 | 0.9173 | 0.93931 | 0.95912 | 0.97935 | 1 | 1.0211 | 1.0423 | 1.064 | 1.0861 | 1.1086 | 1.1316 | 1.1552 | 1.1791 | 1.2036 | 1.2286 | 1.2542 | 1.2802
[26 empty] | 154 |  | 30/31 |  | 0.77455 | 0.77997 | 0.80649 | 0.86214 | 0.89835 | 0.91991 | 0.93931 | 0.95912 | 0.97935 | 1 | 1.0208 | 1.042 | 1.0636 | 1.0857 | 1.1083 | 1.1313 | 1.1548 | 1.1788 | 1.2033 | 1.2283 | 1.2538
[26 empty] | 155 |  | 31/32 |  | 0.75855 | 0.76386 | 0.78984 | 0.84433 | 0.8798 | 0.90091 | 0.91991 | 0.93931 | 0.95912 | 0.97935 | 1 | 1.0208 | 1.042 | 1.0636 | 1.0857 | 1.1083 | 1.1313 | 1.1548 | 1.1788 | 1.2033 | 1.2283
[26 empty] | 156 |  | 32/33 |  | 0.74312 | 0.74832 | 0.77376 | 0.82715 | 0.86189 | 0.88258 | 0.90119 | 0.9202 | 0.9396 | 0.95942 | 0.97965 | 1 | 1.0208 | 1.042 | 1.0636 | 1.0857 | 1.1083 | 1.1313 | 1.1548 | 1.1788 | 1.2033
[26 empty] | 157 |  | 33/34 |  | 0.72799 | 0.73309 | 0.75802 | 0.81032 | 0.84435 | 0.86462 | 0.88285 | 0.90147 | 0.92048 | 0.93989 | 0.95971 | 0.97965 | 1 | 1.0208 | 1.042 | 1.0636 | 1.0857 | 1.1083 | 1.1313 | 1.1548 | 1.1788
[26 empty] | 158 |  | 34/35 |  | 0.71318 | 0.71817 | 0.74259 | 0.79383 | 0.82717 | 0.84702 | 0.86488 | 0.88312 | 0.90175 | 0.92077 | 0.94018 | 0.95971 | 0.97965 | 1 | 1.0208 | 1.042 | 1.0636 | 1.0857 | 1.1083 | 1.1313 | 1.1548
[26 empty] | 159 |  | 35/36 |  | 0.69867 | 0.70356 | 0.72748 | 0.77767 | 0.81034 | 0.82978 | 0.84728 | 0.86515 | 0.8834 | 0.90203 | 0.92105 | 0.94018 | 0.95971 | 0.97965 | 1 | 1.0208 | 1.042 | 1.0636 | 1.0857 | 1.1083 | 1.1313
[26 empty] | 160 |  | 36/37 |  | 0.68445 | 0.68924 | 0.71267 | 0.76185 | 0.79385 | 0.8129 | 0.83004 | 0.84755 | 0.86542 | 0.88367 | 0.90231 | 0.92105 | 0.94018 | 0.95971 | 0.97965 | 1 | 1.0208 | 1.042 | 1.0636 | 1.0857 | 1.1083
[26 empty] | 161 |  | 37/38 |  | 0.67052 | 0.67521 | 0.69817 | 0.74634 | 0.77769 | 0.79636 | 0.81315 | 0.8303 | 0.84781 | 0.86569 | 0.88394 | 0.90231 | 0.92105 | 0.94018 | 0.95971 | 0.97965 | 1 | 1.0208 | 1.042 | 1.0636 | 1.0857
[26 empty] | 162 |  | 38/39 |  | 0.65687 | 0.66147 | 0.68396 | 0.73116 | 0.76186 | 0.78015 | 0.7966 | 0.8134 | 0.83056 | 0.84807 | 0.86596 | 0.88394 | 0.90231 | 0.92105 | 0.94018 | 0.95971 | 0.97965 | 1 | 1.0208 | 1.042 | 1.0636
[26 empty] | 163 |  | 39/40 |  | 0.64351 | 0.64801 | 0.67004 | 0.71628 | 0.74636 | 0.76427 | 0.78039 | 0.79685 | 0.81365 | 0.83081 | 0.84833 | 0.86596 | 0.88394 | 0.90231 | 0.92105 | 0.94018 | 0.95971 | 0.97965 | 1 | 1.0208 | 1.042
[26 empty] | 164 |  | 40/41 |  | 0.63041 | 0.63482 | 0.65641 | 0.7017 | 0.73117 | 0.74872 | 0.76451 | 0.78063 | 0.7971 | 0.81391 | 0.83107 | 0.84833 | 0.86596 | 0.88394 | 0.90231 | 0.92105 | 0.94018 | 0.95971 | 0.97965 | 1 | 1.0208
[26 empty] | 165 |  | 41/42 |  | 0.61758 | 0.62191 | 0.64305 | 0.68742 | 0.71629 | 0.73348 | 0.74895 | 0.76475 | 0.78087 | 0.79734 | 0.81416 | 0.83107 | 0.84833 | 0.86596 | 0.88394 | 0.90231 | 0.92105 | 0.94018 | 0.95971 | 0.97965 | 1
[26 empty] | 166 | Ground segment | 21/22 |  | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401 | 1.4071 | 1.4775 | 1.5513 | 1.6289 | 1.7103 | 1.7959 | 1.8856 | 1.9799 | 2.0789 | 2.1829 | 2.292 | 2.4066 | 2.527 | 2.6533
[26 empty] | 167 |  | 22/23 |  | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401 | 1.4071 | 1.4775 | 1.5513 | 1.6289 | 1.7103 | 1.7959 | 1.8856 | 1.9799 | 2.0789 | 2.1829 | 2.292 | 2.4066 | 2.527
[26 empty] | 168 |  | 23/24 |  | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401 | 1.4071 | 1.4775 | 1.5513 | 1.6289 | 1.7103 | 1.7959 | 1.8856 | 1.9799 | 2.0789 | 2.1829 | 2.292 | 2.4066
[26 empty] | 169 |  | 24/25 |  | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401 | 1.4071 | 1.4775 | 1.5513 | 1.6289 | 1.7103 | 1.7959 | 1.8856 | 1.9799 | 2.0789 | 2.1829 | 2.292
[26 empty] | 170 |  | 25/26 |  | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401 | 1.4071 | 1.4775 | 1.5513 | 1.6289 | 1.7103 | 1.7959 | 1.8856 | 1.9799 | 2.0789 | 2.1829
[26 empty] | 171 |  | 26/27 |  | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401 | 1.4071 | 1.4775 | 1.5513 | 1.6289 | 1.7103 | 1.7959 | 1.8856 | 1.9799 | 2.0789
[26 empty] | 172 |  | 27/28 |  | 0.74622 | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401 | 1.4071 | 1.4775 | 1.5513 | 1.6289 | 1.7103 | 1.7959 | 1.8856 | 1.9799
[26 empty] | 173 |  | 28/29 |  | 0.71068 | 0.74622 | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401 | 1.4071 | 1.4775 | 1.5513 | 1.6289 | 1.7103 | 1.7959 | 1.8856
[26 empty] | 174 |  | 29/30 |  | 0.67684 | 0.71068 | 0.74622 | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401 | 1.4071 | 1.4775 | 1.5513 | 1.6289 | 1.7103 | 1.7959
[26 empty] | 175 |  | 30/31 |  | 0.64461 | 0.67684 | 0.71068 | 0.74622 | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401 | 1.4071 | 1.4775 | 1.5513 | 1.6289 | 1.7103
[26 empty] | 176 |  | 31/32 |  | 0.61391 | 0.64461 | 0.67684 | 0.71068 | 0.74622 | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401 | 1.4071 | 1.4775 | 1.5513 | 1.6289
[26 empty] | 177 |  | 32/33 |  | 0.58468 | 0.61391 | 0.64461 | 0.67684 | 0.71068 | 0.74622 | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401 | 1.4071 | 1.4775 | 1.5513
[26 empty] | 178 |  | 33/34 |  | 0.55684 | 0.58468 | 0.61391 | 0.64461 | 0.67684 | 0.71068 | 0.74622 | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401 | 1.4071 | 1.4775
[26 empty] | 179 |  | 34/35 |  | 0.53032 | 0.55684 | 0.58468 | 0.61391 | 0.64461 | 0.67684 | 0.71068 | 0.74622 | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401 | 1.4071
[26 empty] | 180 |  | 35/36 |  | 0.50507 | 0.53032 | 0.55684 | 0.58468 | 0.61391 | 0.64461 | 0.67684 | 0.71068 | 0.74622 | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401
[26 empty] | 181 |  | 36/37 |  | 0.48102 | 0.50507 | 0.53032 | 0.55684 | 0.58468 | 0.61391 | 0.64461 | 0.67684 | 0.71068 | 0.74622 | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763
[26 empty] | 182 |  | 37/38 |  | 0.45811 | 0.48102 | 0.50507 | 0.53032 | 0.55684 | 0.58468 | 0.61391 | 0.64461 | 0.67684 | 0.71068 | 0.74622 | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155
[26 empty] | 183 |  | 38/39 |  | 0.4363 | 0.45811 | 0.48102 | 0.50507 | 0.53032 | 0.55684 | 0.58468 | 0.61391 | 0.64461 | 0.67684 | 0.71068 | 0.74622 | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025 | 1.1576
[26 empty] | 184 |  | 39/40 |  | 0.41552 | 0.4363 | 0.45811 | 0.48102 | 0.50507 | 0.53032 | 0.55684 | 0.58468 | 0.61391 | 0.64461 | 0.67684 | 0.71068 | 0.74622 | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05 | 1.1025
[26 empty] | 185 |  | 40/41 |  | 0.39573 | 0.41552 | 0.4363 | 0.45811 | 0.48102 | 0.50507 | 0.53032 | 0.55684 | 0.58468 | 0.61391 | 0.64461 | 0.67684 | 0.71068 | 0.74622 | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1 | 1.05
[26 empty] | 186 |  | 41/42 |  | 0.37689 | 0.39573 | 0.41552 | 0.4363 | 0.45811 | 0.48102 | 0.50507 | 0.53032 | 0.55684 | 0.58468 | 0.61391 | 0.64461 | 0.67684 | 0.71068 | 0.74622 | 0.78353 | 0.8227 | 0.86384 | 0.90703 | 0.95238 | 1
[26 empty] | 187 | 1,5% | 21/22 |  | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934 | 1.1098 | 1.1265 | 1.1434 | 1.1605 | 1.1779 | 1.1956 | 1.2136 | 1.2318 | 1.2502 | 1.269 | 1.288 | 1.3073 | 1.327 | 1.3469 | 1.3671 | 1.3876 | 1.4084 | 1.4084
[26 empty] | 188 |  | 22/23 |  | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934 | 1.1098 | 1.1265 | 1.1434 | 1.1605 | 1.1779 | 1.1956 | 1.2136 | 1.2318 | 1.2502 | 1.269 | 1.288 | 1.3073 | 1.327
[26 empty] | 189 |  | 23/24 |  | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934 | 1.1098 | 1.1265 | 1.1434 | 1.1605 | 1.1779 | 1.1956 | 1.2136 | 1.2318 | 1.2502 | 1.269 | 1.288 | 1.3073
[26 empty] | 190 |  | 24/25 |  | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934 | 1.1098 | 1.1265 | 1.1434 | 1.1605 | 1.1779 | 1.1956 | 1.2136 | 1.2318 | 1.2502 | 1.269 | 1.288
[26 empty] | 191 |  | 25/26 |  | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934 | 1.1098 | 1.1265 | 1.1434 | 1.1605 | 1.1779 | 1.1956 | 1.2136 | 1.2318 | 1.2502 | 1.269
[26 empty] | 192 |  | 26/27 |  | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934 | 1.1098 | 1.1265 | 1.1434 | 1.1605 | 1.1779 | 1.1956 | 1.2136 | 1.2318 | 1.2502
[26 empty] | 193 |  | 27/28 |  | 0.91454 | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934 | 1.1098 | 1.1265 | 1.1434 | 1.1605 | 1.1779 | 1.1956 | 1.2136 | 1.2318
[26 empty] | 194 |  | 28/29 |  | 0.90103 | 0.91454 | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934 | 1.1098 | 1.1265 | 1.1434 | 1.1605 | 1.1779 | 1.1956 | 1.2136
[26 empty] | 195 |  | 29/30 |  | 0.88771 | 0.90103 | 0.91454 | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934 | 1.1098 | 1.1265 | 1.1434 | 1.1605 | 1.1779 | 1.1956
[26 empty] | 196 |  | 30/31 |  | 0.87459 | 0.88771 | 0.90103 | 0.91454 | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934 | 1.1098 | 1.1265 | 1.1434 | 1.1605 | 1.1779
[26 empty] | 197 |  | 31/32 |  | 0.86167 | 0.87459 | 0.88771 | 0.90103 | 0.91454 | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934 | 1.1098 | 1.1265 | 1.1434 | 1.1605
[26 empty] | 198 |  | 32/33 |  | 0.84893 | 0.86167 | 0.87459 | 0.88771 | 0.90103 | 0.91454 | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934 | 1.1098 | 1.1265 | 1.1434
[26 empty] | 199 |  | 33/34 |  | 0.83639 | 0.84893 | 0.86167 | 0.87459 | 0.88771 | 0.90103 | 0.91454 | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934 | 1.1098 | 1.1265
[26 empty] | 200 |  | 34/35 |  | 0.82403 | 0.83639 | 0.84893 | 0.86167 | 0.87459 | 0.88771 | 0.90103 | 0.91454 | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934 | 1.1098
[26 empty] | 201 |  | 35/36 |  | 0.81185 | 0.82403 | 0.83639 | 0.84893 | 0.86167 | 0.87459 | 0.88771 | 0.90103 | 0.91454 | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934
[26 empty] | 202 |  | 36/37 |  | 0.79985 | 0.81185 | 0.82403 | 0.83639 | 0.84893 | 0.86167 | 0.87459 | 0.88771 | 0.90103 | 0.91454 | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773
[26 empty] | 203 |  | 37/38 |  | 0.78803 | 0.79985 | 0.81185 | 0.82403 | 0.83639 | 0.84893 | 0.86167 | 0.87459 | 0.88771 | 0.90103 | 0.91454 | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614
[26 empty] | 204 |  | 38/39 |  | 0.77639 | 0.78803 | 0.79985 | 0.81185 | 0.82403 | 0.83639 | 0.84893 | 0.86167 | 0.87459 | 0.88771 | 0.90103 | 0.91454 | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302 | 1.0457
[26 empty] | 205 |  | 39/40 |  | 0.76491 | 0.77639 | 0.78803 | 0.79985 | 0.81185 | 0.82403 | 0.83639 | 0.84893 | 0.86167 | 0.87459 | 0.88771 | 0.90103 | 0.91454 | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015 | 1.0302
[26 empty] | 206 |  | 40/41 |  | 0.75361 | 0.76491 | 0.77639 | 0.78803 | 0.79985 | 0.81185 | 0.82403 | 0.83639 | 0.84893 | 0.86167 | 0.87459 | 0.88771 | 0.90103 | 0.91454 | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1 | 1.015
[26 empty] | 207 |  | 41/42 |  | 0.74247 | 0.75361 | 0.76491 | 0.77639 | 0.78803 | 0.79985 | 0.81185 | 0.82403 | 0.83639 | 0.84893 | 0.86167 | 0.87459 | 0.88771 | 0.90103 | 0.91454 | 0.92826 | 0.94218 | 0.95632 | 0.97066 | 0.98522 | 1
[26 empty] | 208 | 8% | 21/22 |  | 1 | 1.08 | 1.1664 | 1.2364 | 1.3106 | 1.3892 | 1.4726 | 1.5609 | 1.6546 | 1.7538 | 1.8591 | 1.9706 | 2.0888 | 2.2142 | 2.347 | 2.4878 | 2.6371 | 2.7953 | 2.9631 | 3.1409 | 3.3293
[26 empty] | 209 |  | 22/23 |  | 0.92593 | 1 | 1.08 | 1.1448 | 1.2135 | 1.2863 | 1.3635 | 1.4453 | 1.532 | 1.6239 | 1.7214 | 1.8246 | 1.9341 | 2.0502 | 2.1732 | 2.3036 | 2.4418 | 2.5883 | 2.7436 | 2.9082 | 3.0827
[26 empty] | 210 |  | 23/24 |  | 0.85734 | 0.92593 | 1 | 1.06 | 1.1236 | 1.191 | 1.2625 | 1.3382 | 1.4185 | 1.5036 | 1.5938 | 1.6895 | 1.7908 | 1.8983 | 2.0122 | 2.1329 | 2.2609 | 2.3966 | 2.5404 | 2.6928 | 2.8543
[26 empty] | 211 |  | 24/25 |  | 0.79383 | 0.85734 | 0.92593 | 1 | 1.06 | 1.1236 | 1.191 | 1.2625 | 1.3382 | 1.4185 | 1.5036 | 1.5938 | 1.6895 | 1.7908 | 1.8983 | 2.0122 | 2.1329 | 2.2609 | 2.3966 | 2.5404 | 2.6928
[26 empty] | 212 |  | 25/26 |  | 0.7489 | 0.80881 | 0.87352 | 0.9434 | 1 | 1.06 | 1.1236 | 1.191 | 1.2625 | 1.3382 | 1.4185 | 1.5036 | 1.5938 | 1.6895 | 1.7908 | 1.8983 | 2.0122 | 2.1329 | 2.2609 | 2.3966 | 2.5404
[26 empty] | 213 |  | 26/27 |  | 0.70651 | 0.76303 | 0.82407 | 0.89 | 0.9434 | 1 | 1.06 | 1.1236 | 1.191 | 1.2625 | 1.3382 | 1.4185 | 1.5036 | 1.5938 | 1.6895 | 1.7908 | 1.8983 | 2.0122 | 2.1329 | 2.2609 | 2.3966
[26 empty] | 214 |  | 27/28 |  | 0.66652 | 0.71984 | 0.77743 | 0.83962 | 0.89 | 0.9434 | 1 | 1.06 | 1.1236 | 1.191 | 1.2625 | 1.3382 | 1.4185 | 1.5036 | 1.5938 | 1.6895 | 1.7908 | 1.8983 | 2.0122 | 2.1329 | 2.2609
[26 empty] | 215 |  | 28/29 |  | 0.62879 | 0.67909 | 0.73342 | 0.79209 | 0.83962 | 0.89 | 0.9434 | 1 | 1.06 | 1.1236 | 1.191 | 1.2625 | 1.3382 | 1.4185 | 1.5036 | 1.5938 | 1.6895 | 1.7908 | 1.8983 | 2.0122 | 2.1329
[26 empty] | 216 |  | 29/30 |  | 0.5932 | 0.64065 | 0.69191 | 0.74726 | 0.79209 | 0.83962 | 0.89 | 0.9434 | 1 | 1.06 | 1.1236 | 1.191 | 1.2625 | 1.3382 | 1.4185 | 1.5036 | 1.5938 | 1.6895 | 1.7908 | 1.8983 | 2.0122
[26 empty] | 217 |  | 30/31 |  | 0.55962 | 0.60439 | 0.65274 | 0.70496 | 0.74726 | 0.79209 | 0.83962 | 0.89 | 0.9434 | 1 | 1.06 | 1.1236 | 1.191 | 1.2625 | 1.3382 | 1.4185 | 1.5036 | 1.5938 | 1.6895 | 1.7908 | 1.8983
[26 empty] | 218 |  | 31/32 |  | 0.52794 | 0.57018 | 0.61579 | 0.66506 | 0.70496 | 0.74726 | 0.79209 | 0.83962 | 0.89 | 0.9434 | 1 | 1.06 | 1.1236 | 1.191 | 1.2625 | 1.3382 | 1.4185 | 1.5036 | 1.5938 | 1.6895 | 1.7908
[26 empty] | 219 |  | 32/33 |  | 0.49806 | 0.5379 | 0.58094 | 0.62741 | 0.66506 | 0.70496 | 0.74726 | 0.79209 | 0.83962 | 0.89 | 0.9434 | 1 | 1.06 | 1.1236 | 1.191 | 1.2625 | 1.3382 | 1.4185 | 1.5036 | 1.5938 | 1.6895
[26 empty] | 220 |  | 33/34 |  | 0.46987 | 0.50746 | 0.54805 | 0.5919 | 0.62741 | 0.66506 | 0.70496 | 0.74726 | 0.79209 | 0.83962 | 0.89 | 0.9434 | 1 | 1.06 | 1.1236 | 1.191 | 1.2625 | 1.3382 | 1.4185 | 1.5036 | 1.5938
[26 empty] | 221 |  | 34/35 |  | 0.44327 | 0.47873 | 0.51703 | 0.55839 | 0.5919 | 0.62741 | 0.66506 | 0.70496 | 0.74726 | 0.79209 | 0.83962 | 0.89 | 0.9434 | 1 | 1.06 | 1.1236 | 1.191 | 1.2625 | 1.3382 | 1.4185 | 1.5036
[26 empty] | 222 |  | 35/36 |  | 0.41818 | 0.45164 | 0.48777 | 0.52679 | 0.55839 | 0.5919 | 0.62741 | 0.66506 | 0.70496 | 0.74726 | 0.79209 | 0.83962 | 0.89 | 0.9434 | 1 | 1.06 | 1.1236 | 1.191 | 1.2625 | 1.3382 | 1.4185
[26 empty] | 223 |  | 36/37 |  | 0.39451 | 0.42607 | 0.46016 | 0.49697 | 0.52679 | 0.55839 | 0.5919 | 0.62741 | 0.66506 | 0.70496 | 0.74726 | 0.79209 | 0.83962 | 0.89 | 0.9434 | 1 | 1.06 | 1.1236 | 1.191 | 1.2625 | 1.3382
[26 empty] | 224 |  | 37/38 |  | 0.37218 | 0.40195 | 0.43411 | 0.46884 | 0.49697 | 0.52679 | 0.55839 | 0.5919 | 0.62741 | 0.66506 | 0.70496 | 0.74726 | 0.79209 | 0.83962 | 0.89 | 0.9434 | 1 | 1.06 | 1.1236 | 1.191 | 1.2625
[26 empty] | 225 |  | 38/39 |  | 0.35111 | 0.3792 | 0.40954 | 0.4423 | 0.46884 | 0.49697 | 0.52679 | 0.55839 | 0.5919 | 0.62741 | 0.66506 | 0.70496 | 0.74726 | 0.79209 | 0.83962 | 0.89 | 0.9434 | 1 | 1.06 | 1.1236 | 1.191
[26 empty] | 226 |  | 39/40 |  | 0.33124 | 0.35774 | 0.38636 | 0.41727 | 0.4423 | 0.46884 | 0.49697 | 0.52679 | 0.55839 | 0.5919 | 0.62741 | 0.66506 | 0.70496 | 0.74726 | 0.79209 | 0.83962 | 0.89 | 0.9434 | 1 | 1.06 | 1.1236
[26 empty] | 227 |  | 40/41 |  | 0.31249 | 0.33749 | 0.36449 | 0.39365 | 0.41727 | 0.4423 | 0.46884 | 0.49697 | 0.52679 | 0.55839 | 0.5919 | 0.62741 | 0.66506 | 0.70496 | 0.74726 | 0.79209 | 0.83962 | 0.89 | 0.9434 | 1 | 1.06
[26 empty] | 228 |  | 41/42 |  | 0.2948 | 0.31839 | 0.34386 | 0.37136 | 0.39365 | 0.41727 | 0.4423 | 0.46884 | 0.49697 | 0.52679 | 0.55839 | 0.5919 | 0.62741 | 0.66506 | 0.70496 | 0.74726 | 0.79209 | 0.83962 | 0.89 | 0.9434 | 1
[26 empty] | 229 | DND BASE YEAR 2021 | 21/22 |  | 1.0198 | 1.0544 | 1.1271 | 1.1745 | 1.2024 | 1.2272 | 1.2528 | 1.2782 | 1.3022 | 1.3297 | 1.3574 | 1.3855 | 1.4142 | 1.4438 | 1.4737 | 1.5043 | 1.5356 | 1.5675 | 1.6 | 1.6332 | 1.6332

## 16 - Math Models
` Table of Contents
17 - CER
Why we we asking:
Adds traceability of SW tools used and their versions
which Tools, which versions
Which compensation algorithms
NICM vrsion6 with Canadian compensation for TRL
PCEC v 8 Avec

## 17 - Neighbors
` Table of Contents
18 - Description of Legacy or Smilar Systems (Nearest Neighbors)
Why we we asking:
used in analogy
Description of Legacy or Similar Systems for comparison by analogy
and how do they compare?

## 18 - Cost Density Curve
` Table of Contents
18. Cost Density Curve
Why we we asking:
this is a utility function that help you find an optimal cashflow profile.
you can then use this to negotiate a basis of payment that follows earned value
|  | Start | End | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060
| PREP1 | 2024-01-01 | 2024-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9918 | 9.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PREP2 | 2025-01-01 | 2025-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9589 | 9.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase 0 | 2026-01-01 | 2027-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9589 | 12 | 9.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase A | 2028-01-01 | 2029-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9918 | 12 | 9.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase B | 2030-01-01 | 2031-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9589 | 12 | 9.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase C | 2032-01-01 | 2033-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9918 | 12 | 9.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| MAIT | 2034-01-01 | 2038-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9589 | 12 | 12.0329 | 12 | 12 | 2.9918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SAIT | 2038-07-01 | 2040-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.0082 | 12.0329 | 6.0164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LEOP | 2040-10-01 | 2040-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase E | 2041-01-01 | 2055-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9589 | 12 | 12 | 12.0329 | 12 | 12 | 12 | 12.0329 | 12 | 12 | 12 | 12.0329 | 12 | 12 | 12
| Phase X | 2056-01-01 | 2059-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Amount |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060
| Oversight | 11000000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92679.2735 | 375865.9427 | 376895.7124 | 375865.9427 | 375865.9427 | 375865.9427 | 376895.7124 | 375865.9427 | 375865.9427 | 375865.9427 | 376895.7124 | 375865.9427 | 375865.9427 | 375865.9427 | 376895.7124 | 375865.9427 | 375865.9427 | 375865.9427 | 376895.7124 | 375865.9427 | 375865.9427 | 375865.9427 | 376895.7124 | 375865.9427 | 375865.9427 | 375865.9427 | 376895.7124 | 375865.9427 | 375865.9427 | 375865.9427 | 0 | 0 | 0 | 0 | 0 | Total Months | 351.189
| Partner & Overhead Coordination | 7000000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58977.7195 | 239187.4181 | 239842.7261 | 239187.4181 | 239187.4181 | 239187.4181 | 239842.7261 | 239187.4181 | 239187.4181 | 239187.4181 | 239842.7261 | 239187.4181 | 239187.4181 | 239187.4181 | 239842.7261 | 239187.4181 | 239187.4181 | 239187.4181 | 239842.7261 | 239187.4181 | 239187.4181 | 239187.4181 | 239842.7261 | 239187.4181 | 239187.4181 | 239187.4181 | 239842.7261 | 239187.4181 | 239187.4181 | 239187.4181 | 0 | 0 | 0 | 0 | 0 | Total Months | 351.189
| Mission SEITPM | 19000000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 585215.6057 | 2373374.4011 | 2379876.7967 | 2373374.4011 | 2373374.4011 | 2373374.4011 | 2379876.7967 | 2373374.4011 | 1788158.7953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Months | 96.0658
| Instrument Suite | 155000000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5659229.2089 | 22951318.4584 | 23014198.783 | 22951318.4584 | 22951318.4584 | 22951318.4584 | 23014198.783 | 11507099.3915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Months | 81.0411
| Host-Orbiter Interface Coordination | 9000000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261037.7054 | 1058652.9165 | 1061553.3355 | 1058652.9165 | 1058652.9165 | 1058652.9165 | 1061553.3355 | 1058652.9165 | 1058652.9165 | 263938.1244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Months | 102.0164
| Ground Segment | 13000000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152582.1596 | 618805.4251 | 620500.7825 | 618805.4251 | 618805.4251 | 618805.4251 | 620500.7825 | 462832.5509 | 618805.4251 | 618805.4251 | 620500.7825 | 618805.4251 | 618805.4251 | 618805.4251 | 620500.7825 | 618805.4251 | 618805.4251 | 618805.4251 | 620500.7825 | 618805.4251 | 618805.4251 | 618805.4251 | 0 | 0 | 0 | 0 | 0 | Total Months | 252.0986
| Ops Segment | 34000000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1168649.6695 | 2343720.491 | 2343720.491 | 2350141.6431 | 2343720.491 | 2343720.491 | 2343720.491 | 2350141.6431 | 2343720.491 | 2343720.491 | 2343720.491 | 2350141.6431 | 2343720.491 | 2343720.491 | 2343720.491 | 0 | 0 | 0 | 0 | 0 | Total Months | 174.0822
| Science Segment | 16000000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177230.7692 | 718769.2308 | 720738.4615 | 718769.2308 | 718769.2308 | 718769.2308 | 720738.4615 | 718769.2308 | 541538.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 177230.7692 | 718769.2308 | 718769.2308 | 720738.4615 | 718769.2308 | 718769.2308 | 718769.2308 | 720738.4615 | 718769.2308 | 718769.2308 | 718769.2308 | 720738.4615 | 718769.2308 | 718769.2308 | 718769.2308 | 0 | 0 | 0 | 0 | 0 | Total Months | 267.1233
ORCA Cost Density Profile - derived from segment amounts, shapes and Scenario 1 phasing
| Fiscal Year | Annual Cost ($M) | Cumulative ($M)
| 2015 | 0 | 0
| 2016 | 0 | 0
| 2017 | 0 | 0
| 2018 | 0 | 0
| 2019 | 0 | 0
| 2020 | 0 | 0
| 2021 | 0 | 0
| 2022 | 0 | 0
| 2023 | 0 | 0
| 2024 | 0 | 0
| 2025 | 0 | 0
| 2026 | 0.9141 | 0.9141
| 2027 | 3.7072 | 4.6213
| 2028 | 3.7174 | 8.3387
| 2029 | 3.7072 | 12.0459
| 2030 | 3.9682 | 16.0141
| 2031 | 4.7658 | 20.7799
| 2032 | 4.7789 | 25.5588
| 2033 | 4.7658 | 30.3247
| 2034 | 9.8152 | 40.1399
| 2035 | 25.2438 | 65.3837
| 2036 | 25.313 | 90.6967
| 2037 | 25.2438 | 115.9406
| 2038 | 25.2438 | 141.1844
| 2039 | 24.4491 | 165.6335
| 2040 | 24.2514 | 189.8849
| 2041 | 13.9309 | 203.8158
| 2042 | 4.2963 | 208.1122
| 2043 | 4.2963 | 212.4085
| 2044 | 4.3081 | 216.7166
| 2045 | 4.2963 | 221.013
| 2046 | 4.2963 | 225.3093
| 2047 | 4.2963 | 229.6057
| 2048 | 4.3081 | 233.9138
| 2049 | 4.2963 | 238.2101
| 2050 | 4.2963 | 242.5065
| 2051 | 4.2963 | 246.8028
| 2052 | 4.3081 | 251.111
| 2053 | 4.2963 | 255.4073
| 2054 | 4.2963 | 259.7037
| 2055 | 4.2963 | 264
| 2056 | 0 | 264
| 2057 | 0 | 264
| 2058 | 0 | 264
| 2059 | 0 | 264
| 2060 | 0 | 264

## 19 - Jobs
` Table of Contents
20 - Value Chain
Why we we asking:
to calculate jobs created
Yes - ORCA is estimated to create ~2,326 direct job-years and ~5,047 total job-years (direct + indirect, leverage K=2.17) across the Canadian space sector and academia, concentrated in instrument-suite manufacturing (Northstar / Aetheris / Polarion) and university research. Estimate below (all figures fake).
The following table is an input form the Economic modelling
|  | PREP 1 | PREP 2 | Phase 0 | Phase A | Phase B | Phase C | Phase D1 | Phase D2 | LEOP | Phase E (Nominal) | Phase E (EXT) | Phase F | Phase G
| Oversight | no economic value
| Overhead | Services not in space sector except space consultants
| Mission SEITPM | Industrial R&D and consulting | [12 empty] | R&D Jobs Model | Leveraged Ratio | Unleveraged Ratio | LTIP Model (Old Model)
| Space Segment | Industrial R&D & consulting |  |  |  | Space System Manufacturing | [8 empty] | Ground Systems Manufacturing | 2.5376e-05 | 7.2764e-06 | 3.74e-06
| Launch Segment | [8 empty] | no economic value, except launch integration contract |  |  |  |  | Space Systems Manufacturing | 9.4968e-06 | 7.6984e-06
| Ground Segment | Industrial R&D & consulting |  |  |  | GS manufacturing | [8 empty] | Research, Engineering and Consulting Services | 7.5586e-06 | 6.3699e-06 | 7.51e-06
| Ops Segment | [9 empty] | Services |  |  |  | Satellite Operations | 1.0305e-05 | 2.2753e-06 | 5.6e-07
| Science Segment | Academic R&D | [12 empty] | Services | 1.6102e-05 | 6.9867e-06 | 3.78e-06
[15 empty] | Value-Added Products and Applications | 1.6094e-05 | 4.0556e-06 | 1.95e-06
[15 empty] | Universities - Research, Engineering, and Consulting | 4.811e-05 | 4.811e-05
Jobs Created - ORCA (fake estimate)
| Segment | Economic Category | Spend ($M) | Job Factor (jobs / $1M) | Direct Job-Years | Notes
| Oversight | No economic impact | 11 | 0 | 0 | CSA governance - no external job value
| Partner & Overhead Coordination | Services not in space sector | 7 | 0 | 0 | MOU coordination with NASA/ESA/COSD/CSEO/NARD - no direct industrial spend
| Mission SEITPM | Industrial R&D & consulting | 19 | 6.37 | 121 | Prime/engineering (Asterion)
| Instrument Suite | Space systems manufacturing | 155 | 7.7 | 1194 | Radar, sampling arm, avionics (Northstar/Aetheris/Polarion) | [8 empty] | Label | Factors | ratio of employee/$ | Employee / 1M$
| Host-Orbiter Interface Coordination | Research, engineering & consulting | 9 | 7.56 | 68 | ICD verification and integration engineering with the NEREID orbiter (NASA/ESA) | [8 empty] | Academic R&D | ratio1 | 4.811e-05 | 48.11
| Ground Segment | Ground systems manufacturing | 13 | 7.28 | 95 | Meridian Ground Technologies | [8 empty] | Industrial R&D | ratio2 | 6.3699e-06 | 6.3699
| Ops Segment | Satellite operations | 34 | 2.28 | 78 | CSA MOC operations, Phase E-X | [8 empty] | Industrial R&D (Leveraged) | ratio3 | 7.5586e-06 | 7.5586
| Science Segment | Academic R&D | 16 | 48.11 | 770 | Universities (Northern Institute, Laurentia, Boreal) | [8 empty] | Space Systems Manufacturing | ratio4 | 7.6984e-06 | 7.6984
| Total Direct Job-Years |  |  |  | 2326 | [9 empty] | Space Systems Manufacturing (Leveraged) | ratio5 | 9.4968e-06 | 9.4968
| Total Jobs Multiplier (K) |  |  |  | 2.17 | [9 empty] | Ground Segment Manufacturing | ratio6 | 7.2764e-06 | 7.2764
| Total Job-Years (Direct + Indirect) |  |  |  | 5047.42 | [9 empty] | Ground Segment Manufacturing (Leveraged) | ratio7 | 2.5376e-05 | 25.3764 | <--- impressive number.
[15 empty] | SatOps | ratio8 | 2.2753e-06 | 2.2753
[15 empty] | SatOps (Leveraged) | ratio9 | 1.0305e-05 | 10.3047
[15 empty] | Services | ratio10 | 6.9867e-06 | 6.9867
[15 empty] | Services (Leveraged) | ratio11 | 1.6102e-05 | 16.102
[15 empty] | Products & Apps | ratio12 | 4.0556e-06 | 4.0556
[15 empty] | Products & Apps (Leveraged) | ratio13 | 1.6094e-05 | 16.0943 | <-- G&C versus O&M creates 4 times more jobs when writing software. One is for-profit and the other for govt needs.
[15 empty] | No Economic Impact | ratio14 | 0 | 0
[15 empty] | Services Not in Space Sector | ratio15 | 0 | 0
[15 empty] | Mission Operations | ratio 16 | 4.0556e-06 | 4.0556 | <--- using Value added products and application rather than standard SatOps ratios
[15 empty] | Ratio of Total Jobs / Direct Jobs | K | 2.17

## 20 - Lessons Learned
` Table of Contents
21 - Costing Lessons Learned
Why we we asking:
What previous lessons did we learn and apply here? | Applied lessons from prior CSA robotics/servicing costing: budget long-lead space-robotics items early, size autonomy software with a dedicated CER, and carry FX contingency on foreign launch/components.
What new lessons did we learn by doing this? | New lessons are captured below - chiefly that outer-planet instrument missions lack mature cost analogues and that disposal-phase (Phase X) duration is a major cost sensitivity.
|  | ID | Category | Title | Description of Driving Event | Lesson Learned | Corrective Action or Recommendation
|  | LL-01 | Schedule | Long-lead sampling-arm hardware | Sampling-arm end-effector actuators (Aetheris) drove the Phase C/D critical path. | Long-lead sampling-arm items must be identified and ordered before CDR. | Add an advance-procurement line at PDR and carry schedule margin in Phase C.
|  | LL-02 | Cost / RAM | Instrument autonomy software effort underestimated | Flight-software and autonomy scope grew beyond the RAM baseline. | Autonomous instrument-sequencing software is a major cost driver, not a minor line. | Size software with a dedicated CER and a 20% reserve; run agile with EVM.
|  | LL-03 | Procurement | Sole-source sampling-arm supplier | Limited domestic competition for instrument accommodation (near-incumbent Aetheris). | Sole-source premiums must be budgeted and justified early. | Run an RFI in Phase 0; negotiate open-book pricing for the directed contract.
|  | LL-04 | Estimating | Few outer-planet instrument-suite analogues | Outer-planet flagship instrument contributions lack mature parametric cost analogues. | Deep-space instrument missions need bottom-up estimates plus expert judgment. | Build a calibrated CER set and document analogy adjustments in Part B.
|  | LL-05 | Schedule / Ops | Phase X duration uncertainty | Extended ops plus disposal (Phase X) has wide uncertainty. | Disposal-phase duration and cost are highly sensitive to extended-mission scope. | Model Phase X in all three schedule scenarios; tie ops cost to science-pass count.
|  | LL-06 | Risk | FX exposure on instrument hardware | USD exposure on the sampling-arm and avionics procurements (Aetheris, Polarion). | Currency risk on foreign-sourced components can move the estimate materially. | Carry the FX assumption in Constants and hold FX contingency in the risk reserve.
|  | LL-07 | Governance | IGMF gate re-mapping | Removing Phase F/G and adding Phase X required re-mapping the IGMF gates. | Non-standard phasing must be reconciled with IGMF gate nomenclature early. | Document the phase-to-gate mapping in Part D 8 before dating milestones.
|  | LL-08 | Staffing | Scarce space-robotics talent | Recruitment of GNC/robotics specialists lagged the RAM plan. | Specialist availability constrains schedule as much as funding does. | Start recruitment and knowledge transfer in Phase B; budget training.