CADRe Part A • VCS

Mission Cost Analysis Directorate

Cost Analysis Data Requirements

PART A

Velun Coma Surveyor

Planning baseline  •  Revision 1.0  •  23 September 2026

This mission and all named organizations and individuals are fictional.

Revision History

| Rev. | Description | Prepared by | Date |
| --- | --- | --- | --- |
| 1.0 | Template aligned mission concept | Mission Cost Analysis Directorate | 23 Sep 2026 |

Table of Contents

1	Introduction

1.1	Purpose of this document

2	General Descriptive Information

2.1	Mission Overview

2.2	Strategic Objectives

2.3	Selected Mission Requirements

2.4	High-Level Mission Architecture

3	Space Segment Description

3.1	Spacecraft Bus

3.2	Payload

4	Launch Segment Description

5	Ground Segment and Mission Operations

6	Systems Engineering and Project Management Approach

6.1	TRL Levels and Heritage

6.2	Phasing Logic and Naming Conventions

6.3	Project Milestones

6.4	Safety and Mission Assurance

6.5	Prototyping Model Philosophy Qualification and Verification Strategy

6.6	Sparing Strategy

6.7	Risk Assessment

6.8	Organizational Breakdown Structure

List of Figures

Figure 1 – Velun Coma Surveyor mission architecture

Figure 2 – Payload measurement and data path

List of Tables

Table 1 – Strategic Alignment

Table 2 – Selected System Requirements

Table 3 – Costing Phase Crosswalk

Table 4 – Planning Phase Dates

Table 5 – Major Milestones

Table 6 – Mission Organizations

Table 7 – Industrial Partners

Table 8 – Research Institutions

Table 9 – Scientific Leadership

# Introduction

## Purpose of this document

CADRe Part A provides a concise, standardized synopsis of the mission to support cost analysis. It consolidates the mission objectives, system requirements, architecture, delivery boundaries, operations, verification strategy, schedule and participating organizations.

The quantitative values are planning requirements or preliminary allocations. CADRe Part B records cost element parameters, Part C controls the phase schedule and risk register, and Part D records programmatic evidence.

# General Descriptive Information

## Mission Overview

The reference configuration is single flyby spacecraft. Its operational environment is Reference target distance 2.2 AU; closest approach 1,200 ±200 km; relative velocity 6 ±1 km/s. The nominal duration is 48-month cruise, 6-month approach, 36-hour flyby, 6-month downlink and closeout. The flight or installed unit is sized at 650 kg and uses 3150 W power generation or host allocation as stated in the subsystem budget.

The design carries imaging spectrometer, neutral gas mass spectrometer and dust impact analyser. Each produces a separately calibrated record with common time, configuration and quality metadata. The science objectives are quantified in the requirement matrix below.

Figure 1 – Velun Coma Surveyor mission architecture. Labeled boxes identify responsibility boundaries; dimensions are schematic.

## Strategic Objectives

The mission aligns the measurement or service objectives with the sponsoring authority’s stated science, capability and operations priorities.

Table 1 – Strategic Alignment

| Priority | Strategic goal | Mission contribution |
| --- | --- | --- |
| 1 | Primary mission outcome | Estimate gas-production rate to ±20% during encounter, derive dust size distribution over 1–100 µm, and map sunlit surface thermal variation at ≤100 m/pixel near closest approach. |
| 2 | Operational sustainability | Deliver 48-month cruise, 6-month approach, 36-hour flyby, 6-month downlink and closeout. with independently accepted baseline products and contingency procedures. |

## Selected Mission Requirements

The following selected requirements control the major cost and complexity drivers. Their verification methods and approved values belong in the controlled requirements baseline.

Table 2 – Selected System Requirements

| Cost and complexity driver | Preliminary requirement | Principal cost or complexity effect |
| --- | --- | --- |
| Mission architecture | Single flyby spacecraft; 1 unit(s). | Flight hardware allocation, interface control and acceptance testing. |
| Operating environment | Reference target distance 2.2 AU; closest approach 1,200 ±200 km; relative velocity 6 ±1 km/s. | Propellant, navigation, flight dynamics and delivery accuracy. |
| Mission duration | 48-month cruise, 6-month approach, 36-hour flyby, 6-month downlink and closeout. | Recorder capacity, RF equipment, ground contacts and archive processing. |
| Unit mass | ≤650 kg as delivered or at launch, including the budgeted contents. | Launch capacity, structure, separation hardware and qualification loads. |
| Payload allocation | ≤86 kg, with definitions controlled by the mass table. | Launch capacity, structure, separation hardware and qualification loads. |
| Power generation / provision | 3150 W at specified reference; nominal 410 W and peak 720 W. | Generation, storage, power distribution, thermal rejection and eclipse margin. |
| Primary measurement | Estimate gas-production rate to ±20% during encounter, derive dust size distribution over 1–100 µm, and map sunlit surface thermal variation at ≤100 m/pixel near closest approach. | Thermal hardware, environmental test and calibration stability. |
| Instrument 1 | 37 kg / 145 W; 0.45–4.0 µm, 180 spectral channels; ≤100 m/pixel at 1,200 km requires ≤83 µrad IFOV. | Flight hardware allocation, interface control and acceptance testing. |
| Instrument 2 | 24 kg / 110 W; 1–100 u mass range at ≤1 u resolution; 1–10 s sample time through approach. | Launch capacity, structure, separation hardware and qualification loads. |
| Instrument 3 | 25 kg / 90 W; 0.05 m² target; 1–100 µm grains for calibrated 2–20 km/s impact range. | Flight hardware allocation, interface control and acceptance testing. |
| Pointing or positioning | Dual star trackers, four wheels and inertial unit; encounter pointing ≤0.03° and knowledge ≤0.01° at 95% confidence, with autonomous target tracking. | Flight hardware allocation, interface control and acceptance testing. |
| Mission-data volume | 20 GB encounter burst; ≤1 GB/day in cruise | Launch capacity, structure, separation hardware and qualification loads. |

## High-Level Mission Architecture

The architecture separates oversight, space or deployed hardware, launch or delivery, ground services, operations and science or user exploitation.

Tharven Planetary Office owns system requirements, procurement, risk and mission acceptance.

Aruvell Interplanetary Systems owns the integrated unit, interfaces and system-level verification.

Fesrane Spectral Laboratories delivers the measurement equipment and calibration evidence.

Pellorin Launch Union delivers the unit to its destination and verifies interface conditions.

Suvranel Signal Network supplies receiving, networking and ground-service capacity.

Kelruna Volatiles Institute produces, validates and archives the calibrated mission products.

# Space Segment Description

The reference configuration is single flyby spacecraft. Its operational environment is Reference target distance 2.2 AU; closest approach 1,200 ±200 km; relative velocity 6 ±1 km/s. The nominal duration is 48-month cruise, 6-month approach, 36-hour flyby, 6-month downlink and closeout. The flight or installed unit is sized at 650 kg and uses 3150 W power generation or host allocation as stated in the subsystem budget. The segment boundary includes the integrated unit and its mission-specific payload, interfaces, spares and verification articles.

## Spacecraft Bus

The integrated unit provides structural restraint, power, command and data handling, thermal protection, equipment control and the communication interface appropriate to Reference target distance 2.2 AU; closest approach 1,200 ±200 km; relative velocity 6 ±1 km/s. The design shall carry configuration identifiers and independent acceptance records for every delivered unit.

| Parameter | Preliminary allocation / target |
| --- | --- |
| Unit mass | 650 kg |
| Mass composition | 464 kg dry bus + 86 kg payload + 100 kg initial propellant = 650 kg |
| Payload / experiment allocation | 86 kg |
| Generation / provision | 3150 W reference |
| Nominal / peak demand | 410 W / 720 W |
| Storage | 2 TB usable |
| Autonomy | ≥72 h safe configuration with applicable external power |
| Maneuver / mobility | ≥320 m/s; 100 kg propellant at 225 s and initial mass 650 kg gives ~368 m/s ideal |
| Delivery | C3 ≥18 km²/s²; 650 kg spacecraft + 110 kg adaptor = 760 kg; capacity ≥900 kg to injection |
| Design life | 48-month cruise, 6-month approach, 36-hour flyby, 6-month downlink and closeout. |

### Structural Subsystem

The structural design is sized for 650 kg delivery mass and the qualified interface loads. The launch or cargo provider controls final vibration, shock and handling cases; a 6 g axial and 2 g lateral quasi-static concept check is retained until that interface is defined. Enclosures, hinges, restraints and contained fluids receive separate local load paths.

The configuration model records mass properties, lifting points, contamination boundaries, access envelopes and center of gravity before acceptance. Instrument alignment and enclosure sealing are measured before and after environmental testing. The project shall document whether the delivery carrier, lander or host provides final restraint hardware.

### Electrical Power Subsystem

Nominal allocation: 3150 W generation or host provision, 410 W operating demand, 720 W short-duration peak. These values describe distinct operating cases. The system power margin is assessed at the worst insolation, eclipse or host-service case, not by comparing only nameplate generation and nominal demand.

Power distribution uses protected 28 V or the host-qualified equivalent. Independent current telemetry and latching protection isolate a failed load. Battery or host reserve is sized from the longest commanded safe-mode, transfer, eclipse or night interval rather than from an arbitrary percentage of nominal energy.

| Reference generation | Distribution and storage | Protected loads |
| --- | --- | --- |
| 3150 W baseline | Regulated bus, protected battery/host service | 410 W nominal / 720 W peak |

### Command and Data Handling

A redundant or monitored controller executes time-tagged operations, instrument interlocks, fault detection and protected storage. The local allocation is 2 TB usable. A storage analysis includes the worst observation burst, delayed contact, software overhead, file-system reserve and corrected-memory events.

Every science record carries absolute time, equipment serial number, calibration-set ID, operating mode and validity flags. Loss of link initiates a controlled safe state that preserves source data and performs scheduled reacquisition. A corrupted parameter upload must not silently change instrument calibration or safety limits.

Flight and process software controls the following functions:

receive and execute authorized commands;

collect health telemetry and time-correlated payload packets;

manage 2 TB usable storage and priority records;

switch to a safe mode after undervoltage, overtemperature or watchdog failure;

retain the last accepted software and configuration baseline;

reacquire the ground or host link after a missed contact; and

report data quality and calibration status with each product.

A mission-data model checks the 20 GB encounter burst; ≤1 GB/day in cruise planning case against memory capacity, contact availability and the required processing latency. Raw records are retained until integrity checks and ingest acknowledgement complete.

### Thermal Subsystem

12 m² arrays produce ~3.15 kW EOL at 1 AU and ~651 W at 2.2 AU; nominal encounter load constrained to ≤410 W.

The thermal design shall close with numerical hot and cold cases and shall separately report radiator, insulation, heater and sensor allocations. Instrument calibration is repeated across the qualified operating temperature range. Safe-mode heating and peak-mode waste heat are independently assessed.

Thermal verification considers heat from 720 W peak electrical input, the nominal 410 W mode, external heat flux, enclosure conduction and the passive or active rejection path. The final instrument uncertainty budget includes temperature-driven bias and gradients.

The thermal test programme shall establish:

steady and transient operating limits of each component;

heater and cooler demand in cold and hot cases;

radiator or host heat-rejection sizing;

calibration stability across the qualified temperature range; and

safe survival during a commanded outage.

### Attitude Determination and Control Subsystem

Dual star trackers, four wheels and inertial unit; encounter pointing ≤0.03° and knowledge ≤0.01° at 95% confidence, with autonomous target tracking.

The reference control architecture separates safe/recovery, measurement, communications and maneuver or servicing modes. A commanded transition requires validated sensor state and resource availability. For hosted equipment, mechanical positioning takes the place of free-flight attitude determination, while retaining an equivalent repeatability verification requirement.

The control design maintains a mode and pointing error budget. It distinguishes knowledge of where the instrument looked from closed-loop control accuracy, including disturbance rejection and post-facto reconstruction. Engineering tests separately verify sensor alignment, actuator range and degraded operations after a failed sensor or wheel.

| Control element A | Control element B |
| --- | --- |
| Primary position/attitude reference | Independent cross-check and health monitor |
| Science or process pointing | Safe-mode or host restraint |
| Actuator / positioning hardware | Feedback telemetry |
| Alignment calibration | Post-test acceptance evidence |

### Propulsion Subsystem

100 kg monopropellant at 225 s gives ideal Δv ~368 m/s. Against a 320 m/s maneuver requirement, 48 m/s remains for performance dispersion and unusable propellant.

Any maneuver, descent or mobility not carried by the delivered unit is assigned explicitly to the launch or cargo provider. If propulsion is installed, the flight reserve includes residuals, thrust and specific-impulse dispersion, navigation error and unusable propellant. No requirement is treated as closed by nominal rocket-equation capability alone.

| Parameter | Reference value | Units |
| --- | --- | --- |
| Propulsion type | Installed or external; see baseline | — |
| Initial unit mass | 650 | kg |
| Reference performance | ≥320 m/s; 100 kg propellant at 225 s and initial mass 650 kg gives ~368 m/s ideal | m/s or N/A |
| Fuel / propellant allocation | 100 kg monopropellant at 225 s gives ideal Δv ~368 m/s. Against a 320 m/s maneuver requirement, 48 m/s remains for performance dispersion and unusable propellant. | kg / description |
| Performance reserve | Verify at PDR | m/s |
| Residual accounting | Required in final mass budget | kg |

| Maneuver / mobility element | Allocation / assumption |
| --- | --- |
| Initial injection or landing | Included in contracted service unless stated otherwise |
| Operational maintenance | Solar escape/transfer with one target flyby; no capture burn or long-duration target orbit. |
| Navigation and correction | ≥320 m/s; 100 kg propellant at 225 s and initial mass 650 kg gives ~368 m/s ideal |
| Contingency and residuals | Explicit reserve controlled in Part B / Part C |
| Total capability | Reconcile with 100 kg monopropellant at 225 s gives ideal Δv ~368 m/s. Against a 320 m/s maneuver requirement, |

### Telemetry, Tracking and Command

At 1 Mb/s and 70% effective transfer, the 20 GB encounter data set requires about 63.5 hours of contact at maximum range; schedule ≥100 hours over 30 days.

The final link assessment shall include transmitter power, antenna gain or host data-service rate, geometry, coding, weather where relevant and a minimum allocated margin. Distinguish command/control packets, health telemetry, raw measurements and user or science products. A link outage analysis is required before ground-service capacity is baselined.

The communications baseline includes 1 Mb/s X-band at 2.5 AU to 18 m-class antenna. The contact budget carries acquisition, engineering telemetry, protocol framing, retransmission and unavailable weather or host periods. The sizing check compares usable transferred bytes per contact with 20 GB encounter burst; ≤1 GB/day in cruise and any higher burst case.

A separate low-rate command path or host maintenance interface shall support diagnosis after the prime mission-data path becomes unavailable. No unauthenticated measurement data can alter safety-critical command parameters.

## Payload

The payload or process equipment is divided into imaging spectrometer, neutral gas mass spectrometer and dust impact analyser. Each element has a separate delivered mass, operating load, mode list, failure assessment and calibration requirement.

### Imaging spectrometer

37 kg / 145 W; 0.45–4.0 µm, 180 spectral channels; ≤100 m/pixel at 1,200 km requires ≤83 µrad IFOV.

The element is accepted by a traced performance test across the specified environment. Detector or process response, temporal stability, alignment and throughput are measured, not inferred from component labels. Operational anomalies are flagged in the Level 1 record.

The technical budget traces the stated measurement scale to a physical sampling process and detector or process limits. The performance model shall state coverage, dynamic range, timing, throughput, noise, calibration interval and data-rejection logic. Acceptance reports both the verified central value and its uncertainty.

| Parameter | Preliminary requirement / target |
| --- | --- |
| Primary function | Imaging spectrometer |
| Measured performance | 37 kg / 145 W; 0.45–4.0 µm, 180 spectral channels; ≤100 m/pixel at 1,200 km requires ≤83 µrad IFOV. |
| Unit-level calibration | Before integration and after environmental qualification |
| Electrical interface | Protected distribution and commanded safe state |
| Data interface | Time-tagged raw records plus status and quality flags |
| Environmental tolerance | 12 m² arrays produce ~3.15 kW EOL at 1 AU and ~651 W at 2.2 AU; nominal encounter load constrained to ≤410 W. |
| Mass accounting | Within 86 kg payload or experiment allocation |
| Verification | Test against mission-level success criterion |
| Operations mode | Only when power, thermal and link margins permit |
| Fault response | Isolate and report without affecting safe-mode command |

### Neutral gas mass spectrometer

24 kg / 110 W; 1–100 u mass range at ≤1 u resolution; 1–10 s sample time through approach.

This measurement or process provides an independent check on the primary result. The ground model shall retain geometric, thermal and instrumental uncertainty, including changes caused by the spacecraft or host.

For Velun Coma Surveyor, complementarity is intentional: one channel measures a different physical quantity or provides a contextual state. Processing shall preserve the raw evidence, identify retrieval assumptions and reject inconsistent cross-calibration before product release.

| Parameter | Preliminary requirement / target |
| --- | --- |
| Function | Neutral gas mass spectrometer |
| Performance | 24 kg / 110 W; 1–100 u mass range at ≤1 u resolution; 1–10 s sample time through approach. |
| Mass | Included in payload/experiment allocation |
| Power | Mode specific; close against peak load |
| Field / process geometry | Reference target distance 2.2 AU; closest approach 1,200 ±200 km; relative velocity 6 ±1 km/s. |
| Timing | Synchronized to system command clock |
| Calibration | At acceptance and by scheduled in-operation reference |
| Data volume | 20 GB encounter burst; ≤1 GB/day in cruise |
| Quality masks | Record saturation, missing packets and calibration excursions |
| Qualification | Relevant launch, host and operational environment |

### Payload Electronics

The payload electronics supervise instrument power, timing, detector readout, process controls, data formatting and safe-mode interlocks. Interfaces are controlled by released drawings and telemetry dictionaries. Each unit supports configuration rollback after a failed upload.

| Parameter | Preliminary requirement / target |
| --- | --- |
| Primary function | Instrument / process control and time-tagging |
| Sensor interfaces | Imaging spectrometer; Neutral gas mass spectrometer; Dust impact analyser |
| System interface | Protected command and local data bus |
| Buffering | 2 TB usable system allocation |
| Processing | Lossless event flags and reversible screening where practical |
| Timing | Absolute reference and monotonically numbered records |
| Health monitoring | Voltage, temperature, current, reset count and status |
| Mass | Within 86 kg allocation |
| Peak electrical power | Included in 720 W integrated peak |
| Radiation / environment | Qualified for Reference target distance 2.2 AU; closest approach 1,200 ±200 km; relative |

### Onboard Calibration

Calibration is designed around traceable reference states rather than a generic check flag. A pre-deployment baseline, scheduled in-operation reference and post-anomaly verification distinguish genuine environment or biological changes from instrument drift.

| Parameter | Preliminary requirement / target |
| --- | --- |
| Calibration type | Radiometric, geometric, biological, material or electrical as applicable |
| Primary reference | Dust impact analyser |
| Frequency | At commissioning, after anomaly and on a scheduled monthly cadence |
| Environmental dependency | 12 m² arrays produce ~3.15 kW EOL at 1 AU and ~651 W at 2.2 AU; nominal encounter load constrained to ≤410 W. |
| Long-term drift | Trend against accepted reference and flag >2% unexplained change |
| Data linkage | 100% released products identify applicable calibration version |
| Independent verification | Recheck with Neutral gas mass spectrometer |
| Instrument monitoring | On each operating cycle |
| Mass / power | Within payload and system allocations |

Figure 2 – Payload measurement and data path. Components and output interfaces are explicitly labeled.

# Launch Segment Description

C3 ≥18 km²/s²; 650 kg spacecraft + 110 kg adaptor = 760 kg; capacity ≥900 kg to injection

Delivery pricing shall separately identify vehicle or carrier service, packaging and adaptor, loading and contamination controls, integration testing, range or landing support, insurance if applicable and post-delivery transition. Any mass carried by a host rather than the flight unit is shown as a separate line and is not double counted.

The final delivery contractor verifies mechanical fit, safety, compatibility, deployment, insertion or landing dispersions and acceptance criteria. The mission team performs final health checks before the affected unit is declared operational.

Delivery preparation includes controlled packing, shipment and receiving inspection, integrated electrical checkout, safety review, interface sign-off and a final readiness decision. The handover record separates damage observed before launch or cargo installation from anomalies in early operation.

Any alternate provider must meet the same delivered mass, envelope, power-on sequence, schedule and injection or landing accuracy. A provider change triggers re-verification of coupled loads and mission-specific interfaces.

# Ground Segment and Mission Operations

Three 18 m-class deep-space antenna sites; 5 GB/day ingest; 90 TB archive.

At 1 Mb/s and 70% effective transfer, the 20 GB encounter data set requires about 63.5 hours of contact at maximum range; schedule ≥100 hours over 30 days.

| Ground Segment Element | Description |
| --- | --- |
| Mission Planning System | Schedules commanded measurement, service or observation periods and checks resource constraints. |
| Control System | Monitors status, authorizes command, handles anomaly response and keeps configuration history. |
| Receiving Stations / Host Link | Three 18 m-class deep-space antenna sites; 5 GB/day ingest; 90 TB archive. |
| Operations Team | Staffed planned operations with automated alarm and on-call response. |
| Processing and Archive | Level 0 packet retention; Level 1 calibration; Level 2 products with preserved lineage. |
| Data Volume / Availability | 20 GB encounter burst; ≤1 GB/day in cruise; scheduled ground service availability ≥99%. |

The daily return is 20 GB encounter burst; ≤1 GB/day in cruise. Downlink capacity and stored-data volume shall close under a minimum 48-hour missed-contact case, except where host operations impose a different approved case. Science release depends on validation, access permissions and a documented reprocessing path.

Mission operations include daily planning, health trending, commands, flight dynamics or host status, calibrated processing, anomaly resolution and archive integrity. Nominal staffing is a planned shift with continuous alarm routing; time-critical encounters or crew procedures require separate surge coverage.

The data archive retains source packets, released products, calibration files, algorithm version and exceptions. Capacity in Three 18 m-class deep-space antenna sites; 5 GB/day ingest; 90 TB archive. is a planning provision that shall be verified against years of operation, replication and reprocessing.

# Systems Engineering and Project Management Approach

## TRL Levels and Heritage

A similar component class does not establish mission-specific qualification. Critical payload, software, biological, medical or manufacturing elements target TRL 6 at PDR and TRL 8 before acceptance. The evidence register identifies the exact hardware/software configuration, environment and remaining work for each claim.

## Phasing Logic and Naming Conventions

The costing convention separates early concept work, definition, design, subsystem manufacture and test, system integration, delivery, commissioning, nominal operations and closeout. Phase labels are mapped to the project schedule in Part C.

Table 3 – Costing Phase Crosswalk

| Costing nomenclature | Phase description | Project name |
| --- | --- | --- |
| PREP 1 | Pre-gate prototyping | Technology maturation |
| PREP 2 | Phase 0/A prototyping | Concept demonstrations |
| Phase 0 | Concept and feasibility | Concept |
| Phase A | System definition | Definition |
| Phase B | Preliminary design | Preliminary design |
| Phase C | Detailed design | Detailed design |
| Phase D1 | Subsystem manufacture and test | Unit AIT |
| Phase D2 | System assembly, integration and test | System AIT |
| LEOP | Delivery and commissioning | Commissioning |
| Phase E | Nominal operations | Operations |
| Phase E EXT | Extended operations | Extension |
| Phase F | Closeout and disposal | Closeout |
| Phase G | Data exploitation | Science use |

The schedule planning basis is B 16 months; C 12 months; D1 18 months; D2 10 months; cruise 48 months; approach 6 months. Activities with long-lead procurement and parallel unit builds overlap; durations should not be arithmetically summed to infer a delivery date.

Table 4 – Planning Phase Dates and Durations

| Phase | 0 | A | B | C | D1 | D2 | E |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Duration, months | TBD | TBD | 16 | 12 | 18 | 10 | TBD |
| Status | planning | planning | planning | planning | planning | planning | planning |

## Project Milestones

Table 5 – Major Milestones

| Instrument / PM Phase | Gate / Milestone | Major Milestone | Milestone Date |
| --- | --- | --- | --- |
| 0 | MCR | Mission Concept Review | May 2027 |
| A | SRR | System Requirements Review | Mar 2028 |
| B | PDR | Preliminary Design Review | May 2029 |
| C | CDR | Critical Design Review | May 2030 |
| D1 | MRR | Manufacturing Readiness Review | Aug 2030 |
| D1 | EVT | Payload qualification | Nov 2031 |
| D2 | EVT | FM complete | Jul 2032 |
| D2 | SIR | System Integration Review | Sep 2032 |
| D2 | AR | Acceptance | Feb 2033 |
| D2 | LRR | Launch / Delivery Readiness Review | Jun 2033 |
| D2 | L | Launch | Aug 2033 |
| E | EVT | Approach | Aug 2037 |
| D2 | EVT | Flyby | Feb 2038 |
| E | EVT | Closeout | Aug 2038 |

## Safety and Mission Assurance

The project applies controlled requirements, hazard analysis, independent quality oversight, parts and materials screening, nonconformance disposition, serialized configuration and documented readiness reviews. Hazards include stored energy, fluid containment, high voltage, radiation, moving mechanisms, thermal surfaces and potential loss of user service as applicable.

For Velun Coma Surveyor, the initial risk concentration is Ephemeris uncertainty, dust strikes, autonomous tracking error, one-shot encounter sequencing, solar-array deployment and propulsion performance dispersion. Safety-related controls receive independent verification; mission success and medical or food-use claims require separate acceptance evidence.

## Prototyping Model Philosophy Qualification and Verification Strategy

The reference model philosophy comprises an electrical integration article, engineering or breadboard articles for novel functions, a structural/thermal qualification article and 1 flight or delivered unit(s). Every unit receives end-to-end functional, environmental workmanship, communications, safety and calibration testing. Qualification of a representative article does not waive acceptance of later units.

Verification records state the exact serial number, software version, procedures, environmental settings, anomalies and concessions. The commissioning review compares as-delivered performance to the reference allocation before operations begin.

## Sparing Strategy

Flight spares are allocated for critical, long lead and failure-prone units. A maintained engineering article and ground support equipment support anomaly reproduction and software validation. The final spare quantities and holding costs belong in Part B.

## Risk Assessment

The Part C risk register controls risk probability, cost and schedule exposure. Principal threats: Ephemeris uncertainty, dust strikes, autonomous tracking error, one-shot encounter sequencing, solar-array deployment and propulsion performance dispersion. Each has an owner, trigger, planned mitigation and residual exposure. Design reserves on mass, power, data and propellant or consumables are reported separately from financial contingency.

## Organizational Breakdown Structure

### Space Agencies and Government Organizations

Table 6 – Mission Organizations

| Partner | Jurisdiction | Proposed role |
| --- | --- | --- |
| Tharven Planetary Office | Mission jurisdiction | mission authority, procurement, project assurance and acceptance. |

### Industrial Partners

Table 7 – Industrial Partners

| Partner | Domain | Proposed role |
| --- | --- | --- |
| Aruvell Interplanetary Systems | Mission supply chain | integrated unit design, manufacture and system verification. |
| Fesrane Spectral Laboratories | Mission supply chain | payload/process equipment and acceptance calibration. |
| Pellorin Launch Union | Mission supply chain | delivery, campaign operations and associated interfaces. |
| Suvranel Signal Network | Mission supply chain | ground network, receiving interfaces and operations support. |

### Participating Academic Institutions

Table 8 – Research Institutions

| Institution | Domain | Proposed contribution |
| --- | --- | --- |
| Kelruna Volatiles Institute | Science consortium | science or user requirements, calibration, data validation and exploitation. |

### Scientific Leadership (Principal Investigator)

Table 9 – Scientific Leadership

| Position | Assigned individual | Affiliation |
| --- | --- | --- |
| Principal investigator | Tavren Elovar | Kelruna Volatiles Institute |
| Instrument scientist | Mirev Solanar | Fesrane Spectral Laboratories |