## Cover Page
MCAD-FIN-RD-0812
Version Draft 1.0
2026-09-25
Cost Analysis Data Requirement (CADRe)
CADRe Part C - Additional Programmatic Inputs
VPCS KDP-0
Prepared by Issie Grecoff
| Reviewed by [Name] | Name

## 1 - Change History
` Table of Contents
2. Version Control - Baseline Tracker
Purpose: | To track the baseline across time
hold the major and minor releases of the baseline
| Change history and associated files that contain the relevant data |  |  |  |  | Reserved
| File Number | Date | File Version | Author | Changes | Parent Baseline Name | Baseline ID
[6 empty] | SD @ PREP1 | 1
| MCAD-FIN-RD-0812 | 2026-09-25 | Draft 1 | IG | Initial Part C built from CADRe Part A – VPCS, Rev 1.0 (23 Sep 2026) | SD @ KDP-0 | 2 | <<--- We are here now
[6 empty] | SD @ MDR#2 | 3
[6 empty] | SD @ PREP2 | 4
[6 empty] | SD @ KDP-A | 5
[6 empty] | SD @ KDP-B | 6
[6 empty] | SD @ PDR | 7
[6 empty] | SD @ CDR | 8
[6 empty] | SD @ SIR | 9
[6 empty] | SD @ KDP-E | 10
[6 empty] | SD @ Launch (as flown) | 11
[6 empty] | SD @ CR | 12
[6 empty] | SD @ KDP-X | 13
[6 empty] | SD @ end of life | 14

## 4d - CBS in JS format (hidden)
` Table of Contents
4d. CBS (as self referencing list) for use as a javascript array
Why we we asking:
this page is auto-generated and used for drawing it out
Self referencing list for dtree
UID | Parent ID | Level | Node Name | CBS Code | Depth | Icon | Notes | Javascript Code | Depth
1 | -1 | 1 | Space Missions |  | Taxon 1 | Box.png |  | datatable[0] = new Array("1","-1","Space Missions","1","Box.png"); | Taxon 1
2 | 1 | 2 | EO SAR Missions |  | Taxon 2 | EO.png |  | datatable[1] = new Array("2","1","EO SAR Missions","2","EO.png"); | Taxon 2
3 | 2 | 3 | Radarsat Portfolio |  | Phylum | Pouch.png |  | datatable[2] = new Array("3","2","Radarsat Portfolio","3","Pouch.png"); | Phylum
4 | 0 | 4 | Radarsat 1 |  | Mission | Satellite.png |  | datatable[3] = new Array("4","0","Radarsat 1","4","Satellite.png"); | Mission
5 | 0 | 4 | Radarsat 2 |  | Mission | Satellite.png |  | datatable[4] = new Array("5","0","Radarsat 2","4","Satellite.png"); | Design Reference Mission
6 | 0 | 4 | Radarsat Constellation Mission |  | Mission | Satellite.png |  | datatable[5] = new Array("6","0","Radarsat Constellation Mission","4","Satellite.png"); | Segment
7 | 0 | 4 | Radarsat+ Replenishment | 1 | Mission | Satellite.png |  | datatable[6] = new Array("7","0","Radarsat+ Replenishment","4","Satellite.png"); | System of Systems
8 | 0 | 4 | Radarsat+ Next Generation |  | Mission | Satellite.png |  | datatable[7] = new Array("8","0","Radarsat+ Next Generation","4","Satellite.png"); | System
9 | 2 | 5 | Analysis Scenario 1: RCM Proxy |  | Design Reference Mission | Scenario.png |  | datatable[8] = new Array("9","2","Analysis Scenario 1: RCM Proxy","5","Scenario.png"); | Subsystem
10 | 2 | 5 | Analysis Scenario 2: RCM+ |  | Design Reference Mission | Scenario.png |  | datatable[9] = new Array("10","2","Analysis Scenario 2: RCM+","5","Scenario.png"); | Assembly
11 | 2 | 5 | Analysis Scenario 3: Airbus concept |  | Design Reference Mission | Scenario.png |  | datatable[10] = new Array("11","2","Analysis Scenario 3: Airbus concept","5","Scenario.png"); | Component
12 | 2 | 5 | Analysis Scenario 4: MDA Chorus Data Buy |  | Design Reference Mission | Scenario.png |  | datatable[11] = new Array("12","2","Analysis Scenario 4: MDA Chorus Data Buy","5","Scenario.png");
13 | 2 | 5 | Analysis Scenario 5: MDA Chorus+ |  | Design Reference Mission | Scenario.png |  | datatable[12] = new Array("13","2","Analysis Scenario 5: MDA Chorus+","5","Scenario.png");
14 | 2 | 5 | Analysis Scenario 6: Airbus Sentinel 2 |  | Design Reference Mission | Scenario.png |  | datatable[13] = new Array("14","2","Analysis Scenario 6: Airbus Sentinel 2","5","Scenario.png");
15 | 8 | 6 | Government Overhead and Oversight | 1.1 | Segment | Government.png | This WBS includes all CSA Oversight, OGD salaries, and basic overhead for the care and maintenance of CSA staff | datatable[14] = new Array("15","8","Government Overhead and Oversight","6","Government.png");
16 | 8 | 6 | Space Segment | 1.2 | Segment | Satellite.png | The Space Segment includes things we launch into space | datatable[15] = new Array("16","8","Space Segment","6","Satellite.png");
17 | 8 | 6 | Launch Segment | 1.3 | Segment | Rocket.png | The launch segment includes the launch vehicle and seom support services | datatable[16] = new Array("17","8","Launch Segment","6","Rocket.png");
18 | 8 | 6 | Ground Segment | 1.4 | Segment | Facility.png | The ground segment includes the planning desgin and development of the GS, but not the Ops | datatable[17] = new Array("18","8","Ground Segment","6","Facility.png");
19 | 8 | 6 | Ops Segment | 1.5 | Segment | Ops.png | Ops includes SatOps, Mission Ops, Science Ops - typically contracts | datatable[18] = new Array("19","8","Ops Segment","6","Ops.png");
20 | 8 | 6 | Science Segment | 1.6 | Segment | Science.png | Typically G&C | datatable[19] = new Array("20","8","Science Segment","6","Science.png");
21 | 10 | 7 | Gov't Oversight (Salaries and EBP) | 1.1.1 | System of Systems | Government.png |  | datatable[20] = new Array("21","10","Gov't Oversight (Salaries and EBP)","7","Government.png");
22 | 10 | 7 | Government Overhead | 1.1.2 | System of Systems | Government.png |  | datatable[21] = new Array("22","10","Government Overhead","7","Government.png");
23 | 21 | 8 | CSA Oversight | 1.1.1.1 | System | Government.png |  | datatable[22] = new Array("23","21","CSA Oversight","8","Government.png");
24 | 21 | 8 | OGD Oversight | 1.1.1.2 | System | Government.png |  | datatable[23] = new Array("24","21","OGD Oversight","8","Government.png");
25 | 23 | 9 | CSA Project Team | 1.1.1.1.1 | Subsystem | Government.png | This CBS contains all salaries associated with the RAM of the Project team | datatable[24] = new Array("25","23","CSA Project Team","9","Government.png");
26 | 23 | 9 | CSA Internal Services | 1.1.1.1.2 | Subsystem | Government.png | This CBS contains all salaries associated with CSA internal services (finance, HR, audit, eval, policy, Executives, IM, IT, contracts, shipping, etc) | datatable[25] = new Array("26","23","CSA Internal Services","9","Government.png");
27 | 24 | 9 | OGD Internal Services by MOU | 1.1.1.2.1 | Subsystem | Government.png |  | datatable[26] = new Array("27","24","OGD Internal Services by MOU","9","Government.png");
28 | 24 | 9 | OGD User Departments by MOU (RAM portion) | 1.1.1.2.2 | Subsystem | Government.png |  | datatable[27] = new Array("28","24","OGD User Departments by MOU (RAM portion)","9","Government.png");
29 | 21 | 10 | Shared Services | 1.1.1.2.1.1 | Assembly | Government.png |  | datatable[28] = new Array("29","21","Shared Services","10","Government.png");
30 | 21 | 10 | SPAC | 1.1.1.2.1.2 | Assembly | Government.png |  | datatable[29] = new Array("30","21","SPAC","10","Government.png");
31 | 21 | 10 | Justice Canada | 1.1.1.2.1.3 | Assembly | Government.png |  | datatable[30] = new Array("31","21","Justice Canada","10","Government.png");
32 | 23 | 10 | ECCC | 1.1.1.2.2.1 | Assembly | Government.png |  | datatable[31] = new Array("32","23","ECCC","10","Government.png");
33 | 23 | 10 | NRCAN | 1.1.1.2.2.2 | Assembly | Government.png |  | datatable[32] = new Array("33","23","NRCAN","10","Government.png");
34 | 23 | 10 | DND | 1.1.1.2.2.3 | Assembly | Government.png |  | datatable[33] = new Array("34","23","DND","10","Government.png");
35 | 25 | 11 | RAM per Person per FY and Phase | 1.1.1.1.1.1 | Component | Government.png |  | datatable[34] = new Array("35","25","RAM per Person per FY and Phase","11","Government.png");
36 | 25 | 11 | PSPC Procurement Services | 1.1.1.2.1.2.1 | Component | Government.png |  | datatable[35] = new Array("36","25","PSPC Procurement Services","11","Government.png");
37 | 25 | 11 | PSPC Fairness Monitor | 1.1.1.2.1.2.2 | Component | Government.png |  | datatable[36] = new Array("37","25","PSPC Fairness Monitor","11","Government.png");
38 | 31 | 11 | Legal Services | 1.1.1.2.1.3.1 | Component | Government.png |  | datatable[37] = new Array("38","31","Legal Services","11","Government.png");
39 | 22 | 8 | CSA Overhead | 1.1.2.1 | System | Government.png |  | datatable[38] = new Array("39","22","CSA Overhead","8","Government.png");
40 | 34 | 9 | IS Management Overhead | 1.1.2.1.1 | Subsystem | Government.png |  | datatable[39] = new Array("40","34","IS Management Overhead ","9","Government.png");
41 | 34 | 9 | Management Consulting Services | 1.1.2.1.2 | Subsystem | Government.png |  | datatable[40] = new Array("41","34","Management Consulting Services","9","Government.png");
42 | 34 | 9 | Temporary Help | 1.1.2.1.3 | Subsystem | Government.png |  | datatable[41] = new Array("42","34","Temporary Help","9","Government.png");
43 | 34 | 9 | Students | 1.1.2.1.4 | Subsystem | Government.png | This CBS includes any students, FSWEP or PDF assisint Csa project team | datatable[42] = new Array("43","34","Students","9","Government.png");
44 | 34 | 9 | Government Travel & Living | 1.1.2.1.5 | Subsystem | Government.png | This CBS includes any government Travel and Living expenses | datatable[43] = new Array("44","34","Government Travel & Living","9","Government.png");
45 | 34 | 9 | Translation | 1.1.2.1.6 | Subsystem | Government.png | This CBS includes any translation costs | datatable[44] = new Array("45","34","Translation","9","Government.png");
46 | 34 | 9 | Shipping | 1.1.2.1.7 | Subsystem | Government.png | This CBs includes any shipping cost, but not shipping flight HW which is under space segment | datatable[45] = new Array("46","34","Shipping","9","Government.png");
47 | 34 | 9 | Software Licenses | 1.1.2.1.8 | Subsystem | Government.png | This CBS includes any COTs SW not flight Sw or ground SW | datatable[46] = new Array("47","34","Software Licenses","9","Government.png");
48 | 34 | 9 | Public Outreach and STEM initiatives | 1.1.2.1.9 | Subsystem | Government.png | This CBS includes any public relations and STEM | datatable[47] = new Array("48","34","Public Outreach and STEM initiatives","9","Government.png");
49 | 34 | 9 | Other Overhead (Specify) | 1.1.2.1.10 | Subsystem | Government.png | This CBS includes any other misc fees | datatable[48] = new Array("49","34","Other Overhead (Specify)","9","Government.png");
50 | 36 | 10 | Consultants - Industrial Space Experts | 1.1.2.1.2.1 | Assembly | Government.png |  | datatable[49] = new Array("50","36","Consultants - Industrial Space Experts","10","Government.png");
51 | 36 | 10 | Consultants - Academia | 1.1.2.1.2.2 | Assembly | Government.png |  | datatable[50] = new Array("51","36","Consultants - Academia","10","Government.png");
52 | 36 | 10 | Consultants - Non-Space Experts | 1.1.2.1.2.3 | Assembly | Government.png |  | datatable[51] = new Array("52","36","Consultants - Non-Space Experts","10","Government.png");
53 | 12 | 6 | Mission SEITPM and Support Equipment |  | Segment | SEITPM.png |  | datatable[52] = new Array("53","12","Mission SEITPM and Support Equipment","6","SEITPM.png");
54 | 48 | 7 | Project Management |  | System of Systems | SEITPM.png |  | datatable[53] = new Array("54","48","Project Management","7","SEITPM.png");
55 | 48 | 7 | Systems Engineering |  | System of Systems | SEITPM.png |  | datatable[54] = new Array("55","48","Systems Engineering","7","SEITPM.png");
56 | 48 | 7 | Mission Assurance |  | System of Systems | SEITPM.png |  | datatable[55] = new Array("56","48","Mission Assurance","7","SEITPM.png");
57 | 48 | 7 | Assembly, Integration and Testing |  | System of Systems | SEITPM.png |  | datatable[56] = new Array("57","48","Assembly, Integration and Testing","7","SEITPM.png");
58 | 48 | 7 | Support Equipment |  | System of Systems | SEITPM.png |  | datatable[57] = new Array("58","48","Support Equipment","7","SEITPM.png");
59 | 16 | 7 | Space Vehicle 1 … i |  | System of Systems | Satellite.png |  | datatable[58] = new Array("59","16","Space Vehicle 1 … i","7","Satellite.png");
60 | 59 | 8 | Spacecraft SEITPM and Support Equipment |  | System | SEITPM.png |  | datatable[59] = new Array("60","59","Spacecraft SEITPM and Support Equipment","8","SEITPM.png");
61 | 55 | 9 | Project Management |  | Subsystem | SEITPM.png |  | datatable[60] = new Array("61","55","Project Management","9","SEITPM.png");
62 | 55 | 9 | Systems Engineering |  | Subsystem | SEITPM.png |  | datatable[61] = new Array("62","55","Systems Engineering","9","SEITPM.png");
63 | 55 | 9 | Mission Assurance |  | Subsystem | SEITPM.png |  | datatable[62] = new Array("63","55","Mission Assurance","9","SEITPM.png");
64 | 55 | 9 | Assembly, Integration and Testing |  | Subsystem | SEITPM.png |  | datatable[63] = new Array("64","55","Assembly, Integration and Testing","9","SEITPM.png");
65 | 55 | 9 | Support Equipment |  | Subsystem | SEITPM.png |  | datatable[64] = new Array("65","55","Support Equipment","9","SEITPM.png");
66 | 59 | 8 | Bus/Platform |  | System | Widget.png |  | datatable[65] = new Array("66","59","Bus/Platform","8","Widget.png");
67 | 66 | 9 | Platform SEITPM and Support Equipment |  | Subsystem | SEITPM.png |  | datatable[66] = new Array("67","66","Platform SEITPM and Support Equipment","9","SEITPM.png");
68 | 62 | 10 | Project Management |  | Assembly | SEITPM.png |  | datatable[67] = new Array("68","62","Project Management","10","SEITPM.png");
69 | 62 | 10 | Systems Engineering |  | Assembly | SEITPM.png |  | datatable[68] = new Array("69","62","Systems Engineering","10","SEITPM.png");
70 | 62 | 10 | Mission Assurance |  | Assembly | SEITPM.png |  | datatable[69] = new Array("70","62","Mission Assurance","10","SEITPM.png");
71 | 62 | 10 | Assembly, Integration and Testing |  | Assembly | SEITPM.png |  | datatable[70] = new Array("71","62","Assembly, Integration and Testing","10","SEITPM.png");
72 | 62 | 10 | Support Equipment |  | Assembly | SEITPM.png |  | datatable[71] = new Array("72","62","Support Equipment","10","SEITPM.png");
73 | 61 | 9 | Structures and Mechanisms Subsystem (SMS) |  | Subsystem | Widget.png |  | datatable[72] = new Array("73","61","Structures and Mechanisms Subsystem (SMS)","9","Widget.png");
74 | 68 | 10 | Structures and Mechanisms Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[73] = new Array("74","68","Structures and Mechanisms Subsystem SEITPM","10","SEITPM.png");
75 | 69 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[74] = new Array("75","69","Project Management","11","SEITPM.png");
76 | 69 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[75] = new Array("76","69","Systems Engineering","11","SEITPM.png");
77 | 69 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[76] = new Array("77","69","Mission Assurance","11","SEITPM.png");
78 | 69 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[77] = new Array("78","69","Assembly, Integration and Testing","11","SEITPM.png");
79 | 69 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[78] = new Array("79","69","Support Equipment","11","SEITPM.png");
80 | 68 | 10 | Primary Structures |  | Assembly | Widget.png |  | datatable[79] = new Array("80","68","Primary Structures","10","Widget.png");
81 | 75 | 11 | Load Carrying Shell/Truss |  | Component | Widget.png |  | datatable[80] = new Array("81","75","Load Carrying Shell/Truss","11","Widget.png");
82 | 75 | 11 | Equipment Compartments |  | Component | Widget.png |  | datatable[81] = new Array("82","75","Equipment Compartments","11","Widget.png");
83 | 75 | 11 | Booms |  | Component | Widget.png |  | datatable[82] = new Array("83","75","Booms","11","Widget.png");
84 | 75 | 11 | Adapters |  | Component | Widget.png |  | datatable[83] = new Array("84","75","Adapters","11","Widget.png");
85 | 75 | 11 | Other Structures (Specify) |  | Component | Widget.png |  | datatable[84] = new Array("85","75","Other Structures (Specify)","11","Widget.png");
86 | 68 | 10 | Secondary Structures |  | Assembly | Widget.png |  | datatable[85] = new Array("86","68","Secondary Structures","10","Widget.png");
87 | 81 | 11 | Equipment (Instrument) Mountings |  | Component | Widget.png |  | datatable[86] = new Array("87","81","Equipment (Instrument) Mountings","11","Widget.png");
88 | 81 | 11 | Ballast Mass |  | Component | Widget.png |  | datatable[87] = new Array("88","81","Ballast Mass","11","Widget.png");
89 | 81 | 11 | Other Secondary Structures (Specify) |  | Component | Widget.png |  | datatable[88] = new Array("89","81","Other Secondary Structures (Specify)","11","Widget.png");
90 | 68 | 10 | Mechanisms and Pyrotechnics |  | Assembly | Widget.png |  | datatable[89] = new Array("90","68","Mechanisms and Pyrotechnics","10","Widget.png");
91 | 85 | 11 | Positioning |  | Component | Widget.png |  | datatable[90] = new Array("91","85","Positioning","11","Widget.png");
92 | 85 | 11 | Deployment and Storage Equipment |  | Component | Widget.png |  | datatable[91] = new Array("92","85","Deployment and Storage Equipment","11","Widget.png");
93 | 85 | 11 | Docking Mechanisms |  | Component | Widget.png |  | datatable[92] = new Array("93","85","Docking Mechanisms","11","Widget.png");
94 | 85 | 11 | Other Mechanisms (Specify) |  | Component | Widget.png |  | datatable[93] = new Array("94","85","Other Mechanisms (Specify)","11","Widget.png");
95 | 85 | 11 | Pyrotechnics |  | Component | Widget.png |  | datatable[94] = new Array("95","85","Pyrotechnics","11","Widget.png");
96 | 68 | 10 | SMS Other (Specify) |  | Assembly | Widget.png |  | datatable[95] = new Array("96","68","SMS Other (Specify)","10","Widget.png");
97 | 61 | 9 | Thermal Control Subsystem (TCS) |  | Subsystem | Widget.png |  | datatable[96] = new Array("97","61","Thermal Control Subsystem (TCS)","9","Widget.png");
98 | 92 | 10 | Thermal Control Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[97] = new Array("98","92","Thermal Control Subsystem SEITPM","10","SEITPM.png");
99 | 93 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[98] = new Array("99","93","Project Management","11","SEITPM.png");
100 | 93 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[99] = new Array("100","93","Systems Engineering","11","SEITPM.png");
101 | 93 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[100] = new Array("101","93","Mission Assurance","11","SEITPM.png");
102 | 93 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[101] = new Array("102","93","Assembly, Integration and Testing","11","SEITPM.png");
103 | 93 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[102] = new Array("103","93","Support Equipment","11","SEITPM.png");
104 | 92 | 10 | Active Devices |  | Assembly | Widget.png |  | datatable[103] = new Array("104","92","Active Devices","10","Widget.png");
105 | 99 | 11 | Cryogenic Devices |  | Component | Widget.png |  | datatable[104] = new Array("105","99","Cryogenic Devices","11","Widget.png");
106 | 99 | 11 | Liquid Loops |  | Component | Widget.png |  | datatable[105] = new Array("106","99","Liquid Loops","11","Widget.png");
107 | 99 | 11 | Electric Coolers |  | Component | Widget.png |  | datatable[106] = new Array("107","99","Electric Coolers","11","Widget.png");
108 | 99 | 11 | Heaters, Thermistors, and Thermostats |  | Component | Widget.png |  | datatable[107] = new Array("108","99","Heaters, Thermistors, and Thermostats","11","Widget.png");
109 | 99 | 11 | Other Active Devices (Specify) |  | Component | Widget.png |  | datatable[108] = new Array("109","99","Other Active Devices (Specify)","11","Widget.png");
110 | 92 | 10 | Passive Devices |  | Assembly | Widget.png |  | datatable[109] = new Array("110","92","Passive Devices","10","Widget.png");
111 | 105 | 11 | Radiator Panel/Fins |  | Component | Widget.png |  | datatable[110] = new Array("111","105","Radiator Panel/Fins","11","Widget.png");
112 | 105 | 11 | Coatings |  | Component | Widget.png |  | datatable[111] = new Array("112","105","Coatings","11","Widget.png");
113 | 105 | 11 | Heat Pipes |  | Component | Widget.png |  | datatable[112] = new Array("113","105","Heat Pipes","11","Widget.png");
114 | 105 | 11 | Insulation |  | Component | Widget.png |  | datatable[113] = new Array("114","105","Insulation","11","Widget.png");
115 | 105 | 11 | Conductive Structures |  | Component | Widget.png |  | datatable[114] = new Array("115","105","Conductive Structures","11","Widget.png");
116 | 105 | 11 | Heat Activated Structures |  | Component | Widget.png |  | datatable[115] = new Array("116","105","Heat Activated Structures","11","Widget.png");
117 | 105 | 11 | Sun Shields |  | Component | Widget.png |  | datatable[116] = new Array("117","105","Sun Shields","11","Widget.png");
118 | 105 | 11 | Second Surface Mirrors |  | Component | Widget.png |  | datatable[117] = new Array("118","105","Second Surface Mirrors","11","Widget.png");
119 | 105 | 11 | Shutters and Louvers |  | Component | Widget.png |  | datatable[118] = new Array("119","105","Shutters and Louvers","11","Widget.png");
120 | 105 | 11 | Other Passive Devices (Specify) |  | Component | Widget.png |  | datatable[119] = new Array("120","105","Other Passive Devices (Specify)","11","Widget.png");
121 | 92 | 10 | TCS Other (Specify) |  | Assembly | Widget.png |  | datatable[120] = new Array("121","92","TCS Other (Specify)","10","Widget.png");
122 | 61 | 9 | Electric Power Subsystem (EPS) |  | Subsystem | Widget.png |  | datatable[121] = new Array("122","61","Electric Power Subsystem (EPS)","9","Widget.png");
123 | 117 | 10 | Electric Power Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[122] = new Array("123","117","Electric Power Subsystem SEITPM","10","SEITPM.png");
124 | 118 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[123] = new Array("124","118","Project Management","11","SEITPM.png");
125 | 118 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[124] = new Array("125","118","Systems Engineering","11","SEITPM.png");
126 | 118 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[125] = new Array("126","118","Mission Assurance","11","SEITPM.png");
127 | 118 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[126] = new Array("127","118","Assembly, Integration and Testing","11","SEITPM.png");
128 | 118 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[127] = new Array("128","118","Support Equipment","11","SEITPM.png");
129 | 117 | 10 | Electrical Power Generation |  | Assembly | Widget.png |  | datatable[128] = new Array("129","117","Electrical Power Generation","10","Widget.png");
130 | 124 | 11 | Solar Array |  | Component | Widget.png |  | datatable[129] = new Array("130","124","Solar Array","11","Widget.png");
131 | 124 | 11 | Solar Array Positioner |  | Component | Widget.png |  | datatable[130] = new Array("131","124","Solar Array Positioner","11","Widget.png");
132 | 124 | 11 | Radioisotope Thermionic Generator |  | Component | Widget.png |  | datatable[131] = new Array("132","124","Radioisotope Thermionic Generator","11","Widget.png");
133 | 124 | 11 | Chemical (Fuel Cells) |  | Component | Widget.png |  | datatable[132] = new Array("133","124","Chemical (Fuel Cells)","11","Widget.png");
134 | 124 | 11 | Auxiliary Power Units |  | Component | Widget.png |  | datatable[133] = new Array("134","124","Auxiliary Power Units","11","Widget.png");
135 | 124 | 11 | Other Power Sources |  | Component | Widget.png |  | datatable[134] = new Array("135","124","Other Power Sources","11","Widget.png");
136 | 117 | 10 | Electrical Power Conditioning |  | Assembly | Widget.png |  | datatable[135] = new Array("136","117","Electrical Power Conditioning","10","Widget.png");
137 | 131 | 11 | Power Control Electronics |  | Component | Widget.png |  | datatable[136] = new Array("137","131","Power Control Electronics","11","Widget.png");
138 | 131 | 11 | Power Conversion Electronics |  | Component | Widget.png |  | datatable[137] = new Array("138","131","Power Conversion Electronics","11","Widget.png");
139 | 131 | 11 | Power Dissipation Devices |  | Component | Widget.png |  | datatable[138] = new Array("139","131","Power Dissipation Devices","11","Widget.png");
140 | 131 | 11 | Power Distribution Electronics |  | Component | Widget.png |  | datatable[139] = new Array("140","131","Power Distribution Electronics","11","Widget.png");
141 | 131 | 11 | Power Switching Electronics |  | Component | Widget.png |  | datatable[140] = new Array("141","131","Power Switching Electronics","11","Widget.png");
142 | 131 | 11 | Power Regulation Electronics |  | Component | Widget.png |  | datatable[141] = new Array("142","131","Power Regulation Electronics","11","Widget.png");
143 | 131 | 11 | Other Power Conditioning Devices (Specify) |  | Component | Widget.png |  | datatable[142] = new Array("143","131","Other Power Conditioning Devices (Specify)","11","Widget.png");
144 | 117 | 10 | Electrical Power Storage |  | Assembly | Widget.png |  | datatable[143] = new Array("144","117","Electrical Power Storage","10","Widget.png");
145 | 139 | 11 | Rechargeable Batteries |  | Component | Widget.png |  | datatable[144] = new Array("145","139","Rechargeable Batteries","11","Widget.png");
146 | 139 | 11 | Charge Control Electronics |  | Component | Widget.png |  | datatable[145] = new Array("146","139","Charge Control Electronics","11","Widget.png");
147 | 139 | 11 | Other Electrical Power Storage Devices (Specify) |  | Component | Widget.png |  | datatable[146] = new Array("147","139","Other Electrical Power Storage Devices (Specify)","11","Widget.png");
148 | 117 | 10 | Harnesses and Cables |  | Assembly | Widget.png |  | datatable[147] = new Array("148","117","Harnesses and Cables","10","Widget.png");
149 | 117 | 10 | EPS Other (Specify) |  | Assembly | Widget.png |  | datatable[148] = new Array("149","117","EPS Other (Specify)","10","Widget.png");
150 | 61 | 9 | Attitude Control Subsystem (ACS) |  | Subsystem | Widget.png |  | datatable[149] = new Array("150","61","Attitude Control Subsystem (ACS)","9","Widget.png");
151 | 145 | 10 | Attitude Control Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[150] = new Array("151","145","Attitude Control Subsystem SEITPM","10","SEITPM.png");
152 | 146 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[151] = new Array("152","146","Project Management","11","SEITPM.png");
153 | 146 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[152] = new Array("153","146","Systems Engineering","11","SEITPM.png");
154 | 146 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[153] = new Array("154","146","Mission Assurance","11","SEITPM.png");
155 | 146 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[154] = new Array("155","146","Assembly, Integration and Testing","11","SEITPM.png");
156 | 146 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[155] = new Array("156","146","Support Equipment","11","SEITPM.png");
157 | 145 | 10 | Attitude Determination |  | Assembly | Widget.png |  | datatable[156] = new Array("157","145","Attitude Determination","10","Widget.png");
158 | 152 | 11 | Earth (Horizon) Sensors |  | Component | Widget.png |  | datatable[157] = new Array("158","152","Earth (Horizon) Sensors","11","Widget.png");
159 | 152 | 11 | Sun Sensors |  | Component | Widget.png |  | datatable[158] = new Array("159","152","Sun Sensors","11","Widget.png");
160 | 152 | 11 | Star Tracker/Sensors |  | Component | Widget.png |  | datatable[159] = new Array("160","152","Star Tracker/Sensors","11","Widget.png");
161 | 152 | 11 | Global Positioning System (GPS) Receiver |  | Component | Widget.png |  | datatable[160] = new Array("161","152","Global Positioning System (GPS) Receiver","11","Widget.png");
162 | 152 | 11 | Imagers |  | Component | Widget.png |  | datatable[161] = new Array("162","152","Imagers","11","Widget.png");
163 | 152 | 11 | Magnetometers |  | Component | Widget.png |  | datatable[162] = new Array("163","152","Magnetometers","11","Widget.png");
164 | 152 | 11 | Altimeters |  | Component | Widget.png |  | datatable[163] = new Array("164","152","Altimeters","11","Widget.png");
165 | 152 | 11 | Inertial Reference Unit (IRU)/Inertial Measurement Unit (IMU) |  | Component | Widget.png |  | datatable[164] = new Array("165","152","Inertial Reference Unit (IRU)/Inertial Measurement Unit (IMU)","11","Widget.png");
166 | 152 | 11 | Radar |  | Component | Widget.png |  | datatable[165] = new Array("166","152","Radar","11","Widget.png");
167 | 152 | 11 | Rate Gyros |  | Component | Widget.png |  | datatable[166] = new Array("167","152","Rate Gyros","11","Widget.png");
168 | 152 | 11 | Accelerometers |  | Component | Widget.png |  | datatable[167] = new Array("168","152","Accelerometers","11","Widget.png");
169 | 152 | 11 | Bearing and Power Transfer Assembly |  | Component | Widget.png |  | datatable[168] = new Array("169","152","Bearing and Power Transfer Assembly","11","Widget.png");
170 | 152 | 11 | Other Attitude Determination Devices (Specify) |  | Component | Widget.png |  | datatable[169] = new Array("170","152","Other Attitude Determination Devices (Specify)","11","Widget.png");
171 | 145 | 10 | Attitude Control |  | Assembly | Widget.png |  | datatable[170] = new Array("171","145","Attitude Control","10","Widget.png");
172 | 166 | 11 | Reaction Wheel |  | Component | Widget.png |  | datatable[171] = new Array("172","166","Reaction Wheel","11","Widget.png");
173 | 166 | 11 | Momentum Wheel |  | Component | Widget.png |  | datatable[172] = new Array("173","166","Momentum Wheel","11","Widget.png");
174 | 166 | 11 | Control Moment Gyro |  | Component | Widget.png |  | datatable[173] = new Array("174","166","Control Moment Gyro","11","Widget.png");
175 | 166 | 11 | Other Energy Storage Devices |  | Component | Widget.png |  | datatable[174] = new Array("175","166","Other Energy Storage Devices","11","Widget.png");
176 | 166 | 11 | Magnetic Control Devices |  | Component | Widget.png |  | datatable[175] = new Array("176","166","Magnetic Control Devices","11","Widget.png");
177 | 166 | 11 | Spin Control Devices |  | Component | Widget.png |  | datatable[176] = new Array("177","166","Spin Control Devices","11","Widget.png");
178 | 166 | 11 | Control Electronics |  | Component | Widget.png |  | datatable[177] = new Array("178","166","Control Electronics","11","Widget.png");
179 | 166 | 11 | Other Attitude Control Devices (Specify) |  | Component | Widget.png |  | datatable[178] = new Array("179","166","Other Attitude Control Devices (Specify)","11","Widget.png");
180 | 145 | 10 | ACS Other (Specify) |  | Assembly | Widget.png |  | datatable[179] = new Array("180","145","ACS Other (Specify)","10","Widget.png");
181 | 61 | 9 | Propulsion Subsystem |  | Subsystem | Widget.png |  | datatable[180] = new Array("181","61","Propulsion Subsystem","9","Widget.png");
182 | 176 | 10 | Propulsion Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[181] = new Array("182","176","Propulsion Subsystem SEITPM","10","SEITPM.png");
183 | 177 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[182] = new Array("183","177","Project Management","11","SEITPM.png");
184 | 177 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[183] = new Array("184","177","Systems Engineering","11","SEITPM.png");
185 | 177 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[184] = new Array("185","177","Mission Assurance","11","SEITPM.png");
186 | 177 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[185] = new Array("186","177","Assembly, Integration and Testing","11","SEITPM.png");
187 | 177 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[186] = new Array("187","177","Support Equipment","11","SEITPM.png");
188 | 176 | 10 | Tanks |  | Assembly | Widget.png |  | datatable[187] = new Array("188","176","Tanks","10","Widget.png");
189 | 183 | 11 | Oxidizer Tanks |  | Component | Widget.png |  | datatable[188] = new Array("189","183","Oxidizer Tanks","11","Widget.png");
190 | 183 | 11 | Fuel Tanks |  | Component | Widget.png |  | datatable[189] = new Array("190","183","Fuel Tanks","11","Widget.png");
191 | 183 | 11 | Propellant Tanks |  | Component | Widget.png |  | datatable[190] = new Array("191","183","Propellant Tanks","11","Widget.png");
192 | 183 | 11 | Pressurance Tanks |  | Component | Widget.png |  | datatable[191] = new Array("192","183","Pressurance Tanks","11","Widget.png");
193 | 183 | 11 | Plumbing |  | Component | Widget.png |  | datatable[192] = new Array("193","183","Plumbing","11","Widget.png");
194 | 183 | 11 | Other Tanks (Specify) |  | Component | Widget.png |  | datatable[193] = new Array("194","183","Other Tanks (Specify)","11","Widget.png");
195 | 176 | 10 | Maneuvering Thrusters |  | Assembly | Widget.png |  | datatable[194] = new Array("195","176","Maneuvering Thrusters","10","Widget.png");
196 | 190 | 11 | Bipropellant |  | Component | Widget.png |  | datatable[195] = new Array("196","190","Bipropellant","11","Widget.png");
197 | 190 | 11 | Monopropellant |  | Component | Widget.png |  | datatable[196] = new Array("197","190","Monopropellant","11","Widget.png");
198 | 190 | 11 | Solar Electric |  | Component | Widget.png |  | datatable[197] = new Array("198","190","Solar Electric","11","Widget.png");
199 | 190 | 11 | Ion |  | Component | Widget.png |  | datatable[198] = new Array("199","190","Ion","11","Widget.png");
200 | 190 | 11 | Cold Gas |  | Component | Widget.png |  | datatable[199] = new Array("200","190","Cold Gas","11","Widget.png");
201 | 190 | 11 | Other Maneuvering Thrusters (Specify) |  | Component | Widget.png |  | datatable[200] = new Array("201","190","Other Maneuvering Thrusters (Specify)","11","Widget.png");
202 | 176 | 10 | Translation Thrusters |  | Assembly | Widget.png |  | datatable[201] = new Array("202","176","Translation Thrusters","10","Widget.png");
203 | 197 | 11 | Bipropellant |  | Component | Widget.png |  | datatable[202] = new Array("203","197","Bipropellant","11","Widget.png");
204 | 197 | 11 | Monopropellant |  | Component | Widget.png |  | datatable[203] = new Array("204","197","Monopropellant","11","Widget.png");
205 | 197 | 11 | Solar Electric |  | Component | Widget.png |  | datatable[204] = new Array("205","197","Solar Electric","11","Widget.png");
206 | 197 | 11 | Ion |  | Component | Widget.png |  | datatable[205] = new Array("206","197","Ion","11","Widget.png");
207 | 197 | 11 | Cold Gas |  | Component | Widget.png |  | datatable[206] = new Array("207","197","Cold Gas","11","Widget.png");
208 | 197 | 11 | Other Translation Thrusters (Specify) |  | Component | Widget.png |  | datatable[207] = new Array("208","197","Other Translation Thrusters (Specify)","11","Widget.png");
209 | 176 | 10 | Propellant |  | Assembly | Widget.png |  | datatable[208] = new Array("209","176","Propellant","10","Widget.png");
210 | 204 | 11 | Solid Propellant |  | Component | Widget.png |  | datatable[209] = new Array("210","204","Solid Propellant","11","Widget.png");
211 | 204 | 11 | Liquid Propellant |  | Component | Widget.png |  | datatable[210] = new Array("211","204","Liquid Propellant","11","Widget.png");
212 | 204 | 11 | Prussurant Propellant |  | Component | Widget.png |  | datatable[211] = new Array("212","204","Prussurant Propellant","11","Widget.png");
213 | 204 | 11 | Other Propellant (Specify) |  | Component | Widget.png |  | datatable[212] = new Array("213","204","Other Propellant (Specify)","11","Widget.png");
214 | 176 | 11 | Solid Rocket Motors |  | Component | Widget.png |  | datatable[213] = new Array("214","176","Solid Rocket Motors","11","Widget.png");
215 | 176 | 11 | Power Electronics |  | Component | Widget.png |  | datatable[214] = new Array("215","176","Power Electronics","11","Widget.png");
216 | 176 | 11 | Propulsion Other (Specify) |  | Component | Widget.png |  | datatable[215] = new Array("216","176","Propulsion Other (Specify)","11","Widget.png");
217 | 61 | 9 | Telemetry, Tracking, and Command Subsystem (TT&C) |  | Subsystem | Widget.png |  | datatable[216] = new Array("217","61","Telemetry, Tracking, and Command Subsystem (TT&C)","9","Widget.png");
218 | 212 | 10 | TT&C Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[217] = new Array("218","212","TT&C Subsystem SEITPM","10","SEITPM.png");
219 | 213 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[218] = new Array("219","213","Project Management","11","SEITPM.png");
220 | 213 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[219] = new Array("220","213","Systems Engineering","11","SEITPM.png");
221 | 213 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[220] = new Array("221","213","Mission Assurance","11","SEITPM.png");
222 | 213 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[221] = new Array("222","213","Assembly, Integration and Testing","11","SEITPM.png");
223 | 213 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[222] = new Array("223","213","Support Equipment","11","SEITPM.png");
224 | 212 | 10 | Antennas |  | Assembly | Widget.png |  | datatable[223] = new Array("224","212","Antennas","10","Widget.png");
225 | 219 | 11 | Omnidirectional |  | Component | Widget.png |  | datatable[224] = new Array("225","219","Omnidirectional","11","Widget.png");
226 | 219 | 11 | Spiral |  | Component | Widget.png |  | datatable[225] = new Array("226","219","Spiral","11","Widget.png");
227 | 219 | 11 | Horn |  | Component | Widget.png |  | datatable[226] = new Array("227","219","Horn","11","Widget.png");
228 | 219 | 11 | Patch |  | Component | Widget.png |  | datatable[227] = new Array("228","219","Patch","11","Widget.png");
229 | 219 | 11 | Parabolic |  | Component | Widget.png |  | datatable[228] = new Array("229","219","Parabolic","11","Widget.png");
230 | 219 | 11 | Phased Array |  | Component | Widget.png |  | datatable[229] = new Array("230","219","Phased Array","11","Widget.png");
231 | 219 | 11 | Other Antennas (Specify) |  | Component | Widget.png |  | datatable[230] = new Array("231","219","Other Antennas (Specify)","11","Widget.png");
232 | 212 | 10 | Waveguides/Routers |  | Assembly | Widget.png |  | datatable[231] = new Array("232","212","Waveguides/Routers","10","Widget.png");
233 | 227 | 11 | Diplexers |  | Component | Widget.png |  | datatable[232] = new Array("233","227","Diplexers","11","Widget.png");
234 | 227 | 11 | Triplexers |  | Component | Widget.png |  | datatable[233] = new Array("234","227","Triplexers","11","Widget.png");
235 | 227 | 11 | Multiplexers |  | Component | Widget.png |  | datatable[234] = new Array("235","227","Multiplexers","11","Widget.png");
236 | 227 | 11 | Multicouplers |  | Component | Widget.png |  | datatable[235] = new Array("236","227","Multicouplers","11","Widget.png");
237 | 227 | 11 | Coaxial Switches |  | Component | Widget.png |  | datatable[236] = new Array("237","227","Coaxial Switches","11","Widget.png");
238 | 227 | 11 | RF Switches |  | Component | Widget.png |  | datatable[237] = new Array("238","227","RF Switches","11","Widget.png");
239 | 227 | 11 | Filters |  | Component | Widget.png |  | datatable[238] = new Array("239","227","Filters","11","Widget.png");
240 | 227 | 11 | Waveguides |  | Component | Widget.png |  | datatable[239] = new Array("240","227","Waveguides","11","Widget.png");
241 | 227 | 11 | Other Routers (Specify) |  | Component | Widget.png |  | datatable[240] = new Array("241","227","Other Routers (Specify)","11","Widget.png");
242 | 212 | 10 | Radio Frequency Equipment |  | Assembly | Widget.png |  | datatable[241] = new Array("242","212","Radio Frequency Equipment","10","Widget.png");
243 | 237 | 11 | Amplifiers |  | Component | Widget.png |  | datatable[242] = new Array("243","237","Amplifiers","11","Widget.png");
244 | 237 | 11 | Receivers |  | Component | Widget.png |  | datatable[243] = new Array("244","237","Receivers","11","Widget.png");
245 | 237 | 11 | Transmitters |  | Component | Widget.png |  | datatable[244] = new Array("245","237","Transmitters","11","Widget.png");
246 | 237 | 11 | Transceivers |  | Component | Widget.png |  | datatable[245] = new Array("246","237","Transceivers","11","Widget.png");
247 | 237 | 11 | Transponders |  | Component | Widget.png |  | datatable[246] = new Array("247","237","Transponders","11","Widget.png");
248 | 237 | 11 | Modulators |  | Component | Widget.png |  | datatable[247] = new Array("248","237","Modulators","11","Widget.png");
249 | 237 | 11 | Demodulators |  | Component | Widget.png |  | datatable[248] = new Array("249","237","Demodulators","11","Widget.png");
250 | 237 | 11 | Modems |  | Component | Widget.png |  | datatable[249] = new Array("250","237","Modems","11","Widget.png");
251 | 237 | 11 | Traveling Wave Tube Assemblies |  | Component | Widget.png |  | datatable[250] = new Array("251","237","Traveling Wave Tube Assemblies","11","Widget.png");
252 | 237 | 11 | Solid State Power Amplifiers |  | Component | Widget.png |  | datatable[251] = new Array("252","237","Solid State Power Amplifiers","11","Widget.png");
253 | 237 | 11 | Global Positioning System (GPS) Receiver |  | Component | Widget.png |  | datatable[252] = new Array("253","237","Global Positioning System (GPS) Receiver","11","Widget.png");
254 | 237 | 11 | Downconverters |  | Component | Widget.png |  | datatable[253] = new Array("254","237","Downconverters","11","Widget.png");
255 | 237 | 11 | Upconverters |  | Component | Widget.png |  | datatable[254] = new Array("255","237","Upconverters","11","Widget.png");
256 | 237 | 11 | Other RF Equipment (Specify) |  | Component | Widget.png |  | datatable[255] = new Array("256","237","Other RF Equipment (Specify)","11","Widget.png");
257 | 212 | 10 | Command and Data Handling (C&DH) |  | Assembly | Widget.png |  | datatable[256] = new Array("257","212","Command and Data Handling (C&DH)","10","Widget.png");
258 | 252 | 11 | Processors |  | Component | Widget.png |  | datatable[257] = new Array("258","252","Processors","11","Widget.png");
259 | 252 | 11 | Solid State Memory |  | Component | Widget.png |  | datatable[258] = new Array("259","252","Solid State Memory","11","Widget.png");
260 | 252 | 11 | Decoders |  | Component | Widget.png |  | datatable[259] = new Array("260","252","Decoders","11","Widget.png");
261 | 252 | 11 | Command Units |  | Component | Widget.png |  | datatable[260] = new Array("261","252","Command Units","11","Widget.png");
262 | 252 | 11 | Telemetry Units |  | Component | Widget.png |  | datatable[261] = new Array("262","252","Telemetry Units","11","Widget.png");
263 | 252 | 11 | Command Sequencers |  | Component | Widget.png |  | datatable[262] = new Array("263","252","Command Sequencers","11","Widget.png");
264 | 252 | 11 | Timing Units |  | Component | Widget.png |  | datatable[263] = new Array("264","252","Timing Units","11","Widget.png");
265 | 252 | 11 | Frequency Generators |  | Component | Widget.png |  | datatable[264] = new Array("265","252","Frequency Generators","11","Widget.png");
266 | 252 | 11 | Signal Conditioners |  | Component | Widget.png |  | datatable[265] = new Array("266","252","Signal Conditioners","11","Widget.png");
267 | 252 | 11 | Data Switches |  | Component | Widget.png |  | datatable[266] = new Array("267","252","Data Switches","11","Widget.png");
268 | 252 | 11 | Communication Security |  | Component | Widget.png |  | datatable[267] = new Array("268","252","Communication Security","11","Widget.png");
269 | 252 | 11 | Interface Units |  | Component | Widget.png |  | datatable[268] = new Array("269","252","Interface Units","11","Widget.png");
270 | 252 | 11 | Tape Recorders |  | Component | Widget.png |  | datatable[269] = new Array("270","252","Tape Recorders","11","Widget.png");
271 | 252 | 11 | Disk Recorders |  | Component | Widget.png |  | datatable[270] = new Array("271","252","Disk Recorders","11","Widget.png");
272 | 252 | 11 | Command Sensor or Situational Awareness Sensors |  | Component | Widget.png |  | datatable[271] = new Array("272","252","Command Sensor or Situational Awareness Sensors","11","Widget.png");
273 | 252 | 11 | Other C&DH (Specify) |  | Component | Widget.png |  | datatable[272] = new Array("273","252","Other C&DH (Specify)","11","Widget.png");
274 | 212 | 10 | TT&C Other (Specify) |  | Assembly | Widget.png |  | datatable[273] = new Array("274","212","TT&C Other (Specify)","10","Widget.png");
275 | 61 | 9 | Bus Flight Software |  | Subsystem | Widget.png |  | datatable[274] = new Array("275","61","Bus Flight Software","9","Widget.png");
276 | 275 | 10 | Bus FSW Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[275] = new Array("276","275","Bus FSW Subsystem SEITPM","10","SEITPM.png");
277 | 271 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[276] = new Array("277","271","Project Management","11","SEITPM.png");
278 | 271 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[277] = new Array("278","271","Systems Engineering","11","SEITPM.png");
279 | 271 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[278] = new Array("279","271","Mission Assurance","11","SEITPM.png");
280 | 271 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[279] = new Array("280","271","Assembly, Integration and Testing","11","SEITPM.png");
281 | 271 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[280] = new Array("281","271","Support Equipment","11","SEITPM.png");
282 | 270 | 11 | Thermal Control Software |  | Component | Widget.png |  | datatable[281] = new Array("282","270","Thermal Control Software","11","Widget.png");
283 | 270 | 11 | Electrical Power Software |  | Component | Widget.png |  | datatable[282] = new Array("283","270","Electrical Power Software","11","Widget.png");
284 | 270 | 11 | Attitude Control Software |  | Component | Widget.png |  | datatable[283] = new Array("284","270","Attitude Control Software","11","Widget.png");
285 | 270 | 11 | Telemetry, Tracking, and Command Software |  | Component | Widget.png |  | datatable[284] = new Array("285","270","Telemetry, Tracking, and Command Software","11","Widget.png");
286 | 270 | 11 | Other Flight Software (Specify) |  | Component | Widget.png |  | datatable[285] = new Array("286","270","Other Flight Software (Specify)","11","Widget.png");
287 | 59 | 8 | SEITPM and Support Equipment (If Applicable for Integration of Multiple Payloads) |  | System | SEITPM.png |  | datatable[286] = new Array("287","59","SEITPM and Support Equipment (If Applicable for Integration of Multiple Payloads)","8","SEITPM.png");
288 | 282 | 9 | Project Management |  | Subsystem | SEITPM.png |  | datatable[287] = new Array("288","282","Project Management","9","SEITPM.png");
289 | 282 | 9 | Systems Engineering |  | Subsystem | SEITPM.png |  | datatable[288] = new Array("289","282","Systems Engineering","9","SEITPM.png");
290 | 282 | 9 | Mission Assurance |  | Subsystem | SEITPM.png |  | datatable[289] = new Array("290","282","Mission Assurance","9","SEITPM.png");
291 | 282 | 9 | Assembly, Integration and Testing |  | Subsystem | SEITPM.png |  | datatable[290] = new Array("291","282","Assembly, Integration and Testing","9","SEITPM.png");
292 | 282 | 9 | Support Equipment |  | Subsystem | SEITPM.png |  | datatable[291] = new Array("292","282","Support Equipment","9","SEITPM.png");
293 | 59 | 8 | Payload 1 … n (Specify) |  | System | Widget.png |  | datatable[292] = new Array("293","59","Payload 1 … n (Specify)","8","Widget.png");
294 | 293 | 9 | Payload 1 SEITPM and Support Equipment |  | Subsystem | SEITPM.png |  | datatable[293] = new Array("294","293","Payload 1 SEITPM and Support Equipment","9","SEITPM.png");
295 | 289 | 10 | Project Management |  | Assembly | SEITPM.png |  | datatable[294] = new Array("295","289","Project Management","10","SEITPM.png");
296 | 289 | 10 | Systems Engineering |  | Assembly | SEITPM.png |  | datatable[295] = new Array("296","289","Systems Engineering","10","SEITPM.png");
297 | 289 | 10 | Mission Assurance |  | Assembly | SEITPM.png |  | datatable[296] = new Array("297","289","Mission Assurance","10","SEITPM.png");
298 | 289 | 10 | Assembly, Integration and Testing |  | Assembly | SEITPM.png |  | datatable[297] = new Array("298","289","Assembly, Integration and Testing","10","SEITPM.png");
299 | 289 | 10 | Support Equipment |  | Assembly | SEITPM.png |  | datatable[298] = new Array("299","289","Support Equipment","10","SEITPM.png");
300 | 288 | 9 | Payload 1 Structures and Mechanisms Subsystem |  | Subsystem | Widget.png |  | datatable[299] = new Array("300","288","Payload 1 Structures and Mechanisms Subsystem","9","Widget.png");
301 | 295 | 10 | Structures and Mechanims Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[300] = new Array("301","295","Structures and Mechanims Subsystem SEITPM","10","SEITPM.png");
302 | 296 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[301] = new Array("302","296","Project Management","11","SEITPM.png");
303 | 296 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[302] = new Array("303","296","Systems Engineering","11","SEITPM.png");
304 | 296 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[303] = new Array("304","296","Mission Assurance","11","SEITPM.png");
305 | 296 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[304] = new Array("305","296","Assembly, Integration and Testing","11","SEITPM.png");
306 | 296 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[305] = new Array("306","296","Support Equipment","11","SEITPM.png");
307 | 295 | 10 | Structures |  | Assembly | Widget.png |  | datatable[306] = new Array("307","295","Structures","10","Widget.png");
308 | 295 | 10 | Mechanisms and Pyrotechnics |  | Assembly | Widget.png |  | datatable[307] = new Array("308","295","Mechanisms and Pyrotechnics","10","Widget.png");
309 | 295 | 10 | Structures and Mechanisms Other (Specify) |  | Assembly | Widget.png |  | datatable[308] = new Array("309","295","Structures and Mechanisms Other (Specify)","10","Widget.png");
310 | 288 | 9 | Payload 1 Thermal Control Subsystem |  | Subsystem | Widget.png |  | datatable[309] = new Array("310","288","Payload 1 Thermal Control Subsystem","9","Widget.png");
311 | 310 | 10 | Thermal Control Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[310] = new Array("311","310","Thermal Control Subsystem SEITPM","10","SEITPM.png");
312 | 306 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[311] = new Array("312","306","Project Management","11","SEITPM.png");
313 | 306 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[312] = new Array("313","306","Systems Engineering","11","SEITPM.png");
314 | 306 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[313] = new Array("314","306","Mission Assurance","11","SEITPM.png");
315 | 306 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[314] = new Array("315","306","Assembly, Integration and Testing","11","SEITPM.png");
316 | 306 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[315] = new Array("316","306","Support Equipment","11","SEITPM.png");
317 | 316 | 10 | Cryogenic Devices |  | Assembly | Widget.png |  | datatable[316] = new Array("317","316","Cryogenic Devices","10","Widget.png");
318 | 317 | 10 | Liquid Loops |  | Assembly | Widget.png |  | datatable[317] = new Array("318","317","Liquid Loops","10","Widget.png");
319 | 318 | 10 | Electric Coolers |  | Assembly | Widget.png |  | datatable[318] = new Array("319","318","Electric Coolers","10","Widget.png");
320 | 319 | 10 | Electric heaters, Thermisters, and Thermostats |  | Assembly | Widget.png |  | datatable[319] = new Array("320","319","Electric heaters, Thermisters, and Thermostats","10","Widget.png");
321 | 320 | 10 | Passive Devices |  | Assembly | Widget.png |  | datatable[320] = new Array("321","320","Passive Devices","10","Widget.png");
322 | 321 | 10 | Sun Shields |  | Assembly | Widget.png |  | datatable[321] = new Array("322","321","Sun Shields","10","Widget.png");
323 | 322 | 10 | Thermal Control Other (Specify) |  | Assembly | Widget.png |  | datatable[322] = new Array("323","322","Thermal Control Other (Specify)","10","Widget.png");
324 | 288 | 9 | Payload 1 Electrical Power Subsystem |  | Subsystem | Widget.png |  | datatable[323] = new Array("324","288","Payload 1 Electrical Power Subsystem","9","Widget.png");
325 | 319 | 10 | Electrical Power Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[324] = new Array("325","319","Electrical Power Subsystem SEITPM","10","SEITPM.png");
326 | 320 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[325] = new Array("326","320","Project Management","11","SEITPM.png");
327 | 320 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[326] = new Array("327","320","Systems Engineering","11","SEITPM.png");
328 | 320 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[327] = new Array("328","320","Mission Assurance","11","SEITPM.png");
329 | 320 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[328] = new Array("329","320","Assembly, Integration and Testing","11","SEITPM.png");
330 | 320 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[329] = new Array("330","320","Support Equipment","11","SEITPM.png");
331 | 319 | 10 | Power Sources |  | Assembly | Widget.png |  | datatable[330] = new Array("331","319","Power Sources","10","Widget.png");
332 | 319 | 10 | Power Control, Switching, and Distribution Electronics |  | Assembly | Widget.png |  | datatable[331] = new Array("332","319","Power Control, Switching, and Distribution Electronics","10","Widget.png");
333 | 319 | 10 | Power Conditioning, Conversion, and Regulation |  | Assembly | Widget.png |  | datatable[332] = new Array("333","319","Power Conditioning, Conversion, and Regulation","10","Widget.png");
334 | 319 | 10 | Harnesses and Cables |  | Assembly | Widget.png |  | datatable[333] = new Array("334","319","Harnesses and Cables","10","Widget.png");
335 | 319 | 10 | Electrical Power Other (Specify) |  | Assembly | Widget.png |  | datatable[334] = new Array("335","319","Electrical Power Other (Specify)","10","Widget.png");
336 | 288 | 9 | Payload 1 Pointing, Command, and Control Interface |  | Subsystem | Widget.png |  | datatable[335] = new Array("336","288","Payload 1 Pointing, Command, and Control Interface","9","Widget.png");
337 | 336 | 10 | Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[336] = new Array("337","336","Subsystem SEITPM","10","SEITPM.png");
338 | 332 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[337] = new Array("338","332","Project Management","11","SEITPM.png");
339 | 332 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[338] = new Array("339","332","Systems Engineering","11","SEITPM.png");
340 | 332 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[339] = new Array("340","332","Mission Assurance","11","SEITPM.png");
341 | 332 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[340] = new Array("341","332","Assembly, Integration and Testing","11","SEITPM.png");
342 | 332 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[341] = new Array("342","332","Support Equipment","11","SEITPM.png");
343 | 331 | 10 | Computers and Processors |  | Assembly | Widget.png |  | datatable[342] = new Array("343","331","Computers and Processors","10","Widget.png");
344 | 331 | 10 | Command/Telemetric Units |  | Assembly | Widget.png |  | datatable[343] = new Array("344","331","Command/Telemetric Units","10","Widget.png");
345 | 331 | 10 | Control Electronics |  | Assembly | Widget.png |  | datatable[344] = new Array("345","331","Control Electronics","10","Widget.png");
346 | 331 | 10 | Pointing Sensors |  | Assembly | Widget.png |  | datatable[345] = new Array("346","331","Pointing Sensors","10","Widget.png");
347 | 331 | 10 | Payload Positioners |  | Assembly | Widget.png |  | datatable[346] = new Array("347","331","Payload Positioners","10","Widget.png");
348 | 331 | 10 | Security, Encryption, and Decryption Devices |  | Assembly | Widget.png |  | datatable[347] = new Array("348","331","Security, Encryption, and Decryption Devices","10","Widget.png");
349 | 331 | 10 | Data Storage, handling, and Interface |  | Assembly | Widget.png |  | datatable[348] = new Array("349","331","Data Storage, handling, and Interface","10","Widget.png");
350 | 331 | 10 | Multifunctional Digital Electronic Boxes |  | Assembly | Widget.png |  | datatable[349] = new Array("350","331","Multifunctional Digital Electronic Boxes","10","Widget.png");
351 | 331 | 10 | Pointing, Command, and Control Interface Other (Specify) |  | Assembly | Widget.png |  | datatable[350] = new Array("351","331","Pointing, Command, and Control Interface Other (Specify)","10","Widget.png");
352 | 288 | 9 | Payload Signal Electronics |  | Subsystem | Widget.png |  | datatable[351] = new Array("352","288","Payload Signal Electronics","9","Widget.png");
353 | 347 | 10 | Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[352] = new Array("353","347","Subsystem SEITPM","10","SEITPM.png");
354 | 348 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[353] = new Array("354","348","Project Management","11","SEITPM.png");
355 | 348 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[354] = new Array("355","348","Systems Engineering","11","SEITPM.png");
356 | 348 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[355] = new Array("356","348","Mission Assurance","11","SEITPM.png");
357 | 348 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[356] = new Array("357","348","Assembly, Integration and Testing","11","SEITPM.png");
358 | 348 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[357] = new Array("358","348","Support Equipment","11","SEITPM.png");
359 | 347 | 10 | Passive Signal Flow Control |  | Assembly | Widget.png |  | datatable[358] = new Array("359","347","Passive Signal Flow Control","10","Widget.png");
360 | 347 | 10 | Transmitter/Receiver/Transceiver/Transponder |  | Assembly | Widget.png |  | datatable[359] = new Array("360","347","Transmitter/Receiver/Transceiver/Transponder","10","Widget.png");
361 | 347 | 10 | Modulators/Demodulators/Modems |  | Assembly | Widget.png |  | datatable[360] = new Array("361","347","Modulators/Demodulators/Modems","10","Widget.png");
362 | 347 | 10 | Multiplexers/Demultiplexers |  | Assembly | Widget.png |  | datatable[361] = new Array("362","347","Multiplexers/Demultiplexers","10","Widget.png");
363 | 347 | 10 | Amplifiers |  | Assembly | Widget.png |  | datatable[362] = new Array("363","347","Amplifiers","10","Widget.png");
364 | 347 | 10 | Frequency Upconverters/Downconverters |  | Assembly | Widget.png |  | datatable[363] = new Array("364","347","Frequency Upconverters/Downconverters","10","Widget.png");
365 | 347 | 10 | Frequency and Timing |  | Assembly | Widget.png |  | datatable[364] = new Array("365","347","Frequency and Timing","10","Widget.png");
366 | 347 | 10 | Signal Conditioners |  | Assembly | Widget.png |  | datatable[365] = new Array("366","347","Signal Conditioners","10","Widget.png");
367 | 347 | 10 | Multifunctional Digital Electronic Boxes |  | Assembly | Widget.png |  | datatable[366] = new Array("367","347","Multifunctional Digital Electronic Boxes","10","Widget.png");
368 | 347 | 10 | Signal Electronics Other (Specify) |  | Assembly | Widget.png |  | datatable[367] = new Array("368","347","Signal Electronics Other (Specify)","10","Widget.png");
369 | 288 | 9 | Payload 1 Optical Assembly |  | Subsystem | Widget.png |  | datatable[368] = new Array("369","288","Payload 1 Optical Assembly","9","Widget.png");
370 | 364 | 10 | Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[369] = new Array("370","364","Subsystem SEITPM","10","SEITPM.png");
371 | 365 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[370] = new Array("371","365","Project Management","11","SEITPM.png");
372 | 365 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[371] = new Array("372","365","Systems Engineering","11","SEITPM.png");
373 | 365 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[372] = new Array("373","365","Mission Assurance","11","SEITPM.png");
374 | 365 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[373] = new Array("374","365","Assembly, Integration and Testing","11","SEITPM.png");
375 | 365 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[374] = new Array("375","365","Support Equipment","11","SEITPM.png");
376 | 364 | 10 | Structure/Outerbarrel/Cover |  | Assembly | Widget.png |  | datatable[375] = new Array("376","364","Structure/Outerbarrel/Cover","10","Widget.png");
377 | 364 | 10 | Mirrors/Optics |  | Assembly | Widget.png |  | datatable[376] = new Array("377","364","Mirrors/Optics","10","Widget.png");
378 | 364 | 10 | Aft Optics Assembly |  | Assembly | Widget.png |  | datatable[377] = new Array("378","364","Aft Optics Assembly","10","Widget.png");
379 | 364 | 10 | Alignment and Calibration |  | Assembly | Widget.png |  | datatable[378] = new Array("379","364","Alignment and Calibration","10","Widget.png");
380 | 364 | 10 | Thermal |  | Assembly | Widget.png |  | datatable[379] = new Array("380","364","Thermal","10","Widget.png");
374 | 364 | 10 | Control Electronics |  | Assembly | Widget.png |  | datatable[373] = new Array("374","364","Control Electronics","10","Widget.png");
375 | 364 | 10 | Optical Assembly Other |  | Assembly | Widget.png |  | datatable[374] = new Array("375","364","Optical Assembly Other","10","Widget.png");
376 | 288 | 9 | Payload 1 Sensor |  | Subsystem | Widget.png |  | datatable[375] = new Array("376","288","Payload 1 Sensor","9","Widget.png");
377 | 378 | 10 | Sensor SEITPM |  | Assembly | SEITPM.png |  | datatable[376] = new Array("377","378","Sensor SEITPM","10","SEITPM.png");
378 | 379 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[377] = new Array("378","379","Project Management","11","SEITPM.png");
379 | 379 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[378] = new Array("379","379","Systems Engineering","11","SEITPM.png");
380 | 379 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[379] = new Array("380","379","Mission Assurance","11","SEITPM.png");
381 | 379 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[380] = new Array("381","379","Assembly, Integration and Testing","11","SEITPM.png");
382 | 379 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[381] = new Array("382","379","Support Equipment","11","SEITPM.png");
383 | 378 | 10 | Payload Structure |  | Assembly | Widget.png |  | datatable[382] = new Array("383","378","Payload Structure","10","Widget.png");
384 | 378 | 10 | Focal Plan Array |  | Assembly | Widget.png |  | datatable[383] = new Array("384","378","Focal Plan Array","10","Widget.png");
385 | 378 | 10 | Sensor Positioners |  | Assembly | Widget.png |  | datatable[384] = new Array("385","378","Sensor Positioners","10","Widget.png");
386 | 378 | 10 | Sensor Electronics |  | Assembly | Widget.png |  | datatable[385] = new Array("386","378","Sensor Electronics","10","Widget.png");
387 | 378 | 10 | Alignment and Calibration |  | Assembly | Widget.png |  | datatable[386] = new Array("387","378","Alignment and Calibration","10","Widget.png");
388 | 378 | 10 | Magnetometer |  | Assembly | Widget.png |  | datatable[387] = new Array("388","378","Magnetometer","10","Widget.png");
389 | 378 | 10 | Spectrometer |  | Assembly | Widget.png |  | datatable[388] = new Array("389","378","Spectrometer","10","Widget.png");
390 | 378 | 10 | Radiometer |  | Assembly | Widget.png |  | datatable[389] = new Array("390","378","Radiometer","10","Widget.png");
391 | 378 | 10 | Camera |  | Assembly | Widget.png |  | datatable[390] = new Array("391","378","Camera","10","Widget.png");
392 | 378 | 10 | Sounder |  | Assembly | Widget.png |  | datatable[391] = new Array("392","378","Sounder","10","Widget.png");
393 | 378 | 10 | Flight Sensor Software |  | Assembly | Widget.png |  | datatable[392] = new Array("393","378","Flight Sensor Software","10","Widget.png");
394 | 378 | 10 | Other Sensor Types (Specify) |  | Assembly | Widget.png |  | datatable[393] = new Array("394","378","Other Sensor Types (Specify)","10","Widget.png");
395 | 378 | 10 | Mission Sensor Other (Specify) |  | Assembly | Widget.png |  | datatable[394] = new Array("395","378","Mission Sensor Other (Specify)","10","Widget.png");
396 | 288 | 9 | Payload Flight Software |  | Subsystem | Widget.png |  | datatable[395] = new Array("396","288","Payload Flight Software","9","Widget.png");
397 | 396 | 10 | Payload 1 FSW SEITPM |  | Assembly | SEITPM.png |  | datatable[396] = new Array("397","396","Payload 1 FSW SEITPM","10","SEITPM.png");
398 | 392 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[397] = new Array("398","392","Project Management","11","SEITPM.png");
399 | 392 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[398] = new Array("399","392","Systems Engineering","11","SEITPM.png");
400 | 392 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[399] = new Array("400","392","Mission Assurance","11","SEITPM.png");
401 | 392 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[400] = new Array("401","392","Assembly, Integration and Testing","11","SEITPM.png");
402 | 392 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[401] = new Array("402","392","Support Equipment","11","SEITPM.png");
403 | 396 | 10 | CSCI (Specify) |  | Assembly | Widget.png |  | datatable[402] = new Array("403","396","CSCI (Specify)","10","Widget.png");
404 | 288 | 9 | Payload Antenna 1 … n (Specify) |  | Subsystem | Widget.png |  | datatable[403] = new Array("404","288","Payload Antenna 1 … n (Specify)","9","Widget.png");
405 | 399 | 10 | Payload 1 Antenna SEITPM |  | Assembly | SEITPM.png |  | datatable[404] = new Array("405","399","Payload 1 Antenna SEITPM","10","SEITPM.png");
406 | 400 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[405] = new Array("406","400","Project Management","11","SEITPM.png");
407 | 400 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[406] = new Array("407","400","Systems Engineering","11","SEITPM.png");
408 | 400 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[407] = new Array("408","400","Mission Assurance","11","SEITPM.png");
409 | 400 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[408] = new Array("409","400","Assembly, Integration and Testing","11","SEITPM.png");
410 | 400 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[409] = new Array("410","400","Support Equipment","11","SEITPM.png");
411 | 399 | 10 | Structures and Mechanisms |  | Assembly | Widget.png |  | datatable[410] = new Array("411","399","Structures and Mechanisms","10","Widget.png");
412 | 399 | 10 | Antenna Positioners |  | Assembly | Widget.png |  | datatable[411] = new Array("412","399","Antenna Positioners","10","Widget.png");
413 | 399 | 10 | Reflector/Horn |  | Assembly | Widget.png |  | datatable[412] = new Array("413","399","Reflector/Horn","10","Widget.png");
414 | 399 | 10 | Feed |  | Assembly | Widget.png |  | datatable[413] = new Array("414","399","Feed","10","Widget.png");
415 | 399 | 10 | Waveguide/Coad/Cabling |  | Assembly | Widget.png |  | datatable[414] = new Array("415","399","Waveguide/Coad/Cabling","10","Widget.png");
416 | 399 | 10 | Transmit/Receive Modules |  | Assembly | Widget.png |  | datatable[415] = new Array("416","399","Transmit/Receive Modules","10","Widget.png");
417 | 399 | 10 | Antenna Other (Specify) |  | Assembly | Widget.png |  | datatable[416] = new Array("417","399","Antenna Other (Specify)","10","Widget.png");
418 | 288 | 9 | Payload Other (Specify) |  | Subsystem | Widget.png |  | datatable[417] = new Array("418","288","Payload Other (Specify)","9","Widget.png");
419 | 418 | 10 | Booster Adapter |  | Assembly | Widget.png |  | datatable[418] = new Array("419","418","Booster Adapter","10","Widget.png");
420 | 418 | 10 | Space Vehicle Storage |  | Assembly | Widget.png |  | datatable[419] = new Array("420","418","Space Vehicle Storage","10","Widget.png");
421 | 418 | 10 | Space Vehicle Other (Specify) |  | Assembly | Widget.png |  | datatable[420] = new Array("421","418","Space Vehicle Other (Specify)","10","Widget.png");
422 | 12 | 7 | Launch Systems Integration (LSI) |  |  | Rocket.png |  | datatable[421] = new Array("422","12","Launch Systems Integration (LSI)","7","Rocket.png");
423 | 12 | 7 | Launch Operations |  |  | Rocket.png |  | datatable[422] = new Array("423","12","Launch Operations","7","Rocket.png");
424 | 12 | 7 | Launch Operations Support |  |  | Rocket.png |  | datatable[423] = new Array("424","12","Launch Operations Support","7","Rocket.png");
425 | 12 | 7 | Launch Vehicle Services |  |  | Rocket.png |  | datatable[424] = new Array("425","12","Launch Vehicle Services","7","Rocket.png");
426 | 12 | 7 | Launch Insurance |  |  | Rocket.png |  | datatable[425] = new Array("426","12","Launch Insurance","7","Rocket.png");
427 | 13 | 7 | Ground Segment SEITPM |  | Assembly | SEITPM.png |  | datatable[426] = new Array("427","13","Ground Segment SEITPM","7","SEITPM.png");
428 | 422 | 8 | Project Management |  | Component | SEITPM.png |  | datatable[427] = new Array("428","422","Project Management","8","SEITPM.png");
429 | 422 | 8 | Systems Engineering |  | Component | SEITPM.png |  | datatable[428] = new Array("429","422","Systems Engineering","8","SEITPM.png");
430 | 422 | 8 | Mission Assurance |  | Component | SEITPM.png |  | datatable[429] = new Array("430","422","Mission Assurance","8","SEITPM.png");
431 | 422 | 8 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[430] = new Array("431","422","Assembly, Integration and Testing","8","SEITPM.png");
432 | 422 | 8 | Support Equipment |  | Component | SEITPM.png |  | datatable[431] = new Array("432","422","Support Equipment","8","SEITPM.png");
433 | 13 | 7 | Mission Control Centers |  |  | Facility.png |  | datatable[432] = new Array("433","13","Mission Control Centers","7","Facility.png");
434 | 13 | 7 | Science / Data Ops Centers |  |  | Facility.png |  | datatable[433] = new Array("434","13","Science / Data Ops Centers","7","Facility.png");
435 | 13 | 7 | Terminals and Data Networks – incl Antennas |  |  | Facility.png |  | datatable[434] = new Array("435","13","Terminals and Data Networks – incl Antennas ","7","Facility.png");
436 | 13 | 7 | Data Distribution & Archival |  |  | Facility.png |  | datatable[435] = new Array("436","13","Data Distribution & Archival ","7","Facility.png");
437 | 13 | 7 | Training Facilities |  |  | Facility.png |  | datatable[436] = new Array("437","13","Training Facilities ","7","Facility.png");
438 | 433 | 8 | CSA Mission Control |  |  | Facility.png |  | datatable[437] = new Array("438","433","CSA Mission Control","8","Facility.png");
439 | 438 | 9 | SatOps Mission Control Complex at JHCSC |  |  | Facility.png |  | datatable[438] = new Array("439","438","SatOps Mission Control Complex at JHCSC ","9","Facility.png");
440 | 438 | 9 | ISS Mission Operations Complex |  |  | Facility.png |  | datatable[439] = new Array("440","438","ISS Mission Operations Complex","9","Facility.png");
441 | 433 | 8 | NASA Mission Operations Complex |  |  | Facility.png |  | datatable[440] = new Array("441","433","NASA Mission Operations Complex","8","Facility.png");
442 | 435 | 10 | RMPSR |  |  | Facility.png |  | datatable[441] = new Array("442","435","RMPSR","10","Facility.png");
443 | 435 | 10 | OEC |  |  | Facility.png |  | datatable[442] = new Array("443","435","OEC","10","Facility.png");
444 | 435 | 10 | PTOC |  |  | Facility.png |  | datatable[443] = new Array("444","435","PTOC","10","Facility.png");
445 | 439 | 10 | SatOps Mission control SEITPM |  | Assembly | SEITPM.png |  | datatable[444] = new Array("445","439","SatOps Mission control SEITPM","10","SEITPM.png");
446 | 440 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[445] = new Array("446","440","Project Management","11","SEITPM.png");
447 | 440 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[446] = new Array("447","440","Systems Engineering","11","SEITPM.png");
448 | 440 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[447] = new Array("448","440","Mission Assurance","11","SEITPM.png");
449 | 440 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[448] = new Array("449","440","Assembly, Integration and Testing","11","SEITPM.png");
450 | 440 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[449] = new Array("450","440","Support Equipment","11","SEITPM.png");
451 | 434 | 10 | Hardware Components |  |  | Facility.png |  | datatable[450] = new Array("451","434","Hardware Components","10","Facility.png");
452 | 446 | 11 | Workstations |  |  | Facility.png |  | datatable[451] = new Array("452","446","Workstations","11","Facility.png");
453 | 446 | 11 | Servers |  |  | Facility.png |  | datatable[452] = new Array("453","446","Servers","11","Facility.png");
454 | 446 | 11 | Storage and Archive |  |  | Facility.png |  | datatable[453] = new Array("454","446","Storage and Archive","11","Facility.png");
455 | 446 | 11 | Network Equipment |  |  | Facility.png |  | datatable[454] = new Array("455","446","Network Equipment","11","Facility.png");
456 | 446 | 11 | Interface Equipment |  |  | Facility.png |  | datatable[455] = new Array("456","446","Interface Equipment","11","Facility.png");
457 | 446 | 11 | Security Encryption/Decryption |  |  | Facility.png |  | datatable[456] = new Array("457","446","Security Encryption/Decryption","11","Facility.png");
458 | 446 | 11 | Data Processing |  |  | Facility.png |  | datatable[457] = new Array("458","446","Data Processing","11","Facility.png");
459 | 446 | 11 | COTS Hardware Other (Specify) |  |  | Facility.png |  | datatable[458] = new Array("459","446","COTS Hardware Other (Specify)","11","Facility.png");
460 | 446 | 11 | Pre-Operations Maintenance (Specify) |  |  | Facility.png |  | datatable[459] = new Array("460","446","Pre-Operations Maintenance (Specify)","11","Facility.png");
461 | 446 | 11 | Environments |  |  | Facility.png |  | datatable[460] = new Array("461","446","Environments","11","Facility.png");
462 | 434 | 10 | SatOps GS Software |  |  | Facility.png |  | datatable[461] = new Array("462","434","SatOps GS Software","10","Facility.png");
463 | 462 | 11 | SW CSCI |  |  | Facility.png |  | datatable[462] = new Array("463","462","SW CSCI","11","Facility.png");
464 | 429 | 8 | NASA Science Operations Centers |  |  | Facility.png |  | datatable[463] = new Array("464","429","NASA Science Operations Centers","8","Facility.png");
465 | 429 | 8 | HPC (High Performance Computing) |  |  | Facility.png |  | datatable[464] = new Array("465","429","HPC (High Performance Computing)","8","Facility.png");
466 | 429 | 8 | Geospace Observatory |  |  | Facility.png |  | datatable[465] = new Array("466","429","Geospace Observatory","8","Facility.png");
467 | 429 | 8 | Other SODC (specify) |  |  | Facility.png |  | datatable[466] = new Array("467","429","Other SODC (specify)","8","Facility.png");
468 | 435 | 8 | CSA Terminals and Antennas |  |  | Facility.png |  | datatable[467] = new Array("468","435"," CSA Terminals and Antennas","8","Facility.png");
469 | 463 | 9 | CSA St-Hubert Antenna |  |  | Facility.png |  | datatable[468] = new Array("469","463","CSA St-Hubert Antenna","9","Facility.png");
470 | 463 | 9 | Ferme Yves Bachand Antenna |  |  | Facility.png |  | datatable[469] = new Array("470","463","Ferme Yves Bachand Antenna","9","Facility.png");
471 | 463 | 9 | Ferme Beldor Antenna |  |  | Facility.png |  | datatable[470] = new Array("471","463","Ferme Beldor Antenna","9","Facility.png");
472 | 463 | 9 | Transponder |  |  | Facility.png |  | datatable[471] = new Array("472","463","Transponder","9","Facility.png");
473 | 431 | 8 | Digital Earth Canada |  |  | Facility.png |  | datatable[472] = new Array("473","431","Digital Earth Canada","8","Facility.png");
474 | 431 | 8 | Federal Geospatial Platform (FGP) |  |  | Facility.png |  | datatable[473] = new Array("474","431","Federal Geospatial Platform (FGP)","8","Facility.png");
475 | 431 | 8 | EODMS |  |  | Facility.png |  | datatable[474] = new Array("475","431","EODMS","8","Facility.png");
476 | 431 | 8 | Canadian Astronomy Data Centre |  |  | Facility.png |  | datatable[475] = new Array("476","431","Canadian Astronomy Data Centre","8","Facility.png");
477 | 431 | 8 | NASA Data Distribution & Archival |  |  | Facility.png |  | datatable[476] = new Array("477","431","NASA Data Distribution & Archival","8","Facility.png");
478 | 437 | 8 | MMLC |  |  | Facility.png |  | datatable[477] = new Array("478","437","MMLC","8","Facility.png");
479 | 437 | 8 | MOTS |  |  | Facility.png |  | datatable[478] = new Array("479","437","MOTS","8","Facility.png");
480 | 14 | 7 | CSA Mission Operations |  |  | Ops.png |  | datatable[479] = new Array("480","14","CSA Mission Operations","7","Ops.png");
481 | 475 | 8 | CSA SatOps |  |  | Ops.png |  | datatable[480] = new Array("481","475","CSA SatOps","8","Ops.png");
482 | 475 | 8 | CSA ISS Ops |  |  | Ops.png |  | datatable[481] = new Array("482","475","CSA ISS Ops","8","Ops.png");
483 | 475 | 8 | CSA ISS Sustaining Engineering |  |  | Ops.png |  | datatable[482] = new Array("483","475","CSA ISS Sustaining Engineering","8","Ops.png");
484 | 14 | 7 | NASA Mission Operations |  |  | Ops.png |  | datatable[483] = new Array("484","14","NASA Mission Operations","7","Ops.png");
485 | 14 | 7 | Industry Partners (Specify) |  |  | Ops.png |  | datatable[484] = new Array("485","14","Industry Partners (Specify)","7","Ops.png");
486 | 15 | 7 | Mission Science Support |  |  | Science.png |  | datatable[485] = new Array("486","15","Mission Science Support","7","Science.png");
487 | 481 | 8 | Science Maturation Studies & User Requirements |  |  | Science.png |  | datatable[486] = new Array("487","481","Science Maturation Studies & User Requirements","8","Science.png");
488 | 481 | 8 | Science Support for Mission Development |  |  | Science.png |  | datatable[487] = new Array("488","481","Science Support for Mission Development","8","Science.png");
489 | 481 | 8 | Science Support for Commissioning, Including Cal/Val |  |  | Science.png |  | datatable[488] = new Array("489","481","Science Support for Commissioning, Including Cal/Val","8","Science.png");
490 | 481 | 8 | Science Support for Data Handling |  |  | Science.png |  | datatable[489] = new Array("490","481","Science Support for Data Handling","8","Science.png");
491 | 15 | 7 | Science Utilization & Application Development |  |  | Science.png |  | datatable[490] = new Array("491","15","Science Utilization & Application Development","7","Science.png");

## 2 - Phasing Nomenclature
` Table of Contents
7 - Phasing Nomenclature | [5 empty] | What do you call your phases?
Why we we asking:
1. To normalize the naming convention across all investments.
2. Math Models are based on Costing Sub-Phase.
3. We want to output results in your naming convention and scope.
| Based on IGMF rev E |  |  | Based on MCAD-FIN-RPT-0072
Phasing according to |  |  | Phasing according to |  |  | Phasing according to
EPMO |  |  | Costing |  |  | PM
|  |  | PREP | PREP 1 | Prototyping Activities (before Gate 1) | Technology maturation
Pre-Project | Option Analysis & Planning Phase | Pre-Phase 0 |  | PREP 2 | Prototyping Activities (during Phase 0/A) | Concept demonstrations
|  | Phase 0 | Phase 0/A | Phase 0 | Concept & Feasibility | Phase 0
Project | Definition Phase | Detailed Project Requirements |  | Phase A | Mission Requirements | Phase A
|  | Preliminary Definition | Phase B/C | Phase B | Preliminary Design | Phase B
|  | Detailed Definition |  | Phase C | Detailed Design | Phase C
| Implementation Phase | Implementation | Phase D | MAIT | Manufacturing, Assembly, Integration and Test of Subsystems and Components | Phase D1
|  |  |  | SAIT | Spacecraft Level Assembly, Test | Phase D2
|  |  |  | LEOP | Lauch and early operations | LEOP
Post-Project | Post-Implementation Phase | Operations & Disposal | Phase E | Phase E | Nominal Operations (per design life) | Phase E
|  |  | Phase E (EXT) | Phase X | Extended operations (mission extension) | Phase E EXT
|  |  | Phase F | Phase F | Disposal (incl. post-mortem audit reports) | Phase F
|  |  | Phase G | Phase G | Post-Mortem science utilization | Phase G
Specify your labels
here. Repeat text if necessary. Leave blank if not included in your scope
Specify your labels
here. Repeat text if necessary. Leave blank if not included in your scope

## 3 - Phase Durations
` Table of Contents
7b - Phasing Durations
Why we we asking:
1. Durations affect Govt Salaries calculations
2. Durations affect Parametric estimates for Space segment, ground segment, ops
3. Schedule Scenarios are inputs to sensitivity analysis
| Schedule Scenario ID | 1
| Scenario Name | Nominal Schedule used for RAM calculation (PM Nomenclature)
| Scenario Description | Contiguous phase schedule derived from the CADRe Part A milestone dates; includes Phase 0 governance preparation from Oct 2026.
| Rationale | Phase ends are anchored on the Part A gate reviews (MCR, SRR, PDR, CDR, FM-3, L3, commissioning, nominal end). D1 spans three staggered 18-month unit builds; E EXT runs to the 10-year design life.
| Source Doc | CADRe Part A – VPCS Rev 1.0 (23 Sep 2026), Tables 4 & 5
| Phase | Expected Start | Expected End | Total D | Total M | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050
| Phase 0 | 2026-10-01 | 2027-03-18 | 168 | 5.5233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase A | 2027-03-19 | 2028-01-20 | 307 | 10.0932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4274 | 9.6986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase B | 2028-01-21 | 2029-03-22 | 426 | 14.0055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3342 | 11.7041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase C | 2029-03-23 | 2030-03-21 | 363 | 11.9342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.29589 | 11.6712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase D1 | 2030-03-22 | 2032-03-26 | 735 | 24.1644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32877 | 12 | 11.8685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase D2 | 2032-03-27 | 2033-01-28 | 307 | 10.0932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16438 | 9.9616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LEOP | 2033-01-29 | 2033-07-28 | 180 | 5.9178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0384 | 3.9123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase E | 2033-07-29 | 2040-07-27 | 2555 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.0877 | 12 | 12.0329 | 12 | 12 | 12 | 12.0329 | 3.8795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase E EXT | 2040-07-28 | 2043-01-27 | 913 | 30.0164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.1205 | 12 | 9.9288 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase F | 2043-01-28 | 2043-07-28 | 181 | 5.9507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0712 | 3.9123 | 0 | 0 | 0 | 0 | 0 | 0
| Total (months per FY) |  |  | 6135 | 201.6986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.9836 | 12.0329 | 12 | 12 | 12 | 12.0329 | 12 | 12 | 12 | 12.0329 | 12 | 12 | 12 | 12.0329 | 12 | 12 | 12 | 3.9123 | 0 | 0 | 0 | 0 | 0 | 0

## GR&A (hidden)
Costing CSA Ground Rules & Assumptions template
Last review |  |  | 2025-03-31
ID | Catégorie | Category | Category | Sub-category | Items | GR or A | Title | Description | Phase | CBS # linked to GR&A | Impact on Project | Impact on costing, methodology, models, tools & analysis | Excepted source | Do not delete - Mireille | Source/Link | Other rational | Waiver deviation
1 | Hypothèses Programmatiques | Strategy Naratives | Objectifs politiques et stratégiques | Alignement sur la stratégie de l’ASC | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Strategy
2 | Hypothèses Programmatiques | Strategy Naratives | Objectifs politiques et stratégiques | Contraintes gouvernementales ou directives de haut niveau | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Strategy
3 | Hypothèses Programmatiques |  | Objectifs politiques et stratégiques | Type de mission : Flagship, LargeSat, SmallSat, NanoSat, Hosted Payload, Data stream partnership, data stream purchase | [8 empty] | CADRE Part A | CADRE Part A ou contants
4 | Hypothèses Programmatiques |  | Objectifs politiques et stratégiques | Disciplines et secteur : SatCom, Astronomie, exploration spatiale,... | [8 empty] | CADRE Part A | CADRE Part A
5 | Hypothèses Programmatiques |  | Objectifs politiques et stratégiques | Dépendances avec d'autres projets/missions | [8 empty] | CADRE Part A | CADRE Part A
6 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Soumission au Conseil du Tésor (TBSub) - But de l'exercice de costing : Budget Ask, Reprofiling,… Définir le nombre de TBSub + échéancier associé aux TBSub | [8 empty] | CADRE Part C onglet Stratégie contractuelle | Strategy
7 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Enveloppe de la masse salariale | [8 empty] | CADRE Part C onglet RAM | Strategy
8 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Enveloppe des frais de gestion et plan de voyages | [8 empty] | CADRE Part C onglet Overhead Costs | Strategy
9 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Méthodologie d'établissement des coûts | [8 empty] | Plan de l’exercice d’établissement des coûts | Costing Plan
10 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Note de réflexion supplémentaire | [9 empty] | Costing Plan
11 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Au moins 2 façon différentes pour chaque incluant RAM | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
12 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analyse de sensibilité | [8 empty] | À compléter par Finance | Costing Plan
13 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Sufficiency Report or Independent Cost Estimate or Independent Cost Review | [8 empty] | À compléter par Finance | Costing Plan
14 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analogie (nearest neighboors), lesquels. | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
15 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analyse paramétrique (True planning, PCEC, NCIM, SEER, Compact). CER Calibration Plan. | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
16 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Soumission de l'industrie et jugement d'expert | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
17 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analyse Monte Carlo (crystal ball) | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
18 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Bottom up, qui le fait et comment | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
19 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Learning curves | [8 empty] | RASCI = qui fait quoi. bottom up = Plan de l’exercice d’établissement des coûts | Costing Plan
20 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Inducteurs de coûts princicaux | [8 empty] | CADRE Part C onglet CER & Tools | Costing Plan
21 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Normalisation ( Stochométrie) - si applicable | [8 empty] | le choix de l'outil dicte CADRE part B qui collecte info pour l'analyse paramétrique | Costing Plan
22 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Tracabilité - accès aux sources - répertoires normalisés -liens | [8 empty] | CADRE Part C onglet CER & Tools | Costing Plan
23 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Stratégie de financement | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Strategy
24 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Limitation des coûts : Par exemple, les sources de financement instables, les contraintes de personnel ou un budget à ne pas dépasser devraient être documentés. | [8 empty] | CADRE Part C onglet Stratégie contractuelle | Strategy
25 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Enveloppe Services internes - O&M et RAM | [8 empty] | CADRE Part C onglet Services internes | Strategy
26 | Hypothèses Programmatiques | OBS | Partenariats (OGD, internationaux, industriels) | Rôles et responsabilités des principaux partenaires (agences spatiales, industriels, universités et autres ministères) | [8 empty] | CADRE Part C onglet OBS | OBS
27 | Hypothèses Programmatiques | OBS | Partenariats (OGD, internationaux, industriels) | Modalités de partage des coûts et des risques | [8 empty] | CADRE Part C onglet OBS - Cost Sharing provisions | OBS
28 | Hypothèses Programmatiques | Strategy Naratives | Partenariats (OGD, internationaux, industriels) | Si applicable, dépenses éligibles de l'OTAN | [8 empty] | À définir ici | Strategy
29 | Hypothèses Programmatiques | 8. Economic Constants and short answers | Gouvernance et autorités | Ordre de grandeur général du projet (petit, moyen, grand, flagship) | [8 empty] | CERCES scale | Constants
30 | Hypothèses Programmatiques | Costign Plan | Gouvernance et autorités | Nature of the costing perimeter (degree of difficulty of costing exercise) | [8 empty] | Plan de l’exercice d’établissement des coûts | Costing Plan
31 | Hypothèses Programmatiques | 8. Economic Constants and short answers | Gouvernance et autorités | Palier/ Tier | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Constants
32 | Hypothèses Programmatiques | 8. Economic Constants and short answers | Gouvernance et autorités | PCRA | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Constants
33 | Hypothèses Programmatiques | Milestone Register | Gouvernance et autorités | Point de décision | [8 empty] | CADRE Part C - onglet Phasing Model | Milestone Register
34 | Hypothèses Programmatiques | Costign Plan | Gouvernance et autorités | Costing Exercise Schedule and associated milestones - Costing Plan, Internal WebReport Dashboard and power BI dashboard for CLAD | [8 empty] | Plan de l’exercice d’établissement des coûts | Costing Plan
35 | Hypothèses Financières | 8. Inflation Model | Indices économiques et inflation | Taux d’inflation annuel, indice utilisé (IPC, indice sectoriel), taux de déflation | [8 empty] | Inflation Model dans son propre document - Oracle db ID | Inflation Model
36 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | Taux EBP 27% | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
37 | Hypothèses Financières | 8. Inflation Model | Indices économiques et inflation | Modèle d'inflation appliqué | [8 empty] | Inflation Model dans son propre document - Oracle db ID | Inflation Model
38 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | Année de base / Base year | [9 empty] | Constants
39 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | SSC 4% | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
40 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | PSPC 13% | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
41 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | Taux du Fairness Monitor | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
42 | Hypothèses Financières | 8. Economic Constants and short answers | Taux de change | Monnaies concernées et valeur de référence (CAD, USD, EUR, etc.) | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
43 | Hypothèses Financières | 8. Economic Constants and short answers | Taux de change | Seuil de variation accepté avant révision budgétaire | [8 empty] | Defined in constnats, used in risk analysis. risk reserve - Risk register | Constants
44 | Hypothèses Financières | 8. Economic Constants and short answers | Contingence et marges de sécurité | Pourcentage de contingence sur le coût total du projet (p. ex. 10 à 20 %) | [8 empty] | Defined in constnats, used in risk analysis. risk register onglet. Unknown-Unknown Risk margin | Constants
45 | Hypothèses Financières | Strategy Naratives | Contingence et marges de sécurité | Barème d’évaluation des risques majeurs pour justifier la marge appliquée (modèle d’analyse de risques) | [8 empty] | À définir ici | Strategy | Je ne comprends pas la question
46 | Hypothèses Financières | Procurement Plan | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Sunk Costs Report (STDP, EOADP, Cap Demo, Stedia FAST, ESA Program, Cubesats, space hub, Pre-Phase 0 etc) | [8 empty] | CADRe part C - Expenditure plan | Procurement Plan
47 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stratégie contractuel Phase 0/A - 1 / 2 contrats | [8 empty] | CADRe Part C - Procurement strategy | Strategy
48 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Note de réflexion supplémentaire | [9 empty] | Strategy
49 | Hypothèses Financières | Procurement Plan | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Nombre de contrats et valeur approximative prévus par phase | [8 empty] | CADRe Part C - Procurement Plan (list) | Procurement Plan
50 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Contrats en parallèle avec des concepts différents et un down select | [8 empty] | CADRe Part C - Procurement strategy | Strategy
51 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Agile ou waterfall | [8 empty] | CADRe Part C - Procurement strategy | Strategy
52 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | STDP ou CapDemo en même temps que la phase 0 ou A | [8 empty] | PREP 2 | Strategy
53 | Hypothèses Financières | OBS | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Les fournisseurs attendus et leur capacite de production | [8 empty] | OBS | OBS
54 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Type de SOW - SOW directif versus une architecture de mission proposée par le fournisseur | [8 empty] | CADRe Part C - Procurement strategy | Strategy
55 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Freedom of Design of Vendor | [8 empty] | CADRE Part C onglet OBS Maturité orgnisationelle du fourniseur | Strategy
56 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Types de contrat – source unique ou compétitif (Contrat dirigé en Phase E ops aura une incidence sur le design du ground segment) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
57 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Types de contrat – cout remboursable ou prix ferme | [8 empty] | CADRe Part C - Procurement strategy | Strategy
| Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Type de contrat: gonogo, options, milestones in April for CAFÉ | [9 empty] | Strategy | Split next line into 2
58 | Hypothèses Financières | 12 - Dispose, Divest, Descope, Delay | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Gestion du scope change et des risques dans chaque situation : cout remboursable (TA, options, gouvernance) ; prix ferme (descope, go no go, qualité du SOW a décrire le scope) | [8 empty] | Descope est dans DDD | DDDD
59 | Hypothèses Financières |  | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | G&C (cassiope ou radarsat 2) nous appartient pas | [8 empty] | Business model (CADRe part A) et le procurement strategy le repete | CADRE Part A
60 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | incitatif commercial (ex. modele de commercialization comme WFS) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
61 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Pour chaque phase et sous-systeme majeur - CSA led, industry led, academia led (ex. En Phase E, CSA va mener les operations) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
62 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Competitif - ouvert a l'international | [8 empty] | CADRe Part C - Procurement strategy | Strategy
63 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Competitif - ouvert au Canada | [8 empty] | CADRe Part C - Procurement strategy | Strategy
64 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Fausse competition | [8 empty] | CADRe Part C - Procurement strategy | Strategy
65 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | monopole | [8 empty] | CADRe Part C - Procurement strategy | Strategy
66 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Dependences : Le fournisseur X doit etre le meme fournisseur que le fournisseur Y (Ex. Data processing handled by same supplier) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
67 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Long lead Item - flux de trésorie en capital vs contrat vs échéancier | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Strategy
68 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Contenu Canadien | [8 empty] | CADRe Part C - Procurement strategy | Strategy
69 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Chaque contrat couvre quel partie du travail, liste d'inclusions et exclusions. List of inclusions and exclusions | [8 empty] | CBS Dictionary | Strategy
70 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | GFE and GFS (ex. DFL) | [8 empty] | CBS Dictionary | Strategy
71 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Frais de transport et responsabilité | [8 empty] | CBS Dictionary | Strategy
72 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Frais d'assurance et limitation de responsabilité | [8 empty] | CBS Dictionary | Strategy
73 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Qualité du SOW | [8 empty] | RISK posture | Strategy
74 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stabilité des exigences. Par exemple, des exigences très instables, un nombre standard de demandes de modification technique, des exigences stables avec peu ou pas de changements attendus, etc. | [8 empty] | CADRe Part C - Procurement strategy | Strategy
75 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Résultats du RFI | [8 empty] | Procurement strategy | Strategy
76 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stratégie contractuelle Phase BCD - Concurrentiel, source unique (voir note de réflexion du point 2.4.1) | [8 empty] | Procurement strategy | Strategy
77 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stratégie contractuelle Phase EF - Concurrentiel, source unique (voir note de réflexion du point 2.4.1) | [8 empty] | Procurement strategy | Strategy
78 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Capacité du vendeur dans le marché actuel, surcharge contractuel, effectif disponible | [8 empty] | OBS Maturité orgnisationelle du fourniseur | Strategy
79 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Taux standard pour les ingénieurs, techniciens, gestionnaires, etc. | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
80 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Taux spécifiques pour les consultants ou experts externes | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
81 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Barème pour les appels d’offres et la sous-traitance (plafonds, politiques internes) | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
82 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Taux de frais et de profit appliqué au contrat | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
83 | Hypothèses Financières | Risk Register | Plan de gestion des risques financiers | Existence d’une réserve pour risques identifiés (p. ex. volatilité du marché, retards de paiement) | [8 empty] | Registre de risque | Risk Register
84 | Hypothèses Financières | 12 - Dispose, Divest, Descope, Delay | Plan de gestion des risques financiers | Descope Plan and other strategies to deal with funding shortfalls, | [8 empty] | À définir ici et lié au CADRE Part C - onglet DDDD | DDDD
85 | Hypothèses Financières | Procurement Plan | Plan de gestion des risques financiers | Source of funding for each CBS element and Risk to A-Base | [8 empty] | Expenditure plan | Procurement Plan
86 | Hypothèses Financières | 8. Economic Constants and short answers | Taxes | Pays, province et taux de taxes applicables | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
87 | Hypothèses Techniques (Space & Ground Segment) | TRRA | Technologie et niveau de maturité (TRL) | TRL initial prévu pour les composants clés | [8 empty] | CADRE Part C onglet TRL | TRL
88 | Hypothèses Techniques (Space & Ground Segment) | TRRA | Technologie et niveau de maturité (TRL) | Objectifs de TRL à atteindre pour chaque phase du projet | [8 empty] | CADRE Part C onglet TRL | TRL
89 | Hypothèses Techniques (Space & Ground Segment) | 4a. CBS and CBS Dictionary | Sous-systèmes et architecture globale | Liste et description des principaux sous-systèmes (structure, propulsion, contrôle d’attitude, communication, etc.) | [8 empty] | CBS | CBS
90 | Hypothèses Techniques (Space & Ground Segment) | TRRA | Sous-systèmes et architecture globale | Interfaces critiques (par ex. protocole de communication, alignement mécanique) | [8 empty] | TRL assessment tab - worry list | TRL
91 | Hypothèses Techniques (Space & Ground Segment) | Costign Plan | Sous-systèmes et architecture globale | This ground rule should state, at a high level, what is within scope of the estimate. For example, an estimate may cover the space segment, ground segment, and government oversight during phases B, C and D. Further clarification should be given if required, such as refurbishment of the ground segment rather than complete rebuild. | [8 empty] | Perimeter of costing exercise. Further Claraifications in CBs dictionary | Costing Plan
92 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | Stratégie de validation (modèles d’ingénierie, prototypes, simulations) | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
93 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | Méthodes d’essais en environnement (thermique, vibration, vide, etc.) | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
94 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | This assumption should state the expected build approach for the mission. For example, the bus/platform and payloads could be built in series or parallel. | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
95 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | This assumption should state the cost improvement curve, as a percentile, for any items to be acquired with more than a single unit. If appropriate, items should be marked as Xth unit within a lot, such as the 8th unit, to allow for cost improvement curve theory to be reflected. | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
96 | Hypothèses Techniques (Space & Ground Segment) | Engineering Parameters in CADRe part B | Contraintes techniques spécifiques | Estimation de masse et de volume du système | [8 empty] | CADRE part B | CADRE part B
97 | Hypothèses Techniques (Space & Ground Segment) | Engineering Parameters in CADRe part B | Contraintes techniques spécifiques | Consommation électrique maximale | [8 empty] | CADRE part B | CADRE part B
98 | Hypothèses Techniques (Space & Ground Segment) | Engineering Parameters in CADRe part B | Contraintes techniques spécifiques | Besoins minimaux pour assurer la fiabilité | [8 empty] | CADRE part B | CADRE part B
99 | Hypothèses Qualité, Fiabilité et Sécurité | Strategy Naratives | Normes et standards de qualité | ECSS-Q-ST-20, ISO 9001, etc. | [8 empty] | À définir ici | Strategy
100 | Hypothèses Qualité, Fiabilité et Sécurité | Strategy Naratives | Normes et standards de qualité | Méthodes d’assurance qualité (revues, audits internes et externes) | [8 empty] | À définir ici | Strategy
101 | Hypothèses Qualité, Fiabilité et Sécurité | 8. Economic Constants and short answers | Safety and mission assurance | Classe de Mission | [8 empty] | À définir ici | Constants
102 | Hypothèses Qualité, Fiabilité et Sécurité | Strategy Naratives | Safety and mission assurance | La mesure de la surveillance et de la rigueur appliquées par la CSA | [8 empty] | À définir ici | Strategy
103 | Hypothèses Opérationnelles | RAM | Ressources humaines et expertise | Équipe de base (ETP internes) et besoins en personnel spécialisé externe | [8 empty] | CADRE Part C onglet RAM | RAM
104 | Hypothèses Opérationnelles | Strategy Naratives | Ressources humaines et expertise | Disponibilité du personnel et plan de montée en compétence | [8 empty] | À définir ici | Strategy
105 | Hypothèses Opérationnelles | Milestone Register | Calendrier, jalons et ressources temporelles | Dates clés (ex. PDR – Preliminary Design Review, CDR – Critical Design Review, FRR – Flight Readiness Review) / Project Milestone Register (short report, detailed report) | [8 empty] | milestone Register | Milestone Register
106 | Hypothèses Opérationnelles |  | Calendrier, jalons et ressources temporelles | Diagram of Phase Overlaps and Gaps | [8 empty] | we draw it form phasing | GANTT Charts
107 | Hypothèses Opérationnelles | Schedule Constraints and Dependencies | Calendrier, jalons et ressources temporelles | Marges pour délais | [8 empty] | Phasing Model, phases | Schedule Constraints
108 | Hypothèses Opérationnelles | 12 - Dispose, Divest, Descope, Delay | Calendrier, jalons et ressources temporelles | Gestion des retards : conditions de replanification, procédures d’escalade | [8 empty] | À définir ici et lié au CADRE Part C - onglet DDDD | DDDD
109 | Hypothèses Opérationnelles | Phasing Schedules | Calendrier, jalons et ressources temporelles | Modèle de phase utilisé pour analyse de sensibilité (Phasing Model) | [8 empty] | Phasing model (for risk analysis) | Phasing Schedules
110 | Hypothèses Opérationnelles | Phasing Schedules | Calendrier, jalons et ressources temporelles | Échéancier de l'industrie | [8 empty] | Phasing model (for risk analysis) | Phasing Schedules
111 | Hypothèses Opérationnelles | Phasing Schedules | Calendrier, jalons et ressources temporelles | Schedule Scenarios for sensitivity analysis : Adjust Durations - optimistic, pessimistic and expected | [8 empty] | Phasing model (for risk analysis) | Phasing Schedules
112 | Hypothèses Opérationnelles | Strategy Naratives | Planification des infrastructures et installations | Is DFL being used as GFE | [8 empty] | DFL being used? Strategy | Strategy
112 | Hypothèses Opérationnelles | 4a. CBS and CBS Dictionary | Planification des infrastructures et installations | Lieux de développement, sites d’intégration et de test (chambres à vide, bancs de test) | [8 empty] | CBS Dictionary - Ground Segment - Test facilities | CBS Dictionary
113 | Hypothèses Opérationnelles | Schedule Constraints and Dependencies | Planification des infrastructures et installations | Disponibilité des installations (ex. créneaux de test partagés avec d’autres projets) | [8 empty] | schedule risk = risk register -> pessimistic schedule model | Schedule Constraints
114 | Hypothèses Opérationnelles | Schedule Constraints and Dependencies | Gestion de la logistique et de la chaîne d’approvisionnement | Délai de livraison des composants critiques (satellites, propulseurs, éléments électroniques) | [8 empty] | schedule risk = risk register -> pessimistic schedule model | Schedule Constraints
115 | Hypothèses Opérationnelles | Strategy Naratives | Gestion de la logistique et de la chaîne d’approvisionnement | Plans de contingence en cas de rupture d’approvisionnement | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | Strategy
116 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | Description des opérations prévues : phases de lancement, mise à l’orbite, opérations nominales, etc. | [8 empty] | Cadre part A | CADRE Part A
117 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | Mode de supervision et contrôle (centres de contrôle, horaires, équipes) | [8 empty] | À définir ici | Cadre Part A
118 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | Mission Operation Center | [8 empty] | À définir ici | Cadre Part A
119 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | GoC Science Operation Centers (SOCs) | [8 empty] | À définir ici | Cadre Part A
120 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | External Science Operation Centers (ESOCs) | [8 empty] | À définir ici | Cadre Part A
121 | Hypothèses sur la science | Schedule Constraints and Dependencies | Science et applications | Échéancier lié au volet de science du projet | [9 empty] | Schedule Constraints
122 | Hypothèses sur la science | Strategy Naratives | Science et applications | Expected cost of science utilization related to the mission. | [9 empty] | Strategy
123 | Hypothèses sur la science | Strategy Naratives | Portée de la mission sur le milieu public et académique | Coût en lien avec la portée de la mission | [8 empty] | À définir ici | Strategy
124 | Hypothèses Lancement |  | Véhicule de lancement | Sélection du lanceur (ex. Falcon 9, Ariane, etc.) ou fenêtre de lancement partagée | [8 empty] | Cadre part A | CADRE Part A
125 | Hypothèses Lancement |  | Véhicule de lancement | Capacités du lanceur (masse, volume, orbite cible) | [8 empty] | Cadre part A un petit peu et le reste dans le LV database CM list | CADRE Part A
126 | Hypothèses Lancement | Schedule Constraints and Dependencies | Calendrier de lancement | Fenêtres de lancement disponibles (contraintes de météo, alignement orbital, etc.) | [8 empty] | schedule risk = risk register -> pessimistic schedule model | Schedule assumptions and constraints for JCL Analysis
127 | Hypothèses Lancement | 12 - Dispose, Divest, Descope, Delay | Calendrier de lancement | Contingences pour reports éventuels | [8 empty] | schedule risk = risk register -> pessimistic schedule model | DDDD
128 | Hypothèses Lancement | OBS | Contrat et services associés | Responsabilités du fournisseur de lancement (intégration, tests, qualification) | [8 empty] | OBS (roles et responsiblity) - CSa qui paye ou MDa qui paye | OBS
129 | Hypothèses Lancement | 4a. CBS and CBS Dictionary | Contrat et services associés | Assurances (couverture du satellite, du lanceur, etc.) | [8 empty] | CBS Dictionary - if insurance | CBS Dictionary
130 | Hypothèses Opérations en orbite |  | Mode opératoire | Gestion du satellite ou rover (téléopération vs. autonomie) | [9 empty] | Cadre Part A
131 | Hypothèses Opérations en orbite | Engineering Parameters in CADRe part B | Mode opératoire | Durée et fréquence des communications | [8 empty] | CADRE Part B | CADRE part B
132 | Hypothèses Opérations en orbite |  | Maintenance, réparations et évolutions | Possibilité ou non de mise à jour logicielle en vol (OTA updates) | [8 empty] | CADRE part A - Bus FSW section | CADRE Part A
133 | Hypothèses Opérations en orbite |  | Maintenance, réparations et évolutions | Stratégiques de réparation ou d’assistance robotique | [8 empty] | CADRE part A - does it have any robotic repair interfaces | CADRE Part A
134 | Hypothèses Opérations en orbite | 12 - Dispose, Divest, Descope, Delay | Fin de mission et désorbitation | Scénario de désorbitation contrôlée ou passivation (réservoirs, batteries) | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
135 | Hypothèses Opérations en orbite | 12 - Dispose, Divest, Descope, Delay | Fin de mission et désorbitation | Dépôt sur orbite-cimetière pour le matériel en fin de vie (si admissible) | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
136 | Hypothèses Opérations en orbite | Strategy Naratives | Flux de documentation et reporting | Fréquence des rapports d’avancement (hebdomadaires, mensuels) | [8 empty] | À définir ici | Strategy
137 | Hypothèses Opérations en orbite | Strategy Naratives | Classifications et diffusion | Niveau de confidentialité (projet public, secret défense, propriété intellectuelle) | [8 empty] | À définir ici | Strategy
138 | Hypothèses Opérations en orbite | Strategy Naratives | Classifications et diffusion | Politiques de publication ou de diffusion des résultats | [8 empty] | À définir ici et/ou Business Case | Strategy
139 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Réglementations gouvernementales | Exigences fédérales (agences spatiales, ministères, etc.) | [8 empty] | À définir ici et/ou Business Case | Strategy
140 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Réglementations gouvernementales | Normes internationales (ECSS, ISO, NASA, CSA, etc.) | [8 empty] | À définir ici et/ou Business Case | Strategy
141 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Réglementations gouvernementales | Règles et régulations afférentes | [8 empty] | À définir ici et/ou Business Case | Strategy
142 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Contrôle à l’exportation (ex. ITAR, EAR) | Identification des composants ou technologies soumis à licences | [8 empty] | À définir ici | Strategy
143 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Contrôle à l’exportation (ex. ITAR, EAR) | Implications sur la gestion des fournisseurs et des partenaires étrangers | [8 empty] | À définir ici | Strategy
144 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Sécurité et sûreté | Mesures de cybersécurité (protection des données, des communications, etc.) | [8 empty] | À définir ici | Strategy
145 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Sécurité et sûreté | Exigences de sûreté pour le personnel et les installations (accès restreints, habilitations) | [8 empty] | À définir ici | Strategy
146 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Droit spatial et aspects juridiques | Propriété et exploitation des données spatiales | [8 empty] | À définir ici | Strategy
147 | Hypothèses Légales, Réglementaires et Sécuritaires | 12 - Dispose, Divest, Descope, Delay | Droit spatial et aspects juridiques | Protocole en cas de débris spatiaux, en fin de vie du satellite | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
148 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Propriété intellectuelle | Propriété intellectuel en lien avec le projet - enjeux | [8 empty] | À définir ici et/ou Business Case | Strategy
149 | Hypothèses Environnementales | 12 - Dispose, Divest, Descope, Delay | Gestion des débris spatiaux | Respect des lignes directrices d’atténuation des débris (liaisons, désorbitation en fin de vie) | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
150 | Hypothèses Environnementales | 12 - Dispose, Divest, Descope, Delay | Gestion des débris spatiaux | Méthodes envisagées pour minimiser la pollution orbitale | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
151 | Hypothèses Environnementales | Green space | Impacts environnementaux terrestres | Contrôle des émissions lors du lancement (polluants, bruit, etc.) | [8 empty] | CADRE Part C onglet Green Space | Green Space
152 | Hypothèses Environnementales | Strategy Naratives | Impacts environnementaux terrestres | Politique de recyclage ou de réutilisation des composants | [8 empty] | CADRE Part C onglet Green Space | Strategy
153 | Hypothèses sur le risques | Risk Register | Risques | Risque du Projet Phase A à D | [8 empty] | Registre de risque | Risk Register
154 | Hypothèses sur le risques | Risk Register | Risques | Risque du Projet Phase E | [8 empty] | Registre de risque | Risk Register
155 | Hypothèses sur le risques | Risk Register | Risques | Risque du Projet Phase F | [8 empty] | Registre de risque | Risk Register
156 | Hypothèses sur le risques | Risk Register | Risques | Risque Science | [8 empty] | Registre de risque | Risk Register
157 | Hypothèses sur le risques | Risk Register | Risques | Risque Salaire | [8 empty] | Registre de risque | Risk Register
158 | Hypothèses sur le risques | Risk Register | Risques | Schedule Risk Assessment file (ms project) as input to the Joint Cost and Schedule Confidence Analysis Report | [8 empty] | Registre de risque | Risk Register
159 | Hypothèses sur le risques | Risk Register | Risques | Registre de risque | [8 empty] | Registre de risque | Risk Register
160 | Hypothèses sur le risques | Strategy Naratives | Risques | Aspect critique de la mission et impact si la mission n'est pas respectée | [8 empty] | minimum mission success criteria - DRM - CADRE part C Taxon | Strategy
161 | Hypothèse sur les mesures de performance par la valeur acquise | CADRe part D - EVM | Mesures de performance par la valeur acquise (EVM = Earn Value Management) | Seuil orange et rouge pour EVM justifiant une réduction de la portée, une replanification | [9 empty] | pas dans ce fichier, pas avant PDR
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343

## 4-PM's sched Scenarios
|  | VPCS Ref. | 2026-10-01
Phase | Milestone | VPCS Baseline (Part A) | Qelvoria Orbital Systems (Prime / Bus) | Sorevex Signal Engineering (Comms Payload) | Lundrith Launch Consortium (Launch x3) | Pervalin Gateway Services (Ground Segment) | Tervalis Network Ops Institute (Ops / User Validation) | Worst case duration | Worst case (+2 mo/phase) | Realistic case duration | Baseline: Realistic case date (1 month delay per phase) | Optimistic case duration | Optimistic case (-1 month per phase) | Comments
Phase 0 | Mission Concept Review (MCR) | 2027-03-18 | N/A | N/A | N/A | N/A | 2027-02-18 | 7.5 mo | 2027-05-18 | 5.5 mo | 2027-04-18 | 4.5 mo | 2027-02-18 | Closes Phase 0 (Part A: Mar 2027). Only Tervalis contributes (service-region demand & user needs); no industrial contracts yet in place.
Phase A | Phase A Industry Definition Studies Awarded | 2027-05-27 | 2027-05-27 | 2027-05-27 | N/A | 2027-06-24 | N/A | 12.1 mo | 2027-09-27 | 10.1 mo | 2027-07-27 | 9.1 mo | 2027-03-27 | Parallel definition studies for bus, payload and gateway network; award slips directly if the RFP evaluation exceeds 8 weeks.
Phase A | Ka-band Spectrum Coordination Request Filed (40°, 160°, 280°E) | 2027-09-16 | N/A | 2027-08-12 | N/A | 2027-08-26 | 2027-08-05 | 12.1 mo | 2028-01-16 | 10.1 mo | 2027-11-16 | 9.1 mo | 2027-07-16 | Filing is on the critical path for bringing the three slots into use; frequencies remain 'subject to assignment' in Part A. | Phases | Duration (months) | Expected start | Expected finish
Phase A | System Requirements Review (SRR) | 2028-01-20 | 2027-12-16 | 2027-12-09 | N/A | 2028-01-06 | 2027-12-02 | 12.1 mo | 2028-05-20 | 10.1 mo | 2028-03-20 | 9.1 mo | 2027-11-20 | Closes Phase A (Part A: Jan 2028). Requirements baseline for 2.0 Gb/s per spacecraft, eight beams and >=99.5% availability. | Phase 0 | 5.5 | 2026-10-01 | 2027-03-18
Phase B | Prime (Qelvoria) and Payload (Sorevex) Development Contracts Awarded | 2028-04-27 | 2028-04-27 | 2028-04-27 | N/A | N/A | N/A | 16.0 mo | 2028-10-27 | 14.0 mo | 2028-07-27 | 13.0 mo | 2028-01-27 | Assumes a single negotiation window after SRR; a protest or re-bid would consume most of the 14-month Phase B. | Phase A | 10.1 | 2027-03-19 | 2028-01-20
Phase B | Launch Services Contract Awarded (3 x GTO) | 2028-09-21 | 2028-08-24 | N/A | 2028-09-21 | N/A | N/A | 16.0 mo | 2029-03-21 | 14.0 mo | 2028-12-21 | 13.0 mo | 2028-06-21 | Three separate launches of 1,300 kg to GTO (>=1,500 kg capability); Qelvoria supplies launch mass and envelope data before award. | Phase B | 14 | 2028-01-21 | 2029-03-22
Phase B | Cryptographic Boundary & Key-Management Architecture Review | 2028-11-16 | 2028-10-26 | 2028-10-19 | N/A | 2028-10-26 | N/A | 16.0 mo | 2029-05-16 | 14.0 mo | 2029-02-16 | 13.0 mo | 2028-08-16 | Security gate before PDR: 256-bit session keys, <=24 h rotation and authenticated revocation across 3 spacecraft and 4 gateways. | Phase C | 11.9 | 2029-03-23 | 2030-03-21
Phase B | Preliminary Design Review (PDR) | 2029-03-22 | 2029-02-22 | 2029-01-25 | 2029-02-08 | 2029-02-15 | 2029-02-01 | 16.0 mo | 2029-09-22 | 14.0 mo | 2029-06-22 | 13.0 mo | 2028-12-22 | Closes Phase B (Part A: Mar 2029). Critical payload and software elements must demonstrate TRL 6. | Phase D1 | 24.2 | 2030-03-22 | 2032-03-26
Phase C | Deployable Reflector Engineering Model Deployment Test Complete | 2029-10-18 | 2029-10-04 | 2029-09-20 | N/A | N/A | N/A | 13.9 mo | 2030-06-18 | 11.9 mo | 2030-02-18 | 10.9 mo | 2029-06-18 | Gravity-offloaded deployment of the two-reflector EM; retires the top Part A technical risk (reflector deployment) before CDR. | Phase D2 | 10.1 | 2032-03-27 | 2033-01-28
Phase C | Ground Segment CDR (Gateways & Network Control) | 2030-01-24 | 2029-12-13 | 2029-12-13 | N/A | 2030-01-24 | 2030-01-10 | 13.9 mo | 2030-09-24 | 11.9 mo | 2030-05-24 | 10.9 mo | 2029-09-24 | Three protected gateways + one backup, >=7 Gb/s backhaul, dual network-control sites and 150 TB audit archive. | LEOP | 5.9 | 2033-01-29 | 2033-07-28
Phase C | Critical Design Review (CDR) | 2030-03-21 | 2030-02-21 | 2030-01-31 | 2030-02-14 | 2030-02-07 | 2030-02-21 | 13.9 mo | 2030-11-21 | 11.9 mo | 2030-07-21 | 10.9 mo | 2029-11-21 | Closes Phase C (Part A: Mar 2030). Lundrith provides preliminary coupled-loads analysis for all three vehicles. | Phase E | 84 | 2033-07-29 | 2040-07-27
Phase D1 | Manufacturing Readiness Review (MRR) | 2030-06-13 | 2030-05-30 | 2030-05-16 | N/A | N/A | N/A | 26.2 mo | 2031-04-13 | 24.2 mo | 2030-11-13 | 23.2 mo | 2030-01-13 | Part A: Jun 2030. Long-lead TWTAs, reflectors and security processors must be on order before MRR. | Phase E EXT | 30 | 2040-07-28 | 2043-01-27
Phase D1 | Payload Qualification Complete | 2031-04-17 | 2031-03-20 | 2031-04-17 | N/A | N/A | N/A | 26.2 mo | 2032-02-17 | 24.2 mo | 2031-09-17 | 23.2 mo | 2030-11-17 | Part A: Apr 2031. Qualification article covers channelizer, security processors and antenna feeds; flight units still require full acceptance. | Phase F | 6 | 2043-01-28 | 2043-07-28
Phase D1 | FM-1 Unit AIT Complete | 2031-09-25 | 2031-09-25 | 2031-06-26 | N/A | N/A | N/A | 26.2 mo | 2032-07-25 | 24.2 mo | 2032-02-25 | 23.2 mo | 2031-04-25 | Part A: Sep 2031. First flight model after 18-month unit AIT; Sorevex PFM payload delivered to Qelvoria ~3 months earlier. | Total | 201.7
Phase D1 | FM-2 Unit AIT Complete | 2031-12-18 | 2031-12-18 | 2031-09-25 | N/A | N/A | N/A | 26.2 mo | 2032-10-18 | 24.2 mo | 2032-05-18 | 23.2 mo | 2031-07-18 | Interpolated between Part A FM-1 and FM-3 dates (3-month build stagger).
Phase D1 | FM-3 Unit AIT Complete | 2032-03-26 | 2032-03-26 | 2031-12-18 | N/A | N/A | N/A | 26.2 mo | 2033-01-26 | 24.2 mo | 2032-08-26 | 23.2 mo | 2031-10-26 | Part A: Mar 2032. Ends the D1 envelope (24 months for three staggered 18-month unit builds). | 76 MOIS | (Phase 0 start → Launch L3)
Phase D2 | System Integration Review (SIR) | 2032-05-20 | 2032-05-06 | 2032-04-29 | 2032-05-06 | 2032-04-22 | N/A | 12.1 mo | 2033-05-20 | 10.1 mo | 2032-11-20 | 9.1 mo | 2031-11-20 | Part A: May 2032. Final launch ICDs frozen; gateway sites accepted for end-to-end testing.
Phase D2 | Ground Segment Ready / End-to-End Compatibility Test Complete | 2032-08-19 | 2032-07-22 | 2032-07-15 | N/A | 2032-08-19 | 2032-07-29 | 12.1 mo | 2033-08-19 | 10.1 mo | 2033-02-19 | 9.1 mo | 2032-02-19 | Uses Qelvoria spacecraft simulator and Sorevex crypto test loads; confirms protected-session authorization end to end.
Phase D2 | Acceptance Review (AR) - FM-1 to FM-3 | 2032-09-23 | 2032-09-09 | 2032-08-26 | N/A | 2032-09-09 | 2032-09-02 | 12.1 mo | 2033-09-23 | 10.1 mo | 2033-03-23 | 9.1 mo | 2032-03-23 | Part A: Sep 2032. Every unit accepted individually; qualification of a representative article does not waive acceptance.
Phase D2 | Launch / Delivery Readiness Review (LRR) | 2032-11-18 | 2032-11-04 | N/A | 2032-11-04 | 2032-11-11 | 2032-11-11 | 12.1 mo | 2033-11-18 | 10.1 mo | 2033-05-18 | 9.1 mo | 2032-05-18 | Part A: Nov 2032. Flight operations team certified and LEOP network readiness confirmed.
Phase D2 | Launch L1 (FM-1) | 2033-01-12 | 2032-12-02 | N/A | 2033-01-12 | 2033-01-05 | N/A | 12.1 mo | 2034-01-12 | 10.1 mo | 2033-07-12 | 9.1 mo | 2032-07-12 | Part A launch sequence L1-L3: Jan 2033. FM-1 shipped to launch site ~6 weeks before lift-off.
Phase D2 | Launch L2 (FM-2) | 2033-01-20 | 2032-12-09 | N/A | 2033-01-20 | 2033-01-13 | N/A | 12.1 mo | 2034-01-20 | 10.1 mo | 2033-07-20 | 9.1 mo | 2032-07-20 | Separate vehicle and pad; shares the Pervalin LEOP network with L1.
Phase D2 | Launch L3 (FM-3) | 2033-01-28 | 2032-12-16 | N/A | 2033-01-28 | 2033-01-21 | N/A | 12.1 mo | 2034-01-28 | 10.1 mo | 2033-07-28 | 9.1 mo | 2032-07-28 | Last launch; any weather or range slip compresses the commissioning window before Jul 2033.
LEOP | Orbit Raising Complete - All Spacecraft On Station | 2033-03-10 | 2033-03-10 | N/A | 2033-02-11 | 2033-03-03 | N/A | 7.9 mo | 2034-05-10 | 5.9 mo | 2033-10-10 | 4.9 mo | 2032-08-10 | GTO-to-GEO transfer on bipropellant; Lundrith supplies injection-accuracy reports used to confirm the ~190 m/s delta-V reserve.
LEOP | Payload In-Orbit Test Complete (Reflectors Deployed, Beams Calibrated) | 2033-06-16 | 2033-06-02 | 2033-06-16 | N/A | 2033-06-09 | 2033-06-09 | 7.9 mo | 2034-08-16 | 5.9 mo | 2034-01-16 | 4.9 mo | 2032-11-16 | Verifies eight steerable beams per spacecraft, >=0.2 deg beam-centre accuracy and key rotation from all gateways.
Phase E | Commissioning Review / Start of Nominal Operations | 2033-07-28 | 2033-07-14 | 2033-07-14 | N/A | 2033-07-21 | 2033-07-21 | 86.0 mo | 2034-11-28 | 84.0 mo | 2034-03-28 | 83.0 mo | 2032-11-28 | Part A: Commissioning Jul 2033. Start of the 84-month nominal service period.
Phase E | Mid-Mission Performance & Key-Management Audit Review | 2037-01-22 | N/A | 2036-12-18 | N/A | 2037-01-08 | 2036-12-11 | 86.0 mo | 2038-05-22 | 84.0 mo | 2037-09-22 | 83.0 mo | 2036-05-22 | Checks availability trend against >=99.5% monthly target and audit-archive integrity (150 TB).
Phase E | End of Nominal Operations | 2040-07-27 | N/A | N/A | N/A | 2040-06-29 | 2040-06-29 | 86.0 mo | 2041-11-27 | 84.0 mo | 2041-03-27 | 83.0 mo | 2039-11-27 | Part A: Jul 2040 (7 years nominal service).
Phase E EXT | End of Design Life / Extended Operations Complete | 2043-01-27 | N/A | N/A | N/A | 2042-12-30 | 2042-12-16 | 32.0 mo | 2044-07-27 | 30.0 mo | 2043-10-27 | 29.0 mo | 2042-04-27 | Ten-year design life from launch; extension is not funded in the baseline RAM.
Phase F | Graveyard Re-orbit, Passivation & Mission Closeout | 2043-07-28 | 2043-05-25 | N/A | N/A | 2043-06-29 | 2043-07-14 | 8.0 mo | 2045-03-28 | 6.0 mo | 2044-05-28 | 5.0 mo | 2042-09-28 | End-of-life propellant reserve used for super-synchronous disposal; archive handover to Tervalis.
| VPCS Milestone Reference | Realistic Date |  | Phase | Purpose
| Mission Concept Review (MCR) | 2027-03-18 |  | Phase 0 | Mission concept baseline
| System Requirements Review (SRR) | 2028-01-20 |  | Phase A | Requirements baseline
| Cryptographic Boundary & Key-Management Architecture Review | 2028-11-16 |  | Phase B | Security architecture baseline
| Preliminary Design Review (PDR) | 2029-03-22 |  | Phase B | Preliminary design maturity
| Critical Design Review (CDR) | 2030-03-21 |  | Phase C | Design baseline approval
| Manufacturing Readiness Review (MRR) | 2030-06-13 |  | Phase D1 | Manufacturing readiness
| Payload Qualification Complete | 2031-04-17 |  | Phase D1 | Payload qualification
| FM-1 Unit AIT Complete | 2031-09-25 |  | Phase D1 | First flight model complete
| FM-3 Unit AIT Complete | 2032-03-26 |  | Phase D1 | Last flight model complete
| System Integration Review (SIR) | 2032-05-20 |  | Phase D2 | Integrated system readiness
| Acceptance Review (AR) - FM-1 to FM-3 | 2032-09-23 |  | Phase D2 | Flight acceptance
| Launch / Delivery Readiness Review (LRR) | 2032-11-18 |  | Phase D2 | Launch readiness
| Launch L1 (FM-1) | 2033-01-12 |  | Phase D2 | Launch L1
| Launch L3 (FM-3) | 2033-01-28 |  | Phase D2 | Launch L3
| Payload In-Orbit Test Complete (Reflectors Deployed, Beams Calibrated) | 2033-06-16 |  | LEOP | Payload in-orbit test
| Commissioning Review / Start of Nominal Operations | 2033-07-28 |  | Phase E | Commissioning complete
| End of Nominal Operations | 2040-07-27 |  | Phase E | Nominal mission complete
| End of Design Life / Extended Operations Complete | 2043-01-27 |  | Phase E EXT | Design life complete
| Graveyard Re-orbit, Passivation & Mission Closeout | 2043-07-28 |  | Phase F | Mission closeout
Formulas:
Worst case (+2 mo/phase) = EDATE([VPCS Baseline (Part A)],2)
Optimistic case (-1 month per phase) = EDATE([VPCS Baseline (Part A)],-1)

## 5- RAM
Back to Control Panel
Level of Effort
Skillset | Sector (Direction) | Names | Position Number | Level | 0 | A | B | C | D1 - MAIT | D2 - SAIT | D3 - LEOP | E | F | SCI-SUP | 2026/27 Sa baseline | 26/27 | 27/28 | 28/29 | 29/30 | 30/31 | 31/32 | 32/33 | 33/34 | 34/35 | 35/36 | 36/37 | 37/38 | 38/39 | 39/40 | 40/41 | 41/42 | 42/43 | 43/44 | 44/45 | 45/46 | 46/47 | 47/48 | 48/49 | Total
Portfolio Manager | ASCD - Director General's Office | Oriane Valcourt | 11901334 | EN-ENG-6 | 20% | 20% | 20% | 20% | 15% | 15% | 20% | 10% | 10% | 0% | 171243.1037 | 17077.3944 | 34342.4526 | 34248.6207 | 34014.0411 | 25686.4656 | 25756.8394 | 27140.859 | 22707.3047 | 17124.3104 | 17171.2263 | 17124.3104 | 17124.3104 | 17124.3104 | 17171.2263 | 5536.0784 | 0 | 2955.7029 | 5582.9943 | 0 | 0 | 0 | 0 | 0 | 337888.4473
Director General, Space Communications | ASCD - Director General's Office | Castor Hollimere | 11909253 | EX-3 | 5% | 5% | 5% | 5% | 5% | 5% | 10% | 2% | 5% | 0% | 198829.5335 | 4957.1199 | 9968.7136 | 9941.4767 | 9941.4767 | 9941.4767 | 9968.7136 | 11630.1659 | 9162.5007 | 3976.5907 | 3987.4854 | 3976.5907 | 3976.5907 | 3976.5907 | 3987.4854 | 1285.5827 | 0 | 1715.9261 | 3241.1938 | 0 | 0 | 0 | 0 | 0 | 105635.6798
VPCS Mission Manager | ASCD - VPCS Program Office | Seren Aldovane | 11917172 | EX-2 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 0% | 177710.6452 | 47470.6518 | 178197.5237 | 177710.6452 | 177710.6452 | 177710.6452 | 178197.5237 | 177710.6452 | 117824.5922 | 88855.3226 | 89098.7618 | 88855.3226 | 88855.3226 | 88855.3226 | 89098.7618 | 28725.8303 | 0 | 15336.6721 | 28969.2696 | 0 | 0 | 0 | 0 | 0 | 1839183.4584
Lead Project Manager | ASCD - VPCS Program Office | Tamsin Revell | 11925091 | EN-ENG-5 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 30% | 50% | 0% | 154580.3961 | 77078.4441 | 155003.904 | 154580.3961 | 154580.3961 | 154580.3961 | 155003.904 | 154580.3961 | 81652.3298 | 46374.1188 | 46501.1712 | 46374.1188 | 46374.1188 | 46374.1188 | 46501.1712 | 14992.1809 | 0 | 13340.4999 | 25198.7221 | 0 | 0 | 0 | 0 | 0 | 1419090.387
Deputy Project Manager | ASCD - VPCS Program Office | Idris Kalvane | 11933010 | EN-ENG-4 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 20% | 50% | 0% | 134635.2537 | 35964.2116 | 135004.1174 | 134635.2537 | 134635.2537 | 134635.2537 | 135004.1174 | 134635.2537 | 62042.8758 | 26927.0507 | 27000.8235 | 26927.0507 | 26927.0507 | 26927.0507 | 27000.8235 | 8705.1835 | 0 | 11619.2068 | 21947.3907 | 0 | 0 | 0 | 0 | 0 | 1110537.9683
Project Management Engineer | ASCD - VPCS Program Office | Maelis Dorrant | 11940929 | EN-ENG-4 | 50% | 100% | 100% | 100% | 100% | 100% | 50% | 10% | 20% | 0% | 134635.2537 | 35964.2116 | 135004.1174 | 134635.2537 | 134635.2537 | 134635.2537 | 135004.1174 | 123200.4788 | 31021.4379 | 13463.5254 | 13500.4117 | 13463.5254 | 13463.5254 | 13463.5254 | 13500.4117 | 4352.5918 | 0 | 4647.6827 | 8778.9563 | 0 | 0 | 0 | 0 | 0 | 962734.2801
Project Management Engineer (Three-Unit AIT Tracking) | ASCD - VPCS Program Office | Joren Ashvale | 11948848 | EN-ENG-3 | 0% | 0% | 50% | 100% | 100% | 100% | 50% | 0% | 0% | 0% | 119864.8515 | 0 | 11658.0883 | 61410.2116 | 119864.8515 | 119864.8515 | 120193.2484 | 109684.5491 | 19539.6128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562215.4131
Schedule and Cost Management Engineer | ASCD - VPCS Program Office | Liora Fenwyck | 11956767 | EN-ENG-4 | 50% | 100% | 100% | 100% | 100% | 100% | 50% | 20% | 30% | 0% | 134635.2537 | 35964.2116 | 135004.1174 | 134635.2537 | 134635.2537 | 134635.2537 | 135004.1174 | 123200.4788 | 40095.4852 | 26927.0507 | 27000.8235 | 26927.0507 | 26927.0507 | 26927.0507 | 27000.8235 | 8705.1835 | 0 | 6971.5241 | 13168.4344 | 0 | 0 | 0 | 0 | 0 | 1063729.1636
Cost Analyst (CADRe / Parametric Estimating) | ASCD - Finance & Administration | Aurelien Brask | 11964686 | EC-5 | 100% | 100% | 50% | 50% | 30% | 30% | 20% | 10% | 20% | 0% | 113071.6194 | 56380.9171 | 102384.028 | 56535.8097 | 55916.2392 | 33921.4858 | 34014.4214 | 32000.8172 | 14993.6065 | 11307.1619 | 11338.1405 | 11307.1619 | 11307.1619 | 11307.1619 | 11338.1405 | 3655.4661 | 0 | 3903.2943 | 7372.8892 | 0 | 0 | 0 | 0 | 0 | 468983.903
Risk Manager | ASCD - VPCS Program Office | Nerissa Talbrook | 11972605 | EN-ENG-4 | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 10% | 20% | 0% | 134635.2537 | 21099.0041 | 67502.0587 | 67317.6269 | 67317.6269 | 67317.6269 | 67502.0587 | 67317.6269 | 31021.4379 | 13463.5254 | 13500.4117 | 13463.5254 | 13463.5254 | 13463.5254 | 13500.4117 | 4352.5918 | 0 | 4647.6827 | 8778.9563 | 0 | 0 | 0 | 0 | 0 | 555029.2227
Configuration and Data Manager | ASCD - VPCS Program Office | Evander Quill | 11980524 | EN-ENG-3 | 20% | 50% | 100% | 100% | 100% | 100% | 50% | 20% | 30% | 0% | 119864.8515 | 13234.3932 | 71754.7125 | 119864.8515 | 119864.8515 | 119864.8515 | 120193.2484 | 109684.5491 | 35696.738 | 23972.9703 | 24038.6497 | 23972.9703 | 23972.9703 | 23972.9703 | 24038.6497 | 7750.1657 | 0 | 6206.7005 | 11723.7677 | 0 | 0 | 0 | 0 | 0 | 879808.0101
Procurement Officer (Prime & Payload Contracts) | ASCD - Procurement & Contracts | Sabeline Orrick | 11988443 | PG-5 | 50% | 100% | 100% | 50% | 50% | 30% | 20% | 10% | 20% | 0% | 119824.9435 | 32008.0328 | 120153.231 | 118347.6497 | 59912.4717 | 59912.4717 | 59748.328 | 33912.1004 | 15889.1158 | 11982.4943 | 12015.3231 | 11982.4943 | 11982.4943 | 11982.4943 | 12015.3231 | 3873.7927 | 0 | 4136.4227 | 7813.2429 | 0 | 0 | 0 | 0 | 0 | 587667.4831
Procurement Officer (Launch & Gateway Services) | ASCD - Procurement & Contracts | Doran Velisse | 11996362 | PG-4 | 20% | 50% | 100% | 50% | 30% | 50% | 30% | 20% | 20% | 0% | 103553.5562 | 11433.4474 | 61990.2795 | 102276.8685 | 51209.3614 | 31066.0669 | 31434.8878 | 48258.7943 | 24086.8409 | 20710.7112 | 20767.4529 | 20710.7112 | 20710.7112 | 20710.7112 | 20767.4529 | 6695.5176 | 0 | 3574.7255 | 6752.2593 | 0 | 0 | 0 | 0 | 0 | 503156.7999
Contract Technical Authority (Prime) | ASCD - VPCS Program Office | Callum Arventis | 11905281 | EN-ENG-5 | 0% | 50% | 100% | 100% | 100% | 100% | 50% | 10% | 10% | 0% | 154580.3961 | 2752.8016 | 92536.4837 | 154580.3961 | 154580.3961 | 154580.3961 | 155003.904 | 141451.6501 | 35617.0173 | 15458.0396 | 15500.3904 | 15458.0396 | 15458.0396 | 15458.0396 | 15500.3904 | 4997.3936 | 0 | 2668.1 | 5039.7444 | 0 | 0 | 0 | 0 | 0 | 996641.2223
Financial Officer | ASCD - Finance & Administration | Imogen Stavely | 11913200 | FI-3 | 20% | 30% | 50% | 50% | 50% | 50% | 30% | 20% | 30% | 0% | 131685.73 | 13601.5124 | 44737.0699 | 65842.865 | 65842.865 | 65842.865 | 66023.2564 | 61369.158 | 30630.4616 | 26337.146 | 26409.3026 | 26337.146 | 26337.146 | 26337.146 | 26409.3026 | 8514.4746 | 0 | 6818.7953 | 12879.9467 | 0 | 0 | 0 | 0 | 0 | 600270.4591
Administrative Officer | ASCD - Finance & Administration | Pell Marrowin | 11921119 | AS-2 | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 20% | 30% | 0% | 74176.24 | 11624.3313 | 37189.7313 | 37088.12 | 37088.12 | 37088.12 | 37189.7313 | 37088.12 | 22090.2939 | 14835.248 | 14875.8925 | 14835.248 | 14835.248 | 14835.248 | 14875.8925 | 4796.0528 | 0 | 3840.9067 | 7255.0459 | 0 | 0 | 0 | 0 | 0 | 361431.3502
Program Assistant | ASCD - VPCS Program Office | Wrenna Coble | 11929038 | CR-4 | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 20% | 30% | 0% | 61757.9775 | 15397.1944 | 30963.5887 | 30878.9888 | 30878.9887 | 30878.9888 | 30963.5887 | 30878.9888 | 18392.0333 | 12351.5955 | 12385.4355 | 12351.5955 | 12351.5955 | 12351.5955 | 12385.4355 | 3993.1185 | 0 | 3197.8788 | 6040.4378 | 0 | 0 | 0 | 0 | 0 | 306641.0483
Communications and Stakeholder Advisor | ASCD - Director General's Office | Leander Pryce | 11936957 | IS-4 | 20% | 20% | 10% | 10% | 10% | 20% | 50% | 5% | 10% | 0% | 102443.8915 | 10216.3223 | 18552.1678 | 10244.3892 | 10244.3892 | 10244.3892 | 10412.7901 | 25709.2067 | 20151.9765 | 5122.1946 | 5136.228 | 5122.1946 | 5122.1946 | 5122.1946 | 5136.228 | 1655.9424 | 0 | 1768.2096 | 3339.9515 | 0 | 0 | 0 | 0 | 0 | 153300.9686
Lead Space Systems Engineer | ASCD - Space Systems Engineering | Talia Merrowfield | 11944876 | EN-ENG-5 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 20% | 30% | 0% | 154580.3961 | 77078.4441 | 155003.904 | 154580.3961 | 154580.3961 | 154580.3961 | 155003.904 | 154580.3961 | 71234.0346 | 30916.0792 | 31000.7808 | 30916.0792 | 30916.0792 | 30916.0792 | 31000.7808 | 9994.7873 | 0 | 8004.3 | 15119.2333 | 0 | 0 | 0 | 0 | 0 | 1295426.0701
Systems Engineer (Requirements & Verification) | ASCD - Space Systems Engineering | Corvin Ashdane | 11952795 | EN-ENG-4 | 50% | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 0% | 0% | 134635.2537 | 35964.2116 | 135004.1174 | 134635.2537 | 134635.2537 | 134635.2537 | 135004.1174 | 123200.4788 | 21947.3907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855026.0771
Systems Engineer (Interfaces & ICDs) | ASCD - Space Systems Engineering | Ysolde Harrowgate | 11960714 | EN-ENG-4 | 0% | 50% | 100% | 100% | 100% | 100% | 30% | 0% | 0% | 0% | 134635.2537 | 2397.6141 | 80596.7204 | 134635.2537 | 134635.2537 | 134635.2537 | 135004.1174 | 118626.5688 | 13168.4344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 753699.2163
Systems Engineer (MBSE & Digital Engineering) | ASCD - Space Systems Engineering | Brannoc Veyl | 11968633 | EN-ENG-3 | 30% | 100% | 100% | 100% | 50% | 50% | 0% | 0% | 0% | 0% | 119864.8515 | 20918.8796 | 120193.2484 | 119864.8515 | 118222.8672 | 59932.4258 | 60096.6242 | 49752.1233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 548981.0199
Mission Analysis & Flight Dynamics Engineer | ASCD - Space Systems Engineering | Soraya Delmont | 11976552 | EN-ENG-4 | 100% | 100% | 50% | 50% | 30% | 50% | 100% | 20% | 50% | 0% | 134635.2537 | 67133.195 | 121909.4558 | 67317.6269 | 66579.8994 | 40390.5761 | 40870.0989 | 78752.4018 | 62042.8758 | 26927.0507 | 27000.8235 | 26927.0507 | 26927.0507 | 26927.0507 | 27000.8235 | 8705.1835 | 0 | 11619.2068 | 21947.3907 | 0 | 0 | 0 | 0 | 0 | 748977.7608
GEO Orbit, Slot & Station-Keeping Analyst | ASCD - Space Systems Engineering | Halvard Pennick | 11984471 | EN-ENG-3 | 50% | 50% | 50% | 30% | 20% | 50% | 100% | 30% | 50% | 0% | 119864.8515 | 29884.1137 | 60096.6242 | 59341.3114 | 35631.0586 | 23972.9703 | 24531.245 | 70112.7282 | 63314.9133 | 35959.4555 | 36057.9745 | 35959.4555 | 35959.4555 | 35959.4555 | 36057.9745 | 11625.2486 | 0 | 10344.5009 | 19539.6128 | 0 | 0 | 0 | 0 | 0 | 624348.0978
Spacecraft Bus Engineer (Technical Authority) | ASCD - Space Systems Engineering | Marek Oldenbrook | 11992390 | EN-ENG-5 | 20% | 50% | 100% | 100% | 100% | 100% | 50% | 10% | 10% | 0% | 154580.3961 | 17067.3698 | 92536.4837 | 154580.3961 | 154580.3961 | 154580.3961 | 155003.904 | 141451.6501 | 35617.0173 | 15458.0396 | 15500.3904 | 15458.0396 | 15458.0396 | 15458.0396 | 15500.3904 | 4997.3936 | 0 | 2668.1 | 5039.7444 | 0 | 0 | 0 | 0 | 0 | 1010955.7905
Structures & Mechanisms Engineer | ASCD - Space Systems Engineering | Elspeth Carraway | 11901309 | EN-ENG-4 | 0% | 30% | 100% | 100% | 100% | 50% | 20% | 0% | 0% | 0% | 134635.2537 | 1438.5685 | 58833.7616 | 134635.2537 | 134635.2537 | 134635.2537 | 134081.9582 | 60456.7619 | 8778.9563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 667495.7675
Deployable Reflector & Antenna Mechanisms Engineer | ASCD - Communications Payload | Quintus Arrowsmith | 11909228 | EN-ENG-4 | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 10% | 0% | 0% | 134635.2537 | 2397.6141 | 80596.7204 | 134635.2537 | 134635.2537 | 134635.2537 | 135004.1174 | 134635.2537 | 52968.8286 | 13463.5254 | 13500.4117 | 13463.5254 | 13463.5254 | 13463.5254 | 13500.4117 | 4352.5918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 894715.8122
Thermal Control Engineer (Payload Heat Rejection) | ASCD - Space Systems Engineering | Ilse Varnholt | 11917147 | EN-ENG-4 | 0% | 30% | 100% | 100% | 100% | 50% | 50% | 5% | 0% | 0% | 134635.2537 | 1438.5685 | 58833.7616 | 134635.2537 | 134635.2537 | 134635.2537 | 134081.9582 | 67317.6269 | 26484.4143 | 6731.7627 | 6750.2059 | 6731.7627 | 6731.7627 | 6731.7627 | 6750.2059 | 2176.2959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 734665.8489
Electrical Power Systems Engineer | ASCD - Space Systems Engineering | Rowan Kestrell | 11925066 | EN-ENG-4 | 0% | 30% | 100% | 100% | 50% | 50% | 50% | 5% | 0% | 0% | 134635.2537 | 1438.5685 | 58833.7616 | 134635.2537 | 132790.9352 | 67317.6269 | 67502.0587 | 67317.6269 | 26484.4143 | 6731.7627 | 6750.2059 | 6731.7627 | 6731.7627 | 6731.7627 | 6750.2059 | 2176.2959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 598924.0041
AOCS / Pointing Engineer | ASCD - Space Systems Engineering | Anouk Terravin | 11932985 | EN-ENG-4 | 0% | 30% | 100% | 100% | 50% | 50% | 100% | 10% | 20% | 0% | 134635.2537 | 1438.5685 | 58833.7616 | 134635.2537 | 132790.9352 | 67317.6269 | 67502.0587 | 78752.4018 | 52968.8286 | 13463.5254 | 13500.4117 | 13463.5254 | 13463.5254 | 13463.5254 | 13500.4117 | 4352.5918 | 0 | 4647.6827 | 8778.9563 | 0 | 0 | 0 | 0 | 0 | 692873.5907
Propulsion Engineer (Bipropellant) | ASCD - Space Systems Engineering | Fenwick Draye | 11940904 | EN-ENG-4 | 0% | 30% | 100% | 100% | 50% | 100% | 100% | 5% | 50% | 0% | 134635.2537 | 1438.5685 | 58833.7616 | 134635.2537 | 132790.9352 | 67317.6269 | 68424.218 | 134635.2537 | 48431.805 | 6731.7627 | 6750.2059 | 6731.7627 | 6731.7627 | 6731.7627 | 6750.2059 | 2176.2959 | 0 | 11619.2068 | 21947.3907 | 0 | 0 | 0 | 0 | 0 | 722677.7784
Command & Data Handling / Avionics Engineer | ASCD - Space Systems Engineering | Priya Vandermeer | 11948823 | EN-ENG-4 | 0% | 30% | 100% | 100% | 50% | 50% | 30% | 0% | 0% | 0% | 134635.2537 | 1438.5685 | 58833.7616 | 134635.2537 | 132790.9352 | 67317.6269 | 67502.0587 | 62743.7169 | 13168.4344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538430.3558
Flight Software Engineer | ASCD - Space Systems Engineering | Casimir Holt | 11956742 | EN-ENG-4 | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 20% | 0% | 0% | 134635.2537 | 1438.5685 | 58833.7616 | 134635.2537 | 134635.2537 | 134635.2537 | 135004.1174 | 134635.2537 | 62042.8758 | 26927.0507 | 27000.8235 | 26927.0507 | 26927.0507 | 26927.0507 | 27000.8235 | 8705.1835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966275.3717
FDIR & Onboard Autonomy Engineer | ASCD - Space Systems Engineering | Delphine Morvane | 11964661 | EN-ENG-3 | 0% | 30% | 100% | 100% | 100% | 50% | 50% | 10% | 0% | 0% | 119864.8515 | 1280.7477 | 52379.2981 | 119864.8515 | 119864.8515 | 119864.8515 | 119372.2562 | 59932.4258 | 27618.1754 | 11986.4852 | 12019.3248 | 11986.4852 | 11986.4852 | 11986.4852 | 12019.3248 | 3875.0829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 696037.1309
Space Environment & Radiation Effects Engineer | ASCD - Space Systems Engineering | Tobiah Lanreth | 11972580 | EN-ENG-4 | 20% | 50% | 100% | 100% | 50% | 20% | 0% | 0% | 0% | 0% | 134635.2537 | 14865.2075 | 80596.7204 | 134635.2537 | 132790.9352 | 67317.6269 | 66948.7632 | 22353.1408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 519507.6476
EMC / EMI & Passive Intermodulation Specialist | ASCD - Communications Payload | Gwendolen Iserly | 11980499 | EN-ENG-4 | 0% | 20% | 50% | 100% | 100% | 100% | 20% | 0% | 0% | 0% | 134635.2537 | 959.0456 | 34857.6205 | 68977.5136 | 134635.2537 | 134635.2537 | 135004.1174 | 116339.6138 | 8778.9563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 634187.3746
Communications Payload Lead | ASCD - Communications Payload | Aldric Sunmere | 11988418 | EN-ENG-5 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 20% | 0% | 0% | 154580.3961 | 77078.4441 | 155003.904 | 154580.3961 | 154580.3961 | 154580.3961 | 155003.904 | 154580.3961 | 71234.0346 | 30916.0792 | 31000.7808 | 30916.0792 | 30916.0792 | 30916.0792 | 31000.7808 | 9994.7873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1272302.5369
RF / Ka-band Payload Engineer | ASCD - Communications Payload | Mireya Castellane | 11996337 | EN-ENG-4 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 10% | 0% | 0% | 134635.2537 | 35964.2116 | 135004.1174 | 134635.2537 | 134635.2537 | 134635.2537 | 135004.1174 | 134635.2537 | 52968.8286 | 13463.5254 | 13500.4117 | 13463.5254 | 13463.5254 | 13463.5254 | 13500.4117 | 4352.5918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 982689.8068
Digital Channelizer & Onboard Processor Engineer | ASCD - Communications Payload | Oskar Belvanne | 11905256 | EN-ENG-4 | 30% | 100% | 100% | 100% | 100% | 50% | 50% | 5% | 0% | 0% | 134635.2537 | 23496.6183 | 135004.1174 | 134635.2537 | 134635.2537 | 134635.2537 | 134081.9582 | 67317.6269 | 26484.4143 | 6731.7627 | 6750.2059 | 6731.7627 | 6731.7627 | 6731.7627 | 6750.2059 | 2176.2959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 832894.2546
Reflector Antenna RF Optics Engineer | ASCD - Communications Payload | Esmé Thorncastle | 11913175 | EN-ENG-4 | 30% | 100% | 100% | 100% | 100% | 50% | 50% | 0% | 0% | 0% | 134635.2537 | 23496.6183 | 135004.1174 | 134635.2537 | 134635.2537 | 134635.2537 | 134081.9582 | 67317.6269 | 21947.3907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 785753.4726
Optical Engineer (Star Trackers & Reflector Surface Metrology) | ASCD - Communications Payload | Nikolai Farrowden | 11921094 | PC-4 | 0% | 30% | 50% | 100% | 100% | 50% | 30% | 0% | 0% | 0% | 135683.705 | 1449.7711 | 46095.2861 | 69514.6653 | 135683.705 | 135683.705 | 135126.1007 | 63232.3239 | 13270.9816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600056.5387
Link Budget & Ka-band Propagation Engineer | ASCD - Communications Payload | Hesper Valdane | 11929013 | EN-ENG-4 | 100% | 100% | 50% | 50% | 20% | 20% | 50% | 20% | 0% | 0% | 134635.2537 | 67133.195 | 121909.4558 | 67317.6269 | 66211.0357 | 26927.0507 | 27000.8235 | 33787.9157 | 40095.4852 | 26927.0507 | 27000.8235 | 26927.0507 | 26927.0507 | 26927.0507 | 27000.8235 | 8705.1835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620797.622
Payload Calibration & Beam-Pointing Scientist | ASCD - Communications Payload | Ravel Ostrander | 11936932 | PC-3 | 0% | 20% | 50% | 50% | 50% | 100% | 100% | 30% | 0% | 20% | 118607.955 | 844.8786 | 30708.087 | 59303.9775 | 59303.9775 | 59303.9775 | 60278.8374 | 122637.3759 | 86372.5875 | 59303.9775 | 59466.4542 | 59303.9775 | 59303.9775 | 59303.9775 | 59466.4542 | 19172.2448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 854074.762
Payload Test Engineer (Compact Antenna Test Range) | ASCD - AIT & Launch | Juniper Kaltz | 11944851 | EN-ENG-3 | 0% | 0% | 20% | 50% | 100% | 100% | 20% | 0% | 0% | 0% | 119864.8515 | 0 | 4663.2353 | 24859.6418 | 61574.41 | 119864.8515 | 120193.2484 | 103576.3676 | 7815.8451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 442547.5997
Communications Security (COMSEC) Lead | ASCD - Communications Security | Vesper Ingleby | 11952770 | CS-4 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 50% | 0% | 140110.4126 | 69863.2742 | 140494.2767 | 140110.4126 | 140110.4126 | 140110.4126 | 140494.2767 | 140110.4126 | 92895.1229 | 70055.2063 | 70247.1384 | 70055.2063 | 70055.2063 | 70055.2063 | 70247.1384 | 22647.9845 | 0 | 12091.7205 | 22839.9166 | 0 | 0 | 0 | 0 | 0 | 1482483.3244
Cryptographic Engineer (Security Processors) | ASCD - Communications Security | Thane Morcombe | 11960689 | CS-3 | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 20% | 0% | 0% | 122142.9344 | 21316.4518 | 122477.5726 | 122142.9344 | 122142.9344 | 122142.9344 | 122477.5726 | 122142.9344 | 56286.1413 | 24428.5869 | 24495.5145 | 24428.5869 | 24428.5869 | 24428.5869 | 24495.5145 | 7897.461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 965732.3134
Key Management Specialist | ASCD - Communications Security | Lyra Achterberg | 11968608 | CS-3 | 20% | 50% | 100% | 100% | 50% | 100% | 100% | 100% | 50% | 0% | 122142.9344 | 13485.9185 | 73118.4416 | 122142.9344 | 120469.7435 | 61071.4672 | 62075.3817 | 122142.9344 | 122142.9344 | 122142.9344 | 122477.5726 | 122142.9344 | 122142.9344 | 122142.9344 | 122477.5726 | 39487.3048 | 0 | 10541.1026 | 19910.9715 | 0 | 0 | 0 | 0 | 0 | 1500116.0174
Cybersecurity Architect (Ground & Network) | ASCD - Communications Security | Osric Wendell | 11976527 | CS-4 | 30% | 100% | 100% | 100% | 50% | 100% | 100% | 50% | 20% | 0% | 140110.4126 | 24452.146 | 140494.2767 | 140110.4126 | 138191.0919 | 70055.2063 | 71206.7987 | 140110.4126 | 92895.1229 | 70055.2063 | 70247.1384 | 70055.2063 | 70055.2063 | 70055.2063 | 70247.1384 | 22647.9845 | 0 | 4836.6882 | 9135.9666 | 0 | 0 | 0 | 0 | 0 | 1274851.2089
Security Assessment & Authorization Officer | ASCD - Communications Security | Calla Brightwater | 11984446 | CS-3 | 0% | 30% | 50% | 50% | 50% | 100% | 100% | 30% | 20% | 0% | 122142.9344 | 1305.0889 | 41495.1339 | 61071.4672 | 61071.4672 | 61071.4672 | 62075.3817 | 122142.9344 | 64518.2404 | 36642.8803 | 36743.2718 | 36642.8803 | 36642.8803 | 36642.8803 | 36743.2718 | 11846.1914 | 0 | 4216.441 | 7964.3886 | 0 | 0 | 0 | 0 | 0 | 718836.2669
Industrial & Personnel Security Officer | ASCD - Communications Security | Gideon Farlowe | 11992365 | PM-4 | 20% | 50% | 50% | 50% | 50% | 50% | 30% | 20% | 20% | 0% | 87103.7075 | 9617.2039 | 43671.1739 | 43551.8538 | 43551.8538 | 43551.8538 | 43671.1739 | 40592.7141 | 20260.561 | 17420.7415 | 17468.4696 | 17420.7415 | 17420.7415 | 17420.7415 | 17468.4696 | 5631.911 | 0 | 3006.8677 | 5679.639 | 0 | 0 | 0 | 0 | 0 | 407406.7108
Spectrum Management & Coordination Engineer | ASCD - Spectrum & Regulatory Affairs | Anwen Saltmarsh | 11901284 | EN-ENG-5 | 100% | 100% | 100% | 50% | 50% | 50% | 100% | 30% | 30% | 0% | 154580.3961 | 77078.4441 | 155003.904 | 152674.6104 | 77290.198 | 77290.198 | 77501.952 | 90418.944 | 81652.3298 | 46374.1188 | 46501.1712 | 46374.1188 | 46374.1188 | 46374.1188 | 46501.1712 | 14992.1809 | 0 | 8004.3 | 15119.2333 | 0 | 0 | 0 | 0 | 0 | 1105525.1122
Regulatory & Licensing Officer | ASCD - Spectrum & Regulatory Affairs | Bastien Quarrell | 11909203 | PM-5 | 50% | 100% | 50% | 30% | 20% | 50% | 50% | 10% | 30% | 0% | 104039.375 | 27791.3399 | 94205.5163 | 51506.6166 | 30926.7731 | 20807.875 | 21292.442 | 52019.6875 | 23971.8122 | 10403.9375 | 10432.4414 | 10403.9375 | 10403.9375 | 10403.9375 | 10432.4414 | 3363.4647 | 0 | 5387.2443 | 10175.906 | 0 | 0 | 0 | 0 | 0 | 403929.3104
Space Sustainability & GEO Disposal Engineer | ASCD - Spectrum & Regulatory Affairs | Coralie Venn | 11917122 | EN-ENG-3 | 20% | 30% | 30% | 30% | 10% | 10% | 20% | 10% | 100% | 0% | 119864.8515 | 12380.5614 | 36057.9745 | 35959.4555 | 35302.6617 | 11986.4852 | 12019.3248 | 14022.5456 | 15894.4077 | 11986.4852 | 12019.3248 | 11986.4852 | 11986.4852 | 11986.4852 | 12019.3248 | 3875.0829 | 0 | 20689.0018 | 39079.2256 | 0 | 0 | 0 | 0 | 0 | 309251.3169
Safety & Mission Assurance Lead | ASCD - Safety & Mission Assurance | Hollis Grenvale | 11925041 | EN-ENG-5 | 30% | 50% | 100% | 100% | 100% | 100% | 100% | 20% | 30% | 0% | 154580.3961 | 24224.6539 | 92536.4837 | 154580.3961 | 154580.3961 | 154580.3961 | 155003.904 | 154580.3961 | 71234.0346 | 30916.0792 | 31000.7808 | 30916.0792 | 30916.0792 | 30916.0792 | 31000.7808 | 9994.7873 | 0 | 8004.3 | 15119.2333 | 0 | 0 | 0 | 0 | 0 | 1180104.8595
Product Assurance / Quality Engineer | ASCD - Safety & Mission Assurance | Petra Lindqvale | 11932960 | EN-ENG-4 | 0% | 30% | 50% | 100% | 100% | 100% | 50% | 0% | 0% | 0% | 134635.2537 | 1438.5685 | 45739.0999 | 68977.5136 | 134635.2537 | 134635.2537 | 135004.1174 | 123200.4788 | 21947.3907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 665577.6763
EEE Parts & Radiation Hardness Assurance Engineer | ASCD - Safety & Mission Assurance | Ansel Corwyn | 11940879 | EN-ENG-4 | 0% | 30% | 100% | 100% | 100% | 50% | 0% | 0% | 0% | 0% | 134635.2537 | 1438.5685 | 58833.7616 | 134635.2537 | 134635.2537 | 134635.2537 | 134081.9582 | 55882.8519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 654142.9013
Reliability & Availability Engineer | ASCD - Safety & Mission Assurance | Marguerite Aske | 11948798 | EN-ENG-3 | 30% | 50% | 100% | 100% | 50% | 50% | 50% | 20% | 0% | 0% | 119864.8515 | 18784.3 | 71754.7125 | 119864.8515 | 118222.8672 | 59932.4258 | 60096.6242 | 59932.4258 | 35696.738 | 23972.9703 | 24038.6497 | 23972.9703 | 23972.9703 | 23972.9703 | 24038.6497 | 7750.1657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 696004.2912
Software Product Assurance Engineer | ASCD - Safety & Mission Assurance | Tiberius Nolle | 11956717 | EN-ENG-3 | 0% | 20% | 50% | 100% | 100% | 100% | 50% | 10% | 0% | 0% | 119864.8515 | 853.8318 | 31033.5027 | 61410.2116 | 119864.8515 | 119864.8515 | 120193.2484 | 109684.5491 | 27618.1754 | 11986.4852 | 12019.3248 | 11986.4852 | 11986.4852 | 11986.4852 | 12019.3248 | 3875.0829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 666382.895
Materials & Processes Engineer | ASCD - Safety & Mission Assurance | Solenne Ravick | 11964636 | PC-3 | 0% | 0% | 50% | 50% | 100% | 50% | 0% | 0% | 0% | 0% | 118607.955 | 0 | 11535.8422 | 59303.9775 | 60928.744 | 118607.955 | 118120.525 | 49230.4252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417727.4689
System Safety Engineer (Propellant & Launch Site) | ASCD - Safety & Mission Assurance | Everett Dunmoor | 11972555 | EN-ENG-4 | 0% | 20% | 50% | 50% | 50% | 100% | 100% | 0% | 30% | 0% | 134635.2537 | 959.0456 | 34857.6205 | 67317.6269 | 67317.6269 | 67317.6269 | 68424.218 | 134635.2537 | 43894.7814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6971.5241 | 13168.4344 | 0 | 0 | 0 | 0 | 0 | 504863.7583
AIT Manager (Government Witness) | ASCD - AIT & Launch | Rhosyn Calder | 11980474 | EN-ENG-5 | 0% | 0% | 30% | 50% | 100% | 100% | 30% | 0% | 0% | 0% | 154580.3961 | 0 | 9020.719 | 47136.4331 | 79407.7377 | 154580.3961 | 155003.904 | 136200.1517 | 15119.2333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 596468.575
Environmental Test Engineer | ASCD - AIT & Launch | Lucan Firthwood | 11988393 | EN-ENG-4 | 0% | 0% | 20% | 50% | 100% | 100% | 0% | 0% | 0% | 0% | 134635.2537 | 0 | 5237.8647 | 27922.9828 | 69161.9454 | 134635.2537 | 135004.1174 | 111765.7038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483727.8678
Launch Campaign Manager | ASCD - AIT & Launch | Isolde Pemberly | 11996312 | EN-ENG-5 | 0% | 20% | 50% | 50% | 50% | 100% | 100% | 0% | 0% | 0% | 154580.3961 | 1101.1206 | 40021.4998 | 77290.198 | 77290.198 | 77290.198 | 78560.7219 | 154580.3961 | 50397.4442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 556531.7767
Launch Vehicle Interface Engineer (Coupled Loads) | ASCD - AIT & Launch | Barnaby Treloar | 11905231 | EN-ENG-4 | 0% | 20% | 100% | 100% | 50% | 100% | 50% | 0% | 0% | 0% | 134635.2537 | 959.0456 | 47952.2822 | 134635.2537 | 132790.9352 | 67317.6269 | 68424.218 | 123200.4788 | 21947.3907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 597227.231
Launch Site Operations Engineer | ASCD - AIT & Launch | Kestrel Amberly | 11913150 | EN-ENG-3 | 0% | 0% | 0% | 20% | 30% | 100% | 100% | 0% | 0% | 0% | 119864.8515 | 0 | 0 | 591.1143 | 24301.3672 | 35959.4555 | 37207.3635 | 119864.8515 | 39079.2256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257003.3775
Ground Segment Manager | ASCD - Ground Segment | Octavia Ferrand | 11921069 | EN-ENG-5 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 30% | 50% | 0% | 154580.3961 | 41292.0236 | 155003.904 | 154580.3961 | 154580.3961 | 154580.3961 | 155003.904 | 154580.3961 | 81652.3298 | 46374.1188 | 46501.1712 | 46374.1188 | 46374.1188 | 46374.1188 | 46501.1712 | 14992.1809 | 0 | 13340.4999 | 25198.7221 | 0 | 0 | 0 | 0 | 0 | 1383303.9665
Gateway RF & Earth-Station Engineer | ASCD - Ground Segment | Lorcan Westerly | 11928988 | EN-ENG-4 | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 30% | 20% | 0% | 134635.2537 | 23496.6183 | 135004.1174 | 134635.2537 | 134635.2537 | 134635.2537 | 135004.1174 | 134635.2537 | 71116.9231 | 40390.5761 | 40501.2352 | 40390.5761 | 40390.5761 | 40390.5761 | 40501.2352 | 13057.7753 | 0 | 4647.6827 | 8778.9563 | 0 | 0 | 0 | 0 | 0 | 1172211.9804
Network Control Centre Engineer | ASCD - Ground Segment | Sabra Kinloch | 11936907 | EN-ENG-4 | 20% | 50% | 100% | 100% | 100% | 100% | 100% | 50% | 20% | 0% | 134635.2537 | 14865.2075 | 80596.7204 | 134635.2537 | 134635.2537 | 134635.2537 | 135004.1174 | 134635.2537 | 89265.0175 | 67317.6269 | 67502.0587 | 67317.6269 | 67317.6269 | 67317.6269 | 67502.0587 | 21762.9588 | 0 | 4647.6827 | 8778.9563 | 0 | 0 | 0 | 0 | 0 | 1297736.3005
Ground Software Engineer (Network Control) | ASCD - Ground Segment | Emrys Halloway | 11944826 | EN-ENG-4 | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 0% | 134635.2537 | 2397.6141 | 80596.7204 | 134635.2537 | 134635.2537 | 134635.2537 | 135004.1174 | 134635.2537 | 89265.0175 | 67317.6269 | 67502.0587 | 67317.6269 | 67317.6269 | 67317.6269 | 67502.0587 | 21762.9588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1271842.0681
Ground Software Engineer (Independent V&V / Dissimilar Build) | ASCD - Ground Segment | Viveka Stroud | 11952745 | EN-ENG-3 | 0% | 0% | 50% | 100% | 100% | 100% | 50% | 20% | 0% | 0% | 119864.8515 | 0 | 11658.0883 | 61410.2116 | 119864.8515 | 119864.8515 | 120193.2484 | 109684.5491 | 35696.738 | 23972.9703 | 24038.6497 | 23972.9703 | 23972.9703 | 23972.9703 | 24038.6497 | 7750.1657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730091.8846
Terrestrial Backhaul & Network Engineer | ASCD - Ground Segment | Cedric Mallorne | 11960664 | CS-3 | 0% | 30% | 50% | 100% | 50% | 100% | 100% | 50% | 20% | 0% | 122142.9344 | 1305.0889 | 41495.1339 | 62577.339 | 120469.7435 | 61071.4672 | 62075.3817 | 122142.9344 | 80982.4387 | 61071.4672 | 61238.7863 | 61071.4672 | 61071.4672 | 61071.4672 | 61238.7863 | 19743.6524 | 0 | 4216.441 | 7964.3886 | 0 | 0 | 0 | 0 | 0 | 950807.4508
Audit Archive & Data Systems Engineer | ASCD - Ground Segment | Farah Linwood | 11968583 | CS-3 | 0% | 20% | 50% | 50% | 50% | 100% | 50% | 30% | 50% | 0% | 122142.9344 | 870.0593 | 31623.3077 | 61071.4672 | 61071.4672 | 61071.4672 | 62075.3817 | 111769.1509 | 44607.2689 | 36642.8803 | 36743.2718 | 36642.8803 | 36642.8803 | 36642.8803 | 36743.2718 | 11846.1914 | 0 | 10541.1026 | 19910.9715 | 0 | 0 | 0 | 0 | 0 | 696515.9005
Mission Operations Manager | ASCD - Network & Mission Operations | Benedikt Aurel | 11976502 | EN-ENG-5 | 20% | 30% | 50% | 50% | 50% | 100% | 100% | 100% | 100% | 0% | 154580.3961 | 15966.2491 | 52514.9839 | 77290.198 | 77290.198 | 77290.198 | 78560.7219 | 154580.3961 | 154580.3961 | 154580.3961 | 155003.904 | 154580.3961 | 154580.3961 | 154580.3961 | 155003.904 | 49973.9363 | 0 | 26680.9999 | 50397.4442 | 0 | 0 | 0 | 0 | 0 | 1743455.114
Flight Operations Director | ASCD - Network & Mission Operations | Morwenna Tells | 11984421 | EN-ENG-4 | 0% | 0% | 20% | 50% | 50% | 100% | 100% | 100% | 100% | 0% | 134635.2537 | 0 | 5237.8647 | 27922.9828 | 67317.6269 | 67317.6269 | 68424.218 | 134635.2537 | 134635.2537 | 134635.2537 | 135004.1174 | 134635.2537 | 134635.2537 | 134635.2537 | 135004.1174 | 43525.9176 | 0 | 23238.4137 | 43894.7814 | 0 | 0 | 0 | 0 | 0 | 1424699.1891
Spacecraft Controller | ASCD - Network & Mission Operations | Ptolemy Garrick | 11992340 | EN-ENG-3 | 0% | 0% | 0% | 0% | 20% | 100% | 100% | 100% | 100% | 0% | 119864.8515 | 0 | 0 | 0 | 656.7937 | 23972.9703 | 25352.2371 | 119864.8515 | 119864.8515 | 119864.8515 | 120193.2484 | 119864.8515 | 119864.8515 | 119864.8515 | 120193.2484 | 38750.8287 | 0 | 20689.0018 | 39079.2256 | 0 | 0 | 0 | 0 | 0 | 1108076.6629
Spacecraft Controller | ASCD - Network & Mission Operations | Ilona Brackwell | 11901259 | EN-ENG-3 | 0% | 0% | 0% | 0% | 20% | 100% | 100% | 100% | 50% | 0% | 119864.8515 | 0 | 0 | 0 | 656.7937 | 23972.9703 | 25352.2371 | 119864.8515 | 119864.8515 | 119864.8515 | 120193.2484 | 119864.8515 | 119864.8515 | 119864.8515 | 120193.2484 | 38750.8287 | 0 | 10344.5009 | 19539.6128 | 0 | 0 | 0 | 0 | 0 | 1078192.5492
Spacecraft Controller | ASCD - Network & Mission Operations | Dashiell Merrin | 11909178 | EN-ENG-3 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 50% | 0% | 119864.8515 | 0 | 0 | 0 | 0 | 0 | 1641.9843 | 119864.8515 | 119864.8515 | 119864.8515 | 120193.2484 | 119864.8515 | 119864.8515 | 119864.8515 | 120193.2484 | 38750.8287 | 0 | 10344.5009 | 19539.6128 | 0 | 0 | 0 | 0 | 0 | 1029852.5324
Payload & Network Operations Engineer | ASCD - Network & Mission Operations | Saoirse Valentyne | 11917097 | EN-ENG-3 | 0% | 0% | 0% | 20% | 50% | 100% | 100% | 100% | 50% | 0% | 119864.8515 | 0 | 0 | 591.1143 | 24958.1609 | 59932.4258 | 60917.6163 | 119864.8515 | 119864.8515 | 119864.8515 | 120193.2484 | 119864.8515 | 119864.8515 | 119864.8515 | 120193.2484 | 38750.8287 | 0 | 10344.5009 | 19539.6128 | 0 | 0 | 0 | 0 | 0 | 1174609.8654
Flight Dynamics Operations Engineer | ASCD - Network & Mission Operations | Jasper Wrenfield | 11925016 | EN-ENG-3 | 0% | 0% | 0% | 20% | 30% | 100% | 100% | 100% | 100% | 0% | 119864.8515 | 0 | 0 | 591.1143 | 24301.3672 | 35959.4555 | 37207.3635 | 119864.8515 | 119864.8515 | 119864.8515 | 120193.2484 | 119864.8515 | 119864.8515 | 119864.8515 | 120193.2484 | 38750.8287 | 0 | 20689.0018 | 39079.2256 | 0 | 0 | 0 | 0 | 0 | 1156153.9622
Operations Training & Simulation Lead | ASCD - Network & Mission Operations | Philippa Orme | 11932935 | EN-ENG-4 | 0% | 0% | 20% | 50% | 100% | 100% | 100% | 50% | 0% | 0% | 134635.2537 | 0 | 5237.8647 | 27922.9828 | 69161.9454 | 134635.2537 | 135004.1174 | 134635.2537 | 89265.0175 | 67317.6269 | 67502.0587 | 67317.6269 | 67317.6269 | 67317.6269 | 67502.0587 | 21762.9588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021900.019
Operations Support Technologist | ASCD - Network & Mission Operations | Arlo Penhallow | 11940854 | EG-6 | 0% | 0% | 0% | 20% | 50% | 100% | 100% | 100% | 50% | 0% | 103981.4589 | 0 | 0 | 512.7853 | 21650.9339 | 51990.7295 | 52845.3716 | 103981.4589 | 103981.4589 | 103981.4589 | 104266.3396 | 103981.4589 | 103981.4589 | 103981.4589 | 104266.3396 | 33615.9237 | 0 | 8973.7423 | 16950.4022 | 0 | 0 | 0 | 0 | 0 | 1018961.3211
Sustaining Engineer (Bus) | ASCD - Network & Mission Operations | Tamsyn Holloway | 11948773 | EN-ENG-4 | 0% | 0% | 0% | 0% | 20% | 50% | 100% | 100% | 50% | 0% | 134635.2537 | 0 | 0 | 0 | 737.7274 | 26927.0507 | 27554.1191 | 78752.4018 | 134635.2537 | 134635.2537 | 135004.1174 | 134635.2537 | 134635.2537 | 134635.2537 | 135004.1174 | 43525.9176 | 0 | 11619.2068 | 21947.3907 | 0 | 0 | 0 | 0 | 0 | 1154248.3178
Sustaining Engineer (Payload & Crypto) | ASCD - Network & Mission Operations | Gareth Illingworth | 11956692 | EN-ENG-4 | 0% | 0% | 0% | 0% | 20% | 50% | 100% | 100% | 30% | 0% | 134635.2537 | 0 | 0 | 0 | 737.7274 | 26927.0507 | 27554.1191 | 78752.4018 | 134635.2537 | 134635.2537 | 135004.1174 | 134635.2537 | 134635.2537 | 134635.2537 | 135004.1174 | 43525.9176 | 0 | 6971.5241 | 13168.4344 | 0 | 0 | 0 | 0 | 0 | 1140821.6788
IT Systems Administrator | ASCD - Ground Segment | Nadira Coombe | 11964611 | CS-2 | 20% | 30% | 30% | 50% | 50% | 100% | 100% | 100% | 50% | 0% | 101935.0642 | 10528.6354 | 30664.3015 | 31083.2127 | 50967.5321 | 50967.5321 | 51805.3546 | 101935.0642 | 101935.0642 | 101935.0642 | 102214.3384 | 101935.0642 | 101935.0642 | 101935.0642 | 102214.3384 | 32954.3495 | 0 | 8797.1357 | 16616.8118 | 0 | 0 | 0 | 0 | 0 | 1100423.9277
User Community Liaison & Service Manager | ASCD - User Services | Eluned Faircloth | 11972530 | PC-4 | 50% | 100% | 50% | 30% | 20% | 50% | 100% | 0% | 0% | 100% | 135683.705 | 36244.2774 | 122858.8069 | 67172.7274 | 40333.3753 | 27136.741 | 27768.6925 | 102413.3171 | 179920.3102 | 135683.705 | 136055.4412 | 135683.705 | 135683.705 | 135683.705 | 136055.4412 | 43864.869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1462558.819
Service Performance Analyst (Availability) | ASCD - User Services | Hadrian Kells | 11980449 | PC-3 | 0% | 20% | 20% | 20% | 20% | 50% | 100% | 0% | 0% | 100% | 118607.955 | 844.8786 | 23786.5817 | 23721.591 | 23721.591 | 23721.591 | 24274.0116 | 89524.6345 | 157277.3979 | 118607.955 | 118932.9083 | 118607.955 | 118607.955 | 118607.955 | 118932.9083 | 38344.4896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1117514.4034
Data Validation Scientist (Tervalis Liaison) | ASCD - User Services | Marisol Everleigh | 11988368 | PC-3 | 20% | 50% | 20% | 20% | 20% | 50% | 100% | 0% | 50% | 100% | 118607.955 | 13095.618 | 52544.9488 | 23721.591 | 23721.591 | 23721.591 | 24274.0116 | 89524.6345 | 157277.3979 | 118607.955 | 118932.9083 | 118607.955 | 118607.955 | 118607.955 | 118932.9083 | 38344.4896 | 0 | 10236.029 | 19334.7214 | 0 | 0 | 0 | 0 | 0 | 1188094.2605
Total |  |  |  |  | 19.85 | 40.15 | 55.95 | 59.75 | 56.9 | 66.5 | 58.6 | 22.97 | 19.65 | 3.2 |  | 1419660.1939 | 5755310.9533 | 7456783.4686 | 7918292.5845 | 7557440.8487 | 7594167.1051 | 8618737.4953 | 4885359.4643 | 3335245.0297 | 3344382.6873 | 3335245.0297 | 3335245.0297 | 3335245.0297 | 3344382.6873 | 1078243.5986 | 0 | 436324.085 | 824167.716 | 0 | 0 | 0 | 0 | 0 | 73574233.0067
[18 empty] | 28/29 | 29/30 | 30/31 | 31/32 | 32/33 | 33/34 | 34/35 | 35/36 | 36/37 | 37/38 | 38/39 | 39/40 | 40/41 | 41/42 | 42/43 | 43/44 | 44/45 | 45/46 | 46/47 | 47/48 | 48/49 | Total
Distribution By Phase $ (non indexé)
[15 empty] | Phase 0 | 1229854.3384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1229854.3384
[15 empty] | Phase A | 189805.8556 | 4307132.8765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4496938.732
[15 empty] | Phase B | 0 | 1448178.0768 | 7261287.2582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8709465.335
[15 empty] | Phase C | 0 | 0 | 195496.2104 | 7711239.4106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7906735.621
[15 empty] | Phase D1 | 0 | 0 | 0 | 207053.1739 | 7557440.8487 | 7474619.5791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15239113.6017
[15 empty] | Phase D2 | 0 | 0 | 0 | 0 | 0 | 119547.526 | 7244580.0765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7364127.6026
[15 empty] | Phase D3 | 0 | 0 | 0 | 0 | 0 | 0 | 1306786.1454 | 2508186.3114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3814972.4568
[15 empty] | Phase E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1980551.9469 | 2938623.8237 | 2946674.8479 | 2938623.8237 | 2938623.8237 | 2938623.8237 | 2946674.8479 | 950020.8526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20578417.7899
[15 empty] | Phase F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 436324.085 | 824167.716 | 0 | 0 | 0 | 0 | 0 | 1260491.801
[15 empty] | Science support | 0 | 0 | 0 | 0 | 0 | 0 | 67371.2733 | 396621.206 | 396621.206 | 397707.8394 | 396621.206 | 396621.206 | 396621.206 | 397707.8394 | 128222.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2974115.7283
[15 empty] | Total in $ | 1419660.1939 | 5755310.9533 | 7456783.4686 | 7918292.5845 | 7557440.8487 | 7594167.1051 | 8618737.4953 | 4885359.4643 | 3335245.0297 | 3344382.6873 | 3335245.0297 | 3335245.0297 | 3335245.0297 | 3344382.6873 | 1078243.5986 | 0 | 436324.085 | 824167.716 | 0 | 0 | 0 | 0 | 0 | 73574233.0067
[15 empty] | check | 4.6566e-10 | 5.5879e-09 | 1.8626e-09 | 1.8626e-09 | -9.3132e-10 | 2.794e-09 | 0 | 0 | 4.6566e-10 | 9.3132e-10 | 4.6566e-10 | 4.6566e-10 | 4.6566e-10 | 9.3132e-10 | 4.6566e-10 | 0 | -1.7462e-10 | -3.4925e-10 | 0 | 0 | 0 | 0 | 0 | 0
Distribution By Phase (Indexé)
[15 empty] | Phase 0 | 1229854.3384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1229854.3384
[15 empty] | Phase A | 189805.8556 | 4307132.8765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4496938.732
[15 empty] | Phase B | 0 | 1448178.0768 | 7261287.2582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8709465.335
[15 empty] | Phase C | 0 | 0 | 195496.2104 | 7711239.4106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7906735.621
[15 empty] | Phase D1 | 0 | 0 | 0 | 207053.1739 | 7557440.8487 | 7474619.5791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15239113.6017
[15 empty] | Phase D2 | 0 | 0 | 0 | 0 | 0 | 119547.526 | 7244580.0765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7364127.6026
[15 empty] | Phase D3 | 0 | 0 | 0 | 0 | 0 | 0 | 1306786.1454 | 2508186.3114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3814972.4568
[15 empty] | Phase E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1980551.9469 | 2938623.8237 | 2946674.8479 | 2938623.8237 | 2938623.8237 | 2938623.8237 | 2946674.8479 | 950020.8526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20578417.7899
[15 empty] | Phase F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 436324.085 | 824167.716 | 0 | 0 | 0 | 0 | 0 | 1260491.801
[15 empty] | Science support | 0 | 0 | 0 | 0 | 0 | 0 | 67371.2733 | 396621.206 | 396621.206 | 397707.8394 | 396621.206 | 396621.206 | 396621.206 | 397707.8394 | 128222.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2974115.7283
[15 empty] | Total in $ | 1419660.1939 | 5755310.9533 | 7456783.4686 | 7918292.5845 | 7557440.8487 | 7594167.1051 | 8618737.4953 | 4885359.4643 | 3335245.0297 | 3344382.6873 | 3335245.0297 | 3335245.0297 | 3335245.0297 | 3344382.6873 | 1078243.5986 | 0 | 436324.085 | 824167.716 | 0 | 0 | 0 | 0 | 0 | 73574233.0067
Prime bilinguisme non sujet à l'indexation
[15 empty] | Phase 0 | 7352.6575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7352.6575
[15 empty] | Phase A | 1144 | 25960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27104
[15 empty] | Phase B | 0 | 8706.7397 | 43656.3288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52363.0685
[15 empty] | Phase C | 0 | 0 | 1178.6301 | 46490.411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47669.0411
[15 empty] | Phase D1 | 0 | 0 | 0 | 1247.1233 | 45520 | 45021.1507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91788.274
[15 empty] | Phase D2 | 0 | 0 | 0 | 0 | 0 | 728.7671 | 44163.2877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44892.0548
[15 empty] | Phase D3 | 0 | 0 | 0 | 0 | 0 | 0 | 7963.1781 | 15284.1644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23247.3425
[15 empty] | Phase E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12384.9205 | 18376 | 18426.3452 | 18376 | 18376 | 18376 | 18426.3452 | 5940.7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128682.3452
[15 empty] | Phase F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2713.3151 | 5125.1507 | 0 | 0 | 0 | 0 | 0 | 7838.4658
[15 empty] | Science support | 0 | 0 | 0 | 0 | 0 | 0 | 434.8493 | 2560 | 2560 | 2567.0137 | 2560 | 2560 | 2560 | 2567.0137 | 827.6164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19196.4932
[15 empty] | Total in $ | 8496.6575 | 34666.7397 | 44834.9589 | 47737.5342 | 45520 | 45749.9178 | 52561.3151 | 30229.0849 | 20936 | 20993.3589 | 20936 | 20936 | 20936 | 20993.3589 | 6768.3507 | 0 | 2713.3151 | 5125.1507 | 0 | 0 | 0 | 0 | 0 | 450133.7425
[15 empty] | Salaire |  |  |  | 29/30 | 30/31 | 31/32 | 32/33 | 33/34 | 34/35 | 35/36 | 36/37 | 37/38 | 38/39 | 39/40 | 40/41 | 41/42 | 42/43 | 43/44 | 44/45 | 45/46 | 46/47 | 47/48 | 48/49
[15 empty] | Phase 0 | 1237207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1237207
[15 empty] | Phase A | 190950 | 4333093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4524043
[15 empty] | Phase B | 0 | 1456885 | 7304944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8761829
[15 empty] | Phase C | 0 | 0 | 196675 | 7757730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7954405
[15 empty] | Phase D1 | 0 | 0 | 0 | 208300 | 7602961 | 7519641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15330902
[15 empty] | Phase D2 | 0 | 0 | 0 | 0 | 0 | 120276 | 7288743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7409019
[15 empty] | Phase D3 | 0 | 0 | 0 | 0 | 0 | 0 | 1314749 | 2523470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3838219
[15 empty] | Phase E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1992937 | 2957000 | 2965101 | 2957000 | 2957000 | 2957000 | 2965101 | 955962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20707101
[15 empty] | Phase F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 439037 | 829293 | 0 | 0 | 0 | 0 | 0 | 1268330
[15 empty] | Science support | 0 | 0 | 0 | 0 | 0 | 0 | 67806 | 399181 | 399181 | 400275 | 399181 | 399181 | 399181 | 400275 | 129050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2993311
[15 empty] | Total in $ | 1428157 | 5789978 | 7501619 | 7966030 | 7602961 | 7639917 | 8671298 | 4915588 | 3356181 | 3365376 | 3356181 | 3356181 | 3356181 | 3365376 | 1085012 | 0 | 439037 | 829293 | 0 | 0 | 0 | 0 | 0 | 74024366
[15 empty] | FTE |  |  |  | 29/30 | 30/31 | 31/32 | 32/33 | 33/34 | 34/35 | 35/36 | 36/37 | 37/38 | 38/39 | 39/40 | 40/41 | 41/42 | 42/43 | 43/44 | 44/45 | 45/46 | 46/47 | 47/48 | 48/49
[15 empty] | Phase 0 | 9.1908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1908
[15 empty] | Phase A | 1.43 | 32.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.88
[15 empty] | Phase B | 0 | 10.8834 | 54.5704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.4538
[15 empty] | Phase C | 0 | 0 | 1.4733 | 58.113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.5863
[15 empty] | Phase D1 | 0 | 0 | 0 | 1.5589 | 56.9 | 56.2764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114.7353
[15 empty] | Phase D2 | 0 | 0 | 0 | 0 | 0 | 0.91096 | 55.2041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.1151
[15 empty] | Phase D3 | 0 | 0 | 0 | 0 | 0 | 0 | 9.954 | 19.1052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.0592
[15 empty] | Phase E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.4812 | 22.97 | 23.0329 | 22.97 | 22.97 | 22.97 | 23.0329 | 7.4259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160.8529
[15 empty] | Phase F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3916 | 6.4064 | 0 | 0 | 0 | 0 | 0 | 9.7981
[15 empty] | Science support | 0 | 0 | 0 | 0 | 0 | 0 | 0.54356 | 3.2 | 3.2 | 3.2088 | 3.2 | 3.2 | 3.2 | 3.2088 | 1.0345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.9956
[15 empty] | Total FTE | 10.6208 | 43.3334 | 56.0437 | 59.6719 | 56.9 | 57.1874 | 65.7016 | 37.7864 | 26.17 | 26.2417 | 26.17 | 26.17 | 26.17 | 26.2417 | 8.4604 | 0 | 3.3916 | 6.4064 | 0 | 0 | 0 | 0 | 0 | 562.6672
Hypothèses de travail
Salaire au maximum de l'échelon
Incluant Prime Bilinguisme 800$ non indexé à travers les années |  | 800
Ligne applicableTable Inflation Salaires onglet 2F |  | 4
Source livelink gestionnaaire si applicable
Données pour analyse de sensibilité
Distribution By Phase (Indexé)
[8 empty] | Ligne applicableTable Inflation Salaires onglet 2F | [5 empty] | 106 | Phase 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phase 0
[15 empty] | Phase A | 0 | 0 | 0 | 822468.0116 | 1413731.1266 | 1442005.7491 | 129305.1309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3807510.0182 | Phase A
[15 empty] | Phase B | 0 | 0 | 0 | 0 | 0 | 0 | 956416.8615 | 1069573.6516 | 287727.0658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2313717.5789 | Phase B
[15 empty] | Phase C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 812412.6517 | 1125494.6617 | 328001.3014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2265908.6148 | Phase C
[15 empty] | Phase D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 704014.1825 | 494380.4209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1198394.6034 | Phase D1
[15 empty] | Phase D2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489613.6026 | 920101.0407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409714.6433 | Phase D2
[15 empty] | Phase D3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118445.5973 | 785294.3104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 903739.9077 | Phase D3
[15 empty] | Phase E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859046.416 | 1545038.554 | 1571621.683 | 1603054.1167 | 1635115.199 | 687287.4326 | 0 | 0 | 0 | 0 | 7901163.4013 | Phase E
[15 empty] | Phase F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phase F
[15 empty] | Science support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Science support
[15 empty] | Total in $ | 0 | 0 | 0 | 822468.0116 | 1413731.1266 | 1442005.7491 | 1085721.9924 | 1069573.6516 | 1100139.7176 | 1125494.6617 | 1032015.4839 | 983994.0235 | 1038546.6381 | 1644340.7264 | 1545038.554 | 1571621.683 | 1603054.1167 | 1635115.199 | 687287.4326 | 0 | 0 | 0 | 0 | 19800148.7676 | Total in $
[8 empty] | Ligne applicableTable Inflation Salaires onglet 2F | [5 empty] | 127 | Phase 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phase 0
[15 empty] | Phase A | 0 | 0 | 0 | 822468.0116 | 1441451.3447 | 1499109.3985 | 137061.4307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900090.1856 | Phase A
[15 empty] | Phase B | 0 | 0 | 0 | 0 | 0 | 0 | 1013787.0205 | 1155961.4894 | 317063.7228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2486812.2327 | Phase B
[15 empty] | Phase C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895246.2608 | 1264568.7481 | 375757.5709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2535572.5797 | Phase C
[15 empty] | Phase D1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 806517.102 | 577466.245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1383983.347 | Phase D1
[15 empty] | Phase D2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571898.3128 | 1095806.8976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1667705.2103 | Phase D2
[15 empty] | Phase D3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141064.4014 | 953595.3536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1094659.755 | Phase D3
[15 empty] | Phase E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1043153.7068 | 1912952.4014 | 1984019.8933 | 2063380.6891 | 2145915.9166 | 919678.25 | 0 | 0 | 0 | 0 | 10069100.8571 | Phase E
[15 empty] | Phase F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phase F
[15 empty] | Science support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Science support
[15 empty] | Total in $ | 0 | 0 | 0 | 822468.0116 | 1441451.3447 | 1499109.3985 | 1150848.4512 | 1155961.4894 | 1212309.9836 | 1264568.7481 | 1182274.6728 | 1149364.5578 | 1236871.299 | 1996749.0603 | 1912952.4014 | 1984019.8933 | 2063380.6891 | 2145915.9166 | 919678.25 | 0 | 0 | 0 | 0 | 23137924.1674

## 5 - Risk Register
5 - Risk Register ¦ VPCS – Virelan Protected Communications System (3 x GEO Protected SatCom)
| # | ID | Risk Category | Risk Sub-category | Risk Name | Type of Risk | Description | Internal Factors | External Factors | Probability | Mitigation Strategy | Mitigation Strategy Narrative | Cost Impact – Optimistic ($000) | Cost Impact – Most Likely ($000) | Cost Impact – Pessimistic ($000) | Weighted Exposure ($000) | Cost Impact in Phase | Schedule Impact in Phase | Impact on Project | Impact on Analysis
| 1 | R-001 | Spectrum & Regulatory | Spectrum Coordination | Ka-Band Coordination Incomplete for 40°, 160°, 280°E Slots | Governance | International coordination of the 20/30 GHz assignments for the three GEO slots is not completed before bringing-into-use, or imposes constraints that reduce usable beam capacity. | Late filing; incomplete traffic model; limited spectrum staff | Neighbouring operators' prior filings; frequencies 'subject to assignment' (Part A) | 45% | Mitigate | File coordination requests in Phase A (Sep 2027), pre-negotiate with adjacent-slot operators and keep channelization reconfigurable. | 1500 | 6000 | 18000 | 2700 | A–C | A–E | Capacity reduction or delayed service start. | Affects payload design and operations assumptions.
| 2 | R-002 | Spacecraft & Payload Technical | Antenna & Reflector Deployment | Deployable Reflector Deployment Failure | Technical | One of the two deployable reflectors on a spacecraft fails to deploy or latch after GEO arrival, removing up to four of the eight spot beams on that spacecraft. | Hold-down release mechanism design; harness snag; limited deployment cycles under gravity offload | First-deployment thermal environment; launch shock from three separate campaigns | 12% | Mitigate | Qualify the release mechanism with margin, perform deployment tests before and after environmental testing on every flight unit, and use redundant release actuators. | 8000 | 45000 | 160000 | 5400 | C–LEOP | LEOP–E | Permanent loss of up to 50% of one spacecraft's beams. | Drives reflector qualification cost and the mission-success scenario.
| 3 | R-003 | Security & Cryptography | Key Management | Key-Management and Recovery Architecture Immature | Security | The key-management system cannot demonstrate ≤24 h rotation of 256-bit session keys and immediate authenticated revocation across three spacecraft and four gateways by PDR. | Late security requirements; crypto boundary defined after bus architecture; small COMSEC team | Security-authority approval cycles; evolving cryptographic standards | 40% | Mitigate | Hold the Crypto Boundary & Key-Management Architecture Review (Nov 2028), prototype the key chain on a ground testbed and baseline recovery procedures before PDR. | 1200 | 5500 | 14000 | 2200 | B–D1 | B–C | PDR slip or redesign of crypto boundary. | Adds security engineering cost.
| 4 | R-004 | Spacecraft & Payload Technical | Radiation & Environment | Radiation-Induced Upset in Security Processors | Technical | Single-event upsets or latch-up in the security processors cause loss of authenticated control or forced re-keying more often than the availability budget allows. | Limited heritage; incomplete SEE test data | GEO electron and solar-particle environment during 2033–2040 | 35% | Mitigate | Perform heavy-ion and proton SEE testing, implement EDAC and watchdog-driven safe re-key, and verify recovery time against 99.5% availability. | 800 | 4200 | 12000 | 1470 | B–D1 | C–D1 | Service interruptions; possible redesign. | Adds radiation test and design cost.
| 5 | R-005 | Spacecraft & Payload Technical | Thermal Control | High-Duty Payload Thermal Rejection Shortfall | Technical | The 2.8 m² radiator reference cannot reject ≥2.3 kW payload heat during eight-beam high-duty operations at end of life, forcing beam duty-cycle limits. | Payload dissipation growth; radiator area fixed by bus layout; optimistic EOL optical properties | Solstice hot cases; coating degradation in GEO | 40% | Mitigate | Carry ≥15% thermal margin at PDR, trade deployable radiator/heat-pipe options, and correlate the model after FM-1 thermal-vacuum. | 900 | 4800 | 13000 | 1920 | B–D1 | C–D1 | Duty-cycle limits reduce service capacity. | Affects thermal hardware and test cost.
| 6 | R-006 | Ground Segment & Operations | Ground Software | Common-Mode Ground Software Failure | Technical | A defect common to the network-control software at both control sites causes simultaneous loss of beam management or protected-session authorization across all three spacecraft. | Single code base deployed at dual sites; limited independent verification | Third-party operating-system and library vulnerabilities; patch cycles | 30% | Mitigate | Stage deployments between sites, use dissimilar implementations for critical functions, apply independent V&V and maintain a manual fallback for key authorization. | 700 | 3500 | 9500 | 1050 | C–E | D2–E | Network-wide service outage. | Adds ground software and IV&V cost.
| 7 | R-007 | Programmatic Integration & Execution | Schedule Planning & Control | Three-Unit Build Stagger Compression | Schedule | The 18-month unit AIT per flight model and the three-month stagger between FM-1 (Sep 2031), FM-2 and FM-3 (Mar 2032) leave little float before the Jan 2033 L1–L3 launch sequence; an anomaly on FM-1 propagates to FM-2 and FM-3. | Shared integration hall, test crews and GSE across three units; single payload qualification path; limited D1 float | Qelvoria Orbital Systems facility loading; Sorevex payload delivery cadence | 50% | Mitigate | Baseline a resource-loaded three-unit integration schedule, hold a dedicated FM-1 anomaly-recovery buffer, and pre-position second-shift test crews for FM-2/FM-3. | 2500 | 9000 | 22000 | 4500 | D1–D2 | D1–D2 | May slip SIR (May 2032), acceptance (Sep 2032) and one or more of the L1–L3 launches. | Drives D1/D2 standing-army cost and the worst-case (+2 mo/phase) schedule scenario.
| 8 | R-008 | Programmatic Integration & Execution | Schedule Planning & Control | Launch Sequence Congestion (L1–L3 within Jan 2033) | Schedule | Three separate launches planned within a single month cannot be supported by one launch-campaign team, one LEOP network and one flight operations team without slipping at least one launch. | Single launch-campaign team; single LEOP operations team; shared ground support equipment | Lundrith Launch Consortium manifest; range availability at two launch sites | 50% | Mitigate | Stagger launches by at least 4–6 weeks in the realistic scenario, contract a second campaign team, and dry-run concurrent LEOP operations in simulation. | 1200 | 5200 | 14000 | 2600 | D2–LEOP | D2–E | May delay L2/L3 by 1–3 months and compress the six-month commissioning window. | Adds campaign, storage and LEOP-network cost; shifts the start of Phase E revenue/service.
| 9 | R-009 | Programmatic Integration & Execution | Contracting & Procurement | Prime and Payload Contract Award Delay | Schedule | Award of the Qelvoria prime and Sorevex payload development contracts slips beyond Apr 2028 because of bid clarification, negotiation or evaluation delays after SRR. | Late SOW and security requirements; limited procurement staff; evaluation panel availability | Bidder clarification requests; approval cycles; possible bid protest | 45% | Mitigate | Release draft SOWs during Phase A studies, pre-clear evaluation criteria, and run negotiation in parallel with SRR close-out. | 600 | 2800 | 7500 | 1260 | A–B | B–C | Compresses the 14-month Phase B and pushes PDR beyond Mar 2029. | Increases PM/procurement LOE and Phase B duration uncertainty.
| 10 | R-010 | Programmatic Integration & Execution | Contracting & Procurement | Launch Services Contract Terms for Three Vehicles | Programmatic | Launch contract for three separate GTO launches cannot secure firm dates, injection accuracy and re-flight terms at the planned price. | Late mass/envelope freeze; single-provider strategy | Launch market demand; Lundrith consortium manifest priorities | 35% | Mitigate | Award by Sep 2028 with firm manifest slots, injection-accuracy guarantees and re-flight/replacement options priced as options. | 1500 | 6500 | 18000 | 2275 | B–D2 | D2 | May raise launch service price or leave launch dates unprotected. | Widens launch-segment cost range; affects insurance assumptions.
| 11 | R-011 | Programmatic Integration & Execution | Cost & Budget Management | Development Cost Growth | Cost | Actual development costs exceed the preliminary CADRe estimate because of design growth in the payload, reflectors and security processors, labour growth and additional test effort across three flight units. | Immature design at MCR; optimistic learning-curve assumptions for FM-2/FM-3; incomplete WBS | Supplier quotation changes; inflation; market conditions | 55% | Mitigate | Refresh bottoms-up estimates at SRR/PDR/CDR, maintain cost reserves, and reconcile growth with design maturity and Part C schedule scenarios. | 6000 | 22000 | 55000 | 12100 | A–D2 | B–D2 | May require additional funding, descoping or schedule changes. | Widens the cost uncertainty range and contingency requirement.
| 12 | R-012 | Programmatic Integration & Execution | Cost & Budget Management | Recurring-Unit Learning Curve Not Realized | Cost | FM-2 and FM-3 do not achieve the assumed learning-curve savings because of design changes after FM-1 test anomalies and non-recurring rework. | Design changes after FM-1; turnover of AIT technicians | Supplier lot sizes too small for learning | 40% | Accept | Accept residual recurring-cost variance after freezing the FM-1 as-built configuration and applying a conservative 90% learning slope. | 1500 | 6000 | 15000 | 2400 | D1 | D1 | Recurring cost of FM-2/FM-3 higher than estimated. | Affects learning-curve CER and unit-cost assumptions.
| 13 | R-013 | Programmatic Integration & Execution | Requirements & Scope Management | Requirements Maturity at SRR | Technical | Quantitative requirements for throughput, beam count, availability, key rotation and data retention remain unstable after SRR (Jan 2028). | Incomplete trade studies; inadequate traceability; late user input | User-community findings; spectrum coordination outcomes | 55% | Mitigate | Maintain requirement-to-design traceability, close mission trades before PDR, and baseline threshold/objective values with verification methods. | 1200 | 5500 | 14000 | 3025 | A–C | B–C | May cause redesign before or after PDR. | Materially affects cost, schedule and technical uncertainty.
| 14 | R-014 | Programmatic Integration & Execution | Requirements & Scope Management | Service-Region and Beam Scope Growth | Programmatic | Authorized users request additional declared service regions, more than eight beams, or a higher availability target after the baseline is established. | Weak change control; ambiguous success criteria | Changing user demand; new operational theatres | 40% | Mitigate | Operate a formal change-control board and require quantified cost/schedule impacts; hold beam re-pointing as the primary response rather than new hardware. | 1500 | 6500 | 17000 | 2600 | B–D1 | B–D1 | May increase payload scope and development duration. | Requires additional engineering, payload and operations LOE.
| 15 | R-015 | Programmatic Integration & Execution | Schedule Planning & Control | Schedule Margin Insufficient | Schedule | Integrated schedule margin between CDR (Mar 2030) and L1 (Jan 2033) is insufficient to absorb normal test anomalies on three units. | Compressed D1/D2; parallel builds | Supplier and launch provider availability | 50% | Mitigate | Hold explicit funded schedule reserve (1 month per year of development) and track margin burn-down monthly. | 2000 | 7500 | 18000 | 3750 | C–D2 | C–D2 | Launch dates slip; standing-army cost grows. | Supports realistic (+1 mo/phase) scenario.
| 16 | R-016 | Programmatic Integration & Execution | Cost & Budget Management | Funding Gap Between Phases | Programmatic | Funding approval for Phase B/C or D does not arrive before the preceding phase ends, forcing contract slow-down or stop-work. | Late costing packages; incomplete business case | Central budget cycles; competing priorities | 35% | Accept | Accept after aligning the CADRe milestones with budget cycles and preparing bridge-funding options. | 1500 | 6000 | 16000 | 2100 | A–D1 | A–D1 | Contract slow-downs and re-mobilization costs. | Affects phasing of costs across fiscal years.
| 17 | R-017 | Programmatic Integration & Execution | Governance Processes & Controls | Cost/Schedule Baseline Misalignment | Programmatic | The Part C phase schedule, contractor IMS and Part B cost phasing diverge, masking emerging variances. | Multiple unlinked tools; different phase nomenclatures (D1/D2 vs MAIT/SAIT) | Contractor reporting formats | 40% | Mitigate | Use the Part C phasing crosswalk as the single reference and require monthly EVM data mapped to it. | 300 | 1200 | 3000 | 480 | B–E | B–E | Late detection of overruns. | Reduces confidence in estimate-at-completion.
| 18 | R-018 | Programmatic Integration & Execution | Governance Processes & Controls | Review Exit Criteria Not Met | Governance | PDR or CDR close with open actions on the crypto boundary, reflector deployment or thermal margins, carrying unresolved issues into D1. | Pressure to hold dates; inconsistent review criteria | Supplier data late | 40% | Mitigate | Define entrance/exit criteria per review and hold delta reviews rather than waiving criteria. | 800 | 3200 | 8500 | 1280 | B–D1 | B–D1 | Rework in D1 costs more than in C. | Increases uncertainty on D1 estimates.
| 19 | R-019 | Programmatic Integration & Execution | Contracting & Procurement | Contract Change Requests Increase After Award | Cost | Engineering change proposals from Qelvoria Orbital Systems and Sorevex Signal Engineering grow after award as the crypto boundary, frequency plan and beam layout mature through PDR and CDR. | Security requirements immature at contract award; frequency plan still 'subject to assignment'; ambiguous SOW language | Contractor commercial strategy; supplier price changes passed through | 45% | Mitigate | Baseline security and interface requirements before award, pre-price options for anticipated changes (e.g., additional beam re-pointing modes), and enforce a 30-day ECP evaluation turnaround. | 1200 | 4500 | 11000 | 2025 | B–D1 | B–D1 | Contract value growth and schedule disruption during Phase C and D1. | Adds cost growth to the prime and payload contract elements; increases contract-change contingency.
| 20 | R-020 | Programmatic Integration & Execution | Partnership & External Agreements | User Validation Support from Tervalis Not Formalized | Programmatic | Tervalis Network Operations Institute's role in calibration, data validation and user exploitation is not covered by a formal agreement before commissioning. | Late agreement planning | Institute funding cycles | 30% | Mitigate | Sign a support agreement by CDR defining validation deliverables and funding. | 200 | 800 | 2500 | 240 | C–E | LEOP–E | Service validation delayed. | Adds science/user support cost.
| 21 | R-021 | Spacecraft & Payload Technical | Antenna & Reflector Deployment | Reflector Surface Distortion in GEO Thermal Cycle | Technical | Thermo-elastic distortion of the reflectors degrades beam gain and shape during eclipse seasons. | Composite layup variability; limited thermal-distortion testing | Seasonal Sun angles; eclipse transitions | 30% | Mitigate | Perform thermal-distortion testing with photogrammetry and include distortion in the RF performance budget. | 600 | 2600 | 7000 | 780 | C–D1 | C–D1 | Reduced EIRP/G/T and service margin. | Adds reflector test cost.
| 22 | R-022 | Spacecraft & Payload Technical | Communications Payload | Aggregate Throughput Below 2.0 Gb/s | Performance | Channelizer, coding or interference losses reduce usable throughput below 250 Mb/s per 125 MHz beam and below 2.0 Gb/s per spacecraft. | Optimistic 2.0 bit/s/Hz spectral efficiency; implementation losses | Ka-band rain fade; adjacent-satellite interference | 35% | Mitigate | Validate modem/coding assumptions on an end-to-end payload testbed and keep adaptive coding and modulation in the baseline. | 900 | 4500 | 12000 | 1575 | B–D1 | C–D1 | Primary mission requirement not met. | Affects payload design and verification cost.
| 23 | R-023 | Spacecraft & Payload Technical | Communications Payload | TWTA / Power Amplifier Early Failure | Technical | Ka-band travelling-wave tube amplifiers fail early in life, reducing the number of usable beams. | Insufficient redundancy ring; burn-in duration | Supplier lot quality | 20% | Mitigate | Specify redundancy rings, extended burn-in and lot acceptance testing. | 700 | 3200 | 9000 | 640 | D1–E | E | Beam capacity loss in service. | Affects redundancy and spares cost.
| 24 | R-024 | Spacecraft & Payload Technical | Communications Payload | Passive Intermodulation in Ka-band Feeds | Technical | Passive intermodulation (PIM) products generated in the feed chains, reflector joints or multilayer insulation desensitize the 30 GHz receive channels. | Material and joint selection; workmanship of RF interfaces | Limited availability of Ka-band PIM test facilities | 30% | Mitigate | Apply PIM design rules from Phase B, test PIM at unit and antenna-subsystem level and include PIM screening in FM acceptance. | 500 | 2100 | 6000 | 630 | C–D1 | D1 | Receive-sensitivity degradation or late rework of feeds. | Adds payload test cost and facility time.
| 25 | R-025 | Spacecraft & Payload Technical | Power & Energy | Power Margin Shortfall in Eclipse Season | Technical | The 5,400 W array and battery cannot sustain the 4,700 W peak and 3,200 W nominal loads through the longest (~72 min) GEO eclipse at end of life. | Payload power growth; battery sizing on nominal load | Solar array degradation from radiation | 30% | Mitigate | Size the battery on worst eclipse at EOL, hold ≥10% power margin at CDR and define eclipse-season load-shedding modes. | 600 | 2800 | 7500 | 840 | B–D1 | C–D1 | Eclipse-season beam shedding. | Affects EPS cost and availability assumptions.
| 26 | R-026 | Spacecraft & Payload Technical | Power & Energy | Solar Array Deployment Failure | Technical | A solar array wing on one of the three spacecraft fails to deploy after separation or during orbit raising, reducing the 5,400 W generation capability. | Deployment mechanism workmanship; harness routing | Launch vibration and shock environment of three different vehicles | 5% | Mitigate | Perform deployment testing on every flight unit before and after environmental tests and use redundant release devices. | 5000 | 30000 | 120000 | 1500 | LEOP | LEOP–E | Severe power loss and reduced beam capacity on one spacecraft. | Contributes to insurance and mission-success analysis rather than baseline cost.
| 27 | R-027 | Spacecraft & Payload Technical | ADCS & Pointing | Beam-Centre Placement Accuracy Miss (0.2°) | Technical | Thermal distortion and boresight-knowledge errors exceed the ≤0.05° knowledge budget, preventing ≥0.2° beam-centre accuracy after calibration. | STOP analysis immaturity; star-tracker-to-antenna alignment | Diurnal GEO thermal cycling | 30% | Mitigate | Perform integrated structural-thermal-RF analysis, use ground-beacon calibration, and verify alignment before and after environmental tests. | 500 | 2600 | 7000 | 780 | B–D2 | C–LEOP | Beam coverage degraded at region edges. | Adds analysis and calibration LOE.
| 28 | R-028 | Spacecraft & Payload Technical | ADCS & Pointing | Reaction Wheel Degradation Over Ten-Year Life | Technical | One of four reaction wheels degrades before end of design life, reducing pointing margin during station-keeping. | Bearing lubrication life | Supplier lot history | 20% | Accept | Accept with 3-of-4 wheel operation verified and thruster-assisted momentum management. | 300 | 1400 | 4000 | 280 | E–E EXT | E | Increased operations workload. | Minor impact on operations cost.
| 29 | R-029 | Spacecraft & Payload Technical | Propulsion | Delta-V Reserve Consumed by Dispersions | Technical | Only ~190 m/s separates the ~2,040 m/s ideal capability from the 1,850 m/s allocation; dispersions, residuals and GTO injection errors consume the reserve and shorten station-keeping life or disposal capability. | Isp dispersion; unusable propellant; dry-mass growth | Injection accuracy of three different GTO insertions | 35% | Mitigate | Model residuals explicitly, negotiate injection accuracy in the launch contract, and ring-fence end-of-life disposal propellant. | 600 | 3200 | 9000 | 1120 | B–C | LEOP–E | Service life shorter than 7 years or disposal at risk. | Affects propellant, mass and life-cycle cost assumptions.
| 30 | R-030 | Spacecraft & Payload Technical | Propulsion | Bipropellant Thruster or Valve Leak | Technical | A propellant valve or thruster leaks during GTO-to-GEO orbit raising or station-keeping, depleting the 550 kg bipropellant load. | Workmanship; contamination during propellant loading | Supplier quality of valves and thrusters | 10% | Transfer | Transfer financial exposure via launch-plus-one-year insurance; perform leak testing at unit and spacecraft level and after propellant loading. | 2000 | 12000 | 60000 | 1200 | LEOP–E | LEOP–E | Loss of station-keeping capability or of the spacecraft. | Reflected in insurance premium and replacement-option assumptions.
| 31 | R-031 | Spacecraft & Payload Technical | Mass & Performance | Spacecraft Mass Growth Beyond 1,150 kg | Technical | Wet mass grows beyond 1,150 kg (420 kg dry bus + 180 kg payload + 550 kg propellant), eroding the margin between the 1,300 kg launch mass (with 150 kg adaptor) and the ≥1,500 kg vehicle capability, or forcing a propellant off-load. | Immature payload and harness mass estimates; reflector and radiator mass growth | Launch adaptor changes; supplier mass estimates | 50% | Mitigate | Hold ≥15% dry-mass margin at PDR, track mass monthly and trade propellant allocation against station-keeping life. | 800 | 3600 | 9000 | 1800 | B–D1 | C–D1 | Reduced propellant (shorter life) or launch vehicle re-plan. | Affects mass-based CERs for bus and payload.
| 32 | R-032 | Spacecraft & Payload Technical | Mass & Performance | Payload Mass Allocation (180 kg) Exceeded | Technical | The channelizer, security processors, TWTAs and antenna feeds exceed the 180 kg payload allocation defined in Part A. | Late design maturity; heritage mass underestimated | Supplier mass data for new processors | 40% | Mitigate | Carry payload mass margin at unit level and enforce the allocation at each design review; pre-identify mass-reduction options. | 400 | 1800 | 5000 | 720 | B–C | C | Bus redesign or propellant reduction. | Affects payload mass-based cost estimate.
| 33 | R-033 | Spacecraft & Payload Technical | Data Handling | Onboard Storage and Log Throughput Shortfall | Technical | 256 GB usable storage cannot hold 18 GB/day per spacecraft of encrypted network logs and housekeeping through the 48-hour missed-contact case plus file-system reserve and corrected-memory events. | Log volume growth; storage analysis not yet performed | Gateway outages extending missed-contact periods | 25% | Accept | Accept residual risk after storage analysis at PDR confirms margin; implement log-priority management so audit records are never overwritten. | 200 | 900 | 2500 | 225 | B–C | C | Loss of audit or housekeeping data. | Minor avionics cost change; affects data-volume assumptions.
| 34 | R-034 | Spacecraft & Payload Technical | Radiation & Environment | Surface and Internal Charging in GEO | Technical | Electrostatic discharge from surface or internal charging damages payload electronics, harnesses or reflector surfaces. | Grounding and bonding design gaps; dielectric material selection | Geomagnetic substorms in the GEO environment | 20% | Mitigate | Apply charging design rules, conductive coatings and ESD testing at unit and system level. | 400 | 1800 | 6000 | 360 | B–D1 | E | In-orbit anomalies and service interruptions. | Adds design analysis and test cost.
| 35 | R-035 | Spacecraft & Payload Technical | Reliability | Early-Life Spacecraft Anomaly | Technical | A spacecraft anomaly during orbit raising or commissioning of one of the three units requires extended ground and contractor support. | Latent defects; limited burn-in; concurrent commissioning workload | Space environment during LEOP | 30% | Mitigate | Extended burn-in, LEOP contingency simulations and a contracted Qelvoria anomaly-support team through commissioning. | 700 | 3000 | 9000 | 900 | LEOP | LEOP–E | Delayed start of nominal service for the affected spacecraft. | Extends LEOP cost and contractor support.
| 36 | R-036 | Spacecraft & Payload Technical | Communications Payload | Adjacent-Satellite Interference Limits Uplink EIRP | Technical | Coordination agreements with adjacent GEO operators cap uplink EIRP or off-axis emissions, reducing link margin in rain-faded regions and lowering usable capacity below 250 Mb/s per beam. | Beam-edge performance sized on nominal EIRP; limited off-axis pattern control | Coordination outcomes for the 40°, 160° and 280°E slots | 35% | Mitigate | Model coordination constraints in the link budget at SRR, specify low-sidelobe feeds and keep adaptive coding and modulation in the baseline. | 400 | 2000 | 6000 | 700 | A–C | C | Reduced throughput at beam edges. | Affects payload and ground-terminal assumptions.
| 37 | R-037 | Spacecraft & Payload Technical | Antenna & Reflector Deployment | Gravity-Offload Test Rig Unavailable for Three Units | Schedule | The gravity-offload deployment rig used for the reflector EM test (Oct 2029) is not available or not certified for repeated flight-unit deployments in D1. | Single rig shared across programs | Facility owner scheduling | 30% | Mitigate | Procure or reserve a dedicated deployment rig for D1 and schedule deployments for all three units at CDR. | 300 | 1500 | 4000 | 450 | C–D1 | D1 | Deployment tests delayed for FM-2/FM-3. | Adds GSE cost.
| 38 | R-038 | Spacecraft & Payload Technical | Thermal Control | Eclipse-Season Cold Case for Security Processors | Technical | Security processors fall below qualified temperature during eclipse with reduced payload dissipation, causing resets and forced re-keying. | Heater sizing on nominal load | Longest GEO eclipse (~72 min) near equinox | 25% | Mitigate | Size survival heaters on the eclipse cold case and verify in thermal-vacuum with payload off. | 200 | 1000 | 3000 | 250 | B–D1 | C–D1 | Service interruptions in eclipse seasons. | Minor thermal hardware cost.
| 39 | R-039 | Spacecraft & Payload Technical | ADCS & Pointing | Star Tracker Blinding Near Equinox | Technical | Sun or Moon intrusion blinds star trackers during equinox seasons, degrading antenna boresight knowledge below 0.05°. | Tracker accommodation and baffle design | Seasonal geometry | 25% | Mitigate | Use dual trackers with complementary fields of view and gyro propagation through blinding intervals. | 200 | 900 | 2800 | 225 | B–C | E | Temporary beam-pointing degradation. | Minor AOCS design cost.
| 40 | R-040 | Security & Cryptography | Key Management | Loss of Key Material or Recovery Failure in Orbit | Security | A spacecraft loses valid key material after a processor reset and cannot be recovered through the authenticated command path. | Recovery procedure gaps | Radiation events | 10% | Avoid | Design a separate authenticated low-rate recovery path and test key recovery on every unit. | 2000 | 15000 | 60000 | 1500 | C–E | E | Loss of protected service on one spacecraft. | Drives design of recovery path.
| 41 | R-041 | Security & Cryptography | Cryptographic Boundary | Crypto Boundary Certification Delay | Governance | Certification of the cryptographic command boundary by the security authority is not granted before AR (Sep 2032). | Incomplete evidence packages | Security-authority queue | 35% | Mitigate | Engage the certifying authority from Phase B and submit incremental evidence. | 800 | 3500 | 9000 | 1225 | C–D2 | D2 | Launch cannot proceed without certification. | Adds security assurance LOE.
| 42 | R-042 | Security & Cryptography | Cybersecurity | Ground Network Cyber Intrusion | Security | An intrusion into the gateway or network-control networks compromises command authority or user sessions. | Configuration drift; patch management | Persistent threat actors | 25% | Mitigate | Zero-trust architecture, continuous monitoring and regular penetration testing. | 800 | 4000 | 15000 | 1000 | D2–E | E | Service disruption and reputational damage. | Adds cybersecurity operations cost.
| 43 | R-043 | Security & Cryptography | Cybersecurity | Jamming or Uplink Interference Against Service Beams | Security | Deliberate or accidental uplink interference degrades protected beams in one or more service regions. | Limited interference-geolocation capability | Hostile actors; adjacent satellite operators | 30% | Mitigate | Include interference detection/geolocation at the network-control centres and beam-nulling procedures. | 600 | 2800 | 8000 | 840 | C–E | E | Availability below 99.5%. | Adds ground equipment and operations cost.
| 44 | R-044 | Security & Cryptography | Security Accreditation | Security Accreditation of Ground Segment Late | Governance | The gateways, network-control sites and key-management facility are not accredited to operate by LRR (Nov 2032). | Late security documentation; evidence scattered across contractors | Accreditor availability and review queues | 35% | Mitigate | Plan accreditation activities in the ground segment IMS from Ground Segment CDR (Jan 2030) and submit evidence incrementally. | 400 | 1800 | 5000 | 630 | D2 | D2 | Launch or service start delayed pending authorization to operate. | Adds security assessment LOE.
| 45 | R-045 | Security & Cryptography | Supply-Chain Security | Supply-Chain Compromise of Security-Relevant Components | Security | Counterfeit or tampered components enter the security processors, gateway crypto units or network equipment. | Weak supplier vetting; incomplete provenance records | Global electronics supply chain threats | 15% | Mitigate | Trusted supplier programme, provenance tracking, anti-tamper inspection and independent testing of security-relevant parts. | 700 | 3500 | 12000 | 525 | C–D1 | D1 | Rework or replacement of units; potential compromise of protected service. | Adds supply-chain assurance cost.
| 46 | R-046 | Security & Cryptography | Personnel Security | Insider Threat to Key Material | Security | A cleared insider mishandles or exfiltrates key material used to authenticate protected user sessions. | Two-person integrity gaps; insufficient audit review | External coercion or recruitment | 10% | Mitigate | Enforce two-person integrity, audit all key handling via the 150 TB audit archive and conduct periodic re-vetting. | 500 | 2500 | 10000 | 250 | D2–E | E | Compromise of protected sessions and emergency re-keying. | Adds security operations cost.
| 47 | R-047 | Security & Cryptography | Key Management | Key Distribution to Gateways Disrupted | Security | Secure distribution of session key material to the three protected gateways and backup gateway is interrupted, preventing the ≤24 h rotation requirement. | Single key-generation facility | Terrestrial network outages | 25% | Mitigate | Provide redundant key-generation and distribution paths and pre-positioned emergency key material. | 300 | 1500 | 4500 | 375 | D2–E | E | Protected sessions cannot rotate keys on schedule. | Adds key-management infrastructure cost.
| 48 | R-048 | Security & Cryptography | Cryptographic Boundary | Cryptographic Algorithm Transition Mid-Life | Security | Changes in approved cryptographic standards during 2033–2043 require algorithm updates to on-orbit security processors that were not designed for reprogramming. | Limited reprogrammability of security processors | Evolving cryptographic standards (e.g., post-quantum transition) | 30% | Mitigate | Specify crypto-agility and secure on-orbit firmware update capability at SRR. | 800 | 4000 | 15000 | 1200 | B–E | E | Security obsolescence before end of design life. | Adds design and sustaining cost.
| 49 | R-049 | Spectrum & Regulatory | Orbital Slot & Licensing | Bringing-Into-Use Deadline Missed | Governance | Launch or orbit-raising slips cause one or more of the 40°, 160° and 280°E slots to miss its regulatory bringing-into-use deadline, risking loss of filing priority. | Schedule slips in D2/LEOP; launch congestion | Regulatory deadlines fixed by the filing date | 15% | Mitigate | Track regulatory deadlines in the IMS, prioritize launch order by deadline and evaluate interim-use options. | 1000 | 8000 | 40000 | 1200 | D2–LEOP | LEOP | Loss of slot priority and re-coordination. | Significant strategic cost exposure; may require payload re-tuning.
| 50 | R-050 | Spectrum & Regulatory | Orbital Slot & Licensing | Earth-Station Licensing for Gateways Delayed | Governance | Licences for the three protected gateways and the backup gateway are delayed by site, frequency or local planning constraints. | Late site selection | Local regulatory processes | 30% | Mitigate | Select sites in Phase B and file earth-station licences immediately after Ground Segment CDR. | 300 | 1400 | 4000 | 420 | B–D2 | D2 | Ground segment readiness slips past Aug 2032. | Adds ground segment cost and schedule risk.
| 51 | R-051 | External & Environmental Factors | Regulatory & Legal | Export Licensing for Payload Components | Governance | Export licences for TWTAs, channelizer FPGAs or cryptographic technology delay deliveries to Sorevex. | Late export-control planning | Regulatory changes in supplier countries | 30% | Mitigate | Prepare export-control plans at PDR and identify alternate sources for licence-sensitive parts. | 400 | 1800 | 5000 | 540 | B–D1 | C–D1 | Component delivery delays in D1. | Adds procurement LOE and potential re-sourcing cost.
| 52 | R-052 | Spectrum & Regulatory | Space Debris Compliance | GEO Disposal Compliance Not Demonstrated | Technical | Propellant gauging uncertainty prevents demonstrating that disposal to a super-synchronous graveyard orbit can be achieved. | Gauging method accuracy | Regulatory expectations | 20% | Mitigate | Use thermal/gauging methods, and reserve disposal propellant as a protected budget. | 300 | 1500 | 5000 | 300 | E–F | F | Early termination of service. | Affects end-of-life planning.
| 53 | R-053 | Spectrum & Regulatory | Orbital Slot & Licensing | Station-Keeping Box Violation Risk | Technical | Station-keeping errors cause a spacecraft to leave its ±0.10° longitude/inclination box, creating interference and coordination issues. | Flight dynamics process maturity | Perturbations; thruster performance | 15% | Mitigate | Automate station-keeping planning with conservative box margins and independent orbit determination. | 200 | 800 | 2500 | 120 | E | E | Regulatory non-compliance events. | Minor operations cost.
| 54 | R-054 | Launch & Early Orbit | Launch Services | Launch Failure Results in Loss of One VPCS Spacecraft | Cost | One of the three separate launches fails, resulting in loss of a spacecraft and one orbital slot remaining unserved. | Single-spacecraft-per-launch strategy | Launch vehicle reliability | 6% | Transfer | Transfer financial risk through launch-plus-one-year insurance; retain FM-3 long-lead spares to accelerate a replacement unit. | 20000 | 95000 | 260000 | 5700 | D2–LEOP | D2–E | Loss of one-third of constellation capacity. | Insurance premium and replacement options in Part B.
| 55 | R-055 | Launch & Early Orbit | Launch Interface | Launch Vehicle Interface Changes | Technical | Launch-vehicle requirements alter mechanical, electrical, separation or safety interfaces after the design is mature. | Late interface definition | Provider-specific requirements | 30% | Mitigate | Establish interface agreements at launch contract award (Sep 2028) and freeze critical data before D1. | 400 | 1800 | 5000 | 540 | C–D2 | C–D2 | Spacecraft modification and requalification. | Adds launch integration LOE.
| 56 | R-056 | Launch & Early Orbit | Launch Interface | Coupled-Loads Analysis Exceeds Qualification Levels | Technical | Final coupled-loads analysis for any of the three launch vehicles exceeds reflector, payload or bus qualification levels. | Qualification levels based on envelope assumptions made before launch award | Launch vehicle configuration changes | 25% | Mitigate | Envelope all three vehicles at CDR and pre-agree notching strategies with Lundrith. | 500 | 2200 | 6500 | 550 | C–D2 | D2 | Retest or requalification of a flight unit. | Adds environmental test cost.
| 57 | R-057 | Launch & Early Orbit | Orbit Raising | GTO Injection Error Exceeds Correction Capacity | Technical | Injection dispersions for one of the three launches exceed what the ~190 m/s propellant reserve can correct without shortening service life. | Thin delta-V reserve | Launch vehicle upper-stage performance | 10% | Mitigate | Specify injection accuracy in the launch contract and include dispersions in the propellant reserve. | 800 | 4000 | 12000 | 400 | LEOP | LEOP | Reduced service life for the affected spacecraft. | Affects life-cycle cost per year of service.
| 58 | R-058 | Launch & Early Orbit | Commissioning | Commissioning Exceeds Six Months | Schedule | In-orbit testing of three spacecraft, 24 beams, two reflectors per spacecraft and key management across four gateways takes longer than the six months planned (Jan–Jul 2033). | Concurrent commissioning of three units; single IOT team | Weather and link conditions affecting Ka-band calibration | 40% | Mitigate | Commission spacecraft sequentially with a dedicated IOT team and pre-validated calibration procedures. | 800 | 3200 | 8500 | 1280 | LEOP | LEOP–E | Delayed start of Phase E beyond Jul 2033. | Extends LEOP cost and shifts operations phasing.
| 59 | R-059 | Launch & Early Orbit | Insurance & Liability | Launch Insurance Coverage Gap | Cost | Insurance market capacity or premiums change unfavourably before the 2033 launches, leaving part of the three-launch exposure uninsured. | Late insurance strategy | Insurance market conditions | 25% | Transfer | Obtain indicative quotes at CDR and evaluate self-insurance with a replacement-unit option. | 1000 | 5000 | 15000 | 1250 | D2 | D2 | Higher premiums or uninsured exposure. | Affects launch segment cost.
| 60 | R-060 | Launch & Early Orbit | Launch Services | Launch Weather or Range Delay | Schedule | Weather or range conflicts delay one or more of L1–L3 beyond Jan 2033. | Tight launch sequence | Weather; range scheduling at two sites | 35% | Accept | Accept with a launch-window reserve and spacecraft storage provisions. | 300 | 1200 | 3500 | 420 | D2 | D2–LEOP | Short launch delays. | Minor campaign and storage cost.
| 61 | R-061 | Launch & Early Orbit | Orbit Raising | Orbit-Raising Duration Longer Than Planned | Schedule | GTO-to-GEO transfer and drift to the 40°, 160° and 280°E slots take longer than planned, compressing payload in-orbit testing. | Conservative manoeuvre planning | Injection conditions | 30% | Accept | Accept with sequential commissioning and a four-week buffer before the commissioning review. | 200 | 900 | 2500 | 270 | LEOP | LEOP | Later start of payload IOT. | Minor LEOP cost.
| 62 | R-062 | Ground Segment & Operations | Gateways | Gateway Site Readiness Delay | Schedule | One or more of the three protected gateways or the backup gateway is not ready for end-to-end testing by Aug 2032. | Late site selection; construction dependencies | Pervalin Gateway Services contractor performance | 40% | Mitigate | Select sites in Phase B, start civil works after Ground Segment CDR (Jan 2030) and track readiness monthly. | 800 | 3500 | 9500 | 1400 | C–D2 | D2 | End-to-end tests and AR slip. | Adds ground segment cost.
| 63 | R-063 | Ground Segment & Operations | Terrestrial Backhaul | Terrestrial Backhaul Below 7 Gb/s | Technical | Aggregate terrestrial backhaul cannot sustain ≥7 Gb/s with the route diversity required for 99.5% availability. | Under-sized network design | Telecom carrier capacity and SLAs | 30% | Mitigate | Contract diverse carriers with SLAs and test at full aggregate load during end-to-end testing. | 400 | 1800 | 5000 | 540 | C–E | D2–E | Service throughput limited by the ground network. | Adds recurring backhaul cost.
| 64 | R-064 | Ground Segment & Operations | Service Availability | Network Availability Below 99.5% | Performance | Scheduled monthly availability in one or more declared service regions falls below 99.5% due to gateway outages, Ka-band rain fade, eclipse-season constraints or key-management interruptions. | Single backup gateway; maintenance windows | Ka-band propagation; terrestrial backhaul outages | 40% | Accept | Accept residual risk after gateway site-diversity analysis; hold an operational reserve for leasing an additional backup gateway. | 600 | 3000 | 9000 | 1200 | D2–E | E | Service-level shortfall against the primary requirement. | Affects operations cost and availability assumptions.
| 65 | R-065 | Ground Segment & Operations | Mission Operations | Operations LOE Growth | Operational | 24/7 operations of three GEO spacecraft, four gateways and dual network-control sites require more staffing than the ~23 FTE assumed for Phase E in the RAM. | Optimistic staffing model; limited automation | Anomaly workload; user demand | 45% | Accept | Accept residual variance after a quantified staffing model; set an automation and surge-staffing reserve. | 800 | 3200 | 8500 | 1440 | LEOP–E | E | Recurring operations cost growth over 84 months. | Raises Phase E RAM and operations cost.
| 66 | R-066 | Ground Segment & Operations | Mission Operations | Operations Fatigue and Staffing Shortfall | Operational | Shift work across dual network-control sites causes fatigue, errors and turnover among controllers. | Thin shift rosters | Labour market for operators | 35% | Mitigate | Staff to a five-shift model, automate routine tasks and monitor overtime. | 300 | 1200 | 3500 | 420 | E | E | Operator errors and service incidents. | Adds operations LOE.
| 67 | R-067 | Ground Segment & Operations | Archive & Audit | Audit Archive Capacity (150 TB) Insufficient | Technical | Encrypted logs (18 GB/day per spacecraft) plus replication and reprocessing exceed the 150 TB audit/archive capacity before end of design life. | Replication factor underestimated | Audit retention policy changes | 30% | Accept | Accept with scalable storage options costed as a Phase E refresh. | 200 | 900 | 2500 | 270 | D2–E | E | Additional storage procurement. | Minor ground segment cost.
| 68 | R-068 | Ground Segment & Operations | Mission Planning | Beam Planning Tool Cannot Resolve Conflicting Demands | Programmatic | The mission planning system cannot allocate eight steerable beams per spacecraft across competing service regions within the planning cycle. | Tool maturity; optimization algorithms untested | Demand variability between regions | 30% | Mitigate | Prototype the planning tool in Phase C with Tervalis-provided user scenarios. | 300 | 1200 | 3500 | 360 | C–E | D2–E | Service inefficiency and user dissatisfaction. | Adds ground software cost.
| 69 | R-069 | Ground Segment & Operations | Ground Infrastructure | Network Control Site Facility Disruption | Schedule | One of the two network-control sites is unavailable due to power, fire or facility issues. | Facility resilience | Natural events; utility outages | 15% | Transfer | Operate dual sites in hot standby and transfer residual financial risk through facility insurance. | 400 | 2000 | 7000 | 300 | E | E | Temporary service degradation. | Minor operations cost.
| 70 | R-070 | Ground Segment & Operations | Gateways | Rain Fade at Gateways Exceeds Diversity Design | Performance | Heavy rain events at gateway sites exceed site-diversity assumptions, reducing feeder-link availability and network availability below 99.5%. | Gateway spacing optimized for cost | Regional climate; Ka-band propagation | 30% | Accept | Accept after propagation analysis at Ground Segment CDR, with backup gateway switchover procedures. | 300 | 1500 | 4500 | 450 | C–E | E | Availability shortfalls during storm seasons. | Affects operations and availability assumptions.
| 71 | R-071 | Ground Segment & Operations | Mission Operations | Concurrent LEOP of Three Spacecraft Overloads Operations | Operational | Orbit raising of three spacecraft launched within about two weeks overloads flight dynamics and control staff in Jan–Mar 2033. | Single flight dynamics team | Launch sequence timing | 40% | Mitigate | Augment the LEOP team with Qelvoria and Pervalin support and rehearse concurrent LEOP in simulations. | 400 | 1800 | 5000 | 720 | LEOP | LEOP | Errors or delays during orbit raising. | Adds LEOP staffing cost.
| 72 | R-072 | Technological & Engineering Factors | Technology Readiness & Maturity | Security Processor TRL 6 Not Reached by PDR | Technical | The two isolated security processors per spacecraft do not reach TRL 6 by PDR (Mar 2029) as required by Part A, forcing a delta-PDR or fallback to a heritage processor with reduced session throughput. | New processor family; limited environmental and radiation test data; compressed Phase B | Supplier maturity of radiation-tolerant high-performance processors | 35% | Mitigate | Fund an engineering-model environmental and radiation test campaign in Phase B (PREP 2 carry-over) and carry a lower-performance heritage fallback through PDR. | 800 | 3500 | 9500 | 1225 | B–C | B–C | Delta-PDR, redesign or reduced protected-session capacity. | Increases the technology-development cost element and Phase B/C duration uncertainty.
| 73 | R-073 | Technological & Engineering Factors | Technology Readiness & Maturity | Digital Channelizer Maturity | Technical | The 125 MHz x 8 channel digital channelizer does not demonstrate the required spectral efficiency at TRL 6. | Novel firmware; limited breadboard testing | FPGA/ASIC supplier roadmaps | 35% | Mitigate | Build a breadboard channelizer in Phase A (PREP 2) and verify on the payload testbed before PDR. | 700 | 3000 | 8000 | 1050 | A–C | B–C | Payload redesign or throughput reduction. | Affects payload cost and performance CERs.
| 74 | R-074 | Technological & Engineering Factors | Design & Development | Unstable Design Baseline After CDR | Technical | Late changes to beam layout, frequency plan or crypto boundary after CDR cascade into D1 manufacturing. | Late spectrum and security decisions | Coordination outcomes with adjacent operators | 35% | Mitigate | Freeze frequency plan and crypto boundary at CDR; handle later changes through firmware re-configuration where possible. | 1000 | 4000 | 11000 | 1400 | C–D1 | C–D1 | Rework of flight hardware. | Increases D1 cost uncertainty.
| 75 | R-075 | Technological & Engineering Factors | Integration & Verification | Payload–Bus Integration Delay | Schedule | Integration of the Sorevex payload panel, reflectors and security processors with the Qelvoria bus takes longer than planned because interfaces, harnessing, thermal constraints or data interfaces are not closed. | Late ICD closure; insufficient joint reviews | Sorevex delivery timing; test-facility availability | 45% | Mitigate | Freeze ICDs before CDR, run joint interface audits, use a flatsat/payload simulator, and protect D1 integration float. | 1200 | 4800 | 12000 | 2160 | C–D1 | D1–D2 | May delay payload integration, environmental testing and launch readiness. | Adds SE/integration LOE and schedule contingency.
| 76 | R-076 | Technological & Engineering Factors | Software & Algorithms | Flight Software Complexity Growth | Technical | Flight software for beam steering, key handling, safe-mode re-keying and FDIR grows beyond the estimated size and complexity. | Requirements for crypto and beam management still evolving at PDR; limited early prototyping | Supplier software development processes and staffing | 45% | Mitigate | Use incremental software builds with payload-in-the-loop testing from Phase C, track SLOC and requirement growth monthly, and hold a software schedule reserve. | 800 | 3400 | 9000 | 1530 | B–D1 | C–D1 | Flight software delivery slips into D1/D2 and delays FM-1 functional testing. | Increases the flight software cost element and IV&V effort.
| 77 | R-077 | Technological & Engineering Factors | Software & Algorithms | Insufficient Software Validation | Technical | Gaps in validation of key-rotation, revocation and beam-management functions allow defects to be discovered late in end-to-end testing with the Pervalin network-control software. | Limited regression testing; test benches shared across three units | Late partner code deliveries from Sorevex and Pervalin | 35% | Mitigate | Require independent software V&V and end-to-end test campaigns with the network-control software before Acceptance Review (Sep 2032). | 600 | 2400 | 6500 | 840 | C–D2 | D2 | Late defects delay acceptance and LRR. | Adds IV&V and regression-test LOE to D1/D2.
| 78 | R-078 | Technological & Engineering Factors | System Performance & Reliability | Unproven Redundancy of Security Processors | Technical | Switchover between the two isolated security processors does not preserve authenticated sessions as intended. | Inadequate model validation | Supplier delays in redundancy analyses | 30% | Mitigate | Test cross-strapping and switchover on the EM and each flight unit, including under fault injection. | 500 | 2000 | 5500 | 600 | C–D2 | D1–D2 | Redesign of redundancy management. | Affects reliability and availability analysis.
| 79 | R-079 | Technological & Engineering Factors | Parts, Components & Materials | EEE Part Failure or Obsolescence | Technical | Space-grade FPGAs, memory devices or TWTA components are discontinued or fail screening during D1, affecting one or more of the three flight units. | Inadequate part screening; lifetime buys not sized for three units plus spares | Supply-chain obsolescence and allocation of radiation-hardened parts | 35% | Mitigate | Perform lifetime buys for all three units plus spares at CDR, maintain an obsolescence watch list and qualify alternates for single-source parts. | 600 | 2500 | 6500 | 875 | C–D1 | D1 | Delays to unit builds and possible redesign of boards for FM-2/FM-3. | Adds spares, inventory and requalification cost.
| 80 | R-080 | Technological & Engineering Factors | Parts, Components & Materials | Long-Lead Payload Components | Schedule | TWTAs, reflectors, security processors and star trackers for three flight units plus spares arrive later than the Jun 2030 MRR need dates. | Late purchase orders; incomplete forecasts | Supplier backlog for space-qualified RF and optical components | 50% | Mitigate | Authorize long-lead procurement at PDR, track supplier milestones and qualify alternates. | 800 | 3500 | 9000 | 1750 | C–D1 | D1 | Unit AIT delays for FM-1 to FM-3. | Adds procurement management and inventory cost.
| 81 | R-081 | Programmatic Integration & Execution | Industrial Capability & Supplier Performance | Prime Contractor (Qelvoria) Performance | Programmatic | Qelvoria Orbital Systems underperforms on schedule or quality for the three-unit bus build and system-level verification. | Weak performance oversight | Contractor capacity and competing programs | 35% | Transfer | Use incentive fee and performance milestones in the contract; transfer schedule-driven cost via firm-fixed-price elements. | 1500 | 6500 | 18000 | 2275 | B–D2 | B–D2 | Delays across all three units. | Affects prime contract cost and schedule.
| 82 | R-082 | Programmatic Integration & Execution | Industrial Capability & Supplier Performance | Payload Contractor (Sorevex) Performance | Programmatic | Sorevex Signal Engineering is late delivering payload qualification or acceptance calibration evidence. | Weak oversight | Contractor capacity | 35% | Mitigate | Place a resident government engineer at Sorevex during D1 and review calibration evidence monthly. | 1000 | 4500 | 12000 | 1575 | C–D1 | D1 | Payload deliveries to Qelvoria late. | Affects payload cost.
| 83 | R-083 | Programmatic Integration & Execution | Industrial Capability & Supplier Performance | Ground Segment Contractor (Pervalin) Performance | Programmatic | Pervalin Gateway Services is late delivering gateways, backhaul and network-control systems. | Weak oversight | Contractor capacity | 30% | Mitigate | Hold monthly readiness reviews and apply liquidated damages for late gateway acceptance. | 700 | 3000 | 8000 | 900 | C–D2 | D2 | Ground readiness slips past Aug 2032. | Affects ground segment cost.
| 84 | R-084 | Technological & Engineering Factors | Obsolescence & Sustainment | Component Obsolescence for Later Units | Technical | Parts qualified for FM-1 become obsolete before the FM-3 build completes (Mar 2032). | Late lifetime buys | Market product cycles | 30% | Mitigate | Place lifetime buys for all three units at CDR. | 400 | 1600 | 4500 | 480 | D1 | D1 | Redesign on later units. | Adds inventory cost.
| 85 | R-085 | Programmatic Integration & Execution | Contracting & Procurement | Vendor Estimate Understatement | Cost | Initial vendor ROM estimates for the protected payload and gateways are understated. | Limited independent estimates in Phase 0 | Commercial strategy of bidders | 40% | Mitigate | Develop independent cost estimates and analogy checks for Part B. | 1500 | 6000 | 16000 | 2400 | A–B | B | Higher contract prices at award. | Widens cost range.
| 86 | R-086 | Programmatic Integration & Execution | Contracting & Procurement | Insufficient Bid Competition for Protected Payload | Programmatic | Few suppliers can meet protected-communications security requirements, limiting competition for the payload. | Restrictive requirements | Market capacity | 30% | Accept | Accept after market sounding in Phase 0 confirms at least two capable bidders. | 500 | 2500 | 7000 | 750 | A–B | A–B | Higher prices and reduced negotiating leverage. | Affects procurement strategy and payload cost.
| 87 | R-087 | External & Environmental Factors | Market & Supply Chain | Supplier Insolvency or Instability | Programmatic | A tier-2 supplier (e.g., reflector or TWTA maker) fails financially during D1. | Single sources | Market volatility | 20% | Transfer | Monitor supplier financial health and qualify second sources for critical items. | 600 | 3000 | 9000 | 600 | C–D1 | D1 | Delays and requalification. | Adds cost.
| 88 | R-088 | Technological & Engineering Factors | Manufacturing & Assembly | Manufacturing Workmanship Defects | Technical | Workmanship defects in harnesses, RF waveguides or reflector hinges are found late in testing of FM-1 to FM-3. | Insufficient QA inspection points | Supplier workmanship variability | 40% | Mitigate | Define mandatory inspection points and workmanship standards. | 500 | 2200 | 6000 | 880 | D1 | D1 | Rework and retest. | Adds AIT cost.
| 89 | R-089 | Safety, Assurance & Compliance | Test & Verification | Test Facility Contention for Three Units | Schedule | The thermal-vacuum chamber and compact antenna test range cannot accommodate three units on the D1/D2 schedule. | Parallel builds | Facility bookings by other programs | 40% | Mitigate | Book facilities at CDR and identify back-up facilities. | 500 | 2000 | 5500 | 800 | D1–D2 | D1–D2 | Test delays. | Adds facility cost.
| 90 | R-090 | Safety, Assurance & Compliance | Product Assurance & Quality Control | Non-Conformance Backlog | Programmatic | Open non-conformance reports accumulate across three concurrent units. | MRB capacity | Supplier NCRs | 35% | Mitigate | Hold weekly MRBs with resolution targets. | 300 | 1200 | 3500 | 420 | D1–D2 | D1–D2 | Delays to acceptance. | Adds SMA LOE.
| 91 | R-091 | Technological & Engineering Factors | Manufacturing & Assembly | Configuration Drift Between FM-1, FM-2 and FM-3 | Technical | Changes introduced after FM-1 testing are not consistently applied to FM-2 and FM-3. | Weak configuration management | Supplier changes | 30% | Mitigate | Apply strict configuration control and as-built comparison audits at each unit AR. | 400 | 1600 | 4500 | 480 | D1–D2 | D1–D2 | Retest or on-orbit behaviour differences between units. | Adds CM cost.
| 92 | R-092 | Safety, Assurance & Compliance | Test & Verification | Incomplete End-to-End Test Coverage | Technical | End-to-end tests do not cover all protected-session, key-revocation and beam-steering scenarios across the four gateways. | Limited test time | Ground segment readiness | 35% | Mitigate | Define an end-to-end test matrix at CDR. | 400 | 1800 | 5000 | 630 | D2 | D2 | Defects found in orbit. | Adds test cost.
| 93 | R-093 | Safety, Assurance & Compliance | Test & Verification | Environmental Test Failure | Technical | A flight unit fails vibration, acoustic, shock or thermal-vacuum testing; reflector hold-downs, the 2.8 m² radiator panels and payload RF assemblies are the most exposed items. | Weak structural or thermal margins; design flaws not caught at unit level | Test facility anomalies (over-test, chamber failure) | 30% | Mitigate | Maintain qualification margins, perform pre-test analysis and low-level sine surveys, and protect test-anomaly reserve in the D1 schedule. | 1000 | 4500 | 12000 | 1350 | D1 | D1 | Rework and retest of the affected unit; knock-on delay to later units. | Adds AIT cost and supports the worst-case schedule scenario.
| 94 | R-094 | Safety, Assurance & Compliance | Test & Verification | Qualification Article Not Representative of Flight Units | Technical | The structural/thermal qualification article diverges from the flight design after late changes, so Part A's qualification-by-representative-article approach is no longer valid. | Design changes after CDR; mass or radiator changes | Supplier-driven part substitutions | 20% | Avoid | Avoid changes that invalidate qualification; maintain a qualification-by-similarity analysis for every change. | 400 | 1800 | 5000 | 360 | C–D1 | D1 | Delta-qualification of the affected item. | Adds test cost and D1 schedule risk.
| 95 | R-095 | Safety, Assurance & Compliance | System Safety & Human Protection | Propellant Loading Hazard at Launch Site | Safety | A hazard during loading of 550 kg of storable bipropellant per spacecraft (three campaigns) causes injury, contamination or hardware damage. | Procedure gaps; campaign staff fatigue across three campaigns | Launch-site conditions and range safety rules | 5% | Mitigate | Perform hazard analyses, use certified loading teams and independent safety oversight for each campaign. | 500 | 3000 | 15000 | 150 | D2 | D2 | Launch delay and possible hardware damage. | Minor cost; drives safety LOE in D2.
| 96 | R-096 | Technological & Engineering Factors | System Performance & Reliability | Mission-Success Probability Below Target | Technical | Reliability analysis shows that the probability of sustaining ≥99.5% availability with eight beams per spacecraft over seven years is below target. | Single-string payload elements; limited TWTA redundancy | GEO radiation and charging environment | 30% | Mitigate | Apply selective redundancy informed by FMECA and reliability allocation at PDR. | 800 | 3200 | 8500 | 960 | B–C | C–D1 | Design changes adding mass and cost. | Affects reliability-driven cost and spares assumptions.
| 97 | R-097 | Safety, Assurance & Compliance | Product Assurance & Quality Control | Software Assurance Gaps in Security-Critical Code | Technical | Security-critical flight and ground code (key handling, command authentication) is not developed to the required assurance level, blocking crypto certification. | Teams inexperienced with high-assurance processes | Supplier software processes | 30% | Mitigate | Apply high-assurance development processes, static analysis and independent audits from Phase C. | 400 | 1800 | 5000 | 540 | C–D1 | D1 | Rework of security-critical code and certification delay. | Adds software assurance LOE.
| 98 | R-098 | Organizational & Human Factors | Resource & Staffing Capacity | Cleared COMSEC and Crypto Specialists Unavailable | Programmatic | The directorate cannot staff enough security-cleared cryptographic, key-management and cybersecurity specialists when needed for PDR and D2. | Small cleared talent pool; lengthy security clearance processing | Competition from other protected-communications programs | 50% | Mitigate | Start clearance processing a year ahead of need, cross-train staff and pre-qualify cleared contractor support. | 500 | 2200 | 5500 | 1100 | A–E | B–D2 | May delay security reviews and accreditation. | Raises labour-rate and FTE assumptions for CS-classified positions.
| 99 | R-099 | Organizational & Human Factors | Resource & Staffing Capacity | Specialized Resource Availability | Programmatic | VPCS cannot staff enough payload, RF, flight software or GEO operations specialists at the D2/LEOP peak (~66 FTE). | Hiring lead time; skill concentration | Labour-market competition in space communications | 50% | Mitigate | Identify critical skills by phase from the RAM, recruit early, cross-train and maintain contractor support options. | 600 | 2500 | 6000 | 1250 | A–LEOP | B–D2 | May delay technical reviews or operations readiness. | Raises labour-rate and FTE assumptions.
| 100 | R-100 | Organizational & Human Factors | Resource & Staffing Capacity | Knowledge Loss and Continuity Gaps | Programmatic | Loss of key personnel over a 17-year life cycle (2026–2043) undermines continuity of design rationale and operations knowledge. | Weak knowledge management; long mission duration | Retirements; competitive hiring | 45% | Accept | Accept after implementing succession plans for single-point-of-knowledge roles and documenting design rationale. | 300 | 1200 | 3200 | 540 | A–F | B–E | Rework and slower anomaly resolution. | Adds training and overlap LOE.
| 101 | R-101 | Organizational & Human Factors | Leadership, Governance & Culture | Governance and Approval Delays | Governance | Security, spectrum and interdepartmental approvals required at KDP gates (MCR, SRR, PDR, CDR, LRR) take longer than the Part C schedule assumes. | Unclear decision authorities between the Directorate and the security authority; incomplete approval packages | Security-authority and oversight review priorities; approval cycles outside the project's control | 40% | Mitigate | Define authorities, decision timelines, delegated approvals and gate evidence lists in the governance baseline before SRR; pre-brief approvers four weeks ahead of each gate. | 400 | 1500 | 4000 | 600 | A–D2 | A–D2 | Gate passages and contract authorizations slip, delaying phase starts. | Adds PM, governance and stakeholder-coordination LOE; supports the realistic (+1 mo/phase) scenario.
| 102 | R-102 | Organizational & Human Factors | Communication & Coordination | Multi-Party Interface Coordination | Programmatic | Six organizations (Avranel, Qelvoria, Sorevex, Lundrith, Pervalin and Tervalis) own interfaces across space, launch, ground and user segments; coordination failures create late rework in D1/D2. | Insufficient joint working groups; interface ownership not assigned in the Part A responsibility boundaries | Different contractor processes, tools and configuration systems | 40% | Mitigate | Establish an Interface Control Working Group chaired by the Directorate with monthly cadence, a single ICD repository and named owners for every interface. | 400 | 1600 | 4200 | 640 | B–D2 | B–D2 | Interface rework discovered during payload–bus integration or end-to-end testing. | Adds systems-engineering and PM LOE across Phases B–D2.
| 103 | R-103 | External & Environmental Factors | Geopolitical & Economic | Inflation and Cost Escalation | Cost | Inflation over the 2026–2043 life cycle exceeds the economic assumptions used in Parts B and C, particularly for skilled labour and space-grade electronics. | Long program duration; fixed-price assumptions | Macroeconomic trends; labour market | 50% | Mitigate | Include escalation clauses in contracts and re-estimate at each KDP. | 2000 | 8000 | 20000 | 4000 | A–E | A–E | Cost growth in then-year dollars. | Affects then-year cost and salary indexation in the RAM.
| 104 | R-104 | External & Environmental Factors | Geopolitical & Economic | Foreign Exchange Volatility | Cost | Foreign-sourced TWTAs, FPGAs and launch services cost more due to exchange-rate movements. | High foreign content in payload and launch | Currency markets | 30% | Mitigate | Hedge major foreign-currency contracts and prefer domestic sourcing where practical. | 400 | 1800 | 5000 | 540 | B–D1 | B–D1 | Cost growth on foreign-denominated contracts. | Adds exchange-rate uncertainty to the cost range.
| 105 | R-105 | External & Environmental Factors | Geopolitical & Economic | Geopolitical Instability or Sanctions | Strategic | Sanctions or instability disrupt component suppliers or one of the launch vehicles in the Lundrith consortium. | Limited supplier diversification | International conflicts or trade actions | 20% | Accept | Accept after confirming at least two launch-vehicle options and diversified parts sources. | 800 | 4000 | 12000 | 800 | B–D2 | B–D2 | Supplier or vehicle change with re-verification of interfaces. | Affects launch and parts cost.
| 106 | R-106 | External & Environmental Factors | Force Majeure & Environmental Events | Facility Disruption from Natural Event | Schedule | A flood, fire or storm disrupts Qelvoria or Sorevex manufacturing and test facilities during D1/D2. | Facility resilience gaps | Natural hazards | 15% | Transfer | Transfer financial exposure through contractor insurance and require business-continuity plans. | 500 | 2500 | 8000 | 375 | D1–D2 | D1–D2 | Delays to unit builds. | Minor cost; schedule impact covered by reserve.
| 107 | R-107 | External & Environmental Factors | Force Majeure & Environmental Events | Solar Maximum Effects During Early Operations | Technical | Elevated solar activity increases single-event upsets and solar-array degradation during the first years of operations. | Design margins set on average environment | Solar cycle timing | 25% | Accept | Accept with radiation design margins and operational upset-recovery procedures. | 300 | 1400 | 4000 | 350 | E | E | More anomalies and operator workload. | Minor operations cost.
| 108 | R-108 | Strategic & Alignment Factors | Strategic Direction & Policy Alignment | Government Priority Shift | Strategic | Changes in government priorities reduce funding or alter protected-communications requirements after SRR. | Weak link between mission objectives and strategic goals | Policy and budget changes | 25% | Accept | Accept after aligning the mission with stated priorities in Part A Table 1 and maintaining an up-to-date business case. | 2000 | 9000 | 30000 | 2250 | A–E | A–E | Scope reduction, delay or cancellation. | Large cost and schedule impact; not budgeted.
| 109 | R-109 | Strategic & Alignment Factors | Strategic Direction & Policy Alignment | Demand Shift to Commercial Protected Services | Strategic | Users migrate to commercial protected-service offerings, reducing VPCS utilization during Phase E. | Service pricing and access model | Commercial market growth | 20% | Accept | Accept with active user engagement through the User Community Liaison and Tervalis service reviews. | 500 | 2500 | 8000 | 500 | C–E | E | Lower utilization of eight beams per spacecraft. | Affects value-for-money analysis.
| 110 | R-110 | Safety, Assurance & Compliance | Product Assurance & Quality Control | Configuration Management Lapses | Technical | Hardware, software and security baselines become inconsistent between the Avranel, Qelvoria, Sorevex and Pervalin repositories. | Weak CM discipline; multiple repositories | Different contractor tools | 35% | Mitigate | Appoint a single configuration authority and run quarterly configuration audits. | 300 | 1400 | 4000 | 490 | B–D2 | B–D2 | Rework and test invalidation. | Adds CM LOE.
| 111 | R-111 | Data, Knowledge & Integration | Knowledge Management | Knowledge Loss Through Poor Documentation | Programmatic | Design rationale for the crypto boundary, beam management and thermal design is lost across the 17-year life cycle. | Weak knowledge-management discipline | Staff and contractor turnover | 35% | Mitigate | Implement a knowledge-management plan with design-rationale records at each review. | 200 | 900 | 2500 | 315 | A–F | B–E | Slower anomaly resolution in Phase E. | Adds sustaining engineering LOE.
| 112 | R-112 | Data, Knowledge & Integration | Data Integration & Consistency | Classified and Unclassified Data Separation Burden | Programmatic | Separating classified security data from unclassified engineering data slows analyses, reviews and anomaly investigations. | Tooling not designed for dual domains | Security handling rules | 40% | Accept | Accept with dual-domain engineering tools and defined data-release procedures. | 200 | 1000 | 3000 | 400 | B–E | B–D2 | Productivity loss in reviews. | Adds LOE in Phases B–D2.
| 113 | R-113 | End of Life | Disposal & Decommissioning | Insufficient Propellant for Graveyard Re-orbit | Technical | After ten years, propellant remaining is insufficient to re-orbit a spacecraft to a super-synchronous graveyard orbit. | Propellant gauging uncertainty | Pressure to extend operations beyond design life | 15% | Avoid | Ring-fence disposal propellant and end extended operations when the reserve threshold is reached. | 300 | 1500 | 5000 | 225 | E EXT–F | F | Non-compliant disposal. | Affects end-of-life planning and Phase E EXT duration.
| 114 | R-114 | End of Life | Disposal & Decommissioning | Closeout Records and Archive Handover Incomplete | Programmatic | Mission records, calibration history and the audit archive are not fully handed over to Tervalis at closeout (Jul 2043). | Late closeout planning | Records retention rules | 20% | Mitigate | Approve a closeout plan at the start of Phase E EXT. | 100 | 500 | 1500 | 100 | F | F | Records gaps and audit findings. | Minor closeout cost.
| 115 | R-115 | End of Life | Disposal & Decommissioning | Passivation Incomplete at End of Life | Technical | Batteries or propellant tanks cannot be fully passivated after graveyard re-orbit, creating fragmentation risk. | Passivation not designed in | Space sustainability expectations | 15% | Mitigate | Design passivation capability (vent valves, battery disconnect) at PDR. | 150 | 700 | 2000 | 105 | B–F | F | Non-compliant disposal. | Minor design cost.

## 7-Risk Breakdown Structure
Risk Category | Risk Sub-category | Risk Name | Type of Risk | Description | Internal Factors | External Factors | Cost - Impact in Phase | Schedule - Initial Impact in Phase | Parent CBS
Organizational & Human Factors | Leadership, Governance & Culture | Ineffective Governance and Decision-Making | Governance | Governance structures, roles, and escalation paths are unclear or inconsistently applied, delaying key decisions and creating misalignment across the program. | - Unclear authority - Slow approvals - Inconsistent executive oversight | - Evolving government governance expectations - Partner governance incompatibility | All | All
Organizational & Human Factors | Leadership, Governance & Culture | Misaligned Organizational Incentives | Strategic | Incentives prioritize innovation or technical achievement over disciplined cost/schedule performance, reducing accountability. | - Incentives tied to technical milestones - Weak KPIs | - Public/political pressure for innovation | PREP 1 to MAIT | None
Organizational & Human Factors | Leadership, Governance & Culture | Leadership Turnover and Instability | Governance | High turnover in key leadership roles reduces continuity and strategic alignment across program phases. | - Succession gaps - Staffing instability | - Broader public sector mobility pressures | All | All
Organizational & Human Factors | Leadership, Governance & Culture | Risk Governance Culture | Programmatic | Risk processes are inconsistently followed or valued, leading to late identification of major issues. | - Lack of active risk boards - Inconsistent risk scoring | - Changing departmental reporting expectations | PREP 1 to MAIT | PREP 1 to MAIT
Organizational & Human Factors | Communication & Coordination | Internal Miscommunication and Information Silos | Programmatic | Teams lack timely, consistent information sharing, resulting in misaligned decisions and rework. | - Poor knowledge sharing - Unclear reporting paths | - Increased complexity in muti-site or remote collaboration | PREP 1 to MAIT | PREP 1 to MAIT
Organizational & Human Factors | Communication & Coordination | Interface Definition Gaps | Technical | Unclear or incomplete interface definitions lead to integration challenges and design errors. | - Documentation gaps - Inconsistent configuration control | - Partner documentation misalignment | Phase 0 to SAID | Phase 0 to SAID
Organizational & Human Factors | Communication & Coordination | International Coordination Challenges | Programmatic | Communication barriers across time zones, cultures, and languages delay critical alignment with partners. | - Limited resources for partner coordination | - Diverse international work practices | All | All
Organizational & Human Factors | Stakeholder Engagement | Unclear or Misaligned Stakeholder Expectations | Strategic | Stakeholder needs are not fully understood or aligned, causing redefinition of scope or priorities. | - Insufficient early engagement | - User community evolution - Science priorities | PREP 1 to Phase C | PREP 1 to Phase C
Organizational & Human Factors | Stakeholder Engagement | Insufficient Executive Sponsorship | Governance | Executive sponsors are not consistently engaged, weakening decision support and program momentum. | - Competing leadership priorities | - Shifts in departmental focus | PREP 1 to Phase C | PREP 1 to Phase C
Organizational & Human Factors | Resource & Staffing Capacity | Skilled Resource Shortages | Programmatic | Lack of experienced personnel delays technical development and increases rework. | - Training gaps - Turnover | - Labour market shortages in space-specialized skills | PREP 1 to Phase C | PREP 1 to Phase C
Organizational & Human Factors | Resource & Staffing Capacity | Knowledge Loss and Continuity Gaps | Programmatic | Loss of key personnel or weak documentation undermines continuity across phases. | - Insufficient knowledge management | - Competitive hiring environment | All | All
Organizational & Human Factors | Resource & Staffing Capacity | Overreliance on Individual Experts | Programmatic | Critical knowledge is concentrated in a few individuals, creating vulnerability if unavailable. | - Limited SME capacity | - Industry-wide SME scarcity | All | All
Technological & Engineering Factors | Technology Readiness & Maturity | Insufficient Technology Readiness Level (TRL) | Technical | Technology maturity is overestimated or not demonstrated early enough, causing downstream delays. | - Over-optimistic internal assessments | - Vendor overstatements of maturity | PREP 1 to Phase C | PREP 1 to Phase C
Technological & Engineering Factors | Technology Readiness & Maturity | Immature or Unproven Materials/Processes | Technical | New materials or manufacturing processes fail to meet requirements or require redesign. | - Limited early testing | - Supplier process immaturity | MAIT | MAIT
Technological & Engineering Factors | Design & Development | Unstable or Incomplete Design Baseline | Technical | Delays in achieving a stable baseline cascade into integration and manufacturing issues. | - Late requirements - Design churn | - Changing partner specifications | PREP 1 to SAID | PREP 1 to SAID
Technological & Engineering Factors | Design & Development | Design Complexity Beyond Analytical Capability | Technical | Engineering tools or models cannot fully resolve complex design interactions. | - Tool limitations | - Novel mission or payload architectures | PREP 1 to Phase C | PREP 1 to Phase C
Technological & Engineering Factors | Design & Development | Over-Customization Instead of COTS Adoption | Technical | Excessive customization increases cost, lead time, and risk compared with qualified COTS alternatives. | - Preference for bespoke solutions | - Limited space-qualified COTS availability | PREP 1 to Phase C | PREP 1 to Phase C
Technological & Engineering Factors | Parts, Components & Materials | EEE Part Failure or Obsolescence | Technical | Component failures or discontinuations disrupt design choices and testing schedules. | - Inadequte part screening | - Supply chain obsolescence | MAIT & SAID | MAIT & SAID
Technological & Engineering Factors | Parts, Components & Materials | Long-Lead Item Delays | Schedule | Critical components with long procurement cycles delay integration readiness. | - Late ordering | - Supplier backlog or disruption | MAIT & SAID | MAIT & SAID
Technological & Engineering Factors | Integration & Verification | Incomplete Integration Planning | Programmatic | Integration sequencing or planning gaps result in late rework and testing conflicts. | - Inadequate early I&T definition | - Partner delays | MAIT & SAID | MAIT & SAID
Technological & Engineering Factors | Integration & Verification | Environmental or Vibration Test Failures | Technical | Hardware fails during qualification or environmental tests, requiring redesign or rework. | - Weak margins - Design flaws | - Facility constraints | Phase B to Phase C | Phase B to Phase C
Technological & Engineering Factors | Manufacturing & Assembly | Poor Workmanship or QA Deficiencies | Technical | Manufacturing quality issues result in defects discovered late in testing or integration. | - Insufficient QA processes | - Supplier QA variability | MAIT & SAID | MAIT & SAID
Technological & Engineering Factors | Manufacturing & Assembly | Immature Manufacturing Processes | Technical | New or insufficiently validated processes lead to production delays or variability. | - Lac of documentation | - Small-capacity suppliers | MAIT & SAID | MAIT & SAID
Technological & Engineering Factors | Software & Algorithms | Underestimated Software Complexity | Technical | Software complexity is underestimated, requiring additional development time and testing. | - Limited early prototyping | - Integration with partner systems | Phase B to SAID | Phase B to SAID
Technological & Engineering Factors | Software & Algorithms | Insufficient Software Validation | Technical | Gaps in software validation cause faults discovered late in testing. | - Limited regression testing | - Late partner code deliveries | Phase B to SAID | Phase B to SAID
Technological & Engineering Factors | System Performance & Reliability | Insufficient System Margin | Technical | System lacks adequate performance margins, requiring late design changes. | - Underestimated loads | - Evolving partner or payload requirements | Phase B to SAID | Phase B to SAID
Technological & Engineering Factors | System Performance & Reliability | Unproven Redundancy or Fail-Safe Design | Technical | Redundant designs are untested or do not function as intended. | - Inadequate model validation | - Supplier delays in providing redundancy analyses | Phase B to SAID | Phase B to SAID
Technological & Engineering Factors | Obsolescence & Sustainment | Technology Obsolescence During Development | Technical | Long development timelines result in components or systems becoming outdated before launch. | - Slow decision-making | - Rapid commercial technology cycles | LEOP & ATLO
Technological & Engineering Factors | Obsolescence & Sustainment | Inadequate Sustainment Planning | Programmatic | Lifecycle sustainment needs are not fully planned, risking long-term mission continuity. | - Limited spares strategy | - Supplier discontinuation | Phase E & Phase EXT
Programmatic Integration & Execution | Cost & Budget Management | Optimistic Cost Baselines | Cost | Early cost estimates underestimate complexity or required effort, resulting in overruns and re-baselining. | - Immature designs - Optimistic modelling - Incomplete scoping | - Vendor underestimation - Inflation volatility | PREP 1 to Phase A
Programmatic Integration & Execution | Cost & Budget Management | Inadequate Contingency and Reserves | Cost | Cost reserves are insufficient to address risks, requirement changes, or technical growth. | - Pressure to reduce contingency - Lack of quantitative risk analysis | - Unpredictable supplier or market cost changes | All Phases
Programmatic Integration & Execution | Cost & Budget Management | Funding Gaps Across Phases | Programmatic | Delays or gaps in funding between phases disrupt schedules and lead to inefficiencies. | - Internal budget reallocations - Fragmented planning | - Central budget-authority sequencing - Government budget cycles | PREP 1 to Phase C | PREP 1 to Phase C
Programmatic Integration & Execution | Cost & Budget Management | Long-Term Cost Unsustainability | Cost | Operational or lifecycle costs exceed long-term funding, jeopardizing mission continuity. | - Underestimated O&M demands | - Shifting fiscal priorities | Phase E & Phase EXT
Programmatic Integration & Execution | Schedule Planning & Control | Overly Optimistic Schedule Baselines | Schedule | Schedules underestimate duration or complexity of integration, test and partner interactions. | - Underestimated task durations - Limited slack | - Partner timeline dependencies | Phase C, MAIT or SAID | Phase C, MAIT or SAID
Programmatic Integration & Execution | Schedule Planning & Control | Insufficient Schedule Margin | Schedule | Lack of adequate float/margin makes the project vulnerable to minor disruptions. | - Compressed internal timelines | - External approvals - Provider availability |  | PREP 1 to SAID
Programmatic Integration & Execution | Schedule Planning & Control | Poor Schedule Integration Across Teams | Schedule | Schedules are not fully integrated across subsystems or partners, creating conflicting paths. | - Weak configuration control of schedule updates | - Misaligned partner planning cycles |  | PREP 1 to SAID
Programmatic Integration & Execution | Requirements & Scope Management | Evolving or Unstable Requirements | Technical | Requirements shift during development, prompting redesign and rescheduling. | - Incomplete early requirements - Late discoveries | - Regulatory or partner-driven changes | Phase 0 to Phase C | Phase 0 to Phase C
Programmatic Integration & Execution | Requirements & Scope Management | Scope Creep | Programmatic | Additional features or changes are added without corresponding increases in budget or schedule. | - Internal mission re-design | - Requests from science/user community | Phase 0 to Phase C | Phase 0 to Phase C
Programmatic Integration & Execution | Requirements & Scope Management | Unclear Definition of Deliverables | Programmatic | Deliverables or success criteria are not explicitly defined, resulting in rework and disputes. | - Vague SOW - Weak requirement traceability | - Partner interpretation differences | Phase 0 to Phase C | Phase 0 to Phase C
Programmatic Integration & Execution | Contracting & Procurement | Procurement and Contract Delays | Schedule | Delays in contract awards, evaluations, or negotiations slow project initiation and execution. | - Insufficient procurement staffing | - Federal procurement rules and oversight | PREP 1 & 2, Phase 0 to Phase B, MAIT | PREP 1 & 2, Phase 0 to Phase B, MAIT
Programmatic Integration & Execution | Contracting & Procurement | Misaligned Contract Structures | Governance | Contract types or terms do not support risk-sharing or needed flexibility. | - Inexperienced contracting officers | - Mandatory policy constraints | PREP 1 to MAIT | PREP 1 to MAIT
Programmatic Integration & Execution | Contracting & Procurement | Vendor Performance Issues | Programmatic | Prime or subcontractor performance problems cause rework or schedule delays | - Weak performance oversight | - Supplier instability | PREP 1 to MAIT | PREP 1 to MAIT
Programmatic Integration & Execution | Contracting & Procurement | Waste, Fraud, or Abuse Vulnerabilities | Governance | Inadequate internal controls expose the program to misuse of funds or fraudulent activity. | - Limited review time - Weak monitoring | - Complex multinational supply chains | All Phases
Programmatic Integration & Execution | Industrial Capability & Supplier Performance | Supplier Maturity Limitations | Programmatic | Suppliers lack mature processes, certifications, or capacity to deliver quality components on time. | - Insufficient oversight | - Small national supplier base | MAIT & SAID | MAIT & SAID
Programmatic Integration & Execution | Industrial Capability & Supplier Performance | Manufacturing Defects or Quality Issues | Technical | Supplier quality defects result in delays, retesting, or redesign. | - Weak acceptance processes | - Supplier QA inconsistency | MAIT & SAID | MAIT & SAID
Programmatic Integration & Execution | Industrial Capability & Supplier Performance | Overstretched SMEs | Programmatic | Small suppliers lack the throughput or staffing required for schedule-critical work. | - Inadequate supplier monitoring | - High demand across space industry | MAIT & SAID | MAIT & SAID
Programmatic Integration & Execution | Partnership & External Agreements | Misaligned Partner Schedules or Deliverables | Schedule | International partners operate on different timelines or processes, leading to integration delays. | - Insufficient internal integration planning | - Partner readiness issues | SAID & ATLO | SAID & ATLO
Programmatic Integration & Execution | Partnership & External Agreements | Partner Scope or Commitment Changes | Strategic | Changes in partner priorities, scope, or funding affect shared milestones or system architecture. | - Weak MOU/LOA clarity | - Changing political or budgetary environments | PREP 1 to ATLO | PREP 1 to ATLO
Programmatic Integration & Execution | Partnership & External Agreements | Export Control and Licensing Constraints | Governance | Export control requirements (ITAR, TAAs) delay access to components, data, or test facilities. | - Limited early export planning | - Regulatory changes | Phase B to ATLO | Phase B to ATLO
Programmatic Integration & Execution | Governance Processes & Controls | Weak Phase-Gate Discipline | Governance | Phase reviews lack rigor, allowing unresolved issues to carry forward. | - Inconsistent review criteria | - Pressure to meet partner timelines | Phase 0 to ATLO | Phase 0 to ATLO
Programmatic Integration & Execution | Governance Processes & Controls | Fragmented Technical/Cost/Schedule Reporting | Programmatic | Reports are inconsistent or disconnected, obscuring emerging risks. | - Misaligned data system | - Adjusted government reporting frameworks | All Phases | All Phases
External & Environmental Factors | Regulatory & Legal | Export Licensing or Regulatory Delays | Governance | Licensing processes delay hardware transfers, testing, or component acquisition. | - Unclear internal responsibilities | - ITAR/national export regulations | MAIT, SAID, ATLO | MAIT, SAID, ATLO
External & Environmental Factors | Regulatory & Legal | Changes in Laws, Policies, or Standards | Strategic | Domestic or international policy changes impact program scope, design, or compliance obligations. | - Slow adaptation | - New global or national regulations | Phase 0 to Phase C | Phase 0 to Phase C
External & Environmental Factors | Market & Supply Chain | Supplier Insolvency or Instability | Programmatic | Key suppliers face financial or operational challenges that disrupt delivery. | - Dependence on single supplier | - Market volatility | PREP 1 to SAID | PREP 1 to SAID
External & Environmental Factors | Market & Supply Chain | Price Escalation or Market Shock | Cost | Unexpected increase in material or component costs exceed planned budgets. | - Long-term fixed-price contracts | - Global supply shocks | MAIT & SAID | MAIT & SAID
External & Environmental Factors | Market & Supply Chain | Logistics and Shipping Disruptions | Schedule | Transportation or customs delays impact integration timelines. | - Limited logistics planning | - International border issues | MAIT, SAID, ATLO | MAIT, SAID, ATLO
External & Environmental Factors | Geopolitical & Economic | Currency Exchange Volatility | Cost | Foreign-denominated contracts become more expensive due to unstable currency rates. | - High foreign procurement content | - Global economic instability | PREP 1 to SAID
External & Environmental Factors | Geopolitical & Economic | Inflation Spikes | Cost | Inflation increase labour, materials, and subcontractor prices beyond assumptions. | - Long program timeline | - Global economic trends | PREP 1 to SAID
External & Environmental Factors | Geopolitical & Economic | Geopolitical Instability or Sanctions | Strategic | Political instability or sanctions disrupt suppliers, partners, or launch providers. | - Limited diversification | - International conflicts or trade actions | PREP 1 to ATLO | PREP 1 to ATLO
External & Environmental Factors | Force Majeure & Environmental Events | Natural Disasters or Environmental Accidents | Schedule | Floods, fires, or contamination events disrupt testing or manufacturing. | - Facility resilience gaps | - Environmental events | MAIT & SAID | MAIT & SAID
External & Environmental Factors | Force Majeure & Environmental Events | Space Weather Impacts | Technical | Radiation storms or solar activity necessitate design changes or additional testing. | - Margins underestimated | - Solar activity cycles | PREP 1 to SAID | PREP 1 to SAID
Strategic & Alignment Factors | Strategic Direction & Policy Alignment | Shifting Government or Agency Priorities | Strategic | Changes in federal or departmental priorities alter program direction, scope, or funding. | - Misalignment with strategic planning | - New government mandates | Phase 0 to Phase C | Phase 0 to Phase C
Strategic & Alignment Factors | Strategic Direction & Policy Alignment | Policy-Driven Changes in Agency Focus | Strategic | Agency focus shifts between mission delivery and administrative compliance due to policy changes. | - Leadership turnover | - Political direction | Phase 0 to Phase C | Phase 0 to Phase C
Strategic & Alignment Factors | Value, Stewardship & "Mission vs Resources" Balance | Priority on Technology over Stewardship | Strategic | Culture prioritizes technical success over disciplines resource management, contribution to overruns. | - Incentives tied to innovation | - Public expectations for technological leadership | PREP 1 to ATLO
Strategic & Alignment Factors | Value, Stewardship & "Mission vs Resources" Balance | Unclear Mission Success Criteria | Governance | Lack of clear definition of success undermines tracking, reporting, and accountability. | - Weak KPI framework | - Evolving departmental expectations | PREP 1 to ATLO | PREP 1 to ATLO
Safety, Assurance & Compliance | System Safety & Human Protection | Inadequate Hazard Identification and Mitigation | Safety | Hazards are not fully identified or mitigated, increasing risk during testing or integration. | - Limited safety analysis | - New or updated safety regulations | MAIT & SAID | MAIT & SAID
Safety, Assurance & Compliance | System Safety & Human Protection | Safety Procedures Not Followed | Safety | Deviations from safety protocol create risk of injury or system damage. | - Training gaps | - Contractor procedure variance | MAIT & SAID | MAIT & SAID
Safety, Assurance & Compliance | Product Assurance & Quality Control | Inadequate QA or Inspection Processes | Technical | Weak QA processes lead to undetected defects in hardware or documentation. | - Insufficient QA staffing | - Supplier quality variability | MAIT & SAID | MAIT & SAID
Safety, Assurance & Compliance | Product Assurance & Quality Control | Configuration Management Lapses | Technical | CM issues result in inconsistencies between design, test, and manufacturing data. | - Weak configuration discipline | - Partner CM incompatibility | MAIT & SAID | MAIT & SAID
Safety, Assurance & Compliance | Test & Verification | Incomplete or Insufficient Test Plans | Technical | Gaps in test coverage allow defects to be discovered late. | - Inadequate early test planning | - Facility limitations | MAIT, SAID, LEOP, ATLO, Early Ops, Phase E | MAIT, SAID, LEOP, ATLO, Early Ops, Phase E
Safety, Assurance & Compliance | Test & Verification | Late Discovery of Non-Compliance | Technical | Key requirements failures are found late in qualification, increasing cost and schedule impact. | - Weak integration testing | - Late partner deliveries | MAIT & SAID | MAIT & SAID
Safety, Assurance & Compliance | Certification & Standards | Delayed Safety or Standards Certification | Governance | Delays obtaining required certifications impede integration or launch activities | - Incomplete documentation | - Changing standards | LEOP, ATLO, Cruise Out | LEOP, ATLO, Cruise Out
Data, Knowledge & Integration | Data Integration & Consistency | Misaligned Baselines (Cost, Schedule, Technical) | Programmatic | Cost, schedule, and technical baselines are not consistently aligned, obscuring issues. | - Tool integration gaps | - Partner baseline mismatches | PREP 1 to ATLO | PREP 1 to ATLO
Data, Knowledge & Integration | Data Integration & Consistency | Inconsistent Data Exchange Across Teams | Programmatic | Data is inconsistent or incompatible across engineering, finance, and risk systems. | - Multiple unlinked tools | - Partner data format variability | PREP 1 to ATLO | PREP 1 to ATLO
Data, Knowledge & Integration | Knowledge Management | Knowledge Loss Through Poor Documentation | Programmatic | Documentation gaps cause loss of design rationale and technical context across phases. | - Weak KM discipline | - Staff turnover | Phase 0 to Phase C | Phase 0 to Phase C
Data, Knowledge & Integration | Knowledge Management | Absence of a Knowledge Management Framework | Governance | Lack of organizational KM policy results in inconsistent retention of critical program information. | - No formal KM process | - Cross-agency documentation expectations | PREP 1 to Phase C | PREP 1 to Phase C
Spacecraft & Payload Technical | Communications Payload | Payload Performance Below Requirement | Performance | Communications payload throughput, EIRP or G/T falls short of requirements because of implementation losses, interference or component performance. | - Optimistic link budgets - Limited end-to-end testbeds | - Spectrum coordination constraints - Propagation conditions | Phase B to MAIT | Phase C to SAIT
Spacecraft & Payload Technical | Antenna & Reflector Deployment | Deployable Antenna Failure | Technical | Deployable reflectors or booms fail to deploy, latch or hold shape, reducing coverage or beam count. | - Mechanism design margins - Limited deployment test cycles | - Launch loads - On-orbit thermal environment | Phase C to LEOP | LEOP & Phase E
Spacecraft & Payload Technical | Thermal Control | Insufficient Heat Rejection Capability | Technical | Thermal control cannot reject payload dissipation in hot cases or maintain survival temperatures in cold cases. | - Dissipation growth - Fixed radiator area | - Seasonal environment - Coating degradation | Phase B to MAIT | Phase C to MAIT
Spacecraft & Payload Technical | Power & Energy | Power Generation or Storage Shortfall | Technical | Solar array or battery capability does not support peak and eclipse loads through end of life. | - Load growth - Battery sizing assumptions | - Radiation degradation - Eclipse seasons | Phase B to MAIT | Phase C to LEOP
Spacecraft & Payload Technical | ADCS & Pointing | Pointing Knowledge or Control Shortfall | Technical | Attitude determination and control do not meet antenna pointing and knowledge budgets. | - Alignment budgets - STOP analysis immaturity | - Thermal distortion - Sensor blinding geometry | Phase B to SAIT | Phase C to LEOP
Spacecraft & Payload Technical | Propulsion | Propellant or Delta-V Budget Shortfall | Technical | Propulsion capability, residuals and dispersions leave insufficient reserve for orbit raising, station-keeping and disposal. | - Mass growth - Isp dispersion | - Launch injection accuracy | Phase B to Phase C | LEOP & Phase E
Spacecraft & Payload Technical | Mass & Performance | Mass Growth Beyond Allocation | Technical | Spacecraft or payload mass exceeds allocations and erodes launch or propellant margins. | - Immature estimates - Late design changes | - Launch vehicle changes | Phase B to MAIT | Phase C to MAIT
Spacecraft & Payload Technical | Data Handling | Onboard Data Storage or Throughput Shortfall | Technical | Onboard storage or processing cannot handle data volumes under contingency cases. | - Data volume growth | - Ground contact outages | Phase B to Phase C | Phase C
Spacecraft & Payload Technical | Radiation & Environment | Space Environment Effects Exceed Design Basis | Technical | Radiation, charging or single-event effects exceed the design basis for electronics and materials. | - Incomplete radiation test data | - Solar cycle - Geomagnetic activity | Phase B to MAIT | Phase C to MAIT
Spacecraft & Payload Technical | Reliability | Early-Life Failures | Technical | Latent defects cause failures during launch, early orbit or commissioning. | - Limited burn-in | - Launch and space environment | LEOP | LEOP & Phase E
Security & Cryptography | Key Management | Key Management System Failure | Security | Key generation, distribution, rotation or recovery fails, interrupting protected service. | - Architecture immaturity - Procedure gaps | - Network outages - Evolving standards | Phase B to Phase E | Phase B to Phase E
Security & Cryptography | Cryptographic Boundary | Cryptographic Boundary Certification or Agility Gap | Security | The cryptographic boundary cannot be certified on time or cannot be updated as standards evolve. | - Incomplete evidence - Limited reprogrammability | - Certifying authority timelines - Standards changes | Phase B to SAIT | Phase C to Phase E
Security & Cryptography | Cybersecurity | Cyber Attack or Interference Against Mission Systems | Security | Cyber intrusion, jamming or interference compromises command, control or user services. | - Configuration drift - Patch management | - Threat actors | SAIT & Phase E | Phase E
Security & Cryptography | Security Accreditation | Delayed Authorization to Operate | Governance | Security assessment and authorization of mission systems is not completed before operations. | - Late documentation | - Accreditor capacity | SAIT | SAIT & LEOP
Security & Cryptography | Supply-Chain Security | Compromised Components in Security Chain | Security | Counterfeit or tampered components enter security-relevant hardware or software. | - Supplier vetting gaps | - Global supply chain threats | Phase C to MAIT | MAIT
Security & Cryptography | Personnel Security | Insider Threat | Security | A cleared insider mishandles sensitive material or keys. | - Two-person integrity gaps | - External coercion | SAIT & Phase E | Phase E
Spectrum & Regulatory | Spectrum Coordination | Spectrum Coordination Not Achieved | Governance | Frequency coordination with other operators is delayed or constrains mission performance. | - Late filing - Limited spectrum expertise | - Prior filings of other operators | Phase A to Phase C | Phase A to Phase E
Spectrum & Regulatory | Orbital Slot & Licensing | Orbital Slot or Licence Compliance Failure | Governance | Regulatory milestones, licences or station-keeping obligations are not met. | - Schedule slips - Process maturity | - Regulatory deadlines | SAIT to Phase E | LEOP & Phase E
Spectrum & Regulatory | Space Debris Compliance | End-of-Life Disposal Non-Compliance | Technical | The mission cannot demonstrate compliant disposal and passivation. | - Gauging uncertainty - Design omissions | - Sustainability regulations | Phase E to Phase F | Phase F
Launch & Early Orbit | Launch Services | Launch Failure or Delay | Cost | Launch failure, weather or range delays result in loss of hardware or schedule slips. | - Single-spacecraft launches | - Vehicle reliability - Weather | SAIT & LEOP | SAIT & LEOP
Launch & Early Orbit | Launch Interface | Launch Vehicle Interface Changes | Technical | Launch vehicle interface changes after design maturity force spacecraft modifications. | - Late interface definition | - Provider requirements | Phase C to SAIT | Phase C to SAIT
Launch & Early Orbit | Orbit Raising | Orbit Raising Performance Shortfall | Technical | Injection errors or transfer performance consume reserves or delay arrival on station. | - Thin reserves | - Injection accuracy | LEOP | LEOP
Launch & Early Orbit | Commissioning | Commissioning Overrun | Schedule | In-orbit testing takes longer than planned. | - Concurrent commissioning | - Link conditions | LEOP | LEOP & Phase E
Launch & Early Orbit | Insurance & Liability | Insurance Coverage Gap | Cost | Insurance cost or coverage is unfavourable at launch. | - Late strategy | - Insurance market | SAIT | SAIT
Ground Segment & Operations | Gateways | Gateway Readiness or Performance Shortfall | Technical | Gateway sites are late or do not achieve performance and availability targets. | - Site selection delays | - Contractor performance - Propagation | Phase C to SAIT | SAIT & Phase E
Ground Segment & Operations | Terrestrial Backhaul | Terrestrial Network Capacity Shortfall | Technical | Terrestrial backhaul capacity or diversity is insufficient. | - Network design | - Carrier constraints | Phase C to Phase E | SAIT & Phase E
Ground Segment & Operations | Ground Software | Ground Software Defects | Technical | Ground software defects, including common-mode failures, disrupt operations. | - Single code base - Limited IV&V | - Third-party software | Phase C to Phase E | SAIT & Phase E
Ground Segment & Operations | Service Availability | Service Availability Below Target | Performance | Delivered service availability falls short of requirements. | - Redundancy choices | - Propagation - Outages | SAIT & Phase E | Phase E
Ground Segment & Operations | Mission Operations | Operations Staffing and Workload Growth | Operational | Operations require more staff or automation than planned. | - Staffing model | - Anomaly workload | LEOP & Phase E | Phase E
Ground Segment & Operations | Archive & Audit | Archive Capacity Shortfall | Technical | Archive capacity or retention does not meet needs. | - Sizing assumptions | - Policy changes | SAIT & Phase E | Phase E
Ground Segment & Operations | Mission Planning | Mission Planning Capability Shortfall | Programmatic | Planning tools cannot handle operational demand. | - Tool maturity | - Demand variability | Phase C to Phase E | SAIT & Phase E
Ground Segment & Operations | Ground Infrastructure | Ground Facility Disruption | Schedule | A ground facility becomes unavailable. | - Facility resilience | - Natural events | Phase E | Phase E
End of Life | Disposal & Decommissioning | Incomplete Disposal or Closeout | Technical | Disposal manoeuvres, passivation or closeout activities cannot be completed as planned. | - Reserve management - Late planning | - Regulatory expectations | Phase E to Phase F | Phase F