## Cover Page
CSA-FIN-RD-0545
Version Draft 1.0
2026-08-17
Cost Analysis Data Requirement (CADRe)
CADRe Part C - Essential Programmatic Inputs
WildfireSat
Prepared by Mireille Bedirian
| Reviewed by [Name] | Name

## 1 - Change History
` Table of Contents
2. Version Control - Baseline Tracker
Purpose: | To track the baseline across time
hold the major and minor releases of the baseline
| Change history and associated files that contain the relevant data |  |  |  |  | Reserved
| File Number | Date | File Version | Author | Changes | Parent Baseline Name | Baseline ID
[6 empty] | WFS @ PREP1 | 1
[6 empty] | WFS @ KDP-0 | 2
[6 empty] | WFS @ MDR#2 | 3
[6 empty] | WFS @ PREP2 | 4
[6 empty] | WFS @ KDP-A | 5
[6 empty] | WFS @ KDP-B | 6
[6 empty] | WFS @ PDR | 7
| CSA-FIN-RD-0545 | 2026-08-17 | Draft 1 | SS | Initial document ahead of Phase B | WFS @ CDR | 8 | <<--- We are here now
[6 empty] | WFS @ SIR | 9
[6 empty] | WFS @ Launch (as flown) | 10
[6 empty] | WFS @ CR | 11
[6 empty] | WFS @ KDP-X | 12
[6 empty] | WFS @ end of life | 13

## 4d - CBS in JS format (hidden)
` Table of Contents
4d. CBS (as self referencing list) for use as a javascript array
Why we we asking:
this page is auto-generated and used for drawing it out
Self referencing list for dtree
UID | Parent ID | Level | Node Name | CBS Code | Depth | Icon | Notes | Javascript Code | Depth
1 | -1 | 1 | Space Missions |  | Taxon 1 | Box.png |  | datatable[0] = new Array("1","-1","Space Missions","1","Box.png"); | Taxon 1
2 | 1 | 2 | EO SAR Missions |  | Taxon 2 | EO.png |  | datatable[1] = new Array("2","1","EO SAR Missions","2","EO.png"); | Taxon 2
3 | 2 | 3 | Radarsat Portfolio |  | Phylum | Pouch.png |  | datatable[2] = new Array("3","2","Radarsat Portfolio","3","Pouch.png"); | Phylum
4 | 0 | 4 | Radarsat 1 |  | Mission | Satellite.png |  | datatable[3] = new Array("4","0","Radarsat 1","4","Satellite.png"); | Mission
5 | 0 | 4 | Radarsat 2 |  | Mission | Satellite.png |  | datatable[4] = new Array("5","0","Radarsat 2","4","Satellite.png"); | Design Reference Mission
6 | 0 | 4 | Radarsat Constellation Mission |  | Mission | Satellite.png |  | datatable[5] = new Array("6","0","Radarsat Constellation Mission","4","Satellite.png"); | Segment
7 | 0 | 4 | Radarsat+ Replenishment | 1 | Mission | Satellite.png |  | datatable[6] = new Array("7","0","Radarsat+ Replenishment","4","Satellite.png"); | System of Systems
8 | 0 | 4 | Radarsat+ Next Generation |  | Mission | Satellite.png |  | datatable[7] = new Array("8","0","Radarsat+ Next Generation","4","Satellite.png"); | System
9 | 2 | 5 | Analysis Scenario 1: RCM Proxy |  | Design Reference Mission | Scenario.png |  | datatable[8] = new Array("9","2","Analysis Scenario 1: RCM Proxy","5","Scenario.png"); | Subsystem
10 | 2 | 5 | Analysis Scenario 2: RCM+ |  | Design Reference Mission | Scenario.png |  | datatable[9] = new Array("10","2","Analysis Scenario 2: RCM+","5","Scenario.png"); | Assembly
11 | 2 | 5 | Analysis Scenario 3: Airbus concept |  | Design Reference Mission | Scenario.png |  | datatable[10] = new Array("11","2","Analysis Scenario 3: Airbus concept","5","Scenario.png"); | Component
12 | 2 | 5 | Analysis Scenario 4: MDA Chorus Data Buy |  | Design Reference Mission | Scenario.png |  | datatable[11] = new Array("12","2","Analysis Scenario 4: MDA Chorus Data Buy","5","Scenario.png");
13 | 2 | 5 | Analysis Scenario 5: MDA Chorus+ |  | Design Reference Mission | Scenario.png |  | datatable[12] = new Array("13","2","Analysis Scenario 5: MDA Chorus+","5","Scenario.png");
14 | 2 | 5 | Analysis Scenario 6: Airbus Sentinel 2 |  | Design Reference Mission | Scenario.png |  | datatable[13] = new Array("14","2","Analysis Scenario 6: Airbus Sentinel 2","5","Scenario.png");
15 | 8 | 6 | Government Overhead and Oversight | 1.1 | Segment | Government.png | This WBS includes all CSA Oversight, OGD salaries, and basic overhead for the care and maintenance of CSA staff | datatable[14] = new Array("15","8","Government Overhead and Oversight","6","Government.png");
16 | 8 | 6 | Space Segment | 1.2 | Segment | Satellite.png | The Space Segment includes things we launch into space | datatable[15] = new Array("16","8","Space Segment","6","Satellite.png");
17 | 8 | 6 | Launch Segment | 1.3 | Segment | Rocket.png | The launch segment includes the launch vehicle and seom support services | datatable[16] = new Array("17","8","Launch Segment","6","Rocket.png");
18 | 8 | 6 | Ground Segment | 1.4 | Segment | Facility.png | The ground segment includes the planning desgin and development of the GS, but not the Ops | datatable[17] = new Array("18","8","Ground Segment","6","Facility.png");
19 | 8 | 6 | Ops Segment | 1.5 | Segment | Ops.png | Ops includes SatOps, Mission Ops, Science Ops - typically contracts | datatable[18] = new Array("19","8","Ops Segment","6","Ops.png");
20 | 8 | 6 | Science Segment | 1.6 | Segment | Science.png | Typically G&C | datatable[19] = new Array("20","8","Science Segment","6","Science.png");
21 | 10 | 7 | Gov't Oversight (Salaries and EBP) | 1.1.1 | System of Systems | Government.png |  | datatable[20] = new Array("21","10","Gov't Oversight (Salaries and EBP)","7","Government.png");
22 | 10 | 7 | Government Overhead | 1.1.2 | System of Systems | Government.png |  | datatable[21] = new Array("22","10","Government Overhead","7","Government.png");
23 | 21 | 8 | CSA Oversight | 1.1.1.1 | System | Government.png |  | datatable[22] = new Array("23","21","CSA Oversight","8","Government.png");
24 | 21 | 8 | OGD Oversight | 1.1.1.2 | System | Government.png |  | datatable[23] = new Array("24","21","OGD Oversight","8","Government.png");
25 | 23 | 9 | CSA Project Team | 1.1.1.1.1 | Subsystem | Government.png | This CBS contains all salaries associated with the RAM of the Project team | datatable[24] = new Array("25","23","CSA Project Team","9","Government.png");
26 | 23 | 9 | CSA Internal Services | 1.1.1.1.2 | Subsystem | Government.png | This CBS contains all salaries associated with CSA internal services (finance, HR, audit, eval, policy, Executives, IM, IT, contracts, shipping, etc) | datatable[25] = new Array("26","23","CSA Internal Services","9","Government.png");
27 | 24 | 9 | OGD Internal Services by MOU | 1.1.1.2.1 | Subsystem | Government.png |  | datatable[26] = new Array("27","24","OGD Internal Services by MOU","9","Government.png");
28 | 24 | 9 | OGD User Departments by MOU (RAM portion) | 1.1.1.2.2 | Subsystem | Government.png |  | datatable[27] = new Array("28","24","OGD User Departments by MOU (RAM portion)","9","Government.png");
29 | 21 | 10 | Shared Services | 1.1.1.2.1.1 | Assembly | Government.png |  | datatable[28] = new Array("29","21","Shared Services","10","Government.png");
30 | 21 | 10 | SPAC | 1.1.1.2.1.2 | Assembly | Government.png |  | datatable[29] = new Array("30","21","SPAC","10","Government.png");
31 | 21 | 10 | Justice Canada | 1.1.1.2.1.3 | Assembly | Government.png |  | datatable[30] = new Array("31","21","Justice Canada","10","Government.png");
32 | 23 | 10 | ECCC | 1.1.1.2.2.1 | Assembly | Government.png |  | datatable[31] = new Array("32","23","ECCC","10","Government.png");
33 | 23 | 10 | NRCAN | 1.1.1.2.2.2 | Assembly | Government.png |  | datatable[32] = new Array("33","23","NRCAN","10","Government.png");
34 | 23 | 10 | DND | 1.1.1.2.2.3 | Assembly | Government.png |  | datatable[33] = new Array("34","23","DND","10","Government.png");
35 | 25 | 11 | RAM per Person per FY and Phase | 1.1.1.1.1.1 | Component | Government.png |  | datatable[34] = new Array("35","25","RAM per Person per FY and Phase","11","Government.png");
36 | 25 | 11 | PSPC Procurement Services | 1.1.1.2.1.2.1 | Component | Government.png |  | datatable[35] = new Array("36","25","PSPC Procurement Services","11","Government.png");
37 | 25 | 11 | PSPC Fairness Monitor | 1.1.1.2.1.2.2 | Component | Government.png |  | datatable[36] = new Array("37","25","PSPC Fairness Monitor","11","Government.png");
38 | 31 | 11 | Legal Services | 1.1.1.2.1.3.1 | Component | Government.png |  | datatable[37] = new Array("38","31","Legal Services","11","Government.png");
39 | 22 | 8 | CSA Overhead | 1.1.2.1 | System | Government.png |  | datatable[38] = new Array("39","22","CSA Overhead","8","Government.png");
40 | 34 | 9 | IS Management Overhead | 1.1.2.1.1 | Subsystem | Government.png |  | datatable[39] = new Array("40","34","IS Management Overhead ","9","Government.png");
41 | 34 | 9 | Management Consulting Services | 1.1.2.1.2 | Subsystem | Government.png |  | datatable[40] = new Array("41","34","Management Consulting Services","9","Government.png");
42 | 34 | 9 | Temporary Help | 1.1.2.1.3 | Subsystem | Government.png |  | datatable[41] = new Array("42","34","Temporary Help","9","Government.png");
43 | 34 | 9 | Students | 1.1.2.1.4 | Subsystem | Government.png | This CBS includes any students, FSWEP or PDF assisint Csa project team | datatable[42] = new Array("43","34","Students","9","Government.png");
44 | 34 | 9 | Government Travel & Living | 1.1.2.1.5 | Subsystem | Government.png | This CBS includes any government Travel and Living expenses | datatable[43] = new Array("44","34","Government Travel & Living","9","Government.png");
45 | 34 | 9 | Translation | 1.1.2.1.6 | Subsystem | Government.png | This CBS includes any translation costs | datatable[44] = new Array("45","34","Translation","9","Government.png");
46 | 34 | 9 | Shipping | 1.1.2.1.7 | Subsystem | Government.png | This CBs includes any shipping cost, but not shipping flight HW which is under space segment | datatable[45] = new Array("46","34","Shipping","9","Government.png");
47 | 34 | 9 | Software Licenses | 1.1.2.1.8 | Subsystem | Government.png | This CBS includes any COTs SW not flight Sw or ground SW | datatable[46] = new Array("47","34","Software Licenses","9","Government.png");
48 | 34 | 9 | Public Outreach and STEM initiatives | 1.1.2.1.9 | Subsystem | Government.png | This CBS includes any public relations and STEM | datatable[47] = new Array("48","34","Public Outreach and STEM initiatives","9","Government.png");
49 | 34 | 9 | Other Overhead (Specify) | 1.1.2.1.10 | Subsystem | Government.png | This CBS includes any other misc fees | datatable[48] = new Array("49","34","Other Overhead (Specify)","9","Government.png");
50 | 36 | 10 | Consultants - Industrial Space Experts | 1.1.2.1.2.1 | Assembly | Government.png |  | datatable[49] = new Array("50","36","Consultants - Industrial Space Experts","10","Government.png");
51 | 36 | 10 | Consultants - Academia | 1.1.2.1.2.2 | Assembly | Government.png |  | datatable[50] = new Array("51","36","Consultants - Academia","10","Government.png");
52 | 36 | 10 | Consultants - Non-Space Experts | 1.1.2.1.2.3 | Assembly | Government.png |  | datatable[51] = new Array("52","36","Consultants - Non-Space Experts","10","Government.png");
53 | 12 | 6 | Mission SEITPM and Support Equipment |  | Segment | SEITPM.png |  | datatable[52] = new Array("53","12","Mission SEITPM and Support Equipment","6","SEITPM.png");
54 | 48 | 7 | Project Management |  | System of Systems | SEITPM.png |  | datatable[53] = new Array("54","48","Project Management","7","SEITPM.png");
55 | 48 | 7 | Systems Engineering |  | System of Systems | SEITPM.png |  | datatable[54] = new Array("55","48","Systems Engineering","7","SEITPM.png");
56 | 48 | 7 | Mission Assurance |  | System of Systems | SEITPM.png |  | datatable[55] = new Array("56","48","Mission Assurance","7","SEITPM.png");
57 | 48 | 7 | Assembly, Integration and Testing |  | System of Systems | SEITPM.png |  | datatable[56] = new Array("57","48","Assembly, Integration and Testing","7","SEITPM.png");
58 | 48 | 7 | Support Equipment |  | System of Systems | SEITPM.png |  | datatable[57] = new Array("58","48","Support Equipment","7","SEITPM.png");
59 | 16 | 7 | Space Vehicle 1 … i |  | System of Systems | Satellite.png |  | datatable[58] = new Array("59","16","Space Vehicle 1 … i","7","Satellite.png");
60 | 59 | 8 | Spacecraft SEITPM and Support Equipment |  | System | SEITPM.png |  | datatable[59] = new Array("60","59","Spacecraft SEITPM and Support Equipment","8","SEITPM.png");
61 | 55 | 9 | Project Management |  | Subsystem | SEITPM.png |  | datatable[60] = new Array("61","55","Project Management","9","SEITPM.png");
62 | 55 | 9 | Systems Engineering |  | Subsystem | SEITPM.png |  | datatable[61] = new Array("62","55","Systems Engineering","9","SEITPM.png");
63 | 55 | 9 | Mission Assurance |  | Subsystem | SEITPM.png |  | datatable[62] = new Array("63","55","Mission Assurance","9","SEITPM.png");
64 | 55 | 9 | Assembly, Integration and Testing |  | Subsystem | SEITPM.png |  | datatable[63] = new Array("64","55","Assembly, Integration and Testing","9","SEITPM.png");
65 | 55 | 9 | Support Equipment |  | Subsystem | SEITPM.png |  | datatable[64] = new Array("65","55","Support Equipment","9","SEITPM.png");
66 | 59 | 8 | Bus/Platform |  | System | Widget.png |  | datatable[65] = new Array("66","59","Bus/Platform","8","Widget.png");
67 | 66 | 9 | Platform SEITPM and Support Equipment |  | Subsystem | SEITPM.png |  | datatable[66] = new Array("67","66","Platform SEITPM and Support Equipment","9","SEITPM.png");
68 | 62 | 10 | Project Management |  | Assembly | SEITPM.png |  | datatable[67] = new Array("68","62","Project Management","10","SEITPM.png");
69 | 62 | 10 | Systems Engineering |  | Assembly | SEITPM.png |  | datatable[68] = new Array("69","62","Systems Engineering","10","SEITPM.png");
70 | 62 | 10 | Mission Assurance |  | Assembly | SEITPM.png |  | datatable[69] = new Array("70","62","Mission Assurance","10","SEITPM.png");
71 | 62 | 10 | Assembly, Integration and Testing |  | Assembly | SEITPM.png |  | datatable[70] = new Array("71","62","Assembly, Integration and Testing","10","SEITPM.png");
72 | 62 | 10 | Support Equipment |  | Assembly | SEITPM.png |  | datatable[71] = new Array("72","62","Support Equipment","10","SEITPM.png");
73 | 61 | 9 | Structures and Mechanisms Subsystem (SMS) |  | Subsystem | Widget.png |  | datatable[72] = new Array("73","61","Structures and Mechanisms Subsystem (SMS)","9","Widget.png");
74 | 68 | 10 | Structures and Mechanisms Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[73] = new Array("74","68","Structures and Mechanisms Subsystem SEITPM","10","SEITPM.png");
75 | 69 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[74] = new Array("75","69","Project Management","11","SEITPM.png");
76 | 69 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[75] = new Array("76","69","Systems Engineering","11","SEITPM.png");
77 | 69 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[76] = new Array("77","69","Mission Assurance","11","SEITPM.png");
78 | 69 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[77] = new Array("78","69","Assembly, Integration and Testing","11","SEITPM.png");
79 | 69 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[78] = new Array("79","69","Support Equipment","11","SEITPM.png");
80 | 68 | 10 | Primary Structures |  | Assembly | Widget.png |  | datatable[79] = new Array("80","68","Primary Structures","10","Widget.png");
81 | 75 | 11 | Load Carrying Shell/Truss |  | Component | Widget.png |  | datatable[80] = new Array("81","75","Load Carrying Shell/Truss","11","Widget.png");
82 | 75 | 11 | Equipment Compartments |  | Component | Widget.png |  | datatable[81] = new Array("82","75","Equipment Compartments","11","Widget.png");
83 | 75 | 11 | Booms |  | Component | Widget.png |  | datatable[82] = new Array("83","75","Booms","11","Widget.png");
84 | 75 | 11 | Adapters |  | Component | Widget.png |  | datatable[83] = new Array("84","75","Adapters","11","Widget.png");
85 | 75 | 11 | Other Structures (Specify) |  | Component | Widget.png |  | datatable[84] = new Array("85","75","Other Structures (Specify)","11","Widget.png");
86 | 68 | 10 | Secondary Structures |  | Assembly | Widget.png |  | datatable[85] = new Array("86","68","Secondary Structures","10","Widget.png");
87 | 81 | 11 | Equipment (Instrument) Mountings |  | Component | Widget.png |  | datatable[86] = new Array("87","81","Equipment (Instrument) Mountings","11","Widget.png");
88 | 81 | 11 | Ballast Mass |  | Component | Widget.png |  | datatable[87] = new Array("88","81","Ballast Mass","11","Widget.png");
89 | 81 | 11 | Other Secondary Structures (Specify) |  | Component | Widget.png |  | datatable[88] = new Array("89","81","Other Secondary Structures (Specify)","11","Widget.png");
90 | 68 | 10 | Mechanisms and Pyrotechnics |  | Assembly | Widget.png |  | datatable[89] = new Array("90","68","Mechanisms and Pyrotechnics","10","Widget.png");
91 | 85 | 11 | Positioning |  | Component | Widget.png |  | datatable[90] = new Array("91","85","Positioning","11","Widget.png");
92 | 85 | 11 | Deployment and Storage Equipment |  | Component | Widget.png |  | datatable[91] = new Array("92","85","Deployment and Storage Equipment","11","Widget.png");
93 | 85 | 11 | Docking Mechanisms |  | Component | Widget.png |  | datatable[92] = new Array("93","85","Docking Mechanisms","11","Widget.png");
94 | 85 | 11 | Other Mechanisms (Specify) |  | Component | Widget.png |  | datatable[93] = new Array("94","85","Other Mechanisms (Specify)","11","Widget.png");
95 | 85 | 11 | Pyrotechnics |  | Component | Widget.png |  | datatable[94] = new Array("95","85","Pyrotechnics","11","Widget.png");
96 | 68 | 10 | SMS Other (Specify) |  | Assembly | Widget.png |  | datatable[95] = new Array("96","68","SMS Other (Specify)","10","Widget.png");
97 | 61 | 9 | Thermal Control Subsystem (TCS) |  | Subsystem | Widget.png |  | datatable[96] = new Array("97","61","Thermal Control Subsystem (TCS)","9","Widget.png");
98 | 92 | 10 | Thermal Control Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[97] = new Array("98","92","Thermal Control Subsystem SEITPM","10","SEITPM.png");
99 | 93 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[98] = new Array("99","93","Project Management","11","SEITPM.png");
100 | 93 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[99] = new Array("100","93","Systems Engineering","11","SEITPM.png");
101 | 93 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[100] = new Array("101","93","Mission Assurance","11","SEITPM.png");
102 | 93 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[101] = new Array("102","93","Assembly, Integration and Testing","11","SEITPM.png");
103 | 93 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[102] = new Array("103","93","Support Equipment","11","SEITPM.png");
104 | 92 | 10 | Active Devices |  | Assembly | Widget.png |  | datatable[103] = new Array("104","92","Active Devices","10","Widget.png");
105 | 99 | 11 | Cryogenic Devices |  | Component | Widget.png |  | datatable[104] = new Array("105","99","Cryogenic Devices","11","Widget.png");
106 | 99 | 11 | Liquid Loops |  | Component | Widget.png |  | datatable[105] = new Array("106","99","Liquid Loops","11","Widget.png");
107 | 99 | 11 | Electric Coolers |  | Component | Widget.png |  | datatable[106] = new Array("107","99","Electric Coolers","11","Widget.png");
108 | 99 | 11 | Heaters, Thermistors, and Thermostats |  | Component | Widget.png |  | datatable[107] = new Array("108","99","Heaters, Thermistors, and Thermostats","11","Widget.png");
109 | 99 | 11 | Other Active Devices (Specify) |  | Component | Widget.png |  | datatable[108] = new Array("109","99","Other Active Devices (Specify)","11","Widget.png");
110 | 92 | 10 | Passive Devices |  | Assembly | Widget.png |  | datatable[109] = new Array("110","92","Passive Devices","10","Widget.png");
111 | 105 | 11 | Radiator Panel/Fins |  | Component | Widget.png |  | datatable[110] = new Array("111","105","Radiator Panel/Fins","11","Widget.png");
112 | 105 | 11 | Coatings |  | Component | Widget.png |  | datatable[111] = new Array("112","105","Coatings","11","Widget.png");
113 | 105 | 11 | Heat Pipes |  | Component | Widget.png |  | datatable[112] = new Array("113","105","Heat Pipes","11","Widget.png");
114 | 105 | 11 | Insulation |  | Component | Widget.png |  | datatable[113] = new Array("114","105","Insulation","11","Widget.png");
115 | 105 | 11 | Conductive Structures |  | Component | Widget.png |  | datatable[114] = new Array("115","105","Conductive Structures","11","Widget.png");
116 | 105 | 11 | Heat Activated Structures |  | Component | Widget.png |  | datatable[115] = new Array("116","105","Heat Activated Structures","11","Widget.png");
117 | 105 | 11 | Sun Shields |  | Component | Widget.png |  | datatable[116] = new Array("117","105","Sun Shields","11","Widget.png");
118 | 105 | 11 | Second Surface Mirrors |  | Component | Widget.png |  | datatable[117] = new Array("118","105","Second Surface Mirrors","11","Widget.png");
119 | 105 | 11 | Shutters and Louvers |  | Component | Widget.png |  | datatable[118] = new Array("119","105","Shutters and Louvers","11","Widget.png");
120 | 105 | 11 | Other Passive Devices (Specify) |  | Component | Widget.png |  | datatable[119] = new Array("120","105","Other Passive Devices (Specify)","11","Widget.png");
121 | 92 | 10 | TCS Other (Specify) |  | Assembly | Widget.png |  | datatable[120] = new Array("121","92","TCS Other (Specify)","10","Widget.png");
122 | 61 | 9 | Electric Power Subsystem (EPS) |  | Subsystem | Widget.png |  | datatable[121] = new Array("122","61","Electric Power Subsystem (EPS)","9","Widget.png");
123 | 117 | 10 | Electric Power Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[122] = new Array("123","117","Electric Power Subsystem SEITPM","10","SEITPM.png");
124 | 118 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[123] = new Array("124","118","Project Management","11","SEITPM.png");
125 | 118 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[124] = new Array("125","118","Systems Engineering","11","SEITPM.png");
126 | 118 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[125] = new Array("126","118","Mission Assurance","11","SEITPM.png");
127 | 118 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[126] = new Array("127","118","Assembly, Integration and Testing","11","SEITPM.png");
128 | 118 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[127] = new Array("128","118","Support Equipment","11","SEITPM.png");
129 | 117 | 10 | Electrical Power Generation |  | Assembly | Widget.png |  | datatable[128] = new Array("129","117","Electrical Power Generation","10","Widget.png");
130 | 124 | 11 | Solar Array |  | Component | Widget.png |  | datatable[129] = new Array("130","124","Solar Array","11","Widget.png");
131 | 124 | 11 | Solar Array Positioner |  | Component | Widget.png |  | datatable[130] = new Array("131","124","Solar Array Positioner","11","Widget.png");
132 | 124 | 11 | Radioisotope Thermionic Generator |  | Component | Widget.png |  | datatable[131] = new Array("132","124","Radioisotope Thermionic Generator","11","Widget.png");
133 | 124 | 11 | Chemical (Fuel Cells) |  | Component | Widget.png |  | datatable[132] = new Array("133","124","Chemical (Fuel Cells)","11","Widget.png");
134 | 124 | 11 | Auxiliary Power Units |  | Component | Widget.png |  | datatable[133] = new Array("134","124","Auxiliary Power Units","11","Widget.png");
135 | 124 | 11 | Other Power Sources |  | Component | Widget.png |  | datatable[134] = new Array("135","124","Other Power Sources","11","Widget.png");
136 | 117 | 10 | Electrical Power Conditioning |  | Assembly | Widget.png |  | datatable[135] = new Array("136","117","Electrical Power Conditioning","10","Widget.png");
137 | 131 | 11 | Power Control Electronics |  | Component | Widget.png |  | datatable[136] = new Array("137","131","Power Control Electronics","11","Widget.png");
138 | 131 | 11 | Power Conversion Electronics |  | Component | Widget.png |  | datatable[137] = new Array("138","131","Power Conversion Electronics","11","Widget.png");
139 | 131 | 11 | Power Dissipation Devices |  | Component | Widget.png |  | datatable[138] = new Array("139","131","Power Dissipation Devices","11","Widget.png");
140 | 131 | 11 | Power Distribution Electronics |  | Component | Widget.png |  | datatable[139] = new Array("140","131","Power Distribution Electronics","11","Widget.png");
141 | 131 | 11 | Power Switching Electronics |  | Component | Widget.png |  | datatable[140] = new Array("141","131","Power Switching Electronics","11","Widget.png");
142 | 131 | 11 | Power Regulation Electronics |  | Component | Widget.png |  | datatable[141] = new Array("142","131","Power Regulation Electronics","11","Widget.png");
143 | 131 | 11 | Other Power Conditioning Devices (Specify) |  | Component | Widget.png |  | datatable[142] = new Array("143","131","Other Power Conditioning Devices (Specify)","11","Widget.png");
144 | 117 | 10 | Electrical Power Storage |  | Assembly | Widget.png |  | datatable[143] = new Array("144","117","Electrical Power Storage","10","Widget.png");
145 | 139 | 11 | Rechargeable Batteries |  | Component | Widget.png |  | datatable[144] = new Array("145","139","Rechargeable Batteries","11","Widget.png");
146 | 139 | 11 | Charge Control Electronics |  | Component | Widget.png |  | datatable[145] = new Array("146","139","Charge Control Electronics","11","Widget.png");
147 | 139 | 11 | Other Electrical Power Storage Devices (Specify) |  | Component | Widget.png |  | datatable[146] = new Array("147","139","Other Electrical Power Storage Devices (Specify)","11","Widget.png");
148 | 117 | 10 | Harnesses and Cables |  | Assembly | Widget.png |  | datatable[147] = new Array("148","117","Harnesses and Cables","10","Widget.png");
149 | 117 | 10 | EPS Other (Specify) |  | Assembly | Widget.png |  | datatable[148] = new Array("149","117","EPS Other (Specify)","10","Widget.png");
150 | 61 | 9 | Attitude Control Subsystem (ACS) |  | Subsystem | Widget.png |  | datatable[149] = new Array("150","61","Attitude Control Subsystem (ACS)","9","Widget.png");
151 | 145 | 10 | Attitude Control Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[150] = new Array("151","145","Attitude Control Subsystem SEITPM","10","SEITPM.png");
152 | 146 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[151] = new Array("152","146","Project Management","11","SEITPM.png");
153 | 146 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[152] = new Array("153","146","Systems Engineering","11","SEITPM.png");
154 | 146 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[153] = new Array("154","146","Mission Assurance","11","SEITPM.png");
155 | 146 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[154] = new Array("155","146","Assembly, Integration and Testing","11","SEITPM.png");
156 | 146 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[155] = new Array("156","146","Support Equipment","11","SEITPM.png");
157 | 145 | 10 | Attitude Determination |  | Assembly | Widget.png |  | datatable[156] = new Array("157","145","Attitude Determination","10","Widget.png");
158 | 152 | 11 | Earth (Horizon) Sensors |  | Component | Widget.png |  | datatable[157] = new Array("158","152","Earth (Horizon) Sensors","11","Widget.png");
159 | 152 | 11 | Sun Sensors |  | Component | Widget.png |  | datatable[158] = new Array("159","152","Sun Sensors","11","Widget.png");
160 | 152 | 11 | Star Tracker/Sensors |  | Component | Widget.png |  | datatable[159] = new Array("160","152","Star Tracker/Sensors","11","Widget.png");
161 | 152 | 11 | Global Positioning System (GPS) Receiver |  | Component | Widget.png |  | datatable[160] = new Array("161","152","Global Positioning System (GPS) Receiver","11","Widget.png");
162 | 152 | 11 | Imagers |  | Component | Widget.png |  | datatable[161] = new Array("162","152","Imagers","11","Widget.png");
163 | 152 | 11 | Magnetometers |  | Component | Widget.png |  | datatable[162] = new Array("163","152","Magnetometers","11","Widget.png");
164 | 152 | 11 | Altimeters |  | Component | Widget.png |  | datatable[163] = new Array("164","152","Altimeters","11","Widget.png");
165 | 152 | 11 | Inertial Reference Unit (IRU)/Inertial Measurement Unit (IMU) |  | Component | Widget.png |  | datatable[164] = new Array("165","152","Inertial Reference Unit (IRU)/Inertial Measurement Unit (IMU)","11","Widget.png");
166 | 152 | 11 | Radar |  | Component | Widget.png |  | datatable[165] = new Array("166","152","Radar","11","Widget.png");
167 | 152 | 11 | Rate Gyros |  | Component | Widget.png |  | datatable[166] = new Array("167","152","Rate Gyros","11","Widget.png");
168 | 152 | 11 | Accelerometers |  | Component | Widget.png |  | datatable[167] = new Array("168","152","Accelerometers","11","Widget.png");
169 | 152 | 11 | Bearing and Power Transfer Assembly |  | Component | Widget.png |  | datatable[168] = new Array("169","152","Bearing and Power Transfer Assembly","11","Widget.png");
170 | 152 | 11 | Other Attitude Determination Devices (Specify) |  | Component | Widget.png |  | datatable[169] = new Array("170","152","Other Attitude Determination Devices (Specify)","11","Widget.png");
171 | 145 | 10 | Attitude Control |  | Assembly | Widget.png |  | datatable[170] = new Array("171","145","Attitude Control","10","Widget.png");
172 | 166 | 11 | Reaction Wheel |  | Component | Widget.png |  | datatable[171] = new Array("172","166","Reaction Wheel","11","Widget.png");
173 | 166 | 11 | Momentum Wheel |  | Component | Widget.png |  | datatable[172] = new Array("173","166","Momentum Wheel","11","Widget.png");
174 | 166 | 11 | Control Moment Gyro |  | Component | Widget.png |  | datatable[173] = new Array("174","166","Control Moment Gyro","11","Widget.png");
175 | 166 | 11 | Other Energy Storage Devices |  | Component | Widget.png |  | datatable[174] = new Array("175","166","Other Energy Storage Devices","11","Widget.png");
176 | 166 | 11 | Magnetic Control Devices |  | Component | Widget.png |  | datatable[175] = new Array("176","166","Magnetic Control Devices","11","Widget.png");
177 | 166 | 11 | Spin Control Devices |  | Component | Widget.png |  | datatable[176] = new Array("177","166","Spin Control Devices","11","Widget.png");
178 | 166 | 11 | Control Electronics |  | Component | Widget.png |  | datatable[177] = new Array("178","166","Control Electronics","11","Widget.png");
179 | 166 | 11 | Other Attitude Control Devices (Specify) |  | Component | Widget.png |  | datatable[178] = new Array("179","166","Other Attitude Control Devices (Specify)","11","Widget.png");
180 | 145 | 10 | ACS Other (Specify) |  | Assembly | Widget.png |  | datatable[179] = new Array("180","145","ACS Other (Specify)","10","Widget.png");
181 | 61 | 9 | Propulsion Subsystem |  | Subsystem | Widget.png |  | datatable[180] = new Array("181","61","Propulsion Subsystem","9","Widget.png");
182 | 176 | 10 | Propulsion Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[181] = new Array("182","176","Propulsion Subsystem SEITPM","10","SEITPM.png");
183 | 177 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[182] = new Array("183","177","Project Management","11","SEITPM.png");
184 | 177 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[183] = new Array("184","177","Systems Engineering","11","SEITPM.png");
185 | 177 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[184] = new Array("185","177","Mission Assurance","11","SEITPM.png");
186 | 177 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[185] = new Array("186","177","Assembly, Integration and Testing","11","SEITPM.png");
187 | 177 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[186] = new Array("187","177","Support Equipment","11","SEITPM.png");
188 | 176 | 10 | Tanks |  | Assembly | Widget.png |  | datatable[187] = new Array("188","176","Tanks","10","Widget.png");
189 | 183 | 11 | Oxidizer Tanks |  | Component | Widget.png |  | datatable[188] = new Array("189","183","Oxidizer Tanks","11","Widget.png");
190 | 183 | 11 | Fuel Tanks |  | Component | Widget.png |  | datatable[189] = new Array("190","183","Fuel Tanks","11","Widget.png");
191 | 183 | 11 | Propellant Tanks |  | Component | Widget.png |  | datatable[190] = new Array("191","183","Propellant Tanks","11","Widget.png");
192 | 183 | 11 | Pressurance Tanks |  | Component | Widget.png |  | datatable[191] = new Array("192","183","Pressurance Tanks","11","Widget.png");
193 | 183 | 11 | Plumbing |  | Component | Widget.png |  | datatable[192] = new Array("193","183","Plumbing","11","Widget.png");
194 | 183 | 11 | Other Tanks (Specify) |  | Component | Widget.png |  | datatable[193] = new Array("194","183","Other Tanks (Specify)","11","Widget.png");
195 | 176 | 10 | Maneuvering Thrusters |  | Assembly | Widget.png |  | datatable[194] = new Array("195","176","Maneuvering Thrusters","10","Widget.png");
196 | 190 | 11 | Bipropellant |  | Component | Widget.png |  | datatable[195] = new Array("196","190","Bipropellant","11","Widget.png");
197 | 190 | 11 | Monopropellant |  | Component | Widget.png |  | datatable[196] = new Array("197","190","Monopropellant","11","Widget.png");
198 | 190 | 11 | Solar Electric |  | Component | Widget.png |  | datatable[197] = new Array("198","190","Solar Electric","11","Widget.png");
199 | 190 | 11 | Ion |  | Component | Widget.png |  | datatable[198] = new Array("199","190","Ion","11","Widget.png");
200 | 190 | 11 | Cold Gas |  | Component | Widget.png |  | datatable[199] = new Array("200","190","Cold Gas","11","Widget.png");
201 | 190 | 11 | Other Maneuvering Thrusters (Specify) |  | Component | Widget.png |  | datatable[200] = new Array("201","190","Other Maneuvering Thrusters (Specify)","11","Widget.png");
202 | 176 | 10 | Translation Thrusters |  | Assembly | Widget.png |  | datatable[201] = new Array("202","176","Translation Thrusters","10","Widget.png");
203 | 197 | 11 | Bipropellant |  | Component | Widget.png |  | datatable[202] = new Array("203","197","Bipropellant","11","Widget.png");
204 | 197 | 11 | Monopropellant |  | Component | Widget.png |  | datatable[203] = new Array("204","197","Monopropellant","11","Widget.png");
205 | 197 | 11 | Solar Electric |  | Component | Widget.png |  | datatable[204] = new Array("205","197","Solar Electric","11","Widget.png");
206 | 197 | 11 | Ion |  | Component | Widget.png |  | datatable[205] = new Array("206","197","Ion","11","Widget.png");
207 | 197 | 11 | Cold Gas |  | Component | Widget.png |  | datatable[206] = new Array("207","197","Cold Gas","11","Widget.png");
208 | 197 | 11 | Other Translation Thrusters (Specify) |  | Component | Widget.png |  | datatable[207] = new Array("208","197","Other Translation Thrusters (Specify)","11","Widget.png");
209 | 176 | 10 | Propellant |  | Assembly | Widget.png |  | datatable[208] = new Array("209","176","Propellant","10","Widget.png");
210 | 204 | 11 | Solid Propellant |  | Component | Widget.png |  | datatable[209] = new Array("210","204","Solid Propellant","11","Widget.png");
211 | 204 | 11 | Liquid Propellant |  | Component | Widget.png |  | datatable[210] = new Array("211","204","Liquid Propellant","11","Widget.png");
212 | 204 | 11 | Prussurant Propellant |  | Component | Widget.png |  | datatable[211] = new Array("212","204","Prussurant Propellant","11","Widget.png");
213 | 204 | 11 | Other Propellant (Specify) |  | Component | Widget.png |  | datatable[212] = new Array("213","204","Other Propellant (Specify)","11","Widget.png");
214 | 176 | 11 | Solid Rocket Motors |  | Component | Widget.png |  | datatable[213] = new Array("214","176","Solid Rocket Motors","11","Widget.png");
215 | 176 | 11 | Power Electronics |  | Component | Widget.png |  | datatable[214] = new Array("215","176","Power Electronics","11","Widget.png");
216 | 176 | 11 | Propulsion Other (Specify) |  | Component | Widget.png |  | datatable[215] = new Array("216","176","Propulsion Other (Specify)","11","Widget.png");
217 | 61 | 9 | Telemetry, Tracking, and Command Subsystem (TT&C) |  | Subsystem | Widget.png |  | datatable[216] = new Array("217","61","Telemetry, Tracking, and Command Subsystem (TT&C)","9","Widget.png");
218 | 212 | 10 | TT&C Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[217] = new Array("218","212","TT&C Subsystem SEITPM","10","SEITPM.png");
219 | 213 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[218] = new Array("219","213","Project Management","11","SEITPM.png");
220 | 213 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[219] = new Array("220","213","Systems Engineering","11","SEITPM.png");
221 | 213 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[220] = new Array("221","213","Mission Assurance","11","SEITPM.png");
222 | 213 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[221] = new Array("222","213","Assembly, Integration and Testing","11","SEITPM.png");
223 | 213 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[222] = new Array("223","213","Support Equipment","11","SEITPM.png");
224 | 212 | 10 | Antennas |  | Assembly | Widget.png |  | datatable[223] = new Array("224","212","Antennas","10","Widget.png");
225 | 219 | 11 | Omnidirectional |  | Component | Widget.png |  | datatable[224] = new Array("225","219","Omnidirectional","11","Widget.png");
226 | 219 | 11 | Spiral |  | Component | Widget.png |  | datatable[225] = new Array("226","219","Spiral","11","Widget.png");
227 | 219 | 11 | Horn |  | Component | Widget.png |  | datatable[226] = new Array("227","219","Horn","11","Widget.png");
228 | 219 | 11 | Patch |  | Component | Widget.png |  | datatable[227] = new Array("228","219","Patch","11","Widget.png");
229 | 219 | 11 | Parabolic |  | Component | Widget.png |  | datatable[228] = new Array("229","219","Parabolic","11","Widget.png");
230 | 219 | 11 | Phased Array |  | Component | Widget.png |  | datatable[229] = new Array("230","219","Phased Array","11","Widget.png");
231 | 219 | 11 | Other Antennas (Specify) |  | Component | Widget.png |  | datatable[230] = new Array("231","219","Other Antennas (Specify)","11","Widget.png");
232 | 212 | 10 | Waveguides/Routers |  | Assembly | Widget.png |  | datatable[231] = new Array("232","212","Waveguides/Routers","10","Widget.png");
233 | 227 | 11 | Diplexers |  | Component | Widget.png |  | datatable[232] = new Array("233","227","Diplexers","11","Widget.png");
234 | 227 | 11 | Triplexers |  | Component | Widget.png |  | datatable[233] = new Array("234","227","Triplexers","11","Widget.png");
235 | 227 | 11 | Multiplexers |  | Component | Widget.png |  | datatable[234] = new Array("235","227","Multiplexers","11","Widget.png");
236 | 227 | 11 | Multicouplers |  | Component | Widget.png |  | datatable[235] = new Array("236","227","Multicouplers","11","Widget.png");
237 | 227 | 11 | Coaxial Switches |  | Component | Widget.png |  | datatable[236] = new Array("237","227","Coaxial Switches","11","Widget.png");
238 | 227 | 11 | RF Switches |  | Component | Widget.png |  | datatable[237] = new Array("238","227","RF Switches","11","Widget.png");
239 | 227 | 11 | Filters |  | Component | Widget.png |  | datatable[238] = new Array("239","227","Filters","11","Widget.png");
240 | 227 | 11 | Waveguides |  | Component | Widget.png |  | datatable[239] = new Array("240","227","Waveguides","11","Widget.png");
241 | 227 | 11 | Other Routers (Specify) |  | Component | Widget.png |  | datatable[240] = new Array("241","227","Other Routers (Specify)","11","Widget.png");
242 | 212 | 10 | Radio Frequency Equipment |  | Assembly | Widget.png |  | datatable[241] = new Array("242","212","Radio Frequency Equipment","10","Widget.png");
243 | 237 | 11 | Amplifiers |  | Component | Widget.png |  | datatable[242] = new Array("243","237","Amplifiers","11","Widget.png");
244 | 237 | 11 | Receivers |  | Component | Widget.png |  | datatable[243] = new Array("244","237","Receivers","11","Widget.png");
245 | 237 | 11 | Transmitters |  | Component | Widget.png |  | datatable[244] = new Array("245","237","Transmitters","11","Widget.png");
246 | 237 | 11 | Transceivers |  | Component | Widget.png |  | datatable[245] = new Array("246","237","Transceivers","11","Widget.png");
247 | 237 | 11 | Transponders |  | Component | Widget.png |  | datatable[246] = new Array("247","237","Transponders","11","Widget.png");
248 | 237 | 11 | Modulators |  | Component | Widget.png |  | datatable[247] = new Array("248","237","Modulators","11","Widget.png");
249 | 237 | 11 | Demodulators |  | Component | Widget.png |  | datatable[248] = new Array("249","237","Demodulators","11","Widget.png");
250 | 237 | 11 | Modems |  | Component | Widget.png |  | datatable[249] = new Array("250","237","Modems","11","Widget.png");
251 | 237 | 11 | Traveling Wave Tube Assemblies |  | Component | Widget.png |  | datatable[250] = new Array("251","237","Traveling Wave Tube Assemblies","11","Widget.png");
252 | 237 | 11 | Solid State Power Amplifiers |  | Component | Widget.png |  | datatable[251] = new Array("252","237","Solid State Power Amplifiers","11","Widget.png");
253 | 237 | 11 | Global Positioning System (GPS) Receiver |  | Component | Widget.png |  | datatable[252] = new Array("253","237","Global Positioning System (GPS) Receiver","11","Widget.png");
254 | 237 | 11 | Downconverters |  | Component | Widget.png |  | datatable[253] = new Array("254","237","Downconverters","11","Widget.png");
255 | 237 | 11 | Upconverters |  | Component | Widget.png |  | datatable[254] = new Array("255","237","Upconverters","11","Widget.png");
256 | 237 | 11 | Other RF Equipment (Specify) |  | Component | Widget.png |  | datatable[255] = new Array("256","237","Other RF Equipment (Specify)","11","Widget.png");
257 | 212 | 10 | Command and Data Handling (C&DH) |  | Assembly | Widget.png |  | datatable[256] = new Array("257","212","Command and Data Handling (C&DH)","10","Widget.png");
258 | 252 | 11 | Processors |  | Component | Widget.png |  | datatable[257] = new Array("258","252","Processors","11","Widget.png");
259 | 252 | 11 | Solid State Memory |  | Component | Widget.png |  | datatable[258] = new Array("259","252","Solid State Memory","11","Widget.png");
260 | 252 | 11 | Decoders |  | Component | Widget.png |  | datatable[259] = new Array("260","252","Decoders","11","Widget.png");
261 | 252 | 11 | Command Units |  | Component | Widget.png |  | datatable[260] = new Array("261","252","Command Units","11","Widget.png");
262 | 252 | 11 | Telemetry Units |  | Component | Widget.png |  | datatable[261] = new Array("262","252","Telemetry Units","11","Widget.png");
263 | 252 | 11 | Command Sequencers |  | Component | Widget.png |  | datatable[262] = new Array("263","252","Command Sequencers","11","Widget.png");
264 | 252 | 11 | Timing Units |  | Component | Widget.png |  | datatable[263] = new Array("264","252","Timing Units","11","Widget.png");
265 | 252 | 11 | Frequency Generators |  | Component | Widget.png |  | datatable[264] = new Array("265","252","Frequency Generators","11","Widget.png");
266 | 252 | 11 | Signal Conditioners |  | Component | Widget.png |  | datatable[265] = new Array("266","252","Signal Conditioners","11","Widget.png");
267 | 252 | 11 | Data Switches |  | Component | Widget.png |  | datatable[266] = new Array("267","252","Data Switches","11","Widget.png");
268 | 252 | 11 | Communication Security |  | Component | Widget.png |  | datatable[267] = new Array("268","252","Communication Security","11","Widget.png");
269 | 252 | 11 | Interface Units |  | Component | Widget.png |  | datatable[268] = new Array("269","252","Interface Units","11","Widget.png");
270 | 252 | 11 | Tape Recorders |  | Component | Widget.png |  | datatable[269] = new Array("270","252","Tape Recorders","11","Widget.png");
271 | 252 | 11 | Disk Recorders |  | Component | Widget.png |  | datatable[270] = new Array("271","252","Disk Recorders","11","Widget.png");
272 | 252 | 11 | Command Sensor or Situational Awareness Sensors |  | Component | Widget.png |  | datatable[271] = new Array("272","252","Command Sensor or Situational Awareness Sensors","11","Widget.png");
273 | 252 | 11 | Other C&DH (Specify) |  | Component | Widget.png |  | datatable[272] = new Array("273","252","Other C&DH (Specify)","11","Widget.png");
274 | 212 | 10 | TT&C Other (Specify) |  | Assembly | Widget.png |  | datatable[273] = new Array("274","212","TT&C Other (Specify)","10","Widget.png");
275 | 61 | 9 | Bus Flight Software |  | Subsystem | Widget.png |  | datatable[274] = new Array("275","61","Bus Flight Software","9","Widget.png");
276 | 275 | 10 | Bus FSW Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[275] = new Array("276","275","Bus FSW Subsystem SEITPM","10","SEITPM.png");
277 | 271 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[276] = new Array("277","271","Project Management","11","SEITPM.png");
278 | 271 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[277] = new Array("278","271","Systems Engineering","11","SEITPM.png");
279 | 271 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[278] = new Array("279","271","Mission Assurance","11","SEITPM.png");
280 | 271 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[279] = new Array("280","271","Assembly, Integration and Testing","11","SEITPM.png");
281 | 271 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[280] = new Array("281","271","Support Equipment","11","SEITPM.png");
282 | 270 | 11 | Thermal Control Software |  | Component | Widget.png |  | datatable[281] = new Array("282","270","Thermal Control Software","11","Widget.png");
283 | 270 | 11 | Electrical Power Software |  | Component | Widget.png |  | datatable[282] = new Array("283","270","Electrical Power Software","11","Widget.png");
284 | 270 | 11 | Attitude Control Software |  | Component | Widget.png |  | datatable[283] = new Array("284","270","Attitude Control Software","11","Widget.png");
285 | 270 | 11 | Telemetry, Tracking, and Command Software |  | Component | Widget.png |  | datatable[284] = new Array("285","270","Telemetry, Tracking, and Command Software","11","Widget.png");
286 | 270 | 11 | Other Flight Software (Specify) |  | Component | Widget.png |  | datatable[285] = new Array("286","270","Other Flight Software (Specify)","11","Widget.png");
287 | 59 | 8 | SEITPM and Support Equipment (If Applicable for Integration of Multiple Payloads) |  | System | SEITPM.png |  | datatable[286] = new Array("287","59","SEITPM and Support Equipment (If Applicable for Integration of Multiple Payloads)","8","SEITPM.png");
288 | 282 | 9 | Project Management |  | Subsystem | SEITPM.png |  | datatable[287] = new Array("288","282","Project Management","9","SEITPM.png");
289 | 282 | 9 | Systems Engineering |  | Subsystem | SEITPM.png |  | datatable[288] = new Array("289","282","Systems Engineering","9","SEITPM.png");
290 | 282 | 9 | Mission Assurance |  | Subsystem | SEITPM.png |  | datatable[289] = new Array("290","282","Mission Assurance","9","SEITPM.png");
291 | 282 | 9 | Assembly, Integration and Testing |  | Subsystem | SEITPM.png |  | datatable[290] = new Array("291","282","Assembly, Integration and Testing","9","SEITPM.png");
292 | 282 | 9 | Support Equipment |  | Subsystem | SEITPM.png |  | datatable[291] = new Array("292","282","Support Equipment","9","SEITPM.png");
293 | 59 | 8 | Payload 1 … n (Specify) |  | System | Widget.png |  | datatable[292] = new Array("293","59","Payload 1 … n (Specify)","8","Widget.png");
294 | 293 | 9 | Payload 1 SEITPM and Support Equipment |  | Subsystem | SEITPM.png |  | datatable[293] = new Array("294","293","Payload 1 SEITPM and Support Equipment","9","SEITPM.png");
295 | 289 | 10 | Project Management |  | Assembly | SEITPM.png |  | datatable[294] = new Array("295","289","Project Management","10","SEITPM.png");
296 | 289 | 10 | Systems Engineering |  | Assembly | SEITPM.png |  | datatable[295] = new Array("296","289","Systems Engineering","10","SEITPM.png");
297 | 289 | 10 | Mission Assurance |  | Assembly | SEITPM.png |  | datatable[296] = new Array("297","289","Mission Assurance","10","SEITPM.png");
298 | 289 | 10 | Assembly, Integration and Testing |  | Assembly | SEITPM.png |  | datatable[297] = new Array("298","289","Assembly, Integration and Testing","10","SEITPM.png");
299 | 289 | 10 | Support Equipment |  | Assembly | SEITPM.png |  | datatable[298] = new Array("299","289","Support Equipment","10","SEITPM.png");
300 | 288 | 9 | Payload 1 Structures and Mechanisms Subsystem |  | Subsystem | Widget.png |  | datatable[299] = new Array("300","288","Payload 1 Structures and Mechanisms Subsystem","9","Widget.png");
301 | 295 | 10 | Structures and Mechanims Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[300] = new Array("301","295","Structures and Mechanims Subsystem SEITPM","10","SEITPM.png");
302 | 296 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[301] = new Array("302","296","Project Management","11","SEITPM.png");
303 | 296 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[302] = new Array("303","296","Systems Engineering","11","SEITPM.png");
304 | 296 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[303] = new Array("304","296","Mission Assurance","11","SEITPM.png");
305 | 296 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[304] = new Array("305","296","Assembly, Integration and Testing","11","SEITPM.png");
306 | 296 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[305] = new Array("306","296","Support Equipment","11","SEITPM.png");
307 | 295 | 10 | Structures |  | Assembly | Widget.png |  | datatable[306] = new Array("307","295","Structures","10","Widget.png");
308 | 295 | 10 | Mechanisms and Pyrotechnics |  | Assembly | Widget.png |  | datatable[307] = new Array("308","295","Mechanisms and Pyrotechnics","10","Widget.png");
309 | 295 | 10 | Structures and Mechanisms Other (Specify) |  | Assembly | Widget.png |  | datatable[308] = new Array("309","295","Structures and Mechanisms Other (Specify)","10","Widget.png");
310 | 288 | 9 | Payload 1 Thermal Control Subsystem |  | Subsystem | Widget.png |  | datatable[309] = new Array("310","288","Payload 1 Thermal Control Subsystem","9","Widget.png");
311 | 310 | 10 | Thermal Control Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[310] = new Array("311","310","Thermal Control Subsystem SEITPM","10","SEITPM.png");
312 | 306 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[311] = new Array("312","306","Project Management","11","SEITPM.png");
313 | 306 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[312] = new Array("313","306","Systems Engineering","11","SEITPM.png");
314 | 306 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[313] = new Array("314","306","Mission Assurance","11","SEITPM.png");
315 | 306 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[314] = new Array("315","306","Assembly, Integration and Testing","11","SEITPM.png");
316 | 306 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[315] = new Array("316","306","Support Equipment","11","SEITPM.png");
317 | 316 | 10 | Cryogenic Devices |  | Assembly | Widget.png |  | datatable[316] = new Array("317","316","Cryogenic Devices","10","Widget.png");
318 | 317 | 10 | Liquid Loops |  | Assembly | Widget.png |  | datatable[317] = new Array("318","317","Liquid Loops","10","Widget.png");
319 | 318 | 10 | Electric Coolers |  | Assembly | Widget.png |  | datatable[318] = new Array("319","318","Electric Coolers","10","Widget.png");
320 | 319 | 10 | Electric heaters, Thermisters, and Thermostats |  | Assembly | Widget.png |  | datatable[319] = new Array("320","319","Electric heaters, Thermisters, and Thermostats","10","Widget.png");
321 | 320 | 10 | Passive Devices |  | Assembly | Widget.png |  | datatable[320] = new Array("321","320","Passive Devices","10","Widget.png");
322 | 321 | 10 | Sun Shields |  | Assembly | Widget.png |  | datatable[321] = new Array("322","321","Sun Shields","10","Widget.png");
323 | 322 | 10 | Thermal Control Other (Specify) |  | Assembly | Widget.png |  | datatable[322] = new Array("323","322","Thermal Control Other (Specify)","10","Widget.png");
324 | 288 | 9 | Payload 1 Electrical Power Subsystem |  | Subsystem | Widget.png |  | datatable[323] = new Array("324","288","Payload 1 Electrical Power Subsystem","9","Widget.png");
325 | 319 | 10 | Electrical Power Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[324] = new Array("325","319","Electrical Power Subsystem SEITPM","10","SEITPM.png");
326 | 320 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[325] = new Array("326","320","Project Management","11","SEITPM.png");
327 | 320 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[326] = new Array("327","320","Systems Engineering","11","SEITPM.png");
328 | 320 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[327] = new Array("328","320","Mission Assurance","11","SEITPM.png");
329 | 320 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[328] = new Array("329","320","Assembly, Integration and Testing","11","SEITPM.png");
330 | 320 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[329] = new Array("330","320","Support Equipment","11","SEITPM.png");
331 | 319 | 10 | Power Sources |  | Assembly | Widget.png |  | datatable[330] = new Array("331","319","Power Sources","10","Widget.png");
332 | 319 | 10 | Power Control, Switching, and Distribution Electronics |  | Assembly | Widget.png |  | datatable[331] = new Array("332","319","Power Control, Switching, and Distribution Electronics","10","Widget.png");
333 | 319 | 10 | Power Conditioning, Conversion, and Regulation |  | Assembly | Widget.png |  | datatable[332] = new Array("333","319","Power Conditioning, Conversion, and Regulation","10","Widget.png");
334 | 319 | 10 | Harnesses and Cables |  | Assembly | Widget.png |  | datatable[333] = new Array("334","319","Harnesses and Cables","10","Widget.png");
335 | 319 | 10 | Electrical Power Other (Specify) |  | Assembly | Widget.png |  | datatable[334] = new Array("335","319","Electrical Power Other (Specify)","10","Widget.png");
336 | 288 | 9 | Payload 1 Pointing, Command, and Control Interface |  | Subsystem | Widget.png |  | datatable[335] = new Array("336","288","Payload 1 Pointing, Command, and Control Interface","9","Widget.png");
337 | 336 | 10 | Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[336] = new Array("337","336","Subsystem SEITPM","10","SEITPM.png");
338 | 332 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[337] = new Array("338","332","Project Management","11","SEITPM.png");
339 | 332 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[338] = new Array("339","332","Systems Engineering","11","SEITPM.png");
340 | 332 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[339] = new Array("340","332","Mission Assurance","11","SEITPM.png");
341 | 332 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[340] = new Array("341","332","Assembly, Integration and Testing","11","SEITPM.png");
342 | 332 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[341] = new Array("342","332","Support Equipment","11","SEITPM.png");
343 | 331 | 10 | Computers and Processors |  | Assembly | Widget.png |  | datatable[342] = new Array("343","331","Computers and Processors","10","Widget.png");
344 | 331 | 10 | Command/Telemetric Units |  | Assembly | Widget.png |  | datatable[343] = new Array("344","331","Command/Telemetric Units","10","Widget.png");
345 | 331 | 10 | Control Electronics |  | Assembly | Widget.png |  | datatable[344] = new Array("345","331","Control Electronics","10","Widget.png");
346 | 331 | 10 | Pointing Sensors |  | Assembly | Widget.png |  | datatable[345] = new Array("346","331","Pointing Sensors","10","Widget.png");
347 | 331 | 10 | Payload Positioners |  | Assembly | Widget.png |  | datatable[346] = new Array("347","331","Payload Positioners","10","Widget.png");
348 | 331 | 10 | Security, Encryption, and Decryption Devices |  | Assembly | Widget.png |  | datatable[347] = new Array("348","331","Security, Encryption, and Decryption Devices","10","Widget.png");
349 | 331 | 10 | Data Storage, handling, and Interface |  | Assembly | Widget.png |  | datatable[348] = new Array("349","331","Data Storage, handling, and Interface","10","Widget.png");
350 | 331 | 10 | Multifunctional Digital Electronic Boxes |  | Assembly | Widget.png |  | datatable[349] = new Array("350","331","Multifunctional Digital Electronic Boxes","10","Widget.png");
351 | 331 | 10 | Pointing, Command, and Control Interface Other (Specify) |  | Assembly | Widget.png |  | datatable[350] = new Array("351","331","Pointing, Command, and Control Interface Other (Specify)","10","Widget.png");
352 | 288 | 9 | Payload Signal Electronics |  | Subsystem | Widget.png |  | datatable[351] = new Array("352","288","Payload Signal Electronics","9","Widget.png");
353 | 347 | 10 | Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[352] = new Array("353","347","Subsystem SEITPM","10","SEITPM.png");
354 | 348 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[353] = new Array("354","348","Project Management","11","SEITPM.png");
355 | 348 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[354] = new Array("355","348","Systems Engineering","11","SEITPM.png");
356 | 348 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[355] = new Array("356","348","Mission Assurance","11","SEITPM.png");
357 | 348 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[356] = new Array("357","348","Assembly, Integration and Testing","11","SEITPM.png");
358 | 348 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[357] = new Array("358","348","Support Equipment","11","SEITPM.png");
359 | 347 | 10 | Passive Signal Flow Control |  | Assembly | Widget.png |  | datatable[358] = new Array("359","347","Passive Signal Flow Control","10","Widget.png");
360 | 347 | 10 | Transmitter/Receiver/Transceiver/Transponder |  | Assembly | Widget.png |  | datatable[359] = new Array("360","347","Transmitter/Receiver/Transceiver/Transponder","10","Widget.png");
361 | 347 | 10 | Modulators/Demodulators/Modems |  | Assembly | Widget.png |  | datatable[360] = new Array("361","347","Modulators/Demodulators/Modems","10","Widget.png");
362 | 347 | 10 | Multiplexers/Demultiplexers |  | Assembly | Widget.png |  | datatable[361] = new Array("362","347","Multiplexers/Demultiplexers","10","Widget.png");
363 | 347 | 10 | Amplifiers |  | Assembly | Widget.png |  | datatable[362] = new Array("363","347","Amplifiers","10","Widget.png");
364 | 347 | 10 | Frequency Upconverters/Downconverters |  | Assembly | Widget.png |  | datatable[363] = new Array("364","347","Frequency Upconverters/Downconverters","10","Widget.png");
365 | 347 | 10 | Frequency and Timing |  | Assembly | Widget.png |  | datatable[364] = new Array("365","347","Frequency and Timing","10","Widget.png");
366 | 347 | 10 | Signal Conditioners |  | Assembly | Widget.png |  | datatable[365] = new Array("366","347","Signal Conditioners","10","Widget.png");
367 | 347 | 10 | Multifunctional Digital Electronic Boxes |  | Assembly | Widget.png |  | datatable[366] = new Array("367","347","Multifunctional Digital Electronic Boxes","10","Widget.png");
368 | 347 | 10 | Signal Electronics Other (Specify) |  | Assembly | Widget.png |  | datatable[367] = new Array("368","347","Signal Electronics Other (Specify)","10","Widget.png");
369 | 288 | 9 | Payload 1 Optical Assembly |  | Subsystem | Widget.png |  | datatable[368] = new Array("369","288","Payload 1 Optical Assembly","9","Widget.png");
370 | 364 | 10 | Subsystem SEITPM |  | Assembly | SEITPM.png |  | datatable[369] = new Array("370","364","Subsystem SEITPM","10","SEITPM.png");
371 | 365 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[370] = new Array("371","365","Project Management","11","SEITPM.png");
372 | 365 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[371] = new Array("372","365","Systems Engineering","11","SEITPM.png");
373 | 365 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[372] = new Array("373","365","Mission Assurance","11","SEITPM.png");
374 | 365 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[373] = new Array("374","365","Assembly, Integration and Testing","11","SEITPM.png");
375 | 365 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[374] = new Array("375","365","Support Equipment","11","SEITPM.png");
376 | 364 | 10 | Structure/Outerbarrel/Cover |  | Assembly | Widget.png |  | datatable[375] = new Array("376","364","Structure/Outerbarrel/Cover","10","Widget.png");
377 | 364 | 10 | Mirrors/Optics |  | Assembly | Widget.png |  | datatable[376] = new Array("377","364","Mirrors/Optics","10","Widget.png");
378 | 364 | 10 | Aft Optics Assembly |  | Assembly | Widget.png |  | datatable[377] = new Array("378","364","Aft Optics Assembly","10","Widget.png");
379 | 364 | 10 | Alignment and Calibration |  | Assembly | Widget.png |  | datatable[378] = new Array("379","364","Alignment and Calibration","10","Widget.png");
380 | 364 | 10 | Thermal |  | Assembly | Widget.png |  | datatable[379] = new Array("380","364","Thermal","10","Widget.png");
374 | 364 | 10 | Control Electronics |  | Assembly | Widget.png |  | datatable[373] = new Array("374","364","Control Electronics","10","Widget.png");
375 | 364 | 10 | Optical Assembly Other |  | Assembly | Widget.png |  | datatable[374] = new Array("375","364","Optical Assembly Other","10","Widget.png");
376 | 288 | 9 | Payload 1 Sensor |  | Subsystem | Widget.png |  | datatable[375] = new Array("376","288","Payload 1 Sensor","9","Widget.png");
377 | 378 | 10 | Sensor SEITPM |  | Assembly | SEITPM.png |  | datatable[376] = new Array("377","378","Sensor SEITPM","10","SEITPM.png");
378 | 379 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[377] = new Array("378","379","Project Management","11","SEITPM.png");
379 | 379 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[378] = new Array("379","379","Systems Engineering","11","SEITPM.png");
380 | 379 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[379] = new Array("380","379","Mission Assurance","11","SEITPM.png");
381 | 379 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[380] = new Array("381","379","Assembly, Integration and Testing","11","SEITPM.png");
382 | 379 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[381] = new Array("382","379","Support Equipment","11","SEITPM.png");
383 | 378 | 10 | Payload Structure |  | Assembly | Widget.png |  | datatable[382] = new Array("383","378","Payload Structure","10","Widget.png");
384 | 378 | 10 | Focal Plan Array |  | Assembly | Widget.png |  | datatable[383] = new Array("384","378","Focal Plan Array","10","Widget.png");
385 | 378 | 10 | Sensor Positioners |  | Assembly | Widget.png |  | datatable[384] = new Array("385","378","Sensor Positioners","10","Widget.png");
386 | 378 | 10 | Sensor Electronics |  | Assembly | Widget.png |  | datatable[385] = new Array("386","378","Sensor Electronics","10","Widget.png");
387 | 378 | 10 | Alignment and Calibration |  | Assembly | Widget.png |  | datatable[386] = new Array("387","378","Alignment and Calibration","10","Widget.png");
388 | 378 | 10 | Magnetometer |  | Assembly | Widget.png |  | datatable[387] = new Array("388","378","Magnetometer","10","Widget.png");
389 | 378 | 10 | Spectrometer |  | Assembly | Widget.png |  | datatable[388] = new Array("389","378","Spectrometer","10","Widget.png");
390 | 378 | 10 | Radiometer |  | Assembly | Widget.png |  | datatable[389] = new Array("390","378","Radiometer","10","Widget.png");
391 | 378 | 10 | Camera |  | Assembly | Widget.png |  | datatable[390] = new Array("391","378","Camera","10","Widget.png");
392 | 378 | 10 | Sounder |  | Assembly | Widget.png |  | datatable[391] = new Array("392","378","Sounder","10","Widget.png");
393 | 378 | 10 | Flight Sensor Software |  | Assembly | Widget.png |  | datatable[392] = new Array("393","378","Flight Sensor Software","10","Widget.png");
394 | 378 | 10 | Other Sensor Types (Specify) |  | Assembly | Widget.png |  | datatable[393] = new Array("394","378","Other Sensor Types (Specify)","10","Widget.png");
395 | 378 | 10 | Mission Sensor Other (Specify) |  | Assembly | Widget.png |  | datatable[394] = new Array("395","378","Mission Sensor Other (Specify)","10","Widget.png");
396 | 288 | 9 | Payload Flight Software |  | Subsystem | Widget.png |  | datatable[395] = new Array("396","288","Payload Flight Software","9","Widget.png");
397 | 396 | 10 | Payload 1 FSW SEITPM |  | Assembly | SEITPM.png |  | datatable[396] = new Array("397","396","Payload 1 FSW SEITPM","10","SEITPM.png");
398 | 392 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[397] = new Array("398","392","Project Management","11","SEITPM.png");
399 | 392 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[398] = new Array("399","392","Systems Engineering","11","SEITPM.png");
400 | 392 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[399] = new Array("400","392","Mission Assurance","11","SEITPM.png");
401 | 392 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[400] = new Array("401","392","Assembly, Integration and Testing","11","SEITPM.png");
402 | 392 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[401] = new Array("402","392","Support Equipment","11","SEITPM.png");
403 | 396 | 10 | CSCI (Specify) |  | Assembly | Widget.png |  | datatable[402] = new Array("403","396","CSCI (Specify)","10","Widget.png");
404 | 288 | 9 | Payload Antenna 1 … n (Specify) |  | Subsystem | Widget.png |  | datatable[403] = new Array("404","288","Payload Antenna 1 … n (Specify)","9","Widget.png");
405 | 399 | 10 | Payload 1 Antenna SEITPM |  | Assembly | SEITPM.png |  | datatable[404] = new Array("405","399","Payload 1 Antenna SEITPM","10","SEITPM.png");
406 | 400 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[405] = new Array("406","400","Project Management","11","SEITPM.png");
407 | 400 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[406] = new Array("407","400","Systems Engineering","11","SEITPM.png");
408 | 400 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[407] = new Array("408","400","Mission Assurance","11","SEITPM.png");
409 | 400 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[408] = new Array("409","400","Assembly, Integration and Testing","11","SEITPM.png");
410 | 400 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[409] = new Array("410","400","Support Equipment","11","SEITPM.png");
411 | 399 | 10 | Structures and Mechanisms |  | Assembly | Widget.png |  | datatable[410] = new Array("411","399","Structures and Mechanisms","10","Widget.png");
412 | 399 | 10 | Antenna Positioners |  | Assembly | Widget.png |  | datatable[411] = new Array("412","399","Antenna Positioners","10","Widget.png");
413 | 399 | 10 | Reflector/Horn |  | Assembly | Widget.png |  | datatable[412] = new Array("413","399","Reflector/Horn","10","Widget.png");
414 | 399 | 10 | Feed |  | Assembly | Widget.png |  | datatable[413] = new Array("414","399","Feed","10","Widget.png");
415 | 399 | 10 | Waveguide/Coad/Cabling |  | Assembly | Widget.png |  | datatable[414] = new Array("415","399","Waveguide/Coad/Cabling","10","Widget.png");
416 | 399 | 10 | Transmit/Receive Modules |  | Assembly | Widget.png |  | datatable[415] = new Array("416","399","Transmit/Receive Modules","10","Widget.png");
417 | 399 | 10 | Antenna Other (Specify) |  | Assembly | Widget.png |  | datatable[416] = new Array("417","399","Antenna Other (Specify)","10","Widget.png");
418 | 288 | 9 | Payload Other (Specify) |  | Subsystem | Widget.png |  | datatable[417] = new Array("418","288","Payload Other (Specify)","9","Widget.png");
419 | 418 | 10 | Booster Adapter |  | Assembly | Widget.png |  | datatable[418] = new Array("419","418","Booster Adapter","10","Widget.png");
420 | 418 | 10 | Space Vehicle Storage |  | Assembly | Widget.png |  | datatable[419] = new Array("420","418","Space Vehicle Storage","10","Widget.png");
421 | 418 | 10 | Space Vehicle Other (Specify) |  | Assembly | Widget.png |  | datatable[420] = new Array("421","418","Space Vehicle Other (Specify)","10","Widget.png");
422 | 12 | 7 | Launch Systems Integration (LSI) |  |  | Rocket.png |  | datatable[421] = new Array("422","12","Launch Systems Integration (LSI)","7","Rocket.png");
423 | 12 | 7 | Launch Operations |  |  | Rocket.png |  | datatable[422] = new Array("423","12","Launch Operations","7","Rocket.png");
424 | 12 | 7 | Launch Operations Support |  |  | Rocket.png |  | datatable[423] = new Array("424","12","Launch Operations Support","7","Rocket.png");
425 | 12 | 7 | Launch Vehicle Services |  |  | Rocket.png |  | datatable[424] = new Array("425","12","Launch Vehicle Services","7","Rocket.png");
426 | 12 | 7 | Launch Insurance |  |  | Rocket.png |  | datatable[425] = new Array("426","12","Launch Insurance","7","Rocket.png");
427 | 13 | 7 | Ground Segment SEITPM |  | Assembly | SEITPM.png |  | datatable[426] = new Array("427","13","Ground Segment SEITPM","7","SEITPM.png");
428 | 422 | 8 | Project Management |  | Component | SEITPM.png |  | datatable[427] = new Array("428","422","Project Management","8","SEITPM.png");
429 | 422 | 8 | Systems Engineering |  | Component | SEITPM.png |  | datatable[428] = new Array("429","422","Systems Engineering","8","SEITPM.png");
430 | 422 | 8 | Mission Assurance |  | Component | SEITPM.png |  | datatable[429] = new Array("430","422","Mission Assurance","8","SEITPM.png");
431 | 422 | 8 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[430] = new Array("431","422","Assembly, Integration and Testing","8","SEITPM.png");
432 | 422 | 8 | Support Equipment |  | Component | SEITPM.png |  | datatable[431] = new Array("432","422","Support Equipment","8","SEITPM.png");
433 | 13 | 7 | Mission Control Centers |  |  | Facility.png |  | datatable[432] = new Array("433","13","Mission Control Centers","7","Facility.png");
434 | 13 | 7 | Science / Data Ops Centers |  |  | Facility.png |  | datatable[433] = new Array("434","13","Science / Data Ops Centers","7","Facility.png");
435 | 13 | 7 | Terminals and Data Networks – incl Antennas |  |  | Facility.png |  | datatable[434] = new Array("435","13","Terminals and Data Networks – incl Antennas ","7","Facility.png");
436 | 13 | 7 | Data Distribution & Archival |  |  | Facility.png |  | datatable[435] = new Array("436","13","Data Distribution & Archival ","7","Facility.png");
437 | 13 | 7 | Training Facilities |  |  | Facility.png |  | datatable[436] = new Array("437","13","Training Facilities ","7","Facility.png");
438 | 433 | 8 | CSA Mission Control |  |  | Facility.png |  | datatable[437] = new Array("438","433","CSA Mission Control","8","Facility.png");
439 | 438 | 9 | SatOps Mission Control Complex at JHCSC |  |  | Facility.png |  | datatable[438] = new Array("439","438","SatOps Mission Control Complex at JHCSC ","9","Facility.png");
440 | 438 | 9 | ISS Mission Operations Complex |  |  | Facility.png |  | datatable[439] = new Array("440","438","ISS Mission Operations Complex","9","Facility.png");
441 | 433 | 8 | NASA Mission Operations Complex |  |  | Facility.png |  | datatable[440] = new Array("441","433","NASA Mission Operations Complex","8","Facility.png");
442 | 435 | 10 | RMPSR |  |  | Facility.png |  | datatable[441] = new Array("442","435","RMPSR","10","Facility.png");
443 | 435 | 10 | OEC |  |  | Facility.png |  | datatable[442] = new Array("443","435","OEC","10","Facility.png");
444 | 435 | 10 | PTOC |  |  | Facility.png |  | datatable[443] = new Array("444","435","PTOC","10","Facility.png");
445 | 439 | 10 | SatOps Mission control SEITPM |  | Assembly | SEITPM.png |  | datatable[444] = new Array("445","439","SatOps Mission control SEITPM","10","SEITPM.png");
446 | 440 | 11 | Project Management |  | Component | SEITPM.png |  | datatable[445] = new Array("446","440","Project Management","11","SEITPM.png");
447 | 440 | 11 | Systems Engineering |  | Component | SEITPM.png |  | datatable[446] = new Array("447","440","Systems Engineering","11","SEITPM.png");
448 | 440 | 11 | Mission Assurance |  | Component | SEITPM.png |  | datatable[447] = new Array("448","440","Mission Assurance","11","SEITPM.png");
449 | 440 | 11 | Assembly, Integration and Testing |  | Component | SEITPM.png |  | datatable[448] = new Array("449","440","Assembly, Integration and Testing","11","SEITPM.png");
450 | 440 | 11 | Support Equipment |  | Component | SEITPM.png |  | datatable[449] = new Array("450","440","Support Equipment","11","SEITPM.png");
451 | 434 | 10 | Hardware Components |  |  | Facility.png |  | datatable[450] = new Array("451","434","Hardware Components","10","Facility.png");
452 | 446 | 11 | Workstations |  |  | Facility.png |  | datatable[451] = new Array("452","446","Workstations","11","Facility.png");
453 | 446 | 11 | Servers |  |  | Facility.png |  | datatable[452] = new Array("453","446","Servers","11","Facility.png");
454 | 446 | 11 | Storage and Archive |  |  | Facility.png |  | datatable[453] = new Array("454","446","Storage and Archive","11","Facility.png");
455 | 446 | 11 | Network Equipment |  |  | Facility.png |  | datatable[454] = new Array("455","446","Network Equipment","11","Facility.png");
456 | 446 | 11 | Interface Equipment |  |  | Facility.png |  | datatable[455] = new Array("456","446","Interface Equipment","11","Facility.png");
457 | 446 | 11 | Security Encryption/Decryption |  |  | Facility.png |  | datatable[456] = new Array("457","446","Security Encryption/Decryption","11","Facility.png");
458 | 446 | 11 | Data Processing |  |  | Facility.png |  | datatable[457] = new Array("458","446","Data Processing","11","Facility.png");
459 | 446 | 11 | COTS Hardware Other (Specify) |  |  | Facility.png |  | datatable[458] = new Array("459","446","COTS Hardware Other (Specify)","11","Facility.png");
460 | 446 | 11 | Pre-Operations Maintenance (Specify) |  |  | Facility.png |  | datatable[459] = new Array("460","446","Pre-Operations Maintenance (Specify)","11","Facility.png");
461 | 446 | 11 | Environments |  |  | Facility.png |  | datatable[460] = new Array("461","446","Environments","11","Facility.png");
462 | 434 | 10 | SatOps GS Software |  |  | Facility.png |  | datatable[461] = new Array("462","434","SatOps GS Software","10","Facility.png");
463 | 462 | 11 | SW CSCI |  |  | Facility.png |  | datatable[462] = new Array("463","462","SW CSCI","11","Facility.png");
464 | 429 | 8 | NASA Science Operations Centers |  |  | Facility.png |  | datatable[463] = new Array("464","429","NASA Science Operations Centers","8","Facility.png");
465 | 429 | 8 | HPC (High Performance Computing) |  |  | Facility.png |  | datatable[464] = new Array("465","429","HPC (High Performance Computing)","8","Facility.png");
466 | 429 | 8 | Geospace Observatory |  |  | Facility.png |  | datatable[465] = new Array("466","429","Geospace Observatory","8","Facility.png");
467 | 429 | 8 | Other SODC (specify) |  |  | Facility.png |  | datatable[466] = new Array("467","429","Other SODC (specify)","8","Facility.png");
468 | 435 | 8 | CSA Terminals and Antennas |  |  | Facility.png |  | datatable[467] = new Array("468","435"," CSA Terminals and Antennas","8","Facility.png");
469 | 463 | 9 | CSA St-Hubert Antenna |  |  | Facility.png |  | datatable[468] = new Array("469","463","CSA St-Hubert Antenna","9","Facility.png");
470 | 463 | 9 | Ferme Yves Bachand Antenna |  |  | Facility.png |  | datatable[469] = new Array("470","463","Ferme Yves Bachand Antenna","9","Facility.png");
471 | 463 | 9 | Ferme Beldor Antenna |  |  | Facility.png |  | datatable[470] = new Array("471","463","Ferme Beldor Antenna","9","Facility.png");
472 | 463 | 9 | Transponder |  |  | Facility.png |  | datatable[471] = new Array("472","463","Transponder","9","Facility.png");
473 | 431 | 8 | Digital Earth Canada |  |  | Facility.png |  | datatable[472] = new Array("473","431","Digital Earth Canada","8","Facility.png");
474 | 431 | 8 | Federal Geospatial Platform (FGP) |  |  | Facility.png |  | datatable[473] = new Array("474","431","Federal Geospatial Platform (FGP)","8","Facility.png");
475 | 431 | 8 | EODMS |  |  | Facility.png |  | datatable[474] = new Array("475","431","EODMS","8","Facility.png");
476 | 431 | 8 | Canadian Astronomy Data Centre |  |  | Facility.png |  | datatable[475] = new Array("476","431","Canadian Astronomy Data Centre","8","Facility.png");
477 | 431 | 8 | NASA Data Distribution & Archival |  |  | Facility.png |  | datatable[476] = new Array("477","431","NASA Data Distribution & Archival","8","Facility.png");
478 | 437 | 8 | MMLC |  |  | Facility.png |  | datatable[477] = new Array("478","437","MMLC","8","Facility.png");
479 | 437 | 8 | MOTS |  |  | Facility.png |  | datatable[478] = new Array("479","437","MOTS","8","Facility.png");
480 | 14 | 7 | CSA Mission Operations |  |  | Ops.png |  | datatable[479] = new Array("480","14","CSA Mission Operations","7","Ops.png");
481 | 475 | 8 | CSA SatOps |  |  | Ops.png |  | datatable[480] = new Array("481","475","CSA SatOps","8","Ops.png");
482 | 475 | 8 | CSA ISS Ops |  |  | Ops.png |  | datatable[481] = new Array("482","475","CSA ISS Ops","8","Ops.png");
483 | 475 | 8 | CSA ISS Sustaining Engineering |  |  | Ops.png |  | datatable[482] = new Array("483","475","CSA ISS Sustaining Engineering","8","Ops.png");
484 | 14 | 7 | NASA Mission Operations |  |  | Ops.png |  | datatable[483] = new Array("484","14","NASA Mission Operations","7","Ops.png");
485 | 14 | 7 | Industry Partners (Specify) |  |  | Ops.png |  | datatable[484] = new Array("485","14","Industry Partners (Specify)","7","Ops.png");
486 | 15 | 7 | Mission Science Support |  |  | Science.png |  | datatable[485] = new Array("486","15","Mission Science Support","7","Science.png");
487 | 481 | 8 | Science Maturation Studies & User Requirements |  |  | Science.png |  | datatable[486] = new Array("487","481","Science Maturation Studies & User Requirements","8","Science.png");
488 | 481 | 8 | Science Support for Mission Development |  |  | Science.png |  | datatable[487] = new Array("488","481","Science Support for Mission Development","8","Science.png");
489 | 481 | 8 | Science Support for Commissioning, Including Cal/Val |  |  | Science.png |  | datatable[488] = new Array("489","481","Science Support for Commissioning, Including Cal/Val","8","Science.png");
490 | 481 | 8 | Science Support for Data Handling |  |  | Science.png |  | datatable[489] = new Array("490","481","Science Support for Data Handling","8","Science.png");
491 | 15 | 7 | Science Utilization & Application Development |  |  | Science.png |  | datatable[490] = new Array("491","15","Science Utilization & Application Development","7","Science.png");

## 2 - Phasing Nomenclature
` Table of Contents
7 - Phasing Nomenclature | [5 empty] | What do you call your phases?
Why we we asking:
1. To normalize the naming convention across all investments.
2. Math Models are based on Costing Sub-Phase.
3. We want to output results in your naming convention and scope.
| Based on IGMF rev E |  |  | Based on CSA-FIN-RPT-0072
Phasing according to |  |  | Phasing according to |  |  | Phasing according to
EPMO |  |  | Costing |  |  | PM
|  |  | PREP | PREP 1 | Prototyping Activities (before Gate 1)
Pre-Project | Option Analysis & Planning Phase | Pre-Phase 0 |  | PREP 2 | Prototyping Activities (during Phase 0/A)
|  | Phase 0 | Phase 0/A | Phase 0 | Concept & Feasibility | Phase 0
Project | Definition Phase | Detailed Project Requirements |  | Phase A | Mission Requirements | Phase A
|  | Preliminary Definition | Phase B/C | Phase B | Preliminary Design | Phase B
|  | Detailed Definition |  | Phase C | Detailed Design | Phase C
| Implementation Phase | Implementation | Phase D | MAIT | Manufacturing, Assembly, Integration and Test of Canadian Subsystems and Components | Phase D
|  |  |  | SAIT | Spacecraft Level Assembly, Test | Phase D
|  |  |  | LEOP | Lauch and early operations | Phase D
Post-Project | Post-Implementation Phase | Operations & Disposal | Phase E | Phase E | Nominal Operations (per design life) | Phase E
|  |  | Phase E (EXT) | Phase X | Extended operations (mission extension)
|  |  | Phase F | Phase F | Disposal (incl. post-mortem audit reports) | Phase F
|  |  | Phase G | Phase G | Post-Mortem science utilization
Specify your labels
here. Repeat text if necessary. Leave blank if not included in your scope
Specify your labels
here. Repeat text if necessary. Leave blank if not included in your scope

## 3 - Phase Durations
` Table of Contents
7b - Phasing Durations
Why we we asking:
1. Durations affect Govt Salaries calculations
2. Durations affect Parametric estimates for Space segment, ground segment, ops
3. Schedule Scenarios are inputs to sensitivity analysis
| Schedule Scenario ID | 1
| Scenario Name | Nominal Schedule Used by Gaby for RAM calculation (PM Nomenclature)
| Scenario Description | The Schedule used for the salary calculations includes months of effort to prepare the governance
Rationale
Source Doc
| Phase | Expected Start | Expected End | Total D | Total M | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050
| Phase 0 | 2027-03-29 | 2028-08-05 | 495 | 16.274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.09863 | 12.0329 | 4.1753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase A | 2028-09-17 | 2034-04-28 | 2049 | 67.3644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.4438 | 12 | 12 | 12.0329 | 12 | 12 | 0.92055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase B1 | 2034-05-16 | 2035-03-28 | 316 | 10.389
| Phase B2 | 2035-05-03 | 2036-07-11 | 435 | 14.3014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.9808 | 3.3534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase C | 2036-08-11 | 2037-08-12 | 366 | 12.0329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6603 | 4.4055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase D | 2037-08-12 | 2040-09-02 | 1117 | 36.7233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6274 | 12 | 12.0329 | 5.0959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Phase E | 2041-03-29 | 2045-09-26 12:00 | 1642.5 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.09863 | 12 | 12 | 12.0329 | 12 | 5.9014 | 0 | 0 | 0 | 0
| Phase F | 2045-12-22 | 2046-03-22 | 90 | 2.9589
| Phase X | 2046-05-26 | 2046-06-25 | 30 | 0.9863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9918 | 0 | 0 | 0 | 0

## PM's sched Scenarios
|  | CA | 2027-10-01
Phase | Milestone | CSA | COS | DND | Worst case duration | Worst case (2 months delay) | realistic case duration | Baseline: Realistic case date (1 month delay par phase) | Optimistic case duration (EDA) | Optimistic case | Comments
B2 | Contract Award (CA) | CA | CA | CA | CA | CA | CA | 2027-10-01 | CA | CA | Kick-off is 1 month after contract award.
B2 | Payload PDR | CA + 5 mo | N/A | N/A | CA + 7 mo | 2028-05-01 | CA + 6 mo | 2028-04-01 | CA + 5 mo | 2028-02-01 | CSA develops the payload preliminary design and prepares for PDR.
B2 | Bus PDR | N/A | CA + 9 mo | N/A | CA + 11 mo | 2028-09-01 | CA + 9 mo | 2028-07-01 | CA + 8 mo | 2028-05-01 | COS is the selected bus vendor and proceeds with spacecraft bus development.
B2 | Preliminary Design Review (PDR) | CA + 5 mo | CA + 9 mo | N/A | CA + 11 mo | 2028-09-01 | CA + 9 mo | 2028-07-01 | CA + 8 mo | 2028-05-01 | Overall PDR establishes the preliminary integrated spacecraft design baseline.
C | Payload CDR | CA + 15 mo | N/A | N/A | CA + 18 mo | 2029-04-01 | CA + 15 mo | 2029-01-01 | CA + 13 mo | 2028-11-01 | CSA completes detailed payload design and payload-to-bus interfaces.
C | Bus CDR | N/A | CA + 18 mo | N/A | CA + 21 mo | 2029-07-01 | CA + 18 mo | 2029-04-01 | CA + 16 mo | 2028-08-01 | COS completes the detailed spacecraft bus design.
C | Overall CDR | CA + 18 mo | CA + 18 mo | N/A | CA + 21 mo | 2029-07-01 | CA + 18 mo | 2029-04-01 | CA + 16 mo | 2028-08-01 | Final integrated spacecraft design is reviewed before manufacturing.
D | Manufacturing Readiness Review (MRR) | CA + 20 mo | CA + 20 mo | N/A | CA + 23 mo | 2029-09-01 | CA + 20 mo | 2029-06-01 | CA + 18 mo | 2029-04-01 | Confirms readiness to begin major spacecraft and payload manufacturing.
D | Flatsat Integration & Test | CA + 24 mo | CA + 24 mo | N/A | CA + 27 mo | 2030-01-01 | CA + 24 mo | 2029-10-01 | CA + 22 mo | 2029-08-01 | Verifies avionics, software, communications and payload interfaces before flight integration.
D | Flight Hardware Complete | CA + 30 mo | CA + 30 mo | N/A | CA + 34 mo | 2030-10-01 | CA + 30 mo | 2030-04-01 | CA + 27 mo | 2030-01-01 | Flight hardware for both spacecraft is complete and ready for environmental testing.
D | Environmental Test Readiness Review (ETRR) | CA + 31 mo | CA + 31 mo | N/A | CA + 35 mo | 2030-11-01 | CA + 31 mo | 2030-05-01 | CA + 28 mo | 2030-02-01 | Confirms readiness for spacecraft-level environmental testing.
D | Payload 1 ready for integration | CA + 26 mo | N/A | N/A | CA + 30 mo | 2030-06-01 | CA + 26 mo | 2029-08-01 | CA + 23 mo | 2029-08-01 | CSA delivers the first flight payload for integration with the COS spacecraft bus.
D | Acceptance Review (AR/SAR) | CA + 35 mo | CA + 35 mo | N/A | CA + 40 mo | 2031-02-01 | CA + 35 mo | 2030-09-01 | CA + 32 mo | 2030-05-01 | Confirms completion of acceptance testing and required verification activities.
D | Launch Readiness Review (LRR) | CA + 37 mo | CA + 37 mo | N/A | CA + 42 mo | 2031-04-01 | CA + 37 mo | 2030-11-01 | CA + 34 mo | 2030-07-01 | Confirms spacecraft, ground segment, launch-site and operations readiness.
D | Flight Units Complete | CA + 37 mo | CA + 37 mo | N/A | CA + 42 mo | 2031-04-01 | CA + 37 mo | 2030-11-01 | CA + 34 mo | 2030-07-01 | Both SAM spacecraft are integrated, tested and accepted for launch.
D | Launch | CSA support | COS support | N/A | CA + 39 mo | 2031-06-01 | CA + 39 mo | 2031-01-01 | CA + 36 mo | 2030-09-01 | Commercial launch of the two spacecraft into the required HEO configuration. | 56 MOIS
D | Commissioning Complete Review (CCR) | CSA support | COS support | N/A | CA + 42 mo | 2031-09-01 | CA + 42 mo | 2031-04-01 | CA + 39 mo | 2030-12-01 | Confirms completion of spacecraft checkout, payload activation, calibration and initial imaging.
D | LEOP & Commissioning Complete | CSA support | COS support | N/A | CA + 42 mo | 2031-09-01 | CA + 42 mo | 2031-04-01 | CA + 39 mo | 2030-12-01 | Launch and Early Orbit Phase followed by commissioning of both spacecraft and establishment of coordinated HEO operations.
E | Operation | CSA support |  | DND OPS | CA + 43 mo | 2031-10-01 | CA + 43 mo | 2031-05-01 | CA + 40 mo | 2031-01-01 | Routine mission operations begin following successful commissioning; Government of Canada performs mission operations.

## GR&A (hidden)
Costing CSA Ground Rules & Assumptions template
Last review |  |  | 2025-03-31
ID | Catégorie | Category | Category | Sub-category | Items | GR or A | Title | Description | Phase | CBS # linked to GR&A | Impact on Project | Impact on costing, methodology, models, tools & analysis | Excepted source | Do not delete - Mireille | Source/Link | Other rational | Waiver deviation
1 | Hypothèses Programmatiques | Strategy Naratives | Objectifs politiques et stratégiques | Alignement sur la stratégie de l’ASC | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Strategy
2 | Hypothèses Programmatiques | Strategy Naratives | Objectifs politiques et stratégiques | Contraintes gouvernementales ou directives de haut niveau | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Strategy
3 | Hypothèses Programmatiques |  | Objectifs politiques et stratégiques | Type de mission : Flagship, LargeSat, SmallSat, NanoSat, Hosted Payload, Data stream partnership, data stream purchase | [8 empty] | CADRE Part A | CADRE Part A ou contants
4 | Hypothèses Programmatiques |  | Objectifs politiques et stratégiques | Disciplines et secteur : SatCom, Astronomie, exploration spatiale,... | [8 empty] | CADRE Part A | CADRE Part A
5 | Hypothèses Programmatiques |  | Objectifs politiques et stratégiques | Dépendances avec d'autres projets/missions | [8 empty] | CADRE Part A | CADRE Part A
6 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Soumission au Conseil du Tésor (TBSub) - But de l'exercice de costing : Budget Ask, Reprofiling,… Définir le nombre de TBSub + échéancier associé aux TBSub | [8 empty] | CADRE Part C onglet Stratégie contractuelle | Strategy
7 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Enveloppe de la masse salariale | [8 empty] | CADRE Part C onglet RAM | Strategy
8 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Enveloppe des frais de gestion et plan de voyages | [8 empty] | CADRE Part C onglet Overhead Costs | Strategy
9 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Méthodologie d'établissement des coûts | [8 empty] | Plan de l’exercice d’établissement des coûts | Costing Plan
10 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Note de réflexion supplémentaire | [9 empty] | Costing Plan
11 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Au moins 2 façon différentes pour chaque incluant RAM | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
12 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analyse de sensibilité | [8 empty] | À compléter par Finance | Costing Plan
13 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Sufficiency Report or Independent Cost Estimate or Independent Cost Review | [8 empty] | À compléter par Finance | Costing Plan
14 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analogie (nearest neighboors), lesquels. | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
15 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analyse paramétrique (True planning, PCEC, NCIM, SEER, Compact). CER Calibration Plan. | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
16 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Soumission de l'industrie et jugement d'expert | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
17 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Analyse Monte Carlo (crystal ball) | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
18 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Bottom up, qui le fait et comment | [8 empty] | Plan de l’exercice d’établissement des coûts - Méthodologies | Costing Plan
19 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Learning curves | [8 empty] | RASCI = qui fait quoi. bottom up = Plan de l’exercice d’établissement des coûts | Costing Plan
20 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Inducteurs de coûts princicaux | [8 empty] | CADRE Part C onglet CER & Tools | Costing Plan
21 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Normalisation ( Stochométrie) - si applicable | [8 empty] | le choix de l'outil dicte CADRE part B qui collecte info pour l'analyse paramétrique | Costing Plan
22 | Hypothèses Programmatiques | Costign Plan | Budget global et financement | Tracabilité - accès aux sources - répertoires normalisés -liens | [8 empty] | CADRE Part C onglet CER & Tools | Costing Plan
23 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Stratégie de financement | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Strategy
24 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Limitation des coûts : Par exemple, les sources de financement instables, les contraintes de personnel ou un budget à ne pas dépasser devraient être documentés. | [8 empty] | CADRE Part C onglet Stratégie contractuelle | Strategy
25 | Hypothèses Programmatiques | Strategy Naratives | Budget global et financement | Enveloppe Services internes - O&M et RAM | [8 empty] | CADRE Part C onglet Services internes | Strategy
26 | Hypothèses Programmatiques | OBS | Partenariats (OGD, internationaux, industriels) | Rôles et responsabilités des principaux partenaires (agences spatiales, industriels, universités et autres ministères) | [8 empty] | CADRE Part C onglet OBS | OBS
27 | Hypothèses Programmatiques | OBS | Partenariats (OGD, internationaux, industriels) | Modalités de partage des coûts et des risques | [8 empty] | CADRE Part C onglet OBS - Cost Sharing provisions | OBS
28 | Hypothèses Programmatiques | Strategy Naratives | Partenariats (OGD, internationaux, industriels) | Si applicable, dépenses éligibles de l'OTAN | [8 empty] | À définir ici | Strategy
29 | Hypothèses Programmatiques | 8. Economic Constants and short answers | Gouvernance et autorités | Ordre de grandeur général du projet (petit, moyen, grand, flagship) | [8 empty] | CERCES scale | Constants
30 | Hypothèses Programmatiques | Costign Plan | Gouvernance et autorités | Nature of the costing perimeter (degree of difficulty of costing exercise) | [8 empty] | Plan de l’exercice d’établissement des coûts | Costing Plan
31 | Hypothèses Programmatiques | 8. Economic Constants and short answers | Gouvernance et autorités | Palier/ Tier | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Constants
32 | Hypothèses Programmatiques | 8. Economic Constants and short answers | Gouvernance et autorités | PCRA | [8 empty] | Business Case et/ou CADRE Part C onglet CM list | Constants
33 | Hypothèses Programmatiques | Milestone Register | Gouvernance et autorités | Point de décision | [8 empty] | CADRE Part C - onglet Phasing Model | Milestone Register
34 | Hypothèses Programmatiques | Costign Plan | Gouvernance et autorités | Costing Exercise Schedule and associated milestones - Costing Plan, Internal WebReport Dashboard and power BI dashboard for CLAD | [8 empty] | Plan de l’exercice d’établissement des coûts | Costing Plan
35 | Hypothèses Financières | 8. Inflation Model | Indices économiques et inflation | Taux d’inflation annuel, indice utilisé (IPC, indice sectoriel), taux de déflation | [8 empty] | Inflation Model dans son propre document - Oracle db ID | Inflation Model
36 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | Taux EBP 27% | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
37 | Hypothèses Financières | 8. Inflation Model | Indices économiques et inflation | Modèle d'inflation appliqué | [8 empty] | Inflation Model dans son propre document - Oracle db ID | Inflation Model
38 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | Année de base / Base year | [9 empty] | Constants
39 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | SSC 4% | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
40 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | PSPC 13% | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
41 | Hypothèses Financières | 8. Economic Constants and short answers | Indices économiques et inflation | Taux du Fairness Monitor | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
42 | Hypothèses Financières | 8. Economic Constants and short answers | Taux de change | Monnaies concernées et valeur de référence (CAD, USD, EUR, etc.) | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
43 | Hypothèses Financières | 8. Economic Constants and short answers | Taux de change | Seuil de variation accepté avant révision budgétaire | [8 empty] | Defined in constnats, used in risk analysis. risk reserve - Risk register | Constants
44 | Hypothèses Financières | 8. Economic Constants and short answers | Contingence et marges de sécurité | Pourcentage de contingence sur le coût total du projet (p. ex. 10 à 20 %) | [8 empty] | Defined in constnats, used in risk analysis. risk register onglet. Unknown-Unknown Risk margin | Constants
45 | Hypothèses Financières | Strategy Naratives | Contingence et marges de sécurité | Barème d’évaluation des risques majeurs pour justifier la marge appliquée (modèle d’analyse de risques) | [8 empty] | À définir ici | Strategy | Je ne comprends pas la question
46 | Hypothèses Financières | Procurement Plan | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Sunk Costs Report (STDP, EOADP, Cap Demo, Stedia FAST, ESA Program, Cubesats, space hub, Pre-Phase 0 etc) | [8 empty] | CADRe part C - Expenditure plan | Procurement Plan
47 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stratégie contractuel Phase 0/A - 1 / 2 contrats | [8 empty] | CADRe Part C - Procurement strategy | Strategy
48 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Note de réflexion supplémentaire | [9 empty] | Strategy
49 | Hypothèses Financières | Procurement Plan | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Nombre de contrats et valeur approximative prévus par phase | [8 empty] | CADRe Part C - Procurement Plan (list) | Procurement Plan
50 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Contrats en parallèle avec des concepts différents et un down select | [8 empty] | CADRe Part C - Procurement strategy | Strategy
51 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Agile ou waterfall | [8 empty] | CADRe Part C - Procurement strategy | Strategy
52 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | STDP ou CapDemo en même temps que la phase 0 ou A | [8 empty] | PREP 2 | Strategy
53 | Hypothèses Financières | OBS | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Les fournisseurs attendus et leur capacite de production | [8 empty] | OBS | OBS
54 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Type de SOW - SOW directif versus une architecture de mission proposée par le fournisseur | [8 empty] | CADRe Part C - Procurement strategy | Strategy
55 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Freedom of Design of Vendor | [8 empty] | CADRE Part C onglet OBS Maturité orgnisationelle du fourniseur | Strategy
56 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Types de contrat – source unique ou compétitif (Contrat dirigé en Phase E ops aura une incidence sur le design du ground segment) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
57 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Types de contrat – cout remboursable ou prix ferme | [8 empty] | CADRe Part C - Procurement strategy | Strategy
| Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Type de contrat: gonogo, options, milestones in April for CAFÉ | [9 empty] | Strategy | Split next line into 2
58 | Hypothèses Financières | 12 - Dispose, Divest, Descope, Delay | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Gestion du scope change et des risques dans chaque situation : cout remboursable (TA, options, gouvernance) ; prix ferme (descope, go no go, qualité du SOW a décrire le scope) | [8 empty] | Descope est dans DDD | DDDD
59 | Hypothèses Financières |  | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | G&C (cassiope ou radarsat 2) nous appartient pas | [8 empty] | Business model (CADRe part A) et le procurement strategy le repete | CADRE Part A
60 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | incitatif commercial (ex. modele de commercialization comme WFS) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
61 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Pour chaque phase et sous-systeme majeur - CSA led, industry led, academia led (ex. En Phase E, CSA va mener les operations) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
62 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Competitif - ouvert a l'international | [8 empty] | CADRe Part C - Procurement strategy | Strategy
63 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Competitif - ouvert au Canada | [8 empty] | CADRe Part C - Procurement strategy | Strategy
64 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Fausse competition | [8 empty] | CADRe Part C - Procurement strategy | Strategy
65 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | monopole | [8 empty] | CADRe Part C - Procurement strategy | Strategy
66 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Dependences : Le fournisseur X doit etre le meme fournisseur que le fournisseur Y (Ex. Data processing handled by same supplier) | [8 empty] | CADRe Part C - Procurement strategy | Strategy
67 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Long lead Item - flux de trésorie en capital vs contrat vs échéancier | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Strategy
68 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Contenu Canadien | [8 empty] | CADRe Part C - Procurement strategy | Strategy
69 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Chaque contrat couvre quel partie du travail, liste d'inclusions et exclusions. List of inclusions and exclusions | [8 empty] | CBS Dictionary | Strategy
70 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | GFE and GFS (ex. DFL) | [8 empty] | CBS Dictionary | Strategy
71 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Frais de transport et responsabilité | [8 empty] | CBS Dictionary | Strategy
72 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Frais d'assurance et limitation de responsabilité | [8 empty] | CBS Dictionary | Strategy
73 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Qualité du SOW | [8 empty] | RISK posture | Strategy
74 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stabilité des exigences. Par exemple, des exigences très instables, un nombre standard de demandes de modification technique, des exigences stables avec peu ou pas de changements attendus, etc. | [8 empty] | CADRe Part C - Procurement strategy | Strategy
75 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Résultats du RFI | [8 empty] | Procurement strategy | Strategy
76 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stratégie contractuelle Phase BCD - Concurrentiel, source unique (voir note de réflexion du point 2.4.1) | [8 empty] | Procurement strategy | Strategy
77 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Stratégie contractuelle Phase EF - Concurrentiel, source unique (voir note de réflexion du point 2.4.1) | [8 empty] | Procurement strategy | Strategy
78 | Hypothèses Financières | Strategy Naratives | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Capacité du vendeur dans le marché actuel, surcharge contractuel, effectif disponible | [8 empty] | OBS Maturité orgnisationelle du fourniseur | Strategy
79 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Taux standard pour les ingénieurs, techniciens, gestionnaires, etc. | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
80 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Taux spécifiques pour les consultants ou experts externes | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
81 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Barème pour les appels d’offres et la sous-traitance (plafonds, politiques internes) | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
82 | Hypothèses Financières | 8. Economic Constants and short answers | Stratégie contractuelle, coûts de main-d’œuvre et de sous-traitance | Taux de frais et de profit appliqué au contrat | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
83 | Hypothèses Financières | Risk Register | Plan de gestion des risques financiers | Existence d’une réserve pour risques identifiés (p. ex. volatilité du marché, retards de paiement) | [8 empty] | Registre de risque | Risk Register
84 | Hypothèses Financières | 12 - Dispose, Divest, Descope, Delay | Plan de gestion des risques financiers | Descope Plan and other strategies to deal with funding shortfalls, | [8 empty] | À définir ici et lié au CADRE Part C - onglet DDDD | DDDD
85 | Hypothèses Financières | Procurement Plan | Plan de gestion des risques financiers | Source of funding for each CBS element and Risk to A-Base | [8 empty] | Expenditure plan | Procurement Plan
86 | Hypothèses Financières | 8. Economic Constants and short answers | Taxes | Pays, province et taux de taxes applicables | [8 empty] | Financial Constants Reports - CSA-FIN-RPT-XXXX rev 3 | Constants
87 | Hypothèses Techniques (Space & Ground Segment) | TRRA | Technologie et niveau de maturité (TRL) | TRL initial prévu pour les composants clés | [8 empty] | CADRE Part C onglet TRL | TRL
88 | Hypothèses Techniques (Space & Ground Segment) | TRRA | Technologie et niveau de maturité (TRL) | Objectifs de TRL à atteindre pour chaque phase du projet | [8 empty] | CADRE Part C onglet TRL | TRL
89 | Hypothèses Techniques (Space & Ground Segment) | 4a. CBS and CBS Dictionary | Sous-systèmes et architecture globale | Liste et description des principaux sous-systèmes (structure, propulsion, contrôle d’attitude, communication, etc.) | [8 empty] | CBS | CBS
90 | Hypothèses Techniques (Space & Ground Segment) | TRRA | Sous-systèmes et architecture globale | Interfaces critiques (par ex. protocole de communication, alignement mécanique) | [8 empty] | TRL assessment tab - worry list | TRL
91 | Hypothèses Techniques (Space & Ground Segment) | Costign Plan | Sous-systèmes et architecture globale | This ground rule should state, at a high level, what is within scope of the estimate. For example, an estimate may cover the space segment, ground segment, and government oversight during phases B, C and D. Further clarification should be given if required, such as refurbishment of the ground segment rather than complete rebuild. | [8 empty] | Perimeter of costing exercise. Further Claraifications in CBs dictionary | Costing Plan
92 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | Stratégie de validation (modèles d’ingénierie, prototypes, simulations) | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
93 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | Méthodes d’essais en environnement (thermique, vibration, vide, etc.) | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
94 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | This assumption should state the expected build approach for the mission. For example, the bus/platform and payloads could be built in series or parallel. | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
95 | Hypothèses Techniques (Space & Ground Segment) |  | Durée de vie du projet et cycles de développement | This assumption should state the cost improvement curve, as a percentile, for any items to be acquired with more than a single unit. If appropriate, items should be marked as Xth unit within a lot, such as the 8th unit, to allow for cost improvement curve theory to be reflected. | [8 empty] | CADRE Part C onglet QUANTITIES - LLI, spares, EM, PFM, RE-NRE | Quantities
96 | Hypothèses Techniques (Space & Ground Segment) | Engineering Parameters in CADRe part B | Contraintes techniques spécifiques | Estimation de masse et de volume du système | [8 empty] | CADRE part B | CADRE part B
97 | Hypothèses Techniques (Space & Ground Segment) | Engineering Parameters in CADRe part B | Contraintes techniques spécifiques | Consommation électrique maximale | [8 empty] | CADRE part B | CADRE part B
98 | Hypothèses Techniques (Space & Ground Segment) | Engineering Parameters in CADRe part B | Contraintes techniques spécifiques | Besoins minimaux pour assurer la fiabilité | [8 empty] | CADRE part B | CADRE part B
99 | Hypothèses Qualité, Fiabilité et Sécurité | Strategy Naratives | Normes et standards de qualité | ECSS-Q-ST-20, ISO 9001, etc. | [8 empty] | À définir ici | Strategy
100 | Hypothèses Qualité, Fiabilité et Sécurité | Strategy Naratives | Normes et standards de qualité | Méthodes d’assurance qualité (revues, audits internes et externes) | [8 empty] | À définir ici | Strategy
101 | Hypothèses Qualité, Fiabilité et Sécurité | 8. Economic Constants and short answers | Safety and mission assurance | Classe de Mission | [8 empty] | À définir ici | Constants
102 | Hypothèses Qualité, Fiabilité et Sécurité | Strategy Naratives | Safety and mission assurance | La mesure de la surveillance et de la rigueur appliquées par la CSA | [8 empty] | À définir ici | Strategy
103 | Hypothèses Opérationnelles | RAM | Ressources humaines et expertise | Équipe de base (ETP internes) et besoins en personnel spécialisé externe | [8 empty] | CADRE Part C onglet RAM | RAM
104 | Hypothèses Opérationnelles | Strategy Naratives | Ressources humaines et expertise | Disponibilité du personnel et plan de montée en compétence | [8 empty] | À définir ici | Strategy
105 | Hypothèses Opérationnelles | Milestone Register | Calendrier, jalons et ressources temporelles | Dates clés (ex. PDR – Preliminary Design Review, CDR – Critical Design Review, FRR – Flight Readiness Review) / Project Milestone Register (short report, detailed report) | [8 empty] | milestone Register | Milestone Register
106 | Hypothèses Opérationnelles |  | Calendrier, jalons et ressources temporelles | Diagram of Phase Overlaps and Gaps | [8 empty] | we draw it form phasing | GANTT Charts
107 | Hypothèses Opérationnelles | Schedule Constraints and Dependencies | Calendrier, jalons et ressources temporelles | Marges pour délais | [8 empty] | Phasing Model, phases | Schedule Constraints
108 | Hypothèses Opérationnelles | 12 - Dispose, Divest, Descope, Delay | Calendrier, jalons et ressources temporelles | Gestion des retards : conditions de replanification, procédures d’escalade | [8 empty] | À définir ici et lié au CADRE Part C - onglet DDDD | DDDD
109 | Hypothèses Opérationnelles | Phasing Schedules | Calendrier, jalons et ressources temporelles | Modèle de phase utilisé pour analyse de sensibilité (Phasing Model) | [8 empty] | Phasing model (for risk analysis) | Phasing Schedules
110 | Hypothèses Opérationnelles | Phasing Schedules | Calendrier, jalons et ressources temporelles | Échéancier de l'industrie | [8 empty] | Phasing model (for risk analysis) | Phasing Schedules
111 | Hypothèses Opérationnelles | Phasing Schedules | Calendrier, jalons et ressources temporelles | Schedule Scenarios for sensitivity analysis : Adjust Durations - optimistic, pessimistic and expected | [8 empty] | Phasing model (for risk analysis) | Phasing Schedules
112 | Hypothèses Opérationnelles | Strategy Naratives | Planification des infrastructures et installations | Is DFL being used as GFE | [8 empty] | DFL being used? Strategy | Strategy
112 | Hypothèses Opérationnelles | 4a. CBS and CBS Dictionary | Planification des infrastructures et installations | Lieux de développement, sites d’intégration et de test (chambres à vide, bancs de test) | [8 empty] | CBS Dictionary - Ground Segment - Test facilities | CBS Dictionary
113 | Hypothèses Opérationnelles | Schedule Constraints and Dependencies | Planification des infrastructures et installations | Disponibilité des installations (ex. créneaux de test partagés avec d’autres projets) | [8 empty] | schedule risk = risk register -> pessimistic schedule model | Schedule Constraints
114 | Hypothèses Opérationnelles | Schedule Constraints and Dependencies | Gestion de la logistique et de la chaîne d’approvisionnement | Délai de livraison des composants critiques (satellites, propulseurs, éléments électroniques) | [8 empty] | schedule risk = risk register -> pessimistic schedule model | Schedule Constraints
115 | Hypothèses Opérationnelles | Strategy Naratives | Gestion de la logistique et de la chaîne d’approvisionnement | Plans de contingence en cas de rupture d’approvisionnement | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | Strategy
116 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | Description des opérations prévues : phases de lancement, mise à l’orbite, opérations nominales, etc. | [8 empty] | Cadre part A | CADRE Part A
117 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | Mode de supervision et contrôle (centres de contrôle, horaires, équipes) | [8 empty] | À définir ici | Cadre Part A
118 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | Mission Operation Center | [8 empty] | À définir ici | Cadre Part A
119 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | GoC Science Operation Centers (SOCs) | [8 empty] | À définir ici | Cadre Part A
120 | Hypothèses Opérationnelles |  | Plan de gestion de mission (SatOps) | External Science Operation Centers (ESOCs) | [8 empty] | À définir ici | Cadre Part A
121 | Hypothèses sur la science | Schedule Constraints and Dependencies | Science et applications | Échéancier lié au volet de science du projet | [9 empty] | Schedule Constraints
122 | Hypothèses sur la science | Strategy Naratives | Science et applications | Expected cost of science utilization related to the mission. | [9 empty] | Strategy
123 | Hypothèses sur la science | Strategy Naratives | Portée de la mission sur le milieu public et académique | Coût en lien avec la portée de la mission | [8 empty] | À définir ici | Strategy
124 | Hypothèses Lancement |  | Véhicule de lancement | Sélection du lanceur (ex. Falcon 9, Ariane, etc.) ou fenêtre de lancement partagée | [8 empty] | Cadre part A | CADRE Part A
125 | Hypothèses Lancement |  | Véhicule de lancement | Capacités du lanceur (masse, volume, orbite cible) | [8 empty] | Cadre part A un petit peu et le reste dans le LV database CM list | CADRE Part A
126 | Hypothèses Lancement | Schedule Constraints and Dependencies | Calendrier de lancement | Fenêtres de lancement disponibles (contraintes de météo, alignement orbital, etc.) | [8 empty] | schedule risk = risk register -> pessimistic schedule model | Schedule assumptions and constraints for JCL Analysis
127 | Hypothèses Lancement | 12 - Dispose, Divest, Descope, Delay | Calendrier de lancement | Contingences pour reports éventuels | [8 empty] | schedule risk = risk register -> pessimistic schedule model | DDDD
128 | Hypothèses Lancement | OBS | Contrat et services associés | Responsabilités du fournisseur de lancement (intégration, tests, qualification) | [8 empty] | OBS (roles et responsiblity) - CSa qui paye ou MDa qui paye | OBS
129 | Hypothèses Lancement | 4a. CBS and CBS Dictionary | Contrat et services associés | Assurances (couverture du satellite, du lanceur, etc.) | [8 empty] | CBS Dictionary - if insurance | CBS Dictionary
130 | Hypothèses Opérations en orbite |  | Mode opératoire | Gestion du satellite ou rover (téléopération vs. autonomie) | [9 empty] | Cadre Part A
131 | Hypothèses Opérations en orbite | Engineering Parameters in CADRe part B | Mode opératoire | Durée et fréquence des communications | [8 empty] | CADRE Part B | CADRE part B
132 | Hypothèses Opérations en orbite |  | Maintenance, réparations et évolutions | Possibilité ou non de mise à jour logicielle en vol (OTA updates) | [8 empty] | CADRE part A - Bus FSW section | CADRE Part A
133 | Hypothèses Opérations en orbite |  | Maintenance, réparations et évolutions | Stratégiques de réparation ou d’assistance robotique | [8 empty] | CADRE part A - does it have any robotic repair interfaces | CADRE Part A
134 | Hypothèses Opérations en orbite | 12 - Dispose, Divest, Descope, Delay | Fin de mission et désorbitation | Scénario de désorbitation contrôlée ou passivation (réservoirs, batteries) | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
135 | Hypothèses Opérations en orbite | 12 - Dispose, Divest, Descope, Delay | Fin de mission et désorbitation | Dépôt sur orbite-cimetière pour le matériel en fin de vie (si admissible) | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
136 | Hypothèses Opérations en orbite | Strategy Naratives | Flux de documentation et reporting | Fréquence des rapports d’avancement (hebdomadaires, mensuels) | [8 empty] | À définir ici | Strategy
137 | Hypothèses Opérations en orbite | Strategy Naratives | Classifications et diffusion | Niveau de confidentialité (projet public, secret défense, propriété intellectuelle) | [8 empty] | À définir ici | Strategy
138 | Hypothèses Opérations en orbite | Strategy Naratives | Classifications et diffusion | Politiques de publication ou de diffusion des résultats | [8 empty] | À définir ici et/ou Business Case | Strategy
139 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Réglementations gouvernementales | Exigences fédérales (agences spatiales, ministères, etc.) | [8 empty] | À définir ici et/ou Business Case | Strategy
140 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Réglementations gouvernementales | Normes internationales (ECSS, ISO, NASA, CSA, etc.) | [8 empty] | À définir ici et/ou Business Case | Strategy
141 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Réglementations gouvernementales | Règles et régulations afférentes | [8 empty] | À définir ici et/ou Business Case | Strategy
142 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Contrôle à l’exportation (ex. ITAR, EAR) | Identification des composants ou technologies soumis à licences | [8 empty] | À définir ici | Strategy
143 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Contrôle à l’exportation (ex. ITAR, EAR) | Implications sur la gestion des fournisseurs et des partenaires étrangers | [8 empty] | À définir ici | Strategy
144 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Sécurité et sûreté | Mesures de cybersécurité (protection des données, des communications, etc.) | [8 empty] | À définir ici | Strategy
145 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Sécurité et sûreté | Exigences de sûreté pour le personnel et les installations (accès restreints, habilitations) | [8 empty] | À définir ici | Strategy
146 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Droit spatial et aspects juridiques | Propriété et exploitation des données spatiales | [8 empty] | À définir ici | Strategy
147 | Hypothèses Légales, Réglementaires et Sécuritaires | 12 - Dispose, Divest, Descope, Delay | Droit spatial et aspects juridiques | Protocole en cas de débris spatiaux, en fin de vie du satellite | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
148 | Hypothèses Légales, Réglementaires et Sécuritaires | Strategy Naratives | Propriété intellectuelle | Propriété intellectuel en lien avec le projet - enjeux | [8 empty] | À définir ici et/ou Business Case | Strategy
149 | Hypothèses Environnementales | 12 - Dispose, Divest, Descope, Delay | Gestion des débris spatiaux | Respect des lignes directrices d’atténuation des débris (liaisons, désorbitation en fin de vie) | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
150 | Hypothèses Environnementales | 12 - Dispose, Divest, Descope, Delay | Gestion des débris spatiaux | Méthodes envisagées pour minimiser la pollution orbitale | [8 empty] | CADRE Part C onglet DDDD - dispose, descope, divest, delay | DDDD
151 | Hypothèses Environnementales | Green space | Impacts environnementaux terrestres | Contrôle des émissions lors du lancement (polluants, bruit, etc.) | [8 empty] | CADRE Part C onglet Green Space | Green Space
152 | Hypothèses Environnementales | Strategy Naratives | Impacts environnementaux terrestres | Politique de recyclage ou de réutilisation des composants | [8 empty] | CADRE Part C onglet Green Space | Strategy
153 | Hypothèses sur le risques | Risk Register | Risques | Risque du Projet Phase A à D | [8 empty] | Registre de risque | Risk Register
154 | Hypothèses sur le risques | Risk Register | Risques | Risque du Projet Phase E | [8 empty] | Registre de risque | Risk Register
155 | Hypothèses sur le risques | Risk Register | Risques | Risque du Projet Phase F | [8 empty] | Registre de risque | Risk Register
156 | Hypothèses sur le risques | Risk Register | Risques | Risque Science | [8 empty] | Registre de risque | Risk Register
157 | Hypothèses sur le risques | Risk Register | Risques | Risque Salaire | [8 empty] | Registre de risque | Risk Register
158 | Hypothèses sur le risques | Risk Register | Risques | Schedule Risk Assessment file (ms project) as input to the Joint Cost and Schedule Confidence Analysis Report | [8 empty] | Registre de risque | Risk Register
159 | Hypothèses sur le risques | Risk Register | Risques | Registre de risque | [8 empty] | Registre de risque | Risk Register
160 | Hypothèses sur le risques | Strategy Naratives | Risques | Aspect critique de la mission et impact si la mission n'est pas respectée | [8 empty] | minimum mission success criteria - DRM - CADRE part C Taxon | Strategy
161 | Hypothèse sur les mesures de performance par la valeur acquise | CADRe part D - EVM | Mesures de performance par la valeur acquise (EVM = Earn Value Management) | Seuil orange et rouge pour EVM justifiant une réduction de la portée, une replanification | [9 empty] | pas dans ce fichier, pas avant PDR
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343

## 4 - RAM LoE
` Table of Contents
9 - RAM LoE Inputs
Why we we asking:
to salculate salaries
| These are defaults | These are provided by PM | Auto from Name | Headers are populated from Tab #2 where you pick names | Calculated using durations above, and rates on left
| dB ID |  | Name | Role on Project | New or Existing | Level | Rate | 0 | Planning | B | C | D | E | F | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036
| 1 | CSA - Project Team | Justin | Project Manager; PM; Project Manager; Commitment=Commitment; Space Segment; SU; ESS; ZZZ-0001; Max Echelon; Labour Rates; FF-CSA | Exisiting | EN-ENG-06 | 174775 | 20% | 40% | 40% | 50% | 60% | 25% | 10% | 0.3 FTE | 0.4 FTE | 0.4 FTE | 0.6 FTE | 0.6 FTE | 0.4 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.1 FTE
| 2 | CSA - Project Team | Arian | Systems Engineering; Systems Engineering; Systems Engineer; Commitment=0.0; Space Segment; SU; ESS; ZZZ-0002; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-06 | 174775 | 0% | 25% | 60% | 80% | 90% | 20% | 5% | 0.2 FTE | 0.6 FTE | 0.7 FTE | 0.9 FTE | 0.9 FTE | 0.4 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.1 FTE
| 3 | CSA - Project Team | Clara | Systems Engineering; Mission Requirements; Requirements Engineer; Commitment=0.7; Space Segment; SU; ESS; ZZZ-0003; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-05 | 157770 | 70% | 30% | 70% | 80% | 40% | 5% | 0% | 0.6 FTE | 0.7 FTE | 0.7 FTE | 0.5 FTE | 0.4 FTE | 0.2 FTE | 0.1 FTE | 0.1 FTE | 0.1 FTE | 0.1 FTE | 0.0 FTE
| 4 | CSA - Payload Team | Thomas | Payload Engineering; Payload Systems; Payload Systems Engineer; Commitment=0.2; Space Segment; SU; ESS; ZZZ-0004; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-06 | 174775 | 20% | 25% | 50% | 70% | 90% | 20% | 0% | 0.3 FTE | 0.5 FTE | 0.6 FTE | 0.9 FTE | 0.9 FTE | 0.4 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.1 FTE
| 5 | CSA - Payload Team | Sophie | Payload Engineering; Optical Systems; Optical Engineer; Commitment=0.4; Space Segment; SU; ESS; ZZZ-0005; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-05 | 157770 | 40% | 20% | 40% | 70% | 80% | 10% | 0% | 0.4 FTE | 0.4 FTE | 0.5 FTE | 0.8 FTE | 0.8 FTE | 0.3 FTE | 0.1 FTE | 0.1 FTE | 0.1 FTE | 0.1 FTE | 0.0 FTE
| 6 | CSA - Payload Team | Marc | Payload Engineering; Detector Engineering; Detector Engineer; Commitment=0.9; Space Segment; SU; ESS; ZZZ-0006; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-05 | 157770 | 90% | 15% | 30% | 60% | 70% | 10% | 0% | 0.6 FTE | 0.3 FTE | 0.4 FTE | 0.7 FTE | 0.7 FTE | 0.3 FTE | 0.1 FTE | 0.1 FTE | 0.1 FTE | 0.1 FTE | 0.0 FTE
| 7 | CSA - Payload Team | Elena | Payload Engineering; Remote Sensing; Remote Sensing Specialist; Commitment=0.5; Space Segment; SU; ESS; ZZZ-0007; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-05 | 157770 | 50% | 15% | 30% | 60% | 60% | 20% | 0% | 0.4 FTE | 0.3 FTE | 0.4 FTE | 0.6 FTE | 0.6 FTE | 0.3 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.1 FTE
| 8 | CSA - Payload Team | David | Payload Engineering; Payload Electronics; Payload Electronics Engineer; Commitment=0.9; Space Segment; SU; ESS; ZZZ-0008; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-05 | 157770 | 90% | 20% | 40% | 70% | 90% | 25% | 0% | 0.6 FTE | 0.4 FTE | 0.5 FTE | 0.9 FTE | 0.9 FTE | 0.5 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.1 FTE
| 9 | CSA - Payload Team | Nadia | Payload Engineering; Calibration; Payload Calibration Engineer; Commitment=1.0; Space Segment; SU; ESS; ZZZ-0009; Max Echelon; Labour Rates; FF-CSA | New | EN-ENG-05 | 157770 | 100% | 10% | 20% | 60% | 80% | 30% | 10% | 0.6 FTE | 0.2 FTE | 0.4 FTE | 0.8 FTE | 0.8 FTE | 0.5 FTE | 0.3 FTE | 0.3 FTE | 0.3 FTE | 0.3 FTE | 0.1 FTE
| 10 | CSA - Payload Team | Liam | Software Engineering; Payload Software; Payload Software Engineer; Commitment=0.9; Space Segment; SU; ESS; ZZZ-0010; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-05 | 157770 | 90% | 20% | 30% | 60% | 90% | 30% | 5% | 0.6 FTE | 0.3 FTE | 0.4 FTE | 0.8 FTE | 0.9 FTE | 0.5 FTE | 0.3 FTE | 0.3 FTE | 0.3 FTE | 0.3 FTE | 0.1 FTE
| 11 | CSA - Payload Team | Amira | Software Engineering; Data Processing; Payload Data Processing Engineer; Commitment=0.5; Space Segment; SU; ESS; ZZZ-0011; Max Echelon; Labour Rates; FF-CSA | New | EN-ENG-05 | 157770 | 50% | 10% | 20% | 40% | 80% | 50% | 10% | 0.3 FTE | 0.2 FTE | 0.3 FTE | 0.7 FTE | 0.8 FTE | 0.6 FTE | 0.5 FTE | 0.5 FTE | 0.5 FTE | 0.5 FTE | 0.2 FTE
| 12 | CSA - Payload Team | Julien | Electrical Engineering; Electrical Interfaces; Electrical Engineer; Commitment=0.7; Space Segment; SU; ESS; ZZZ-0012; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-05 | 157770 | 70% | 20% | 40% | 60% | 80% | 20% | 0% | 0.5 FTE | 0.4 FTE | 0.5 FTE | 0.8 FTE | 0.8 FTE | 0.4 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.1 FTE
| 13 | CSA - Project Team | Émile | Mechanical Engineering; Mechanical Integration; Mechanical Engineer; Commitment=0.3; Space Segment; SU; ESS; ZZZ-0013; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-05 | 157770 | 30% | 20% | 30% | 50% | 70% | 10% | 0% | 0.3 FTE | 0.3 FTE | 0.4 FTE | 0.6 FTE | 0.7 FTE | 0.3 FTE | 0.1 FTE | 0.1 FTE | 0.1 FTE | 0.1 FTE | 0.0 FTE
| 14 | CSA - Project Team | Hannah | Thermal Engineering; Thermal Control; Thermal Engineer; Commitment=0.5; Space Segment; SU; ESS; ZZZ-0014; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-05 | 157770 | 50% | 20% | 30% | 50% | 80% | 15% | 0% | 0.4 FTE | 0.3 FTE | 0.4 FTE | 0.7 FTE | 0.8 FTE | 0.4 FTE | 0.1 FTE | 0.1 FTE | 0.1 FTE | 0.1 FTE | 0.0 FTE
| 15 | CSA - Project Team | Owen | Software Engineering; Flight Interfaces; Flight Software Engineer; Commitment=0.3; Space Segment; SU; ESS; ZZZ-0015; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-05 | 157770 | 30% | 15% | 20% | 50% | 80% | 40% | 5% | 0.2 FTE | 0.2 FTE | 0.3 FTE | 0.7 FTE | 0.8 FTE | 0.5 FTE | 0.4 FTE | 0.4 FTE | 0.4 FTE | 0.4 FTE | 0.1 FTE
| 16 | CSA - Project Team | Claire | Integration and Test; Payload Integration; Integration and Test Engineer; Commitment=0.9; Space Segment; SU; ESS; ZZZ-0016; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-05 | 157770 | 90% | 10% | 10% | 30% | 90% | 20% | 5% | 0.5 FTE | 0.1 FTE | 0.2 FTE | 0.8 FTE | 0.9 FTE | 0.4 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.1 FTE
| 17 | CSA - Project Team | Noah | Integration and Test; Environmental Testing; Test Engineer; Commitment=0.7; Space Segment; SU; ESS; ZZZ-0017; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-05 | 157770 | 70% | 10% | 10% | 30% | 85% | 15% | 0% | 0.4 FTE | 0.1 FTE | 0.2 FTE | 0.7 FTE | 0.8 FTE | 0.4 FTE | 0.1 FTE | 0.1 FTE | 0.1 FTE | 0.1 FTE | 0.0 FTE
| 18 | CSA - Project Team | Isabelle | Integration and Test; Verification and Validation; Verification Engineer; Commitment=0.9; Space Segment; SU; ESS; ZZZ-0018; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-05 | 157770 | 90% | 15% | 20% | 50% | 90% | 30% | 5% | 0.5 FTE | 0.2 FTE | 0.3 FTE | 0.8 FTE | 0.9 FTE | 0.5 FTE | 0.3 FTE | 0.3 FTE | 0.3 FTE | 0.3 FTE | 0.1 FTE
| 19 | CSA - Project Team | William | Mission Assurance; Quality Assurance; Quality Assurance Engineer; Commitment=0.5; Space Segment; SU; ESS; ZZZ-0019; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-05 | 157770 | 50% | 15% | 15% | 40% | 75% | 25% | 5% | 0.3 FTE | 0.1 FTE | 0.3 FTE | 0.7 FTE | 0.8 FTE | 0.4 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.1 FTE
| 20 | CSA - Project Team | Emma | Mission Assurance; Reliability; Reliability Engineer; Commitment=0.8; Space Segment; SU; ESS; ZZZ-0020; Max Echelon; Labour Rates; FF-CSA | New | EN-ENG-05 | 157770 | 80% | 10% | 10% | 40% | 70% | 25% | 5% | 0.5 FTE | 0.1 FTE | 0.2 FTE | 0.6 FTE | 0.7 FTE | 0.4 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.1 FTE
| 21 | CSA - Project Team | Alexandre | Project Management; Configuration Management; Configuration Manager; Commitment=0.7; Space Segment; SU; ESS; ZZZ-0021; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-04 | 137411 | 70% | 20% | 30% | 50% | 75% | 25% | 10% | 0.5 FTE | 0.3 FTE | 0.4 FTE | 0.7 FTE | 0.8 FTE | 0.4 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.2 FTE | 0.1 FTE
| 22 | CSA - Operations Team | Olivia | Mission Operations; Spacecraft Operations; Mission Operations Officer; Commitment=0.5; Space Segment; SU; ESS; ZZZ-0022; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ENG-04 | 137411 | 50% | 10% | 0% | 20% | 70% | 80% | 50% | 0.3 FTE | - | 0.1 FTE | 0.6 FTE | 0.7 FTE | 0.8 FTE | 0.8 FTE | 0.8 FTE | 0.8 FTE | 0.8 FTE | 0.3 FTE
| 23 | CSA - Operations Team | Benjamin | Mission Operations; Spacecraft Operations; Flight Software Engineer; Commitment=0.4; Space Segment; SU; ESS; ZZZ-0023; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ADM-04 | 141340 | 40% | 5% | 0% | 10% | 40% | 60% | 30% | 0.2 FTE | - | 0.0 FTE | 0.3 FTE | 0.4 FTE | 0.5 FTE | 0.6 FTE | 0.6 FTE | 0.6 FTE | 0.6 FTE | 0.2 FTE
| 24 | CSA - Operations Team | Charlotte | Logistics; Logistics and Operations; Logistics Specialist; Commitment=0.7; Space Segment; SU; ESS; ZZZ-0024; Max Echelon; Labour Rates; FF-CSA | Existing | EN-ADM-04 | 141340 | 70% | 10% | 10% | 30% | 60% | 70% | 30% | 0.4 FTE | 0.1 FTE | 0.2 FTE | 0.5 FTE | 0.6 FTE | 0.7 FTE | 0.7 FTE | 0.7 FTE | 0.7 FTE | 0.7 FTE | 0.3 FTE
| 25 | DND - Operations Team | Alex | Mission Operations; Spacecraft Operations; Mission Operations Officer; Commitment=0.8; DND Operations; DND; Space Operations; ZZZ-0025; Max Echelon; Labour Rates; FF-DND | Existing | AS-06 | 165000 | 80% | 5% | 0% | 10% | 50% | 80% | 50% | 0.4 FTE | - | 0.0 FTE | 0.4 FTE | 0.5 FTE | 0.7 FTE | 0.8 FTE | 0.8 FTE | 0.8 FTE | 0.8 FTE | 0.3 FTE
| 26 | DND - Operations Team | Jordan | Mission Operations; Mission Planning; Mission Planner; Commitment=0.1; DND Operations; DND; Space Operations; ZZZ-0026; Max Echelon; Labour Rates; FF-DND | Existing | AS-05 | 150000 | 10% | 5% | 0% | 15% | 40% | 70% | 40% | 0.1 FTE | - | 0.1 FTE | 0.3 FTE | 0.4 FTE | 0.6 FTE | 0.7 FTE | 0.7 FTE | 0.7 FTE | 0.7 FTE | 0.3 FTE
| 27 | DND - Data Team | Taylor | Data Exploitation; EO Data Analysis; Data Exploitation Analyst; Commitment=1.0; Data Usage; DND; Information Management; ZZZ-0027; Max Echelon; Labour Rates; FF-DND | Existing | AS-05 | 150000 | 100% | 0% | 0% | 0% | 20% | 100% | 60% | 0.5 FTE | - | - | 0.2 FTE | 0.2 FTE | 0.7 FTE | 1.0 FTE | 1.0 FTE | 1.0 FTE | 1.0 FTE | 0.4 FTE
| 28 | DND - Data Team | Morgan | Data Exploitation; Intelligence Support; Geospatial Intelligence Analyst; Commitment=0.2; Data Usage; DND; Information Management; ZZZ-0028; Max Echelon; Labour Rates; FF-DND | Existing | AS-05 | 150000 | 20% | 0% | 0% | 0% | 10% | 80% | 50% | 0.1 FTE | - | - | 0.1 FTE | 0.1 FTE | 0.6 FTE | 0.8 FTE | 0.8 FTE | 0.8 FTE | 0.8 FTE | 0.3 FTE
| 29 | CSA Internal Services | N/A | Multiple roles |  |  |  | this is a percentage, economic constants used in analysis are defined in CADRe Part D
| 31 | Horizontal Services | N/A | Infrastructure |  |  |  | this is a percentage, economic constants used in analysis are defined in CADRe Part D
| 32 | Horizontal Services | N/A | Fairness Monitor |  |  |  | this is a percentage, economic constants used in analysis are defined in CADRe Part D
| 33 | Horizontal Services | N/A | SS support |  |  |  | this is a percentage, economic constants used in analysis are defined in CADRe Part D
| 34 | Horizontal Services | N/A | Legal Services |  |  |  | this is a percentage, economic constants used in analysis are defined in CADRe Part D
| 37 | DND Client Departments | N/A | Covered by DND Operations / Data Team rows 25-28 |  |  |  | this is a percentage, economic constants used in analysis are defined in CADRe Part D
[8 empty] | 16.20 FTE | 4.20 FTE | 6.55 FTE | 12.35 FTE | 19.15 FTE | 10.10 FTE | 3.85 FTE | 10.98 FTE | 6.55 FTE | 8.97 FTE | 17.45 FTE | 19.15 FTE | 13.12 FTE | 10.10 FTE | 10.10 FTE | 10.10 FTE | 10.10 FTE | 4.01 FTE
| Salary without inflation in "Then Year" | 1719868 | 1051150 | 1430339 | 2751051 | 3014333 | 2036880 | 1548153 | 1548153 | 1548153 | 1548153 | 612693
| EBP 27% | 464364 | 283811 | 386192 | 742784 | 813870 | 549958 | 418001 | 418001 | 418001 | 418001 | 165427
| Salary and EBP in Then Year | 2184232 | 1334961 | 1816531 | 3493834 | 3828203 | 2586837 | 1966155 | 1966155 | 1966155 | 1966155 | 778120
| Bring historic data into Base Year 2026 | 2184232 | 1334961 | 1816531 | 3493834 | 3828203 | 2586837 | 1966155 | 1966155 | 1966155 | 1966155 | 778120
| Apply inflation to future years | 2184232 | 1361660 | 1889919 | 3707685 | 4143770 | 2856078 | 2214210 | 2258494 | 2303664 | 2349737 | 948524
| Salary and EBP in "Base Year" 2026 with inflation | 2184232 | 1361660 | 1889919 | 3707685 | 4143770 | 2856078 | 2214210 | 2258494 | 2303664 | 2349737 | 948524
Please provide an explanation why positions are required

## 5 - Risk Register
5 - Risk Register
| # | ID | Risk Category | Risk Sub-category | Risk Name | Type of Risk | Description | Internal Factors | External Factors | Probability | Mitigation Strategy | Mitigation Strategy Narrative | Cost Impact – Optimistic ($000) | Cost Impact – Most Likely ($000) | Cost Impact – Pessimistic ($000) | Weighted Exposure ($000) | Cost Impact in Phase | Schedule Impact in Phase | Impact on Project | Impact on Analysis
| 1 | R-001 | Programmatic Integration & Execution | Schedule Planning & Control | Payload–Bus Integration Delay | Schedule | Integration of the CSA payload with the COS spacecraft bus takes longer than planned because interfaces, harnessing, thermal constraints, data interfaces or software dependencies are not closed before integration. | Late ICD closure; interface changes; insufficient joint reviews; limited integration margin | COS supplier delivery timing; payload vendor dependencies; test-facility availability | 50% | Mitigate | Freeze interface control documents before CDR, run joint interface audits, use flatsat/interface simulators, and protect D-phase integration float. | 400 | 1800 | 4200 | 900 | B2–D | C–D | May delay payload integration, environmental testing and launch readiness. | Adds systems-engineering and integration LOE plus schedule contingency to the estimate.
| 2 | R-002 | Programmatic Integration & Execution | Schedule Planning & Control | Launch Availability Mismatch | Schedule | A suitable commercial launch opportunity for two spacecraft into the selected HEO is not available when SAM hardware is ready. | Launch readiness date may move; limited schedule reserve; two-spacecraft deployment constraints | Launch-provider manifest changes; vehicle availability; orbital insertion constraints | 40% | Accept | Retain a launch-window reserve and storage allowance, but treat residual provider-manifest uncertainty as an accepted program exposure after technical compatibility is demonstrated. | 800 | 3500 | 8000 | 1400 | D | D–E | May extend storage, campaign and commissioning activities. | Adds launch-campaign, storage, insurance and program-management exposure.
| 3 | R-003 | Programmatic Integration & Execution | Contracting & Procurement | Procurement Schedule Delay | Schedule | PSPC procurement activities for the bus, payload-related procurement, launch or support services take longer than assumed. | Incomplete SOWs; procurement staffing limits; late technical inputs | Federal procurement review cycles; bid clarification; contracting timelines | 45% | Mitigate | Complete acquisition strategy early, baseline technical data packages before solicitation, and maintain an integrated procurement schedule tied to B2 need dates. | 500 | 2200 | 5000 | 990 | B1–B2 | B1–B2 | Contract award or supplier start dates may slip. | Increases PM/procurement LOE and schedule uncertainty.
| 4 | R-004 | Supply Chain & Commercial | Long-Lead Components | Supply Chain and Long-Lead Procurement | Schedule | Space-qualified detectors, electronics, optics or other specialized components arrive later than required because of long lead times or constrained supply. | Late purchase orders; incomplete forecasts; limited qualified alternates | Supplier backlog; semiconductor/optical supply constraints; obsolescence | 50% | Mitigate | Identify long-lead items before CDR, authorize early procurement for critical items, track supplier milestones, and qualify alternates where practical. | 300 | 1600 | 4000 | 800 | B2–D | C–D | May delay manufacturing and integration. | Adds procurement management, inventory and contingency assumptions.
| 5 | R-005 | Programmatic Integration & Execution | Cost & Budget Management | Development Cost Growth | Cost | Actual development costs exceed the preliminary CADRe estimate because of design growth, labour growth, supplier pricing and additional test effort. | Immature design; optimistic labour assumptions; incomplete WBS | Supplier quotation changes; inflation; market conditions | 55% | Mitigate | Refresh bottoms-up estimates at PDR/CDR, maintain cost reserves, and reconcile cost growth with design maturity and Part C schedule scenarios. | 1500 | 5500 | 12000 | 3025 | B1–D | B2–D | May require additional funding, descoping or schedule changes. | Widens the cost uncertainty range and contingency requirement.
| 6 | R-006 | Technological & Engineering Factors | Payload Performance | Payload Performance Shortfall | Technical | The payload cannot simultaneously meet ≤5 m GSD, ≥50 km swath, radiometric performance, mass, power and data-rate requirements. | Unclosed optical and detector trades; immature payload architecture; limited test data | Detector availability; environmental sensitivity; HEO imaging geometry | 45% | Mitigate | Run end-to-end performance models, prototype critical functions, maintain error budgets and demonstrate performance before CDR. | 900 | 4200 | 9000 | 1890 | B2–D | B2–D | May require redesign, additional test articles or payload changes. | Increases payload engineering, verification and integration LOE.
| 7 | R-007 | Programmatic Integration & Execution | Requirements & Scope Management | Stakeholder and Scope Growth | Programmatic | CSA, DND and other authorized users introduce additional mission, security, operational or data requirements after the baseline is established. | Incomplete stakeholder workshops; weak change control; ambiguous success criteria | Changing user needs; departmental priorities; security requirements | 45% | Mitigate | Baseline measurable requirements, operate a formal change-control board and require quantified cost/schedule impacts for changes. | 700 | 3000 | 7500 | 1350 | B1–C | B1–C | May increase scope, interfaces and development duration. | Requires additional engineering, software and operations LOE.
| 8 | R-008 | Ground Segment & Operations | Ground Infrastructure | Ground Segment Capacity Growth | Technical | Final data rates, contact geometry, latency or processing requirements require more receiving, processing, storage or dissemination capability than planned. | Incomplete link/data-volume models; early infrastructure assumptions | Ground-station service levels; HEO contact geometry; supplier capacity | 45% | Accept | Accept residual ground-capacity growth after confirming the baseline data-volume and contact model, while retaining scalable processing, storage and station-service options. | 700 | 2800 | 6500 | 1260 | C–D | C–D | May require additional ground infrastructure and software. | Increases ground-segment CAPEX/OPEX and operations LOE.
| 9 | R-009 | Organizational & Human Factors | Resource & Staffing Capacity | Specialized Resource Availability | Programmatic | SAM cannot staff enough spacecraft, payload, software, systems-engineering or mission-operations specialists when needed. | Small internal talent pool; hiring lead time; skill concentration | Canadian space labour-market competition; supplier hiring demand | 50% | Mitigate | Identify critical skills by phase, recruit early, cross-train staff and maintain qualified contractor/industry support options. | 400 | 1900 | 4200 | 950 | B1–E | B1–D | May delay technical reviews, integration or operations readiness. | Raises labour-rate and FTE assumptions.
| 10 | R-010 | Technological & Engineering Factors | System Integration | Two-Spacecraft Technical Integration | Technical | The two-spacecraft coordinated constellation introduces issues in common software, timing, mission planning, communications, ADCS, configuration or observation coordination. | Inconsistent spacecraft baselines; insufficient constellation simulation | COS build variation; ground-system interoperability; launch separation dispersions | 40% | Mitigate | Use common interfaces, synchronized software/configuration baselines, constellation simulation and integrated flatsat/mission-scenario testing. | 800 | 3600 | 8200 | 1440 | C–D | C–D | May increase system integration and verification effort. | Adds systems-engineering, software and test LOE.
| 11 | R-011 | Organizational & Human Factors | Leadership, Governance & Culture | Governance and Approval Delays | Governance | Governance, security, data-access or interdepartmental approvals take longer than planned. | Unclear authorities; slow decision cycles; incomplete approval packages | Departmental review priorities; security or policy approvals | 40% | Mitigate | Define authorities, decision timelines, data-access rules and approval gates in the governance baseline before CDR. | 300 | 1300 | 3200 | 520 | B2–D | B2–D | May delay decisions and operational readiness. | Adds PM, governance and stakeholder-coordination LOE.
| 12 | R-012 | Programmatic Integration & Execution | Requirements & Scope Management | Requirements Maturity | Technical | Quantitative requirements for coverage, resolution, swath, data rate, storage, availability, reliability and orbit remain unstable after B2. | Incomplete trade studies; inadequate traceability | Payload supplier findings; user changes; orbit-analysis results | 60% | Mitigate | Maintain requirement-to-design traceability, close mission trades before CDR, and baseline threshold/objective values with verification methods. | 900 | 4000 | 9500 | 2400 | B1–C | B2–C | May cause redesign before or after CDR. | Materially affects cost, schedule and technical uncertainty.
| 13 | R-013 | Ground Segment & Operations | Mission Operations | Operations LOE Growth | Operational | 24-hour government operations for two spacecraft require more staffing, automation, training or infrastructure than assumed. | Underdeveloped CONOPS; optimistic staffing model; limited simulator time | Operational service demands; anomaly workload; staffing availability | 50% | Accept | Accept residual operations-workload variance after completing the quantified 24-hour staffing model and setting a controlled automation/surge-staffing reserve. | 500 | 2400 | 6000 | 1200 | C–E | D–E | May increase recurring operations staffing and infrastructure. | Raises lifecycle labour and ground cost assumptions.
| 14 | R-014 | Ground Segment & Operations | Data Exploitation | Data Product and User Growth | Programmatic | DND or other authorized users request more products, lower latency, new formats or additional interfaces after initial demonstrations. | Incomplete product catalogue; unclear release criteria | User feedback; operational requirements; security constraints | 45% | Mitigate | Baseline a product catalogue and interface requirements and process additions through configuration control. | 400 | 1800 | 4200 | 810 | C–E | C–D | May increase processing, software and dissemination work. | Adds software, storage and analyst LOE.
| 15 | R-015 | Launch & Early Orbit | Launch Interface | Launch Vehicle Interface Changes | Technical | Launch-vehicle requirements alter spacecraft mechanical, electrical, separation, safety or deployment interfaces after the design is mature. | Late interface definition; insufficient launch margin | Provider-specific requirements; range/safety constraints | 30% | Mitigate | Establish launch technical interface agreements early and freeze critical interface data before D-phase hardware completion. | 350 | 1500 | 3500 | 450 | C–D | C–D | May require spacecraft modifications and additional qualification. | Adds launch integration and systems-engineering LOE.
| 16 | R-016 | Technological & Engineering Factors | Orbit & Mission Analysis | HEO Coverage/24-Hour Objective Infeasible | Technical | Detailed orbit and imaging analysis shows that the selected HEO geometry cannot meet the 24-hour concurrent observation objective over the defined Arctic area of interest. | Insufficient early geometry analysis; optimistic phasing assumptions | Actual orbit-insertion performance; Earth geometry; payload field of view | 35% | Mitigate | Run high-fidelity constellation and imaging simulations before CDR and preserve alternate orbital/phasing options. | 1200 | 4800 | 11000 | 1680 | B2–C | B2–C | May require orbit, payload or constellation redesign. | Could materially change spacecraft, launch and operations cost assumptions.
| 17 | R-017 | Technological & Engineering Factors | Orbit & Mission Analysis | Orbit Phasing and Geometry Changes | Technical | Final mission analysis requires changes to apogee, perigee, inclination or spacecraft phasing to satisfy coverage and observation geometry. | Orbit trade not closed; interface coupling with payload | Launch insertion constraints; stationkeeping performance | 45% | Accept | Accept residual uncertainty in exact HEO phasing until orbit analysis is closed; maintain bounded delta-v and mission-planning reserves. | 600 | 2500 | 6000 | 1125 | B2–C | B2–C | May alter propulsion, ADCS, thermal and launch requirements. | Changes design drivers and cost-model assumptions across subsystems.
| 18 | R-018 | Programmatic Integration & Execution | Mass & Performance | Spacecraft Mass Growth | Technical | A spacecraft exceeds the ≤600 kg allocation because of payload, bus, harness, thermal, propulsion or margin growth. | Underestimated subsystem mass; late configuration changes | Supplier mass growth; integration findings | 45% | Mitigate | Maintain a mass budget with ≥20% design margin, track mass at reviews and require quantified impacts for changes. | 500 | 2200 | 5500 | 990 | B2–D | C–D | May require redesign, reduced margin or launch changes. | Adds engineering, structural and launch-performance uncertainty.
| 19 | R-019 | Technological & Engineering Factors | Power & Energy | Power Margin Shortfall | Technical | End-of-life power generation or battery capacity is insufficient to maintain the required ≥20% nominal and ≥10% peak margins. | Underestimated payload/X-band loads; degradation assumptions | HEO illumination/eclipses; component performance | 35% | Mitigate | Maintain mode-based power budgets, run end-of-life and worst-case cases, and preserve array/battery growth paths. | 450 | 1900 | 4500 | 665 | B2–D | C–D | May restrict payload duty cycle or require hardware changes. | Adds power-system redesign and verification LOE.
| 20 | R-020 | Technological & Engineering Factors | Thermal Control | HEO Thermal Margin Shortfall | Technical | Thermal analysis shows hot/cold cases exceed component or payload limits in the highly elliptical orbit. | Incomplete thermal model; insufficient payload dissipation data | HEO radiation/eclipse environment; supplier thermal characteristics | 40% | Mitigate | Complete hot/cold orbital analyses before CDR, correlate with thermal testing, and preserve radiator/heater margin. | 500 | 2400 | 5800 | 960 | B2–D | C–D | May require thermal redesign, additional testing or operational constraints. | Adds thermal analysis, hardware and environmental-test costs.
| 21 | R-021 | Technological & Engineering Factors | ADCS & Pointing | Pointing Performance Shortfall | Technical | Attitude knowledge and control errors exceed the ≤0.05° absolute pointing target during imaging. | Insufficient sensor characterization; underestimated disturbance torques | HEO dynamics; star-tracker performance; spacecraft flexibility | 30% | Mitigate | Maintain an end-to-end pointing error budget, test sensor/actuator performance and validate pointing in representative simulations. | 500 | 2200 | 5200 | 660 | B2–D | C–D | May degrade imaging performance or require ADCS redesign. | Increases ADCS, simulation and test LOE.
| 22 | R-022 | Technological & Engineering Factors | ADCS & Pointing | Reaction Wheel Saturation | Technical | Disturbance torques or operational profiles cause reaction wheels to saturate more often than planned, interrupting observations or increasing propellant use. | Incomplete disturbance model; insufficient momentum management analysis | HEO environmental torques; payload operational modes | 25% | Accept | Accept residual reaction-wheel saturation exposure after validating disturbance models and maintaining defined momentum-unloading and observation-recovery modes. | 250 | 1200 | 3000 | 300 | C–E | D–E | May interrupt observation operations and increase propellant consumption. | Adds ADCS analysis and operational constraints.
| 23 | R-023 | Technological & Engineering Factors | Navigation & Flight Dynamics | Orbit Knowledge Error | Technical | Onboard or ground orbit determination performance is worse than assumed, reducing pointing, targeting or phasing accuracy. | Navigation algorithm maturity; insufficient sensor validation | GPS performance; HEO geometry; tracking-service availability | 25% | Mitigate | Validate orbit-determination performance with representative trajectories and establish ground-support fallbacks. | 250 | 1100 | 2800 | 275 | B2–D | D | May increase calibration, planning and commissioning time. | Adds flight-dynamics and software-support LOE.
| 24 | R-024 | Technological & Engineering Factors | Propulsion | Delta-V Budget Shortfall | Technical | The preliminary 99.6 m/s total delta-V budget is insufficient after orbit maintenance, phasing, collision avoidance and disposal needs are fully analyzed. | Optimistic maneuver assumptions; contingency too low | Injection dispersions; drag; collision-avoidance requirements | 30% | Mitigate | Maintain a quantified delta-V budget through CDR and preserve the 40 m/s disposal allocation while validating maneuver requirements. | 500 | 2300 | 5500 | 690 | B2–C | C–E | May require propellant changes, reduced maneuver capability or orbit redesign. | Increases propulsion and spacecraft mass uncertainty.
| 25 | R-025 | Technological & Engineering Factors | Propulsion | Iodine Propulsion Performance Below Model | Technical | The selected iodine propulsion system does not achieve assumed thrust, efficiency or lifetime performance in the SAM configuration. | Insufficient qualification evidence; incomplete system-level analysis | Supplier performance; thermal environment; thruster lifetime | 20% | Mitigate | Require supplier qualification evidence, system-level performance testing and conservative propulsion margins before flight. | 300 | 1400 | 3500 | 280 | B2–D | D–E | May reduce orbit-maintenance capability or require alternate propulsion hardware. | Adds propulsion qualification and contingency cost.
| 26 | R-026 | Technological & Engineering Factors | Radiation & Environment | Radiation Environment Exceeds Design Basis | Technical | Radiation exposure or single-event effects in the mission orbit exceed assumptions used for component selection and shielding. | Insufficient radiation analysis; optimistic component tolerance | Solar activity; HEO radiation environment | 30% | Mitigate | Perform radiation analysis early, select appropriately qualified components and maintain shielding and fault-tolerance margins. | 450 | 1800 | 4800 | 540 | B2–D | C–D | May require component substitution, shielding or software changes. | Adds radiation analysis, parts assurance and test LOE.
| 27 | R-027 | Technological & Engineering Factors | EMC & RF | EMC/EMI Performance Failure | Technical | Spacecraft emissions or susceptibility cause interference between payload, ADCS, C&DH and X-band/S-band systems. | Insufficient EMC control plan; late harness/filter changes | Supplier unit characteristics; combined spacecraft configuration | 25% | Mitigate | Maintain an EMC control plan, test high-risk combinations early and preserve filtering/grounding options. | 300 | 1300 | 3200 | 325 | C–D | D | May require harness, filtering or software changes and repeat tests. | Adds EMC testing and integration LOE.
| 28 | R-028 | Technological & Engineering Factors | Payload Calibration | Calibration Accuracy Insufficient | Technical | The payload calibration approach cannot achieve the required radiometric/geometric accuracy or maintain performance over mission life. | Incomplete calibration architecture; insufficient error budget | Detector drift; thermal changes; reference-device stability | 40% | Mitigate | Develop calibration error budgets, test representative references and plan periodic in-flight calibration observations. | 400 | 1800 | 4200 | 720 | B2–D | C–D | May reduce product quality or require payload/processing changes. | Adds calibration hardware, testing and data-processing LOE.
| 29 | R-029 | Technological & Engineering Factors | Payload Detector | Detector Performance Degradation | Technical | Detector noise, sensitivity, defects or radiation degradation exceed assumptions and reduce imaging performance. | Limited detector characterization; reliance on candidate/COTS technology | Supplier process variation; radiation environment | 25% | Transfer | Use detector warranty, supplier performance clauses, acceptance criteria and replacement/spares provisions to transfer a defined portion of degradation exposure to the payload supplier. | 500 | 2200 | 5200 | 550 | B2–D | C–D | May reduce payload performance or require detector replacement. | Adds detector screening, calibration and contingency cost.
| 30 | R-030 | Technological & Engineering Factors | Payload SWIR | SWIR Instrument Selection Delay | Schedule | The SWIR payload trade study does not converge on a flight-ready instrument before the payload CDR need date. | Open detector/optics trade; incomplete data-rate and accommodation analysis | Limited qualified SWIR suppliers; supplier lead time | 35% | Mitigate | Time-box the SWIR trade, establish quantitative selection criteria and maintain at least one alternate instrument concept. | 300 | 1200 | 2800 | 420 | B2–C | B2–C | May delay payload CDR and downstream procurement. | Adds payload engineering and procurement contingency.
| 31 | R-031 | Technological & Engineering Factors | Data Handling | Onboard Storage/Throughput Shortfall | Technical | The spacecraft data chain cannot sustain ≥1 TB storage, payload data generation, compression and prioritization requirements. | Underestimated payload data rate; C&DH processing assumptions | Instrument output rates; compression performance | 30% | Accept | Accept limited residual growth in storage/throughput demand after end-to-end data-flow testing and retention of scalable storage and compute options. | 350 | 1500 | 3600 | 450 | B2–C | C–D | May require additional storage or processing hardware/software. | Adds C&DH and payload-electronics LOE.
| 32 | R-032 | Ground Segment & Operations | Communications | X-Band Link Margin Shortfall | Technical | The ≥500 Mbps peak mission-data downlink cannot be demonstrated with adequate end-to-end margin for the required contact geometry. | Incomplete link budget; optimistic antenna assumptions | Ground-station weather; interference; HEO geometry | 30% | Mitigate | Validate link budgets with conservative losses, perform representative end-to-end tests and retain lower-rate contingency modes. | 450 | 2000 | 4800 | 600 | B2–D | C–D | May reduce data throughput or increase required ground contacts. | Adds RF, ground-station and operations LOE.
| 33 | R-033 | Ground Segment & Operations | Ground Infrastructure | Receiving Station Availability Below Requirement | Technical | Available ground-station contacts are insufficient to sustain command, telemetry and mission-data requirements. | Underestimated contact needs; single-station dependence | Commercial station outages; Arctic geometry; weather | 35% | Accept | Accept residual station-outage exposure within the ground availability requirement while maintaining geographically diverse contracted contacts. | 500 | 2100 | 5000 | 735 | C–D | D–E | May delay data delivery or commanding. | Adds station capacity, service fees and operational contingency.
| 34 | R-034 | Ground Segment & Operations | Processing & Archive | Ground Processing Capacity Shortfall | Technical | The ground segment cannot sustain the ≥1 TB/day raw-data-equivalent processing requirement with required reprocessing and product headroom. | Incomplete workload model; insufficient compute/storage margin | Cloud/service performance; software-processing efficiency | 30% | Mitigate | Benchmark representative workloads, size processing for reprocessing peaks and maintain scalable compute capacity. | 400 | 1800 | 4200 | 540 | B2–D | D–E | May breach priority-data latency requirements. | Adds compute, software and operations cost.
| 35 | R-035 | Ground Segment & Operations | Archive | Archive Capacity/Retention Shortfall | Technical | The planned ~2 PB archive does not provide sufficient capacity for raw data, products, metadata, redundancy and five-year retention. | Storage growth model incomplete; retention policy not frozen | Cloud/storage pricing; product-volume growth | 25% | Accept | Accept residual uncertainty in archive growth after sizing the 2 PB baseline and retaining scalable storage procurement options. | 250 | 1200 | 3000 | 300 | C–E | D–E | May require storage expansion or retention-policy changes. | Adds recurring archive and data-management cost.
| 36 | R-036 | Ground Segment & Operations | Latency & Availability | Priority Product Latency Miss | Performance | Priority observations cannot consistently achieve ≤6-hour processed-product availability after raw-data receipt. | Slow processing chain; manual QC; bottlenecked contacts | Ground outages; increased product complexity | 35% | Accept | Accept residual latency variation after establishing an end-to-end latency budget, priority queues and operational thresholds for degraded conditions. | 350 | 1500 | 3600 | 525 | C–E | D–E | May reduce usefulness of priority mission products. | Adds software automation, staffing and ground-capacity LOE.
| 37 | R-037 | Ground Segment & Operations | User Access & Security | Government Data Access Delay | Programmatic | Authorized users cannot consistently receive released products within 30 minutes of product generation because of security, network or dissemination controls. | Manual approval workflows; fragmented user-management processes | Government network constraints; classification changes | 30% | Mitigate | Define access-control architecture and automated release workflows early and conduct end-to-end user acceptance testing. | 250 | 1100 | 2600 | 330 | C–D | D–E | May delay operational exploitation of products. | Adds cybersecurity, dissemination and user-support LOE.
| 38 | R-038 | Ground Segment & Operations | Autonomy | 72-Hour Autonomous Operation Shortfall | Technical | A spacecraft cannot maintain safe autonomous operation for the required 72 hours without ground intervention. | Insufficient fault-management analysis; limited simulation of communications gaps | Extended contact outages; unexpected spacecraft anomalies | 25% | Mitigate | Perform long-duration autonomy simulations, fault-injection testing and recovery rehearsals before flight. | 350 | 1600 | 3800 | 400 | C–D | D | May increase commissioning risk and operator workload. | Adds software, testing and operational contingency.
| 39 | R-039 | Software & Autonomy | Flight Software | Flight Software Complexity Growth | Technical | Flight software scope grows beyond estimates because of autonomy, constellation coordination, payload interfaces and fault-management requirements. | Incomplete software architecture; underestimated integration complexity | Late subsystem changes; vendor software dependencies | 50% | Mitigate | Baseline software architecture early, prototype high-risk functions and maintain incremental integration milestones. | 500 | 2400 | 6200 | 1200 | B2–D | C–D | May extend development and verification activities. | Increases software labour, test automation and schedule contingency.
| 40 | R-040 | Software & Autonomy | Software Verification | Insufficient Software Validation | Technical | Software defects or inadequate validation allow faults to survive into integrated system testing. | Weak regression testing; late code drops; incomplete test coverage | Supplier software interfaces; changing requirements | 40% | Mitigate | Establish automated regression, requirements-based test coverage and independent software reviews before CDR. | 300 | 1500 | 3600 | 600 | C–D | D | May delay integration and acceptance testing. | Adds software verification LOE and test schedule.
| 41 | R-041 | Data, Knowledge & Integration | Configuration Management | Configuration Management Lapses | Technical | Hardware, software, requirements and test evidence become inconsistent between CSA, COS and ground-segment baselines. | Weak CM discipline; inconsistent repositories | Multiple suppliers; partner configuration practices | 35% | Mitigate | Maintain a single controlled baseline, formal change board and configuration audits at each major review. | 300 | 1300 | 3200 | 455 | B2–D | B2–D | May invalidate test evidence or cause rework. | Adds configuration-management and reconciliation LOE.
| 42 | R-042 | Safety, Assurance & Compliance | Verification & Validation | Incomplete Test Coverage | Technical | Verification plans do not fully demonstrate quantitative requirements before launch. | Late verification planning; incomplete traceability | Test facility limits; supplier evidence gaps | 40% | Mitigate | Derive verification methods from requirements, close the verification matrix before CDR and conduct readiness audits. | 400 | 1800 | 4200 | 720 | C–D | C–D | May lead to late qualification or acceptance rework. | Adds test engineering and qualification contingency.
| 43 | R-043 | Safety, Assurance & Compliance | Environmental Testing | Environmental Test Failure | Technical | Qualification or acceptance testing reveals a failure under vibration, thermal-vacuum or EMC conditions. | Insufficient margin; design flaw; test-article differences | Facility conditions; workmanship defects | 30% | Mitigate | Retain environmental design margin, perform analysis-before-test reviews and maintain repair/retest plans. | 600 | 2600 | 6200 | 780 | D | D | May require redesign, replacement hardware and repeat testing. | Adds environmental test, hardware and schedule contingency.
| 44 | R-044 | Safety, Assurance & Compliance | Qualification & Acceptance | Qualification Model Diverges from Flight Design | Technical | The QM does not adequately represent the final flight configuration, reducing the value of qualification evidence. | Late flight design changes; inadequate configuration control | Supplier substitutions; component obsolescence | 25% | Avoid | Prevent configuration divergence by making the QM configuration-controlled and requiring formal disposition of all design changes before qualification. | 350 | 1500 | 3600 | 375 | C–D | D | May require supplemental qualification or re-test. | Adds assurance and test LOE.
| 45 | R-045 | Manufacturing, Assembly & Test | Test Facilities | Test Facility Availability | Schedule | Required thermal-vacuum, vibration, EMC or cleanroom facilities are unavailable at planned dates. | Late booking; inaccurate duration estimates | National test-facility demand; facility outages | 30% | Mitigate | Reserve critical facilities early and maintain qualified alternate facilities where practical. | 250 | 1000 | 2500 | 300 | C–D | D | May extend D-phase MAIT and launch readiness. | Adds facility reservation, travel and schedule contingency.
| 46 | R-046 | Manufacturing, Assembly & Test | Workmanship & Quality | Manufacturing Workmanship Defects | Technical | Hardware defects discovered during inspection or test require repair, replacement or retest. | Process variation; training gaps; inadequate inspection | Supplier QA variability; staffing turnover | 45% | Mitigate | Use certified processes, in-process inspections and first-article demonstrations for critical manufacturing steps. | 300 | 1400 | 3400 | 630 | D | D | May slow MAIT and increase retest activity. | Adds manufacturing rework and QA LOE.
| 47 | R-047 | Manufacturing, Assembly & Test | Nonconformance Management | Non-Conformance Backlog | Programmatic | The number of material and process nonconformances exceeds the capacity of review boards to disposition them without affecting the build schedule. | Insufficient MRB staffing; late defect trending | Supplier defect rates; test-facility throughput | 40% | Mitigate | Set disposition turnaround targets, staff review boards during peak activity and trend recurring defect causes. | 250 | 900 | 2300 | 360 | D | D | May stop hardware flow and consume schedule reserve. | Adds QA/MRB labour and schedule contingency.
| 48 | R-048 | Manufacturing, Assembly & Test | Manufacturing Processes | Manufacturing Process Immaturity | Technical | New or insufficiently validated processes produce variable hardware quality or unexpected production delays. | Limited process qualification; incomplete work instructions | Small supplier capacity; tooling maturity | 35% | Mitigate | Qualify critical processes early and establish objective process-acceptance criteria before production. | 400 | 1500 | 3500 | 525 | B2–D | C–D | May cause rework or production delays. | Adds manufacturing engineering and supplier-assurance LOE.
| 49 | R-049 | Supply Chain & Commercial | Supplier Performance | COS Bus Contractor Performance | Programmatic | Canadian Orbital Systems does not meet bus development milestones, technical deliverables or acceptance criteria within the baseline schedule. | Weak schedule control; incomplete deliverable definitions | Supplier staffing changes; subcontractor delays | 40% | Transfer | Place schedule and performance obligations, liquidated remedies and recovery support requirements in the COS contract while retaining government technical oversight. | 600 | 2800 | 7000 | 1120 | B2–D | B2–D | May delay PDR/CDR or flight-hardware readiness. | Adds oversight, recovery and potential rework costs.
| 50 | R-050 | Supply Chain & Commercial | Supplier Performance | Ground Segment Supplier Performance | Programmatic | Earth Daily Analytics does not deliver required receiving, processing, archive or integration capabilities to planned need dates. | Incomplete ground requirements; integration complexity | Subcontractor delays; software delivery issues | 30% | Mitigate | Use phased ground deliveries, acceptance tests and clear interface milestones tied to spacecraft integration dates. | 450 | 1900 | 4500 | 570 | C–D | D | May delay end-to-end mission testing or operations readiness. | Adds contractor oversight and ground rework contingency.
| 51 | R-051 | Supply Chain & Commercial | Supplier Performance | Launch Provider Performance Issue | Programmatic | Northern Launch Services experiences contractual, technical or execution issues that prevent the planned launch campaign from proceeding on baseline dates. | Insufficient provider oversight; incomplete service definition | Provider schedule; subcontractor issues; launch-site constraints | 25% | Transfer | Use launch-service contractual commitments, defined interfaces and launch insurance/financial remedies to transfer a portion of launch-provider performance exposure. | 800 | 3200 | 7500 | 800 | D | D | May move launch and extend commissioning schedule. | Adds launch-management and contingency costs.
| 52 | R-052 | Supply Chain & Commercial | Data Rights & IP | Insufficient Vendor Data Rights | Governance | Contracts do not provide sufficient design, interface, software or maintenance information for government operation and sustainment. | Incomplete procurement data-rights requirements | Supplier IP restrictions; proprietary interfaces | 25% | Mitigate | Define lifecycle data, software, interface and escrow requirements before contract award. | 350 | 1500 | 4000 | 375 | B2–D | B2–E | May increase sustainment dependency and transition cost. | Adds procurement/legal effort and long-term support assumptions.
| 53 | R-053 | Supply Chain & Commercial | Obsolescence | EEE Component Obsolescence | Technical | A selected electrical, electronic or detector component becomes obsolete before or during production. | Long design-to-flight duration; insufficient obsolescence tracking | Commercial technology cycles; manufacturer discontinuation | 40% | Mitigate | Maintain obsolescence monitoring, qualify alternates and require supplier lifecycle notifications. | 250 | 1100 | 2800 | 440 | C–D | C–D | May cause redesign or procurement delays. | Adds redesign, qualification and inventory contingency.
| 54 | R-054 | External & Environmental Factors | Market & Supply Chain | Supplier Insolvency or Instability | Programmatic | A critical supplier experiences financial or operational distress that disrupts delivery or technical support. | Single-source dependency; limited transition documentation | Market conditions; supplier financial health | 25% | Transfer | Require subcontractor continuity, escrow, transition assistance and supplier-performance provisions so a defined portion of insolvency exposure can be shifted contractually. | 400 | 1800 | 4500 | 450 | B2–D | C–D | May require redesign, reprocurement or schedule recovery. | Adds supplier monitoring and contingency cost.
| 55 | R-055 | External & Environmental Factors | Geopolitical & Economic | Inflation and Cost Escalation | Cost | Labour, materials, launch services or subcontractor prices increase beyond the cost model assumptions over the multi-year program. | Long procurement horizon; limited fixed-price coverage | Inflation; supplier repricing; economic conditions | 55% | Mitigate | Apply explicit escalation assumptions, refresh estimates annually and align contract mechanisms and reserves with exposure. | 800 | 2800 | 6500 | 1540 | B1–E | B1–E | May reduce purchasing power and increase lifecycle funding requirements. | Changes the economic constants and total cost estimate.
| 56 | R-056 | Programmatic Integration & Execution | Funding & Budget | Funding Gap Between Phases | Programmatic | Funding availability is insufficient to transition cleanly between development, manufacturing, launch or operations phases. | Long-range budget uncertainty; incomplete phasing profile | Government budget cycles; competing priorities | 35% | Accept | Accept residual inter-phase funding uncertainty after defining minimum critical-path funding and protecting long-lead commitments. | 600 | 2500 | 6000 | 875 | B1–E | B1–E | May defer procurement or compress downstream work. | Adds schedule contingency and financing assumptions.
| 57 | R-057 | Launch & Early Orbit | Insurance & Liability | Launch Insurance Coverage Gap | Cost | Launch insurance exclusions, deductibles or limits leave material SAM development/launch exposure uninsured. | Incomplete policy review; insufficient valuation basis | Insurer terms; launch-provider liability regime | 20% | Transfer | Purchase launch insurance for defined physical-loss exposures and contractually require evidence of coverage, exclusions and deductibles before launch campaign entry. | 500 | 2200 | 6000 | 440 | D | D | May increase retained financial exposure after launch anomaly. | Adds insurance premium and reserve assumptions.
| 58 | R-058 | External & Environmental Factors | Weather & Logistics | Launch Weather Delay | Schedule | Weather repeatedly violates launch constraints or disrupts launch-site processing, extending campaign duration. | Limited weather contingency; insufficient standby planning | Seasonal weather; launch-site conditions | 35% | Accept | Treat residual weather-driven launch delay as an accepted external exposure after incorporating seasonal statistics and standby/storage reserve into the schedule and estimate. | 250 | 1200 | 3000 | 420 | D | D | May extend campaign and delay commissioning. | Adds campaign and staffing contingency.
| 59 | R-059 | Regulatory, Environmental & External | Spectrum & Licensing | Spectrum Authorization Delay | Governance | Required radio-frequency authorization or coordination is not completed in time for spacecraft and ground-system testing or operations. | Late frequency application; incomplete technical data | Coordination with other users; licensing timelines | 25% | Mitigate | Submit coordination packages early and maintain a technically compliant contingency configuration. | 250 | 1100 | 2600 | 275 | B2–D | C–D | May delay communications testing or operations readiness. | Adds RF coordination and licensing LOE.
| 60 | R-060 | Data, Knowledge & Integration | Data Governance | Security Classification or Data Policy Changes | Governance | Changes in security classification or government data-release policy require redesigned dissemination, storage or user-access controls. | Incomplete data-classification baseline; late security architecture | Government security policy; authorized-user requirements | 35% | Mitigate | Define classification and data-release rules early and design separable data products and access controls. | 300 | 1400 | 3500 | 490 | B2–D | C–E | May delay ground-system acceptance or limit product dissemination. | Adds cybersecurity, data-management and user-acceptance LOE.
| 61 | R-061 | External & Environmental Factors | Arctic Logistics | Arctic Logistics Disruption | Schedule | Remote Arctic field, calibration, validation or receiving-station activities are disrupted by transportation, weather or limited local infrastructure. | Late logistics planning; dependence on limited transport windows | Arctic weather; seasonal access; transportation availability | 35% | Accept | Accept residual transportation disruption exposure after pre-positioning critical equipment, using alternate routes and maintaining schedule reserve. | 250 | 1000 | 2500 | 350 | C–E | D–E | May delay calibration, validation or ground-site work. | Adds travel, logistics and schedule-contingency cost.
| 62 | R-062 | Organizational & Human Factors | Knowledge Management | Knowledge Loss and Continuity Gaps | Programmatic | Loss of key personnel or incomplete documentation reduces continuity between design, test, launch and operations phases. | Single points of knowledge; incomplete technical records | Staff turnover; retirement/mobility; supplier turnover | 40% | Accept | Accept residual personnel-continuity exposure after establishing controlled records, deputies and handover requirements for critical functions. | 250 | 1000 | 2400 | 400 | B1–E | B2–E | May slow decisions and increase rework. | Adds documentation and transition LOE.
| 63 | R-063 | People, Safety & Security | Operations Staffing | Operations Fatigue and Staffing Shortfall | Operational | Sustained 24-hour operations create fatigue or insufficient coverage during LEOP and nominal operations. | Understaffed shifts; insufficient surge planning | Hiring constraints; anomaly-driven workload | 40% | Mitigate | Use shift and overtime limits, maintain backup staffing and rehearse high-workload anomaly scenarios. | 350 | 1500 | 3800 | 600 | D–E | D–E | May increase operational errors or reduce response capability. | Raises recurring operations FTE and training assumptions.
| 64 | R-064 | Ground Segment & Operations | Data Exploitation | DND Data Exploitation Workload Growth | Operational | DND analysts require greater data exploitation, geospatial analysis or product validation capacity than assumed. | Underestimated analyst workload; immature product workflows | User demand; data volume; priority tasking | 45% | Accept | Accept residual DND exploitation workload uncertainty after quantifying analyst demand and defining a scalable surge-support model. | 300 | 1400 | 3300 | 630 | C–E | D–E | May delay validation and product uptake. | Adds user-support and data-analyst LOE.
| 65 | R-065 | Programmatic Integration & Execution | Commissioning | Commissioning Exceeds 90 Days | Schedule | LEOP, calibration, software updates or constellation coordination require more than the planned 90 days after launch. | Incomplete commissioning procedures; limited pre-launch rehearsal | Launch insertion dispersions; early anomalies; ground readiness | 40% | Mitigate | Run full mission simulations, validate commissioning scripts before launch and maintain contingency procedures. | 450 | 2000 | 5000 | 800 | D | D | Delays start of nominal operations and consumes schedule reserve. | Adds launch-support, contractor and operations costs.
| 66 | R-066 | Spacecraft & Payload Technical | Reliability | Early-Life Spacecraft Anomaly | Technical | One spacecraft experiences an early-life anomaly in power, ADCS, C&DH, communications or payload systems after launch. | Latent workmanship or integration defects | Launch environment; component infant mortality | 30% | Mitigate | Use rigorous acceptance testing, trend telemetry after launch and maintain anomaly-response staffing and spares. | 500 | 2500 | 6500 | 750 | D–E | D–E | May reduce constellation availability and increase recovery effort. | Adds anomaly-resolution and operations LOE.
| 67 | R-067 | Safety, Assurance & Compliance | Mission Reliability | Mission-Success Probability Below Target | Technical | Reliability analysis indicates the preliminary ≥0.85 five-year mission-success target is not supported by the current architecture or component reliability. | Insufficient reliability allocation; common-cause risks | Supplier reliability data; environmental loads | 30% | Mitigate | Allocate reliability targets to subsystems, conduct fault-tree and reliability growth analyses, and maintain recovery paths for credible single-point failures. | 600 | 2600 | 6500 | 780 | B2–C | C–D | May drive redundancy or component changes. | Adds reliability analysis, qualification and hardware contingency.
| 68 | R-068 | Spacecraft & Payload Technical | End of Life | End-of-Life Disposal Capability Insufficient | Technical | The spacecraft does not retain the required 40 m/s disposal allocation after actual orbit and stationkeeping requirements are closed. | Delta-V growth; inadequate propellant margin | Actual drag/insertion dispersions; collision avoidance needs | 20% | Mitigate | Protect the 40 m/s disposal allocation in the propulsion budget and continuously reconcile remaining delta-V through operations. | 350 | 1600 | 3800 | 320 | B2–E | D–F | May constrain mission extension or require revised disposal strategy. | Adds propulsion analysis and operations planning.
| 69 | R-069 | Strategic & Alignment Factors | Strategic Direction & Policy | Government Priority Shift | Strategic | Changes in government or departmental priorities reduce funding, scope or support for the SAM mission. | Weak strategic traceability; inflexible mission architecture | Government priority changes; fiscal pressures | 30% | Accept | Accept residual policy-priority exposure as external and maintain a traceable minimum viable mission configuration that can proceed if scope pressure emerges. | 1000 | 4500 | 12000 | 1350 | B1–E | B1–E | May change scope, funding or operating period. | Creates broad cost and schedule uncertainty across the baseline.
| 70 | R-070 | Mission & Science | Observation Concept | Observation Cadence Shortfall | Performance | End-to-end mission simulation shows that the planned observation cadence and 24-hour concurrent objective cannot be achieved within pointing, power, communications and data-volume limits. | Insufficient integrated mission simulation; independent subsystem assumptions | Actual orbit geometry; user tasking demand; environmental constraints | 35% | Accept | Accept residual observation-loss exposure from geometry and Arctic environmental conditions after defining priority tasking and alternate observation modes. | 700 | 3000 | 7000 | 1050 | B2–C | C–D | May reduce observation volume or require architecture changes. | Adds mission analysis, software and operations modelling LOE.
| 71 | R-071 | Mission & Science | Science & Calibration | Reference Data or Validation Shortfall | Technical | Calibration/validation activities lack sufficient reference observations or independent data to demonstrate product quality. | Late validation planning; incomplete ground-truth approach | Reference-data access; seasonal conditions; field logistics | 30% | Accept | Accept residual reference-data availability risk after securing baseline sources and defining alternate validation approaches. | 250 | 1100 | 2600 | 330 | C–E | D–E | May delay product validation and acceptance. | Adds science-support and data-acquisition LOE.
| 72 | R-072 | People, Safety & Security | Cybersecurity | Cybersecurity Controls Arrive Late | Security | Security requirements or controls are introduced after spacecraft/ground-system interfaces have been established, causing redesign. | Late threat modelling; fragmented security ownership | Government cybersecurity requirements; threat environment | 30% | Mitigate | Perform threat modelling at architecture start and integrate security verification into every major software and ground release. | 350 | 1600 | 4000 | 480 | B2–D | C–D | May require hardware/software changes and delay acceptance. | Adds cybersecurity engineering and verification LOE.
| 73 | R-073 | Ground Segment & Operations | Cybersecurity | Supply-Chain Cyber Compromise | Security | Vendor software, remote-access infrastructure or development environments introduce malicious code or unauthorized access pathways. | Weak supplier-security requirements; insufficient scanning | Supplier cyber incidents; third-party dependencies | 20% | Mitigate | Require secure development evidence, software integrity checks, segmented supplier access and acceptance scanning. | 300 | 1200 | 3500 | 240 | B2–D | C–D | May delay acceptance and require remediation or rework. | Adds cybersecurity assurance and supplier oversight cost.
| 74 | R-074 | External & Environmental Factors | Natural Events | Facility Disruption from Natural Event | Schedule | Fire, flood, severe storm or other event closes a critical spacecraft, test or ground facility. | Concentrated critical resources; inadequate continuity planning | Extreme weather; facility incident | 20% | Transfer | Use facility insurance/contractual recovery provisions and geographically separated backup capacity to transfer and contain a portion of major site-disruption exposure. | 400 | 1800 | 4500 | 360 | D–E | D–E | May disrupt integration, test or operations. | Adds contingency facilities and schedule reserve.
| 75 | R-075 | Schedule & Program Management | Management Reserve | Schedule Margin Insufficient | Schedule | The nominal schedule contains insufficient float to absorb integration, procurement, test or commissioning delays before the 1 January 2031 launch baseline. | Compressed D-phase sequencing; limited slack between milestones | Supplier delays; facility availability; launch dates | 55% | Mitigate | Protect explicit schedule reserve in Part C and use critical-path reviews to prevent reserve consumption without governance approval. | 500 | 2200 | 5200 | 1210 | B2–D | B2–D | Small disruptions may directly move launch and operations dates. | Increases schedule risk allowance and PM LOE.
| 76 | R-076 | Programmatic Integration & Execution | Earned Value & Reporting | Cost/Schedule Baseline Misalignment | Programmatic | Cost, schedule and technical baselines are updated inconsistently, obscuring emerging variance and making the cost model stale. | Unlinked planning systems; inconsistent change control | Supplier reporting differences; evolving Part C/Part D baselines | 40% | Mitigate | Reconcile Part A, Part C and Part D baselines at formal control points and maintain a single change log. | 250 | 1100 | 2600 | 440 | B1–E | B2–E | May lead to late management response and estimate revisions. | Reduces estimate traceability and increases analysis uncertainty.
| 77 | R-077 | Supply Chain & Commercial | Procurement Pricing | Vendor Estimate Understatement | Cost | Supplier proposals omit engineering, testing, documentation or support activities that are later added after award. | Incomplete SOW; insufficient independent estimate | Vendor pricing strategy; subcontractor exclusions | 35% | Mitigate | Require priced WBS, assumptions and exclusions and perform an independent government estimate before award. | 500 | 2200 | 5000 | 770 | B2–D | B2–D | Contract value may increase after award. | Increases procurement and contingency allowance.
| 78 | R-078 | Supply Chain & Commercial | Competitive Procurement | Insufficient Bid Competition | Programmatic | Too few compliant bids are received for a major contract, reducing pricing leverage or requiring procurement restart. | Overly narrow requirements; unrealistic bid conditions | Limited Canadian supplier base; market capacity | 30% | Accept | Accept residual competition risk after conducting market sounding, provided procurement rules and minimum technical requirements remain satisfied. | 300 | 1200 | 2800 | 360 | B1–B2 | B1–B2 | May delay contract award and increase procurement cost. | Adds procurement schedule and price uncertainty.
| 79 | R-079 | External & Environmental Factors | Market & Commercial | Foreign Exchange Volatility | Cost | Foreign-denominated procurement or services become more expensive than the estimate due to exchange-rate movement. | High foreign content in selected components or services | Currency-market volatility | 30% | Mitigate | Identify foreign-currency exposure and include explicit exchange-rate assumptions or contingency in the estimate. | 250 | 1000 | 2500 | 300 | B2–D | B2–D | May increase procurement cost. | Adds economic-constant uncertainty to the estimate.
| 80 | R-080 | Safety, Assurance & Compliance | Security & Handling | Sensitive Information Handling Failure | Security | Sensitive mission, spacecraft or user data are mishandled during development or operations. | Inconsistent access control; training gaps | Contractor handling practices; personnel turnover | 20% | Mitigate | Apply role-based access, controlled repositories, training and auditable handling procedures across CSA, DND and suppliers. | 350 | 1500 | 4000 | 300 | B2–E | B2–E | May require security remediation and temporarily restrict information exchange. | Adds security-management and compliance LOE.
| 81 | R-081 | Spacecraft & Payload Technical | Power & Energy | Solar Array Deployment Failure | Technical | One or both spacecraft solar-array panels fail to deploy or latch as required after launch, reducing available power for spacecraft and payload operations. | Insufficient deployment test coverage; mechanism tolerance stack; thermal distortion; incomplete contingency procedures | Launch shock; mechanism aging during storage; unexpected post-separation attitude or thermal conditions | 15% | Mitigate | Qualify the deployment mechanism, perform release/deployment tests, protect battery margin and maintain recovery procedures for partial deployment. | 500 | 2200 | 6500 | 330 | D | D–E | May reduce available spacecraft power and delay commissioning or constrain payload duty cycle. | Adds deployment-test, mechanism assurance and contingency operations LOE.
| 82 | R-082 | Spacecraft & Payload Technical | Power & Energy | Battery Capacity Degradation Exceeds Model | Technical | Battery capacity degrades faster than predicted, reducing eclipse and peak-load capability during the mission. | Conservative capacity model not maintained; insufficient life-test data; temperature excursions | Battery supplier variability; long-term degradation environment | 15% | Mitigate | Use life-test data, thermal limits, end-of-life sizing margin and battery state-of-charge management rules. | 400 | 1800 | 5200 | 270 | D–E | E | May constrain payload operations or autonomy and reduce available mission modes. | Adds battery analysis, test and operations-model effort.
| 83 | R-083 | Spacecraft & Payload Technical | Communications & TT&C | Antenna Deployment or RF Hardware Failure | Technical | A communications antenna or RF chain does not perform as required after launch, reducing commanding or mission-data downlink capability. | Insufficient deployment verification; RF interface mismatch; component defect | Launch environment; radiation; external interference | 20% | Transfer | Use supplier acceptance criteria, component screening, spare RF hardware and contractual replacement obligations for defined failures. | 450 | 2100 | 6000 | 420 | D–E | D–E | May reduce command margin or mission-data return and require alternate operating modes. | Adds RF test, spare hardware and contingency operations allowance.
| 84 | R-084 | Spacecraft & Payload Technical | ADCS & Navigation | Star Tracker Performance Degradation | Technical | Star tracker performance is degraded by bright-object intrusion, contamination or unexpected HEO viewing geometry, reducing attitude knowledge during imaging. | Incomplete keep-out analysis; insufficient sensor testing; thermal calibration gaps | Sun/Moon geometry; contamination; stray light environment | 20% | Mitigate | Perform representative HEO star-tracker testing, validate keep-out zones and retain alternate attitude sensors and operating modes. | 350 | 1600 | 4500 | 320 | C–D | D–E | May reduce imaging opportunities or require alternate attitude modes. | Adds ADCS analysis, testing and software LOE.
| 85 | R-085 | Spacecraft & Payload Technical | Payload Accommodation | Payload Contamination Degrades Optical Performance | Technical | Particulate or molecular contamination accumulates on optical surfaces and reduces imaging performance. | Weak contamination-control implementation; insufficient witness samples; late cleanliness activities | Launch vehicle plume; outgassing; facility contamination | 20% | Mitigate | Set contamination budgets, use witness samples, bake-out and controlled handling, and verify optical performance before launch. | 400 | 1900 | 5200 | 380 | D | D | May reduce payload sensitivity, calibration stability or image quality. | Adds contamination-control, test and payload requalification effort.
| 86 | R-086 | Mission & Science | Observation Environment | Cloud/Weather Obscures Priority Observations | Performance | Cloud cover, snow or atmospheric conditions reduce usable optical observations for priority targets during selected passes. | Tasking assumptions too optimistic; insufficient cloud-aware scheduling | Seasonal cloud cover; Arctic weather variability; atmospheric conditions | 50% | Accept | Treat weather obscuration as an inherent optical Earth-observation limitation and compensate through priority tasking, repeat observations and trend analysis. | 150 | 700 | 1800 | 350 | E | E | May reduce useful observation yield without directly affecting spacecraft availability. | Adds observation-yield uncertainty to mission-benefit and data-volume analysis.
| 87 | R-087 | Mission & Science | Geolocation & Product Quality | Level-1B Geolocation Accuracy Miss | Performance | The processed imagery does not meet the required geolocation accuracy under representative reference conditions. | Inadequate geometric calibration; time synchronization error; attitude knowledge error | Ground-control data quality; seasonal terrain/ice changes | 25% | Mitigate | Maintain an end-to-end geolocation error budget, use calibration targets and validate products before operational declaration. | 300 | 1400 | 4000 | 350 | C–D | D | May require calibration updates, software changes or payload rework before operational use. | Adds validation campaigns, processing development and calibration LOE.
| 88 | R-088 | Mission & Science | Calibration & Validation | Onboard Calibration Reference Degrades | Technical | The onboard calibration reference degrades or drifts faster than expected, reducing radiometric stability over mission life. | Insufficient lifetime characterization; thermal sensitivity | Radiation, contamination and aging environment | 20% | Mitigate | Characterize drift, include periodic ground/in-flight calibration and retain software correction approaches based on calibration trending. | 250 | 1200 | 3500 | 240 | D–E | E | May increase calibration frequency and reduce confidence in long-term data products. | Adds calibration-analysis and ground-processing LOE.
| 89 | R-089 | Ground Segment & Operations | Mission Planning | Mission Planning System Cannot Resolve Conflicting Priorities | Programmatic | The mission planning system cannot consistently optimize competing observations, spacecraft constraints and government priorities within the required planning cadence. | Unresolved priority rules; insufficient algorithm testing; incomplete constraint models | Changing user priorities; late target requests | 30% | Mitigate | Define tasking priorities, test representative scenarios and use operator override rules with auditable decision logic. | 250 | 1100 | 3000 | 330 | C–D | D–E | May reduce observation efficiency or increase manual operations workload. | Adds mission-planning software and operations LOE.
| 90 | R-090 | Ground Segment & Operations | Data Processing | Processing Algorithm Changes Affect Archive Consistency | Data | Processing updates create inconsistent product versions or metadata across the archive. | Weak software/configuration controls; incomplete provenance tracking | User-driven algorithm revisions; third-party processing dependencies | 30% | Mitigate | Version algorithms and products, retain processing provenance and validate backward compatibility before production release. | 220 | 1000 | 2800 | 300 | D–E | E | May require reprocessing of historical data and increase storage demand. | Adds data-management and reprocessing costs.
| 91 | R-091 | Ground Segment & Operations | Cybersecurity & Access | Ground Segment Denial-of-Service Disrupts Operations | Security | A denial-of-service event reduces access to mission-control or data-processing infrastructure during a critical operational period. | Insufficient network segmentation; inadequate capacity planning | Internet-originated attacks; service-provider outages | 30% | Transfer | Include service-level commitments, redundant connectivity and incident-response responsibilities in ground-service contracts while retaining internal recovery capability. | 300 | 1300 | 3600 | 390 | E | E | May delay commanding or data dissemination and increase recovery workload. | Adds cybersecurity service and continuity provisions to operations cost.
| 92 | R-092 | Supply Chain & Commercial | Configuration & Lifecycle | Critical Component Obsolescence Before Procurement | Technical | A critical component becomes obsolete or unavailable before sufficient flight quantities are procured. | Slow component decisions; long design cycle; insufficient lifetime buy strategy | Commercial product lifecycle changes; supplier discontinuation | 40% | Avoid | Avoid dependence on vulnerable parts by selecting long-life components where practical and completing lifetime-buys or qualified alternates before design freeze. | 350 | 1500 | 4200 | 600 | B2–C | B2–C | May force redesign of electronics or payload interfaces. | Adds component analysis, qualification and procurement effort.
| 93 | R-093 | Programmatic Integration & Execution | Schedule Planning & Control | Review Exit Criteria Are Not Met | Governance | A major design or readiness review cannot close because required evidence or actions remain incomplete. | Weak entry/exit criteria; late evidence generation; unclear action ownership | Independent review availability; supplier evidence delays | 40% | Accept | Accept limited residual review-slip risk after enforcing objective entry and exit criteria and retaining schedule reserve around major reviews. | 250 | 1100 | 3000 | 440 | B2–D | B2–D | May delay release to the next lifecycle activity and consume schedule reserve. | Adds review-management and rework contingency.
| 94 | R-094 | Programmatic Integration & Execution | Procurement & Contracting | Contract Change Requests Increase After Award | Cost | Supplier and government requirements generate more contract changes than planned after award. | Incomplete SOW; unresolved interfaces; immature specifications | Supplier interpretation; market changes; policy constraints | 40% | Mitigate | Freeze priced requirements before award, use controlled change boards and require quantified cost and schedule impacts for each change. | 300 | 1400 | 3800 | 560 | B2–D | B2–D | May increase contracted scope and reduce management reserve. | Adds contract-management LOE and change-order contingency.
| 95 | R-095 | Launch & Early Orbit | Launch Vehicle | Launch Failure Results in Loss of One or Both Spacecraft | Cost | A launch failure results in partial or total loss of spacecraft and launch investment. | Limited opportunity for rapid rebuild; two-spacecraft dependence on one launch | Launch vehicle failure; launch-site incident | 5% | Transfer | Maintain launch insurance for defined physical-loss exposures and preserve design records, critical spares and supplier support for potential rebuild. | 5000 | 30000 | 70000 | 1500 | D | D–E | May cause major mission delay and require spacecraft replacement or rebuild. | Requires explicit mission-loss and insurance assumptions in the estimate.
| 96 | R-096 | Launch & Early Orbit | Orbit Insertion | HEO Injection Error Exceeds Correction Capacity | Technical | Launch vehicle injection dispersions exceed the propulsion margin available for orbit correction and constellation phasing. | Insufficient dispersion analysis; optimistic delta-v reserve | Launch vehicle performance dispersions; upper-stage performance | 10% | Mitigate | Model worst-case insertion dispersions, reserve correction delta-v and confirm separation/phasing strategy with the launch provider. | 1200 | 5500 | 14000 | 550 | D | D | May prevent the spacecraft from reaching the required HEO geometry or alter observation coverage. | Adds flight-dynamics, propulsion and mission-analysis contingency.
| 97 | R-097 | Spacecraft & Payload Technical | Propulsion | Thruster Lifetime Is Insufficient | Technical | The propulsion system does not provide the required cumulative operating life for orbit maintenance, phasing, collision avoidance and disposal. | Incomplete life testing; underestimated duty cycle; thermal cycling | Thruster supplier performance variability; mission environment | 15% | Transfer | Use supplier life-performance guarantees, qualification evidence, warranty provisions and spare/repair obligations to transfer a defined portion of thruster lifetime exposure. | 450 | 2000 | 6000 | 300 | B2–D | D–E | May constrain orbit maintenance or end-of-life disposal. | Adds propulsion qualification, analysis and operations planning.
| 98 | R-098 | Operations | LEOP & Commissioning | Commissioning Anomaly Requires Extended Ground Support | Schedule | A commissioning anomaly requires contractor support beyond the planned 90-day readiness window. | Incomplete anomaly procedures; limited simulator fidelity; staffing constraints | Supplier response time; ground-station availability; unexpected spacecraft behaviour | 40% | Accept | Accept residual commissioning-support duration after reserving a defined contractor support extension and maintaining a validated anomaly-response simulator. | 350 | 1700 | 5000 | 680 | D | D–E | May delay nominal operations and increase early operations labour. | Adds commissioning staffing and contractor-support contingency.
| 99 | R-099 | Operations | Sustainment | Operational Staffing Model Is Underestimated | Cost | The 24-hour government operations concept requires more staff than planned to sustain shifts, leave coverage, training and anomaly response. | Underestimated workload; insufficient cross-training; excessive manual procedures | Labour availability; staffing policy; attrition | 40% | Accept | Accept residual staffing uncertainty after completing a quantified workload study and defining minimum safe shift coverage. | 500 | 2200 | 6000 | 880 | D–E | E | May increase recurring operations cost or require automation investment. | Increases lifecycle LOE range and operations-cost uncertainty.
| 100 | R-100 | End of Life | Disposal & Decommissioning | Deorbit Requirement Cannot Be Achieved | Technical | At end of mission, remaining propulsion capability is insufficient to execute the planned controlled disposal profile. | Propellant depletion; degraded propulsion efficiency; underestimated manoeuvre budget | Orbit perturbations; launch injection dispersions; spacecraft degradation | 10% | Avoid | Avoid reliance on late-life performance by allocating disposal delta-v explicitly in the design, monitoring propellant reserves and defining an earlier disposal trigger. | 700 | 3000 | 8000 | 300 | E–F | E–F | May require an alternate disposal profile or extended operations to achieve compliance. | Adds end-of-life analysis and contingency delta-v allowance.

## Risk Breakdown Structure
Risk Category | Risk Sub-category | Risk Name | Description | Internal Factors | External Factors | Cost - Impact in Phase | Schedule - Initial Impact in Phase | Parent CBS
Programmatic | Schedule | Integration Schedule | SAM payload and COS bus integration may take longer than planned due to interface issues or design iterations. | Payload-bus interface maturity and coordination | External supplier schedule | High
Programmatic | Schedule | Development Schedule | Development activities may take longer than planned, delaying major design reviews and downstream activities. | Design iteration and project management | Contractor performance and supply chain | Medium
Programmatic | Procurement | PSPC Procurement Delay | PSPC procurement activities may take longer than assumed for the payload, bus or supporting services. | Procurement planning and documentation | Government procurement timelines | High
Programmatic | Procurement | Supply Chain Delay | Long-lead spacecraft and payload components may not be available when required. | Supplier selection and procurement planning | Component availability and supplier capacity | Medium
Programmatic | Cost | Cost Growth | Actual program costs may exceed the preliminary estimate due to design growth, labour requirements or supplier pricing. | Estimate maturity and scope definition | Market pricing and supplier quotations | Medium
Technical | Payload | Payload Performance | The payload may not simultaneously achieve the required spatial resolution, swath, imaging quality and data-generation performance. | Payload design maturity | Detector and component performance | Medium
Technical | Payload | Payload Integration | The CSA payload may experience mechanical, electrical, thermal or software interface issues during integration with the COS bus. | Interface definition and integration testing | Bus interface constraints | Medium
Technical | Spacecraft Bus | Bus Performance | The COS spacecraft bus may experience performance issues involving power, thermal control, communications, ADCS or onboard processing. | Bus design maturity and subsystem interactions | Component availability and environmental conditions | Medium
Technical | Constellation | Two-Spacecraft Coordination | Coordinating two spacecraft to provide continuous Arctic observation may introduce additional attitude, communications, mission-planning and operational complexity. | Constellation architecture and mission planning | Orbital and communications constraints | Medium
Technical | Ground Segment | Ground Capacity | Ground receiving, processing and storage capacity may be insufficient for the final mission data volume. | Initial data-volume assumptions | Receiving-station and network availability | Medium
Technical | Ground Segment | Data Processing | Data processing may not achieve the required throughput or product latency. | Processing architecture and software development | External infrastructure dependencies | Medium
Technical | Software | Software Growth | Mission planning, spacecraft control and data-processing software may require greater development effort than initially estimated. | Requirements growth and software complexity | Third-party software and interface dependencies | Medium
Technical | Operations | Mission Operations | The two-spacecraft constellation may require more operational staffing and automation than initially planned. | Operational concept and automation level | Mission anomalies and workload variability | Medium
Technical | Data | Data Product Requirements | DND and other authorized users may require additional data products, processing or interfaces beyond the initial baseline. | User requirements and product definition | Changes in operational data needs | Medium
Technical | Cybersecurity | Data Security | Ground systems and data-distribution interfaces may require additional cybersecurity controls or infrastructure. | System architecture and security design | Threat environment and government security requirements | Medium
Launch | Launch Vehicle | Launch Availability | A suitable commercial launch opportunity may not be available when both spacecraft are ready. | Launch campaign planning | Commercial launch-provider availability | Medium
Launch | Launch Vehicle | Launch Interface | Launch-vehicle requirements may require changes to spacecraft mechanical, electrical or separation interfaces. | Spacecraft-launch interface definition | Launch-provider requirements | Low
Launch | Launch Campaign | Launch Campaign Delay | Launch-site processing, transportation or campaign activities may take longer than planned. | Campaign planning and logistics | Launch-site conditions and provider schedule | Medium
Programmatic | Requirements | Requirements Growth | Preliminary requirements may change following analysis of coverage, orbit, payload performance, data volume and operational needs. | Requirements maturity | Stakeholder changes | High
Programmatic | Stakeholders | Stakeholder Alignment | Different government stakeholders may introduce conflicting or additional requirements during development. | Stakeholder coordination | Government user needs | Medium
Programmatic | Governance | Approval Delays | Governance, security, data-access or interdepartmental approvals may take longer than planned. | Decision and approval processes | Government organizational dependencies | Medium
Resources | Personnel | Specialized Skills | Availability of specialized spacecraft, payload, remote-sensing and systems-engineering personnel may constrain project execution. | Resource planning and retention | Labour-market availability | Medium
Resources | Operations | Operations Staffing | 24-hour operations for two spacecraft may require more personnel than initially estimated. | Staffing model and automation | Personnel availability | Medium
Schedule | Testing | Environmental Testing | Environmental testing may identify hardware or interface problems requiring corrective action and retesting. | Test planning and hardware maturity | Unexpected test results | Medium
Schedule | Manufacturing | Hardware Delivery | Flight hardware may not be delivered according to the planned integration schedule. | Manufacturing and supplier management | Supplier delays and component shortages | Medium
Operations | Commissioning | Commissioning Delay | Spacecraft or payload commissioning may take longer than planned before operational imaging begins. | Commissioning procedures and spacecraft maturity | On-orbit anomalies | Medium
Operations | Availability | Spacecraft Availability | One spacecraft may experience an anomaly that reduces the planned continuous Arctic observation capability. | Redundancy and spacecraft reliability | On-orbit component failure | Medium
Data | User Data Usage | Data Exploitation | DND users may require additional analyst support, data products or integration with operational systems. | Initial user requirements | Changes in user workflows | Medium